## Slide 1: Progress update on the implementation of the Broadcasting Digital Migration (BDM) programme
Portfolio Committee on Communications
23 JANUARY 2018

## Slide 2: OUTLINE
High Level Overview
STB Procurement & Distribution
Implementation Rollout Phases
Implementation Challenges and Mitigation
Roadmap Towards 2019 Target
Risks and Issues associated with 2019 Target
Funding Required
Key Enablers

## Slide 3
HIGH LEVEL OVERVIEW
Below is the progress update since the last committee meeting:
Transmission Network: Digital transmission network fully deployed and active across the country. 87.3% of South Africans in a position to receive digital terrestrial television (DTT) broadcasts, the remaining 12.7% outside DTT coverage can receive via direct-to-home (DTH) satellite. Government currently distributing subsidized decoders for both DTT and DTH platforms.
Digital Broadcast Content: Currently all three SABC channels and News Channel live on air on the DTT and Satellite network, additional six channels from e.tv. In addition, all 18 SABC radio stations available throughout the country in the digital TV network. There is room in the network for further channel expansion.
Receiver Standards Framework: SABS National Standards for STBs and Integrated Digital TV in force, manufacturers already producing receivers according to published standards. This was an area of uncertainty for some time in the industry.
STB Distribution: Subsidized STB distribution ongoing.

## Slide 4
As per Statistics South Africa, 2013:
  Total households 15.1 million
  Households owning television sets estimated at 12 million
  Households with commercial pay TV subscription estimated at 4.5
  The Government commitment to migrate totals 5 million free STB kits and installations
  There is an additional estimated 2.5 million households owning television sets households that do not qualify for the subsidy that will require STBs or IDTVs in order to migrate.
  Approximately 3 million households do not own television sets. It is believed that household that do not have television sets are either households that do not have access to electricity and/or households that were historically never had access to terrestrial television services.
The R2.45-billion budget only sufficient for 1.5 million kits (STBs, aerials and installation costs).
USAASA ordered 1.5 million STB kits from various manufacturers between 2014 and 2015.
To date, over 851 720 STB kits have been delivered to the SAPO warehouses.
So far, over 563 667 registrations have been recorded with 283 478 installations allocated to installers and completed nationwide.
A total of 23 161 installations completed in the Northern Cape SKA region in order to comply with the international radio telescope project requirements.
Analogue broadcasts have been switched off in the SKA as a result (18 transmitters)
STB PROCUREMENT & DISTRIBUTION

## Slide 5
Rollout Considerations
Short-Term – Phase 1
    STB Clearance: Clearing of existing DTT kits (Rollout plan completed and in force)
    The planned sequence starts with predominantly flat provinces along borders (Free State and North West).
    The registration process for indigents to be activated nationally with a target timeline for June 2018 (including data analysis).
Medium-Term (April – July 2018) – Phase 2
    Acquisition of DTH decoders to connect already registered DTH households.
Long-term (July 2018 – June 2019) – Phase 3
    New procurement of devices for the remainder of the provinces.
    Rollout in the remainder of the border and inland provinces with targeted completion date of 30 June 2019.
IMPLEMENTATION ROLLOUT PHASES

## Slide 6
Lack of resources
  Project coordination (Administration, Logistics and financial management).
  Multitasking and juggling between various assignments with limited resources.
Absence of DTH Devices
  Negative impact on provincial planning and connecting the already qualified registered households impacting on programme reputation.
Lack of real-time registration technology
  Stringent, real-time registration process.
  Data integrity (real time data).
IMPLEMENTATION CHALLENGES

## Slide 7
  To mitigate the challenges, some interventions are the following:
    Developed a broader coordination mechanism and partnership.
    Discussions underway in soliciting advise on procurement model.
    Developed a fast tracking mechanism with intensified awareness programme through various platforms.
    Use of existing, qualified local installers in collaboration with municipalities;
    Complementing installer capacity with Public Works EPWP installer training program; and
MITIGATION

## Slide 8: ROADMAP TOWARDS 2019 TARGET (1)
  Constitutional and Technology Considerations
  Constitutional Issues
    The current arrangement only caters for television owning households indigents only
    Exclusion of poor non-television owning households who historically never had television sets due to lack TV signal coverage is in conflict with the obligation of universal access to information.
    There is additional estimated 3.1 million households without television sets across the country who would need to be afforded access to television broadcast services.
  Technology Evolution
    The current analogue service is gradually being phased away throughout the world.
    Digital TV is becoming the de facto technology for consumer equipment.
    Integrated Digital Television (IDTV) sets are emerging as the default choice for TV viewing.
    It is proposed that a consideration be made to issue IDTVs for poor households who currently do not have TV sets, in the place of STBs.
    It is also proposed that current TV owning, subsidy eligible households be afforded a choice between a subsidized STB or IDTV.

## Slide 9: ROADMAP TOWARDS 2019 TARGET (1)
  Rollout Approach
  Public Private Partnership (PPP)
  Collaboration of private sector and commercial broadcasters to expedite implementation rollout.
  Opportunity to utilise distribution channels and marketing platforms of industry to boost the rollout process.
  TV manufacturers encouraged to produce low cost IDTVs and also to market existing models for unsubsidized market.
  DSTV and OVHD (by e.tv) also encouraged to market their digital satellite STBs and link with government’s migration project.
  Potential budget savings benefit on:
    Education and Public Awareness Campaigns.
    Distribution networks.

## Slide 10
Rollout Approach
Targeting switch-off in a cell coverage approach, i.e. transmitter service area per local and district municipalities.
The overall aim is to migrate households beyond the 85% threshold across the country (Government subsidy and retail) to enable switch off of analogue services.
Procurement and installation for the remaining 3.5 million households.
Augmenting of Department’s resources by means of Private Public Partnership in the area of marketing and project human resources
ROADMAP TOWARDS 2019 TARGET (2)

## Slide 11: ROADMAP TOWARDS 2019 TARGET (3)
  Rollout Approach
New Institutional Arrangement:
  Minister to announce the registration period for the qualifying households.
  Local registration teams and installers on the ground at the same time for the remaining kits in the storage
  Ensure collaboration with the municipalities across the country.
  Industry distribution networks to increase uptake of the non-subsidized households in the Retail Market to complement the SAPO processes for the subsidized market.

## Slide 12: FUNDING REQUIREMENTS
  Funding is required for:
  Project management;
  Public Education and Consumer Awareness;
  Network transmission (Dual Illumination);
  Contact Centre (Consumer Support during and post implementation);
  Procurement of migration devices (IDTV/STBs);
  Distribution of devices; and
  Installations of devices and activation of services.

## Slide 13: FUNDING REQUIRED
STB and aerials are based on the current USAASA procurement figures for the remaining 3.5 million kits including installations.
It is anticipated that savings could be realised with the envisaged revised procurement process to be undertaken in consideration of current prices in the market.

## Slide 14
Important Assumptions
  Funding in place and procurement processes started by no later than June 2018.
  Delivery of first batch of migration devices (IDTV/STBs) starts in July 2018.
Aggressive and Radical Rollout Approach
  Creation of a clear, simple message for targeted audience
  Use of Radio (Community and National) and Television (all platforms).
  Availability and use of private sector resources.
  Promotion of the DTT migration message through private and government platforms.
  Use of Community Development Workers for registration of households through local registration centres.
  Reliable database and adequate number of installers to service their local municipalities
KEY ENABLERS

## Slide 15
THANK YOU