## Slide 1: PROGRESS REPORT PAYMENT OF SOCIAL GRANT ON 01 APRIL 2018
13 FEBRUARY 2018

## Slide 2: Purpose
The purpose of this presentation is to give progress:
SASSA’s change programme in relation to insourcing grant payment functions;
SASSA and SAPO Project Plan;
SASSA engagement with Banks;
SASSA’s Contingency Plan

## Slide 3: SASSA’s Strategic Objective - The Integrated Value Chain
SASSA aims to provide an integrated grant administration and payment service that improves:
    Beneficiary experience
    Efficiency and effectiveness
    Fraud and Risk management
    SASSA ownership
SASSA require the grant application and the card application to form part of a “one stop” process

## Slide 4: Social Assistance Coverage
As at June 2017, a total of 17,3 million citizens are in receipt of social grants;
This number is expected to increase at a rate of approximately 2% per annum over the Medium Term Expenditure Framework, and projected at 18,3 million by 2019/20;
The amount allocated for social grants in 2017/18 is R151 billion. This amount is expected to grow by approximately 8% per annum, reaching an amount of R176 billion in 2019/20
This amount includes about R600 million allocated for social relief of distress (disasters, school uniform project, food parcels, etc)
The bulk of the grants money is used for direct consumption.

## Slide 5: Current Payment Channels
Payment Channel | Method of Payment | Customer Touch Point | No of Beneficiaries | Total
Paypoint (Biometric CVM) | Cash payment | SASSA Cash Pay-points | 1,936,662 | 2,894,040
Merchant (Biometric CVM) | Cash payment | Merchants | 215,117 | 
ATM (Biometric CVM) | Cash payment | Merchants | 742,261 | 
ATM (PIN CVM) | Electronic payment | Commercial Banks (ATMs) | 5,375,936 | 7,778,157
 |  | Private Commercial Bank Accounts | (2,001,233) | 
Merchant (PIN CVM) | Electronic payment | Merchants | 2,402,221 | 
Total |  |  | 10,672,197 | 10,672,197
[1]

## Slide 6: SASSA Insourcing Services
Direct transfers to ACB beneficiaries bank accounts through SASSA Pay Master General (PMG) account’
  Commercial personal accounts;
  SASSA/Grindrod Accounts;
Alternative Payments – Local Economic Development (using Cooperative banks & Local/village/township shops);
Management/Administration of Regulation 26A deductions in relation to funeral covers;
Biometric Enrolment currently performed by CPS;
Reconciliations (Grants Payment Control and Monitoring);

## Slide 7: PHASE 1: Direct payments to beneficiaries receiving grants via personal bank accounts
For the payment cycle of January and February 2018 SASSA deposited grant money directly into the bank accounts of approximately 2 million, and preparations were as follows:
      Test run for 98 beneficiaries was successfully implemented in December 2017 for January 2018 payment.
      Test run conducted in January 2018 for direct transfers into 2 160 093 accounts valued at R2, 3 billion for February payments (majority are EPE accounts) 2 044 140

## Slide 8: Phase 2: Direct Payment (ACB) Transfers – Bank Accounts verification and Collection of Mandates
SASSA sent out letters to approximately 2 million beneficiaries on 17 December 2017 to beneficiaries who previously received their grants through bank accounts;
The letters were to advise them of this direct payment option. Many responses have been received, but a number of beneficiaries have indicated that they do not want bank payments, because of the cost;
This information is also being validated with Bankserv to confirm which accounts are still valid or dormant. To date Nedbank has confirmed 198 000 active accounts.
A file of the above 1.2 million beneficiaries was also sent to Bankserv to verify if these bank accounts are still active and valid. The response received from Bankserv indicated that the majority of these accounts are indeed still active….meaning direct payment can be made

## Slide 9: Phase3: Direct Payment Transfers - Temporary Direct Transfers to SASSA branded Card Payment Cards (Grindrod Accounts)
:
A pilot of direct transfer to Accounts of 5,776,924 million beneficiaries who are still using the SASSA payment card (5,776,924) for electronic payment (Grindrod Accounts – Test file)
Direct deposits into the accounts of beneficiaries who are still using the SASSA Payment Card/ Grindrod accounts (2.8 million) for payment at pay-points and retailers using Biometric CVM.
This segment of beneficiates would subsequently be migrated to the SASSA/SAPO card.

## Slide 10: Cash Payment
Cash payment services means provision of payment cards, security, mobile ATM or payment machines, loading of money, online & off-line solution.
A separate payment file for this cash payment service provider will be created as part of the month-to-month payment process.
The objective with the cash payment is to migrate the beneficiaries who are using SASSA card for cash payment (2,894,040) to a new cash payment card to access their money at SASSA cash pay-points. The breakdown of these beneficiaries is depicted in the table below- Cash beneficiaries per region.

## Slide 11: Cash Payment Services
SASSA has taken a decision to follow an open tender process to appoint a service provider who will be responsible for cash payment services to 2.5 million beneficiaries.
At the briefing session the prospective service providers requested an extension of the due date for submission of the proposals and was granted to the 28/02/’18
Tight time frames are set, & will only be completed by 06 April 2018 ( contracting)
A new service provider would given 2 months from date of award to set up & be ready to pay grants & starting the 01 June 2018.
A phase in period of at least 6 months would be required to take over cash payments from CPS. This implies that the court will have to be approached to extend the suspension of the invalidity of the current payment contract until 30 September 2018

## Slide 12: Regional Breakdown
Region | No of Beneficiaries
Eastern Cape | 402,005
Free State | 195,129
Gauteng | 295,410
Kwazulu-Natal | 781,343
Limpopo | 549,056
Mpumalanga | 255,065
North West | 230,906
Northern Cape | 69,022
Western Cape | 116,104
Total | 2,894,040

## Slide 13: Regulation 26A deductions
Business processes were reviewed, to enable local offices to receive the mandate as provided for in the Social Assistance Act, 2004.
Enhancements to the scanning solution conducted to accommodate this.
Socpen system enhanced, to enable the capturing of mandate to enable help desk and call centre officials to respond to enquiries
All 17 insurance companies registered have registered as entities with SASSA to enable payment directly on a monthly basis.
Process flow for funds from SASSA to the insurance companies documented
Approval obtained from National Treasury to utilise the services of QLink,
The Services Agreement was signed with QLink on 16/01/2018.

## Slide 14: Regulation 26A Deductions
There are 723 348 beneficiaries who have Regulation 26A deductions effected from their grants. SASSA will be managing this directly with effect from March 2018;
Work done to date to achieve this includes the following:
  Data base of funeral policies obtained and analysed
  A total of 10 561 exceptions identified,
  8 017 beneficiary with multiple policies (although within the 10% limit); and
  2 544 beneficiaries where the value of the deductions exceeds 10% of the value of a single grant (but not more than the combined total which that beneficiary receives).
  Letters were posted to all 10 561 beneficiaries on 18 October 2017 to advise them of the anomaly and to indicate how to resolve the problem.

## Slide 15: Biometric Enrolment
The Current Biometric Identity Access Management Solution for staff is in development stage. The Solution configuration will be expanded to enable enrolment of beneficiaries;
The additional Infrastructure requirements have been finalised and the current Project Scope will be varied. The report and motivation for the scope variation has been submitted to BAC;
SAPO is attending to the on-boarding function, processes and the infrastructure readiness;
Technical Teams are meeting daily at War Room;
A task team with DHA has been established to finalise the legal requirements for bulk verification of biometric data;
Final Data Sets migration from CPS will be done under the auspices of Information Regulator

## Slide 16: Migration to Banks
    SASSA, through National Treasury and SARB, has been engaging with banks on the requirements and expectations from that sector. Meetings were held on 10 November 2017; 30 November 2017; 1 December 2017; 10 January 2018
    Requirements for low cost product finalised and provided to National Treasury on 12 January 2018.
    Agreement reached at the IMC Technical Committee that the requirements for low cost product for all banks (including PostBank) should be the same.
    The Product is expected to be low cost to the fiscus and to the beneficiaries.
    Meetings to asses the banks willingness to develop the low cost product have taken place and were concluded.
    Collectively banks did not agree to develop a low cost product siting amongst others competition and limited time for creation of such.

## Slide 17: Requirements for Low Cost Product
Free EMV compliant bank card on account opening, with first free biometrically enabled EMV compliant card issued to account holders once this is approved;
No minimum account opening deposit and no minimum account balance
No monthly service fee charged to the beneficiary (account holder) (this will be covered by the subsidy)
Free first payment card replacement
Free mini-statement or balance enquiry
Unlimited free point of sale purchases
Two (2) free withdrawals on own infrastructure
Three (3) free cash back transactions at merchants / retailers
Free PIN resets on USSD or other electronic means; 1 free PIN reset per annum in bank infrastructure
Free cell phone balance enquiry
Free SMS and/or email notification for transactions and balances
No EFT debits or stop orders
The maximum cost for this bank account which SASSA will be willing to subsidise is R6,71 per month. However, it will be limited to the specific product agreed to for social grant beneficiaries only.

## Slide 18: Cooperative financial Institutions as a Payment Channel
Cooperative Banking Development Institution Agency (CBDI) is willing to explore the use of the CFI’s as a social grant payment channel.
It is a fact that CFI’s in their true nature are ambitious to grow as financial players in the country , mostly in the space of social grants payment.
In the recent developments and considering the pressure SASSA has to reduce beneficiaries paid via Cash , CFIs becomes more relevant to be engaged further.
A meeting be convened with the nine (9) cooperatives financial institutions which have been migrated to an electronic accounting system to establish their willingness to serve as a payment channel for social grants

## Slide 19: Cooperative financial Institutions as a Payment Channel
Cooperative Banking Development Institution Agency (CDBA) has a total of 27 accredited cooperative financial institutions (CFI’s)
Of the 27 CFI’s only one cooperative financial institution (CFIs) is currently used by SASSA to pay social grants .
Different SASSA teams visited the north west province to confirm the operations of the CFI being used for payment of social grants

## Slide 20: Challenge with EPE cards
CPS and Grindrod have embarked on an aggressive roll out of the current EPE account. SASSA has had to implement the following steps:
  Issued circular confirming that no marketing of any product will take place at any SASSA office or pay point
  CPS staff to concentrate on functions for which they have been contracts only – enrolment and payment. Anything else will be seen as a breach of contract
  Only SASSA branded cards to be issued by CPS enrolment officers
  Beneficiaries who choose to take the EPE account still have to complete the “method of payment” form and return this personally to SASSA for capturing on the system

## Slide 21: Communication
Once the details of the product banks are willing to offer are made known, the following will be implemented:
  Beneficiaries using the current expired, but valid SASSA card will be moved to the SASSA/SAPO card, if they do not want an account with another bank. These beneficiaries will then all receive a PostBank account which meets the minimum requirements.
  A card swap plan has been developed, but finer details such as dates and venues are being finalised (dependent on availability of the new card). Details will be communicated through multiple channels to beneficiaries.
  All banks which offer a low cost product will be permitted to have a presence at SASSA offices, to market their products. This will afford them the same opportunity as SAPO and avoid issues of uncompetitive behaviour
  “Request for method of payment” forms will be made available to banks, and placed on SASSA’s web site, to try and prevent multiple trips to local offices by beneficiaries who wish to change payment method

## Slide 22: SAPO as a Payment partner
Under the leadership of the Inter-Ministerial Committee on Comprehensive Social Security (IMC), an Implementation Protocol was signed with SAPO on 17 November 2017 and a Service Agreement on 8 December 2017. In terms of the Agreements, SAPO will provide the following services to SASSA for a period of 5 years:
Electronic banking services, through a corporate holding account and special disbursement accounts for beneficiaries
On-boarding of new beneficiaries through instant account opening and card issuance at SASSA local offices
Biometric authentication of beneficiaries
Development of software, in conjunction with other state entities

## Slide 23: Project Governance & Subcommittee's
The following Functional Area Groups were Established:(18/12/’17)
Technology, Banking & Info Security
Grants Administration, Physical Infrastructure & physical Security
Human Capacity
Legal
Finance
Change & Communication Management
Audit, Risk Management & Compliance

## Slide 24: Provisioning of Electronic Payment
Development & Approval of Specifications of:
  Holding/Control Account 19/12/’17
  Implementation/opening the holding account in process – (application to the NT as per the PFMA)
  Special Disbursement Account 19/12/’17
Card body production
  Development of an implementation plan
  Application for exemption 03/01/’18 (procurement freeze)
  Procurement of the card production (advert closed 22/01/’18 & currently evaluation in process)
  Card spec and design 31/01/’18

## Slide 25: Provisioning of Electronic Payment
Identification of card issuance sites 31/01/’18
Receipt of 1st batch of Card (02/02/’18) 16/03/’18
1st card issue – 19/3/2018
Card swop – commences 2/4/2018 - 30/09/2018
      and be concluded within a period of 6 months as part of the phase out of CPS and phase in of SAPO as SASSA’s payment part
Beneficiary data transfer to SAPO – 26/3/2018
Biometric verification with Home Affairs – 1/3/2018

## Slide 26: Phase out of CPS
The SASSA/Grindrod Card (expired)was honoured by Banks and Merchants for the January 2018 payments despite for few merchants
Several meetings the last being in January 2018, where SASSA, CPS and Grindrod Bank engaged on phasing out of CPS and outlining SASSA’s responsibility for payments of grants by:
  SASSA effecting payment into 3rd party bank accounts and
  SASSA paying directly into accounts held at Grindrod Bank.
  Setting the process for individual beneficiary data transfer to SASSA to ensure adherence to the protection of personal information as regulated

## Slide 27: Compliance with Constitutional Court Judgement
Progress post April 2017:
  Payments taken place monthly, without disruption since 1 April 2017
  First quarterly report submitted to Constitutional Court on 20 June 2017
  Engagement with Independent Panel of Experts (appointed by Concourt): on-going
  IMC engagements : on-going
  Second quarterly report submitted to Concourt on 15 September 2017
  Third quarterly report submitted 18 December 2017

## Slide 28: Compliance with Constitutional Court Judgement
Panel of Experts reports, September, November 2017 and January 2018
Court Directives: 07 and 29 November 2017
Monthly repots to court as per the above directions: 8 December 2017, 8 January and 8 February 2018
In the December 2017 SASSA reported the need to retain the services of CPS to allow for phase-in/ phase-out;
A letter was written to the Court on 18 December 2017;
A formal application lodged on 7 February 2018.

## Slide 29: Conclusion
In conclusion
  It is recommended that the meeting notes the progress made to date.

## Slide 30
Thank you