

**MINISTRY**

**PUBLIC WORKS**

**REPUBLIC OF SOUTH AFRICA**

Department of Public Works l Central Government Offices l 256 Madiba Street l Pretoria l Contact: +27 (0)12 406 2034 l +27 (0)12 406 1224

Private Bag X9155 l CAPE TOWN, 8001 l RSA 4th Floor Parliament Building l 120 Plain Street l CAPE TOWN l Tel: +27 21 468 6900 Fax: +27 21 462 4592

 [www.publicworks.gov.za](http://www.publicworks.gov.za)

**NATIONAL ASSEMBLY**

**WRITTEN REPLY**

**QUESTION NUMBER: 3247 [NW3579E]**

**INTERNAL QUESTION PAPER NO.: No. 37 of 2017**

**DATE OF PUBLICATION: 20 OCTOBER 2017**

**DATE OF REPLY: OCTOBER 2017**

**3247. Mr J Selfe (DA) asked the Minister of Public Works:**

What amount has his department spent on (i) building new and (ii) upgrading existing correctional service facilities (a)(aa) in each of the past five financial years and (bb) since 1 April 2017, and (b) in each case, what are the relevant details of the (i) facility concerned, (ii) work done and (iii) date of completion? **NW3579E**

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**The Minister of Public Works:**

**REPLY:**

The Department of Public Works provides service delivery infrastructure to the Department of Correctional Services, for the past five financial years and since 1 April 2017, the amount that was spent on (i) building new, (ii) upgrading existing correctional facilities is presented as follows:

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Item** | **Financial Year** | **TOTAL ALLOCATION** | **EXPENDITURE** | **Planning Stage (4-4A)** | **Tender Stage (4B)** | **Evaluation & Adjudication (5-5A)** | **Construction Stage (5B)** | **Practical Completion Stage (6A)** |
|  | 2013/14 | 680 137 750 | 300 325 570 | 106 | 14 | 11 | 46 | 22 |
|  | 2014/15 | 454 648 915 | 359 875 110 | 110 | 12 | 4 | 46 | 19 |
|  | 2015/16 | 576 165 972 | 482 579 915 | 98 | 3 | 13 | 41 | 15 |
|  | 2016/17 | 447 521 941 | 536 295 194 | 72 | 13 | 1 | 34 | 13 |
|  | 2017/18 | 243 897 506.00 | 243 002 430.80 | 79 | 4 | 1 | 23 | 9 |
| **Total** | **2 402 372 084** | **1 922 078 220** | **465** | **46** | **30** | **190** | **78** |

In each case the relevant details on (i) relevant details of the facility concerned, (ii) work done, (iii) date of completion are provided as follows:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
| **CLIENT DEPT** | **TOWN** | **DESCRIPTION** | **STATUS**  | **FINANCIAL TENDER DATE** | **FIRST DELIVERY DATE** | **STATUS** |
| CORRECTIONAL SERVICES | HEILBRON | IMPLEMENTATION OF EMERGENCY BACK-UP POWER SUPPLY | 6A | 2016/12/05 | 2017/06/04 | Project Completed  |
| CORRECTIONAL SERVICES | KROONSTAD | IMPLEMENTATION OF EMERGENCY BACK-UP POWER SUPPLY AT KROONSTA D MEDIUM A, MEDIUM B, MEDIUM C & YOUTH CENTRE AND COLLEGE | 6A | 2014/12/02 | 2017/08/02 | Project Completed  |
| CORRECTIONAL SERVICES | VIRGINIA | INSTALLATION OF BACK UP POWER GENERATOR AT VIRGINIA PRISON | 6A | 2016/12/05 | 2017/05/04 | Project Completed  |
| CORRECTIONAL SERVICES | ZASTRON | INSTALLATION OF BACK UP POWER GENERATOR | 6A | 2016/12/05 | 2017/05/30 | Project Completed  |
| CORRECTIONAL SERVICES | VENTERSBURG | INSTALLATION FOR BACK UP POWER GENERATOR | 6A | 2017/01/26 | 2017/09/21 | Project Completed  |
| CORRECTIONAL SERVICES | SASOLBURG | GROENPUNT CORRECTIONAL CENTRE: REPAIR OF RIOT DAMAGE TO MAXI MUM CENTRE | 6A | 2016/09/27 | 2017/05/08 | Project Completed  |
| CORRECTIONAL SERVICES | VILJOENSDRIF | GROENPUNT MEDIUM PRISON: UPGRADING OF THE EXISTING KITCHEN A ND CONVERSION FROM STEAM TO ELECTRICAL | 5B | 2015/05/19 | 2017/08/14 | On construction  |
| CORRECTIONAL SERVICES | GROOTVLEI (FS) | SEWAGE AND WATER INFRASTRUCTURE UPGRADE | 5B | 2016/03/15 | 2018/01/16 | On construction  |
| CORRECTIONAL SERVICES | PAARL | BOUNDARY FENCE PROJECT | 6A | 2015/12/04 | 2017/06/15 | Project Completed  |
| CORRECTIONAL SERVICES | PAARL | OUTSIDE KITCHEN: UPGRADE KITCHEN AND REFURBISH EQUIPMENT, IN CLUDING PAINTINGS & FLOORING | 5B | 2017/04/10 | 2017/12/09 | On construction  |
| CORRECTIONAL SERVICES | TZANEEN | REPLACEMENT OF TEMPORARY PRISON WITH A FACILITY FOR 494 INMA TES INCLUDING SECURITY FENCE AND SPORTFIELD: ADDITIONAL ACCO MODATION REQUIREMENTS | 5B | 2017/01/10 | 2017/09/27 | On construction  |
| CORRECTIONAL SERVICES | DURBAN | PAROLE BOARD FACILITIES: UPGRADING AND EXPANSION OF EXISTING AND PROVISION OF NEW STRUCTURES\_(NEW) | 6A | 2016/06/23 | 2017/05/12 | Project Completed  |
| CORRECTIONAL SERVICES | ESTCOURT | HERITAGE - REPLACEMENNT OF EXISTING CORRUGATED IRON BUILDING AND REBUID WITH BRICK | 5B | 2012/04/17 | 2017/11/15 | On construction  |
| CORRECTIONAL SERVICES | PIETERMARITZBURG | REPAIR AND MAINTENANCE OF INTEGRATED SECURITY SYSTEM | 5B | 2016/02/22 | 2019/02/21 | On construction  |
| CORRECTIONAL SERVICES | KOKSTAD | KOKSTAD MEDIUM AND MAXIMUM CORRECTIONAL CENTRES: FOLLOW ON C ONTRACT: INTEGRATED SECURITY SYSTEM | 5B | 2016/02/22 | 2019/02/21 | On construction  |
| CORRECTIONAL SERVICES | LADYSMITH (KZN) | SUPPLY AND INSTALLATION OF STANDBY GENERATOR AT DUNDEE, VRYH EID, LADYSMITH, POMEROY, NEWCASTLE, UTRECHT AND KRANSKOP | 5B | 2016/08/05 | 2017/08/04 | On construction  |
| CORRECTIONAL SERVICES | KURUMAN | REPLACEMENT OF FOUR IN ONE SLICER, KITCHEN FLOORING , FOOD P ROCESSOR AND MEAT SAW | 6A | 2016/03/18 | 2017/04/18 | Project Completed  |
| CORRECTIONAL SERVICES | KIMBERLEY | REPAIR AND MAINTENANCE PROJECT: FOLLOW ON CONTRACT FOR INTER GRATED SECURITY SYSTEM AT TSHWELOPELE (KIMBERLEY)CENTRE | 5B | 2015/10/05 | 2018/10/05 | On construction  |
| CORRECTIONAL SERVICES | RUSTENBURG | RUSTENBURG PRISON: REPAIR & RENOVATION AND UPGRADING OF BUIL DINGS, WET SERVICES AND CIVIL INFRASTRUCTURE. | 5B | 2014/07/14 | 2018/07/26 | On construction  |
| CORRECTIONAL SERVICES | STANDERTON | STANDERTON CORRECTIONAL CENTRE: ADAPTATION AND COMPLETE UPGRADING PHASE 2: WCS 044954 | 5B | 2013/12/20 | 2018/04/29 | On construction  |
|  |  |  |  |  |  |  |