OUTLINE OF CONSULTATION PROCESS:

| CABINET MEMO: MINISTER XINGWANA | 21 SEPTEMBER 2011 |
| --- | --- |
| Establish Interdepartmental Committee for coordination and oversight: guidelines developed | October 2011 |
| First deadline for departmental submissions | 9 February 2012 |
| Second deadline for departmental submissions | 30 May 2012 |
| Discussion Document to departments and provinces for input | 8 June |
| National consultative workshop on discussion document with national departments and provinces. | 13-14 June |
| Provincial consultations: Hosted by Premiers offices and Offices on the Rights of the Child or coordinating department. | July to September |
| Chief Directors meeting: Finalised inputs and identified gaps. | 27 July 2012 |
| Third deadline for final departmental inputs and provincial reports | 17 August 2012 |
| Consolidation of inputs and drafting of final report | 31 August 2012 |
| Final report presented at National Children’s Rights machinery. | 3-5 September 2012 |
| Final report to all government Departments | 4 October 2012 |
| Report to and approved by DG Clusters Social Cluster: 2October. D&A Cluster: 1 November ICTS Cluster: 6 November JCPS: 6 November | October - November 2012 |
| Report to Cabinet | 5 December 2012 - released |
| Report to Parliament &public | December/January 2012 |
| Engage Parliament &Public/feedback | March / April 2013 |
| Final inputs consolidated & printing | 31 May - June 2013 |
| Depositing | July 2013 |