## Sheet1
ANNEXURE A 1 - EXPANSIONS/VARIATIONS OF CONTRACTS FOR 2017/18 FINANCIAL YEARS (QUARTERS 3 AND 4)
NR | Correspondance date | Project Manager | Office | WCS No | WCS Project Description | Contract Amount | Contract No | Supplier | Variation Order No | Variation Order Amount | % of Contract Amount | Short Description | Date Received by VO Com Secretariat | Date to be Dealt with by VO Committee |  | Decision of VO Committee | Executing unit informed on
1 | 2017-10-02 | C M Dyatyi | Bloemfontein | 048352 | Bloemfontein High Court: repair of roof, ceilings and floors as well as plastering of walls and painting of walls | 15282394.69 | 0001 | Varymix Nineteen (PTY) LTD | 9, 10, 11 | 945988.38 | 6.19% | Various | 2017-10-02 | 2017-10-10 | Approved | VO 9 is approved. It is noted that only 2 quotations were received and the highest quote was recommended. The design team should be held responsible for this flawed detail. VO 10 and 11 - approved. | 2017-10-12
2 | 2017-10-02 | JP Kriel | Cape Town | 054351 | DOD: Oudtshoorn: Health Centre South Cape: Oral health section: Installation of a centralised ventilation system | 2220520.47 | 0001 | Mpuma Koloni Cooling and Electrical CC | 1 | 26578.53 | 1.197% | Steel cage for condensers & surgery doors | 2017-10-02 | 2017-10-10 | Approved | VO 1 is approved | 2017-10-12
3 | 2017-09-28 | N Mkengcele | Port Elizabeth | NA | Port Elizabeth: New Brighton SAPS: Cell block: Renovations including repairs to concrete roof and paint | 1624810.99 | 0001 |  | 1,2,3,4 & 5 | 230519.46 | 14.19% | Various | 2017-10-03 | 2017-10-10 | Approved | VO 1, 2,3,4 & 5 is approved | 2017-10-12
4 | 2017-09-01 | N Mchunu | Durban | 046725 | Ntuzuma SAPS: Construction of CCTV Room | 8518775.4 | 0002 | Umzingwane Construction and Projects | 1, 3, 4 , 7, 8 | 199095.44 | 2.337% | Various | 2017-10-05 | 2017-10-10 | Approved | VO 1 approved on condition that the pricing is done based on the contract. VO 3, 4, 7 & 8 is approved. | 2017-10-12
5 | 2017-10-04 | F Mathews | Cape Town | 032271 | Ladismith Magistrates Offce: Additional accommodation: Completion of existing contract | 16564200 | 0001 | Slyahlangana Construction (PTY) LTD | 4.9 | 92090.34 | 0.556% | Various | 2017-10-06 | 2017-10-17 | Approved | It is noted that the extended completion date was 5 July 2017. The project manager must clarify wether this is an expost facto application or indicate the situation around the completion date. VO 4 and 9 - approved | 2017-10-18
6 | 2017-10-10 | G Lukhele | HO SMP | 052500 | Beitbridge Land Port of Entry: 36 Months repair, maintenance of buildings, civil, mechanical and electrical infrastructure and installations | 67023061.83 | 0001 | Caledon River Projects CC | 1 | 1457873.13 | 2.175% | Various Mechanical Engineering works | 2017-10-10 | 2017-10-17 | Approved | VO 1 approved | 2017-10-18
7 | 2017-09-19 | JP Marairs | Kimberley | 053008 | Kimberley New Generation correctional centre: Maintenance of integrated security system | 14820962.6 | 0001 | JFE Group Empowerment (PTY) LTD | 1 | 1590049.66 | 10.73% | CCTV Recording HDD and Bosch Video Jets Repair | 2017-10-12 | 2017-10-17 | Approved | VO 1 approved | 2017-10-18
8 | 2017-08-22 | N Nair | Durban | 046386 | Durban: Chatsworth Magistrates office: Additional accommodation, upgrading of electricity including repairs and renovations | 167176880 | 0001 | Radip Builders and Constractors cc | 1 | 2427091.45 | 1.452% | Recording system and data networks | 2017-10-12 | 2017-10-17 | Approved | VO 1 was approved on condition that value related preliminaries are removed from the VO and dealt with in terms of conditions of contract. | 2017-10-18
9 | 2017-09-12 | T Dibakoane | Polokwane | 039804 | Dzanani SAPS: Upgrading of police station, repair and renovation of existing office block & construction of additional accommodation | 58324600 | 0001 | Chryselda Building Construction CC | 2 | 315786.81 | 0.5414% | Replacing of existing roof construction | 2017-10-16 | 2017-10-24 | Approved | VO 2 is approved. | 2017-10-26
10 | 2017/19/27 | L Marite | Bloemfontein | 052154 | Bloemfontein Air force base: Upgrading and refurbishment of sick bay: Building 24 | 14131168.68 | 0001 | Central Bridge Trading 389 CC | 4 | 510819.41 | 3.615% | Medical Gas installation | 2017-10-23 | 2017-10-31 | Approved | VO 4 was approved. R51 000.00 for P&G's to be removed as previously indicated | 2017-11-10
11 | 2017-10-09 | A Visser | Bloemfontein | 051540 | DPW: Repairs and renovations to lifts installations: Free State (RAMP) | 18488848.32 | 0001 | Sigma Lifts and Escalators (PTY) Ltd | 3 | 563217.02 | 3.046% | Construction of new lift schaft | 2017-10-23 | 2017-10-31 | Approved | VO 3 is approved. | 2017-11-10
12 | 2017-10-24 | F Motimele | Polokwane | 039789 | Vuwani SAPS: Upgradting of police station and construction of additional accommodation | 42895160.4 | 0002 | MUMS BUSINESS ENTERPRISE CC | 5 | 199037.16 | 0.464% | Changes to existing liftes | 2017-10-26 | 2017-10-31 | Approved | VO 5 approved. | 2017-11-10
13 | 2017-10-23 | L Maupe | Nelspruit | 045457 | Middelburg (MPU) 4 SAI Balalion: Are Military Health Unit: Upgrading of Buildings and construction of new sick bay facility | 42858720 | 0001 | Exilite 454 CC | 3 | 128329.8 | 0.2994% | Separation wall between Block E and F | 2017-10-26 | 2017-10-31 | Approved | VO 3 approved | 2017-11-10
14 | 2017-10-18 | K Kgorane | PM | 045688 | Dolomite Risk Mangement Strategy: Completion contract: Lyttleton & Wierda Bridge SAPS and Home Affairs: Upgrading of Civil Engineering Services | 3181407.12 | 0002 | MAAUASO PROJECT CC | 1 | 27668.43 | 0.8697% | Additional piping items | 2017-10-27 | 2017-11-07 | Approved | VO 1 is approved. | 2017-11-10
15 | 2017-10-27 | E Krause | Bloemfontein | 049859 | Bloemfontein SANDF Tempe: MP Repair and renovations to buildings 1, 2, 5 to 8 and 21 | 2724397.05 | 0001 | SOLOMON & SMITH PROPERTY DEVELOPERS AND BUILDERS | 5 & 6 | 183211.29 | 6.725% | Various | 2017-10-27 | 2017-10-31 | Approved | VO 5 & 6 approved. Submission to NT to approve VO6 will be withdrawn and the work to be done in separate contract | 2017-11-10
16 | 2017-09-28 | A Engelbrecht | Cape Town | 044464 | Goodwood Prison: Repairs to buildings and wet services | 45278600 | 0001 | Nolitha Electrical | 5 | 1941029.21 | 4.287% | Replace cupboards, PVC floor & Wall tile | 2017-10-30 | 2017-11-07 | Approved | VO 5 approved. | 2017-11-10
17 | 2017-10-23 | N Mchunu | Durban | 046725 | Ntuzuma SAPS: Construction of CCTV Room | 8518775.4 | 0002 | Umzingwane Construction and Projects | 1,2,3,4,5,6,7,8 | 199095.44 | 2.337% | Various | 2017-11-01 | 2017-11-07 | Approved | issuing VO 1 was approved on condition that the pricing is done based on the contract. The principle for issuing VO’s 3, 4, 7 and 8 is approved. | 2017-11-13
18 | 2017-10-26 |  | Cape Town | 042528 | Cape Town: Dept of Arts & Culture: Iziko Museum: Courtyard Project | 194800000 | 0001 | Superway Construction (PTY) LTD | 1 | 49020 | 0.02516% | Move museum fossils collection | 2017-11-01 | 2017-11-07 | Approved | approval of VO 1 noted | 2017-12-20
19 | 2017-11-03 | J Bapela | Pretoria | 046424 | Upgrading of an Existing C-Max into high security detention facility (completion contract): PTA Prison: PTA Management Area | 169988000 | 0003 | Raubex Joint Venture | 3 | 493022.18 | 0.29% | Walkway bridge | 2017-11-06 | 2017-11-14 | Approved | VO 3 is approved on condition that item 1.6 is removed from this VO as it is considered to be part of the P&Gs. | 2017-11-17
20 | 2017-10-30 | J Bapela | Pretoria | 046424 | Upgrading of an Existing C-Max into high security detention facility (completion contract): PTA Prison: PTA Management Area | 169988000 | 0003 | Raubex Joint Venture | 1 & 2 | 15955961.64 | 9.387% | Electrical and Buidling work | 2017-11-06 | 2017-11-14 | Approved | VO 1 & 2 is approved. Investigation should be instituted to ascertain who should be held responsible for this additional scope. The matter should be referred to Legal Services immediately by the PM to commence with the process of recovering the costs of the VO’s. The PM should ensure that the Indemnity Insurance of the professional team is active for the duration of the contract period | 2017-11-17
21 | 2017-09-12 | T Koleke | Port Elizabeth | 046173 | Dimbaza Magistrate court: Construction of a new building | 81749948.4 | 0001 | Transtruct (PTY) LTD | 14, 15, 17 & 18 | 3345280.3 | 4.092% | Various | 2017-11-08 | 2017-11-14 | Approved | VO 14, 15, 17 and 18 is approved | 2017-11-17
22 | 2017-09-22 | K Thobejane | Mmabatho | 050728 | Losperfontein Prison: Bane Marine X4, Extractor fan, electrical Stove, Convection oven X3, Band saw, Cooking pots X4, Tilting pans | 15880838.4 | 0001 | Ngaatendwe Trading CC | 2 | 48329.6 | 0.3043% | Various | 2017-11-09 | 2017-11-14 | Approved | VO 2 is approved. The mark-up should be aligned with the mark-up provided for in the BOQ. | 2017-11-17
23 | 2017-09-12 | C Dyantyi | Bloemfontein | 048368 | Frankfort Magistrate's office: Repair and renovations | 3385186 | 0001 | DJ and SS Cleaning Services CC | 1 | 108552.57 | 3.207% | New roof | 2017-11-13 | 2017-11-21 | Approved | VO 1 approved | 2017-11-22
24 | 2017-08-29 | C Dyantyi | Bloemfontein | 047822 | Rouxville Magistrate Office: Additional Accommodation | 7396646.04 | 0001 | RO Swika Projects CC | 1 | -6.38 | -8.626e-05% | Court room furniture | 2017-11-14 | 2017-11-21 | Approved | VO 1 is approved. Extended completion date is in the past (27/09/2017) and approval of VO does not constitute extension of time | 2017-11-22
25 | 2017-11-14 | S Majozi | Durban | 028207 | SANDF SMIT STREET: Repairs and renovations including electrical and fencing | 19423309.69 | 0002 | Serengeti Interiors CC | 4, 6, 7 & 8 | 669348.14 | 3.446% | Various | 2017-11-16 | 2017-11-21 | Approved | VO 4, 6, 7 & 8 is approved. | 2017-11-22
26 | 2017-10-16 | S Cosa | Kimberley | 049340 | Roodepan SAPS: Rebahilitation of buildings for SAPS | 4972148.87 | 0001 | Mmanyane Construction | 1 | 8721 | 0.1754% | Provision and laying of self levelling screet | 2017-11-16 | 2017-11-21 | Approved | VO 1 approved | 2017-11-22
27 | 2017-11-17 | D Sewada | Pretoria | 048747 | Pretoria: Thaba Tshwane: Installation for facilities for people with disabilities at army college | 901562.14 | 0001 | Kgapeng Investment CC | 1 | 103756.74 | 11.51% | Foundation and structural support | 2017-11-21 | 2017-11-28 | Approved | Approval of VO 1 was noted with no further comments | 2017-11-28
28 | 2017-11-22 | N Kadi | Mmabatho | 054054 | Mahikeng Magistrate's office: Construction of facilities for people with disabilities | 1063739.52 | 0001 | SEOKE BUILDING CONSTRUCTION | 3 | 130790.88 | 12.3% | Various | 2017-11-23 | 2017-11-28 | Approved | VO 3 approved | 2017-11-28
29 | 2017-11-29 | K Thobejane | Mmabatho | 050728 | Losperfontein Prison: Bane Marine X4, Extractor fan, electrical Stove, Convection oven X3, Band saw, Cooking pots X4, Tilting pans | 15880838.4 | 0001 | NGAATENDWE TRADING CC | 5 | 187485.54 | 1.181% | Various | 2017-11-29 | 2017-12-05 |  | VO 5 is approved | 2017-12-05
30 | 2017-11-29 | K Thobejane | Mmabatho | 050728 | Losperfontein Prison: Bane Marine X4, Extractor fan, electrical Stove, Convection oven X3, Band saw, Cooking pots X4, Tilting pans | 15880838.4 | 0001 | NGAATENDWE TRADING CC | 1 & 3 | 365210.4 | 2.3% | Various | 2017-11-29 | 2017-12-05 | Approved | VO 1 & 3 is approved | 2017-12-05
31 | 2017-11-27 | S Maahlo | Pretoria | 045665 | Maintenance Project: Electrical & Mechanical work at Home Affairs Coperation Building | 15688628.7 | 0001 | ANGLYN TRADING CC JV DUMEZULU | 5 | 198615.17 | 1.266% | Burnt Cable & circuit breaker | 2017-11-30 | 2017-11-05 | Approved | • Principle for issuing VO 5 is noted with comments for noting by the executing office. • The instruction was issued by the Act DDG-Projects on 17 March 2016. This was confirmed by the Head of Projects on 19 April 2016. • VO Committee notification (DPW24-1) was received by the Committee on 30 November 2017. • In terms of delegation 5.2 (previously 7.2), the notification had to reach the Committee within 5 days after site instruction was issued. This non-compliance should be referred to the Inspectorate & Compliance unit | 2017-12-05
32 | 2017-11-27 | S Maahlo | Pretoria | 045665 | MaintenanceProject: Electrical & Mechanical work at Home Affairs Coperation Building | 15688628.7 | 0001 | ANGLYN TRADING CC JV DUMEZULU | 6 | 106602.49 | 0.6795% | Burnt Cable & circuit breaker | 2017-11-30 | 2017-11-05 | Approved | • Principle for issuing VO 5 is noted with comments for noting by the executing office. • The instruction was issued by the Act DDG-Projects on 17 March 2016. This was confirmed by the Head of Projects on 19 April 2016. • VO Committee notification (DPW24-1) was received by the Committee on 30 November 2017. • In terms of delegation 5.2 (previously 7.2), the notification had to reach the Committee within 5 days after site instruction was issued. This non-compliance should be referred to the Inspectorate & Compliance unit | 2017-12-05
33 | 2017-11-27 | S Maahlo | Pretoria | 045665 | Maintenance Project: Electrical & Mechanical work at Home Affairs Coperation Building | 15688628.7 | 0001 | ANGLYN TRADING CC JV DUMEZULU | 7 | 419575.86 | 2.674% | Burnt Cable & circuit breaker | 2017-11-30 | 2017-11-05 | Approved | • Principle for issuing VO 5 is noted with comments for noting by the executing office. • The instruction was issued by the Act DDG-Projects on 17 March 2016. This was confirmed by the Head of Projects on 19 April 2016. • VO Committee notification (DPW24-1) was received by the Committee on 30 November 2017. • In terms of delegation 5.2 (previously 7.2), the notification had to reach the Committee within 5 days after site instruction was issued. This non-compliance should be referred to the Inspectorate & Compliance unit | 2017-12-05
34 | 2017-12-05 | GH Smith | Cape Town | 049596 | Antarctica SANAE IV Research Base: refurbishing of exising vbase | 155786000 | 0001 | NOLITHA ELECTRICAL (PTY) LTD | 11 & 12 | 2074273.37 | 0.6795% | DB's & LED Lights | 2017-12-05 | 2017-12-06 | Approved | Principle fo risusing VO 11 & 12 is approved | 2017-12-06
35 | 2017-12-05 | GH Smith | Cape Town | 049596 | Antarctica SANAE IV Research Base: refurbishing of exising vbase | 155786000 | 0001 | NOLITHA ELECTRICAL (PTY) LTD | 14;15 & 16 | 2270747.97 | 0.6795% | DB's & LED Lights | 2017-12-05 | 2017-12-06 | Approved | Principle fo risusing VO 11 & 12 is approved | 2017-12-06
36 | 2017-12-11 | E van Helsdingen | Special and Major | 044114 | Cofimvaba, Nqamakwe, Goedemoed & Willowvale Psions: Repair and Maintenanace of water and sewer works | 26319491.63 | 0001 | WATER SOLUTIONS SA HEAD OFFICE | 1 | 214149 | 0.8137% | MCC in clear water pump house | 2017-12-11 | 2017-12-12 | Approved | vO 1 approved | 2017-12-13
37 | 2017-12-11 | E van Helsdingen | Special and Major | 044114 | Cofimvaba, Nqamakwe, Goedemoed & Willowvale Psions: Repair and Maintenanace of water and sewer works | 26319491.63 | 0001 | WATER SOLUTIONS SA HEAD OFFICE | 2 | 73347.6 | 0.2787% | MCC in clear water pump house | 2017-12-11 | 2017-12-12 | Approved | VO 2 approved | 2017-12-13
38 | 2017-12-04 | JP Kriel | Cape Town | 053914 | DOD: Bredasdorp: SAMHS: Refurbishment and upgrading of sick bay complex | 17303658 | 0001 | R Conrad Trading CC | 2 | 11192.72 | 0.06468% | Various | 2018-01-08 | 2018-01-16 | Approved | VO 2 is approved | 2018-01-18
39 | 2017-12-01 | JP Kriel | Cape Town | 052456 | DOD: Bredasdorp: Overberg AFB: Upgrading, repair and renovation of building, mechanical and electrical infrastructure | 249880000 | 0001 | Raubex Joint Venture | 1 | 1007464.28 | 0.4032% | Various | 2018-01-08 | 2018-01-16 | Approved | Principle for issuing VO 1 is approved. | 2018-01-18
40 | 2017-11-08 | I Molotsi | Johannesburg | 046946 | 46 Brigade Kensington: Repairs and renovations to Military base | 38683999.55 | 0001 | Zidlaphi Kgomo and Associates CC | 1 | 149502.2 | 0.3865% | Removal of asbestos | 2018-01-08 | 2018-01-16 | Approved | Approval of VO 1 noted without further comments | 2018-01-18
41 | 2017-12-15 | D Sewada | Pretoria | 039074 | Pretoria: Central Police Station and single quarters: Sealing of roof of residential block, replacement of down pipes and upgrading of wet services | 12361273.08 | 0001 | Splish Splash Construction | 13 | 72680.61 | 0.588% | Props for supporting a collapsing penthouse roof | 2018-01-08 | 2018-01-16 | Approved | Approval of VO 13 is noted. | 2018-01-18
42 | 2017-12-19 | A Engelbrecht | Cape Town | 050784 | Voorberg, Dwarsrivier and Obiqua Prisons: Maintenance and operation of water and sewerage works | 29100166.68 | 0001 | Zana Manzi Services PTY LTD | 1 | 34734.06 | 0.1194% | Cleaning of reed bed | 2018-01-18 | 2018-01-23 | Approved | VO 1 is approved | 2018-01-23
43 | 22/01/2018 | E Van helsdingen | HO:SMP | 038691 | Sandton Leeuwkop Prison Farm: Repair of mediu, kitchen, cells, egneral infrsatructure and wet works- Completion Contract | 3635111.73 | 0004 | MAGODA CIVILS(PTY)LTD | 1 | 239405.24 | 6.586% | Subsoil drainage with surface V-Drain alaong medium A cell block building to deal with high underground water table | 2018-01-23 | 2018-01-30 | Approved | VO 1 approved | 2018-02-07
44 | 2018-01-15 | K Kgorane | HO SMP | 045677 | DRMS: Centurion: Lyttleton Police Station, Wierda Bridge Police Station and Irene Home Affairs | 3181880.52 | 0001 | Gora Projects CC | 2 | 149302.39 | 4.692% | Additional piping items and water line | 2018-01-25 | 2018-01-30 | Approved | VO 2 approved | 2018-02-07
45 | 2017-11-29 | K Thobejane | Mmabatho | 051875 | Ganyesa Police Station: Repair and maintenance of Civil, electrical and structural elements to police station for disabled and four houses | 7127319.9 | 0001 | GMD Projects CC T/a GMD Serivce | 2,,6 | 247770.21 | 3.476% | Various | 2018-02-08 | 2018-02-12 | Approved | VO 2 & 6 is approved. | 2018-02-14
46 | 2018-02-08 | E van Helsdingen | HO SMP | 038691 | Sandton Leeuwkop Prison Farm: Repair of mediu, kitchen, cells, egneral infrsatructure and wet works- Completion Contract | 3635111.73 | 0001 | Magoda Civils (PTY) Ltd | 2 | 31920 | 0.8781% | Geysers at cells | 2018-02-09 | 2018-02-20 | Approved | VO 2 approved | 2018-02-21
47 | 2018-01-29 | MF Dube | Durban | 044487 | DCS: Napierville Prison Old and New prison: Upgrade of airconditioning and ventilation system, Contract 3 | 3331516.62 | 0003 | Mishoe Trading and Projects (PTY) LTD | 5 | 74381.35 | 2.233% | Various | 2018-02-12 | 2018-02-20 | Approved | VO 5 is approved. | 2018-02-21
48 | 2018-01-06 | AL Naude | Cape Town | 048960 | SAS: Wingfield Military Base: Repairs and maintenance of buildings | 18563921.34 | 0002 | Ilitha Painters and Decorators CC | 10 | 218068.43 | 1.175% | New regulation of SANS on smoke ventilation | 2018-02-12 | 2018-02-20 | Approved | VO 10 is approved. Approval of VO does not constitute extension of time. The 50% pre-payment condition is not approved. (Refer to supplier quotation). | 2018-02-21
49 | 2018-01-25 | T Moeng | Mmabatho | 043801 | Zeerust Police Station: Construction of additional accommodation and repairs and renovations to existing facilities | 72373523.54 | 0001 | K2017341003 (South Africa) (PTY) Ltd | 12, 13, 15 | 2303602.36 | 3.183% | Various | 2018-02-14 | 2018-02-20 | Approved | Principle for issuing VO 12 is approved. Approval to execute work outside DPW property should be sought from the DG or any other delegated official. Principle for issuing VO 13 & 15 is approved. | 2018-02-21
50 | 2018-02-08 | JP Kriel | Cape Town | 053914 | DOD: Bredasdorp: SAMHS: Refurbishment and upgrading of sick bay complex | 17303658 | 0001 | R Conrad Trading CC | 3 | 19954 | 0.1153% | Various | 2018-02-14 | 2018-02-20 | Approved | VO 3 is approved. | 2018-02-21
51 | 2018-02-12 | JP Kriel | Cape Town | 052086 | DOD: Simonstown Naval Base: Repairs to building 1032: FMU East Yard | 38786876 | 0001 | Nolitha Electrical (PTY) LTD | 5 | 9885.28 | 0.02549% | Anodised aluminium door signage | 2018-02-14 | 2018-02-20 | Approved | VO 5 approved | 2018-02-21
52 | 2017-12-11 | S Masha | Pretoria | 052454 | Wonderboom Signal formation: Upgrading of the mess and the supply and installation of kitchen equipment | 37525983.56 | 0001 | TTTB Supplying and Construction CC | 1 | 526090.68 | 1.402% | Upgrading | 2018-02-21 | 2018-02-28 | Approved | VO 1 is approved | 2018-03-08
53 | 2018-02-16 | E van Helsdingen | HO SMP | 044114 | Confimvaba, Nqamakwe, Goedemoed & Willowvale prisons: Repairs and maintenance of water and sewer works | 26319491.63 | 0001 | Water solutions SA Head Office | 4 | 35956.28 | 0.1366% | Screen rakes and Flocculant building tiling | 2018-02-21 | 2018-02-28 | Approved | VO 4 is approved | 2018-03-08
54 | 2018-02-19 | A Ndlovu | Polokwane | 048604 | Lulekani Magistrate: Repairs and renovations to building | 17914275.03 | 0001 | Segabokeng Building Construction CC | 1 | 555396.62 | 3.1% | Diesel Booster and Main distribution | 2018-02-21 | 2018-02-28 | Approved | VO 1 is approved. | 2018-03-08
55 | 2018-02-19 | T Moeng | Mmabatho | 043801 | Zeerust Police Station: Construction of additional accommodation and repairs and renovations to existing facilities | 72373523.54 | 0001 | K2017341003 (South Africa) (PTY) Ltd | 16 | 13857.33 | 0.01915% | Omit ImproNet Access | 2018-02-22 | 2018-02-28 | Approved | VO 16 is approved. PM should note that approval of a VO does not constitute extension of time. | 2018-03-08
56 | 2018-02-15 | JP Kriel | Cape Town | 052456 | DOD: Bredasdorp: Overberg AFB: Upgrading, repair and renovation of building, mechanical and electrical infrastructure | 249880000 | 0001 | Raubex Joint Venture | 3, 4 | 5931740.13 | 2.374% | Various | 2018-02-26 | 2018-03-06 | Approved | VO 3 and 4 is approved. | 2018-03-08
57 | 2018-02-19 | S Govender | Durban | 034003 | Justice: Umbumbulu Magistrate court: Additional accommodation and alterations | 33504000 | 0001 | Tauris Garden Trading 500CC | 7 | 12340.61 | 0.03683% | Various | 2018-02-27 | 2018-03-06 | Approved | VO 7 is approved. | 2018-03-08
58 | 2018-02-12 | S Lidovho | HO SMP | 041821 | Tzaneen Correctional Center: Replacement of temporary prison with facility for 494 inmates including security fence and sprotfield: Additional accommodation | 37445591.95 | 0003 | Musan Trading Enterprise CC | 14,15,16,20, 21, 29 and 30 | 1758340.81 | 4.696% | Various | 2018-02-26 | 208/03/06 | Approved | VO 14, 15, 16, 20, 21, 29 and 30 - approved. | 2018-03-08
59 | 2018-02-13 | A Weels | Kimberley | NA | De Aar Area: Maintenance of the kitchen equipment for the period of 24 months | 2827462.2 |  |  | 1 | 206619.3 | 7.308% | provisioning and installing of 3 cooking oil jacket pots | 2018-02-28 | 2018-03-06 | Approved | VO 1 approved | 2018-03-08
60 | 2018-02-26 | JP Kriel | Cape Town | 053914 | DOD: Bredasdorp: SAMHS: Refurbishment and upgrading of sick bay complex | 17303658 | 0001 | R Conrad Trading CC | 1 & 4 | 91709.37 | 0.53% | Replacment of windows and density lab | 2018-03-01 | 2018-03-13 | Approved | VO 1 & 4 approved | 2018-03-14
61 | 2018-03-06 | N Mnqumevu | Port Elizabeth | 046173 | Dimbaza Magistrate office: Construction of new building | 81749948.4 | 0001 | Transtruct (PTY) LTD | 19 & 20 | 85878.03 | 0.105% | Supply and installation of raised floor to server room and fibre cement duct covers | 2018-03-08 | 2018-03-13 | Approved | VO 19 & 20 approved | 2018-03-14
62 | 2018-03-09 | MF Dube | Durban | 044487 | DCS: Napierville Prison Old and New prison: Upgrade of airconditioning and ventilation system, Contract 3 | 3331516.62 | 0003 | Mishoe Trading and Projects (PTY) LTD | 4 & 6 | 496154.07 | 14.89% | Riser ducting and extraction ducting | 2018-03-12 | 2018-03-20 | Approved | VO4 & 6 is approved. | 2018-03-23
63 | 2018-03-12 | A Ndlovu | Polokwane | 048604 | Lulekani Magistrate: Repairs and renovations to building | 17914275.03 | 0001 | Segabokeng building Construction CC | 2 | 187000.86 | 1.044% | Upgrade main distribution boards | 2018-03-12 | 2018-03-20 | Approved | VO 2 approved | 2018-03-23
64 | 2018-03-07 | T Moeng | Mmabatho | 043801 | Zeerust Police Station: Construction of additional accommodation and repairs and renovations to existing facilities | 72373523.54 | 0001 | K2017341003 (South Africa) (PTY) Ltd | 14 | 240530.7 | 0.3323% | Raising surface bed level and extending parapet walls | 2018-03-15 | 2018-03-20 | Approved | VO 14 approved | 2018-03-23
65 | 2018-03-16 | N Mkhwanazi | Mthatha | 046711 | MT Ayliff SAPS: Repairs and renovations including Electrical and Civil Works | 30038726.87 | 0001 | Condor Construction (PTY) Ltd | 6,7 & 8 | 5398197.17 | 17.97% | Various | 2018-03-22 | 2018-03-27 | Approved | VO 6, 7 & 8 supported and recommended for approval by National Treasury. NT did not approve the VO based on the correpsondnece dated 10 April 2018 | 2018-03-28
65 | 2018-03-01 | A Xentssa | Kimberley | NA | Kimberley Galeshewe SAPS: Community Centre: Assessment and repairs to the airconditioners | 1996957.61 |  | Hi Tech Engineers | 1 | 342022.51 | 17.13% | Heat Exchanger | 2018-03-23 | 2018-04-03 | Approved | VO 1 approved | 2018-03-28