## Q3 & Q4 2017 Expansions
Annexure B1 Expansions of contract for Quarter 3 & 4 FY 2017/2018 submitted to NT
Line Reference | Department/ Entity | Project Description | Supplier | Reason for extension | Original Contract Value | Value of Contract Extension | Value of previous extensions | Award/ Recommendation | Supported/Not supported by NT | Contract Start | Contract End Date | Quarter | Proceed Yes/No
1 | Public Works | Repairs and maintenance of local records centres | Burewa Trading 84cc | Continuity of Service | 8962017.66 | 2348325.82 |  | 2017-08-16 | Supported | 2016-09-01 | 2018-08-31 | Q3 | N/A
2 | Public Works | Construction of a new Police Station | Pieterse Du Toit & Associstes (Pty) and Regional Planners | Continuity of Service | 349331.97 | 48588.79 | 399315.84 | 2017-08-10 | Conditional Supported | 2017-10-25 | 2018-10-24 | Q3 | Yes
3 | Public Works | Restoration of old Magistrate court | Lubbe Construction | Continuity of Service | 118217794.17 | 12354108.01 | 15288987.56 | 2017-08-07 | Not supported | Not Stated | Not Stated | Q3 | NO
4 | Public Works | Construction of facilities for people with diability at Mahikeng Magistrates Office | Seoke Building Construction | Continuity of Service | 1063739.52 | 132435.52 | 495454.08 | 2018/01/25 | Not supported | Not Stated | Not Stated | Q4 | NO
5 | Public Works | Construction of facilities for disabled persons | Seoke Building Construction | Unforeseen requirements during execution of the project | R1 063 739.52 | 132435.52 | 495454.08 | 2018-01-28 | Not supported | 2017/12/02 | 2018/03/27 | Q4 | NO
6 | Public Works | Construction of facilities for disabled persons | Seoke Building Construction | Unforeseen requirements during execution of the project | R1 063 739.52 | 758714.82 | 627889.6 | 2018-01-28 | Not supported | 2017/12/02 | 2018/03/27 | Q4 | NO
7 | Public Works | Repairs and maintenance of local centres | Burewa Trading 84 CC | Additional work required to the facade | 8962017 | 2348325.82 |  | 2017-07-19 | Conditional Support | 2016-09-01 | 2018-08-31 | Q4 | Yes
8 | Public Works | Office accomodation | JHI Arrowheads | Not cost-effective to re-locate | 1292247.12 | 2693718.36 |  | 2017-12-06 | Not supported | 2018-06-01 | 2022-04-30 | Q4 | NO
9 | Public Works | Replacement of existing air -conditioning plant | Namasthethu Electrical Pty Ltd | Unforseen requirement identified upon construction | R2 304 950.04 | R3 677 950.48 |  | 2018/03/20 | Not Supported | 2018/01/23 | 2018/06/22 | Q4 | NO