## Slide 1: MATHEMATIC,SCIENCE AND TECHNOLOGY CONDITIONAL GRANT
Division of Revenue Act 2021,Schedule 5, Part A :
Specific purpose conditional allocation to the province
Grant purpose:
To provide schools, learners and teachers with resources to increase learners participation and success rate in MST subject in whole country
Outputs:
Information, Communication and Technology (ICT) resources including ICT integration;
Workshop (Technical) machinery, equipment and tools;
Laboratory(Science) equipment, manipulatives, apparatus and consumables;
Learner supports, MST subjects competitions, camps etc.
Teacher support(training of teachers and subject advisors)
DBE-Cuba support programme for Eastern Cape, Gauteng, Limpopo and Kwa-Zulu Natal

## Slide 2
2021/22 Fourth Quarter MST Conditional Grant Expenditure
OUTPUTS | 2021/22 Allocation | Adjustment | Total Adjusted Budget | Actual Expenditure | Under Expenditure | Funds Committed end of year | % Spent
Information, Communication and Technology( ICT) | 13 029 000 |  |  | 0 | 13 029 000 | 1 429 802 | 0
Workshops machinery, Equipment and Tools | 9 902 040 | 7 580 000 | 17 482 040 | 21 688 286 | -4 206 246 | 4 775 700 | 124,1
Laboratory Equipment/apparatus, Manipulatives and Consumables | 9 902 040 |  |  | 1 126 311 | 8 775 729 | 1 533 300 | 11,4
Teachers support | 7 817 400 |  |  | 8 847 171 | -1 029 771 | 2 425 000 | 113,2
Leaner support | 7 817 400 |  |  | 3 802 299 | 4 015 101 | 9 782 198 | 48,6
DBE-Cuba MST support program | 3 126 960 |  |  | 3 126 960 |  | 0 | 100
Grant Administration | 521 160 |  |  | 91 981 | 429 170 | 0 | 17,6
Total | 52 116 00 | 7 580 000 | 59 696 000 | 38 683 008 | 21 012 992 | 19 946 000 | 64,8

## Slide 3: Reasons for under-expending
Under expending:
Delayed procurement processes
Delayed delivery of ordered goods by service providers
Late commitment of funds:
Delayed procurement processes
Provisional approval of rollover of funds ( What for and amounts):
Total amount is R19 946 000
ICT – R 1 429 802
Workshops & Laboratories – R 6 309 000
Teacher support – R 2 425 0000
Learner support – R 9 782 198

## Slide 4: Non- Financial Performance 2021/22
Information, Communication and Technology (ICT) resources including ICT integration(Achieved);
60 schools were provided smart classrooms
Workshop (Technical) machinery, equipment and tools;
9 schools supplied with Civil Technology tools and consumable
16 schools supplied with Electrical Technology equipment and consumables.
7 schools were supplied with Mechanical Technology equipment & consumables.
Laboratory(Science) equipment, manipulatives, apparatus and consumables;
30 schools provided with Physical Sciences kits
30 schools provided with Life Sciences kits
10 schools supplied with Agricultural Technology equipment and PPEs
70 GET schools were supplied with Maths kits

## Slide 5: Non- Financial Performance …Cont…
Learner supports, MST subjects competitions, camps etc:
1 900 learners were registered for Olympiads.
3 400 learners supplied with Maths and Science Mind The Gap Study guides
Teacher support(training of teachers and subject advisors)
1 150 Maths teachers attended a training.
1 300 Physical sciences educators attended training.
1 400 Life Sciences teachers were trained.
1 600 GET teachers attended Maths and science training.
160 Technical Subject Teachers attended training
DBE-Cuba support programme for Eastern Cape, Gauteng, Limpopo and Kwa-Zulu Natal
Developed training material and learner support material for grade 11 and 12 Maths and Sciences.
Participated in teacher training in 4 districts

## Slide 6
2022/23 MST Conditional Grant Expenditure First Quarter
OUTPUTS | 2022/23 Allocation | Transfers to date | Actual Expenditure | Commitments | Available Budget | % Spent | % Transfers
Information, Communication and Technology( ICT) | 18 343 000 |  | 1 429 801 |  | 16 913 199 | 7,8 | 
Workshops machinery, Equipment and Tools | 8 092 500 |  | 4 596 169 |  | 3 496 331 | 56,8 | 
Laboratory Equipment/apparatus, Manipulatives and Consumables | 8 092 500 |  | 2 282 151 |  | 5 810 349 | 28,2 | 
Teachers support | 8 092 500 |  | 971 428 | 2 877 020 | 7 121 072 | 12,0 | 
Leaner support | 7 553 000 |  | 10 216 950 | 93 013 | -2 663 950 | 135,3 | 
DBE-Cuba MST support program |  |  |  |  |  |  | 
Grant Administration | 3 776 500 |  | 770 422 |  | 3 006 078 | 20,4 | 
Total | 53 950 000 |  | 20 266 921 | 2 970 033 | 33 683 079 | 37,6 | 

## Slide 7: Reasons for under-expending (Norm 25%):
Under expending:
The province is at 37,6% expenditure which is above the 25%

## Slide 8: Procurement Plan:
MST CG Activities (Procurement Process) :
Procured for Physical, Life and Agricultural Sciences material
Procured for ICT for FET schools
Procured for ICTs for CAT and EGD
Waiting for a contract to procure for Coding & Robotics, GET Maths, Natural Science and Technology Kits
Waiting for a contract to procure for GET posters

## Slide 9: Challenges/ Plans to Improve Spending
MST CG Activities (Procurement Process) :
Finalisation of the contracts has taken too long.
ICT procurement had been delayed, waiting for a contract
Procurement will be done following the quotation route.

## Slide 10: Thank You