QUARTER 1 Reporting template on the implementation of APP/2013/2014

| Strategic Objective 1: To ensure the creation and implementation of an enabling legislative framework that promotes the attainment of gender equality |
| --- |
| Sub-Strategy 1. To monitor and evaluate the policies and practices of the public and private sector institutions and provide reports to Parliament |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for Variance | Corrective Action |
| National Employment Equity (EE) Report presented to Parliament | 1 National EE Report presented to Parliament | 1 National EE Report presented to Parliament | 1 National EE Report presented to Parliament | Report was tabled in parliament. have not been called by parliament to present the report | Awaiting date from parliament to present on the report | Follow-ups will be made with parliament to provide a date to present on the report |
| Provincial Employment Equity Report | 1 Provincial EE Report per province | 1 Provincial EE Report per province and dialogues on findings | Finalize Provincial EE Reports | Reports are pending on four provinces, namely, GP, LIM, FS and EC | Secondary hearings are to be held to provide further information that will be included in the report | Secondary hearings are scheduled for the next quarter |

| Strategic Objective 1: To ensure the creation and implementation of an enabling legislative framework that promotes the attainment of gender equality |
| --- |
| Sub-Strategy 2. To initiate and/or review legislation that impact on gender equality |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for Variance | Corrective action |
| Submissions to parliament and/or provincial legislatures and SALRC | 12 Submissions made to Parliament on the review of gender implications in legislation | 12 Submissions made to Parliament of the review of gender implications in legislation | 3 Submissions made to Parliament on the review of gender implications in legislation | 10 submissions were made this quarter | No variance. Exceeded target by 7 submissions | No corrective action |
|  | Submission to Department of Justice & Constitutional Development (DOJCD) on implementation of legislation that enhances the justice facilities for gender equality | Submission to DOJCD on the Domestic Violence Act, Maintenance Act, Sexual Offences Act, Maternity benefits and Sex work | Review and submit to the DOJCD gender gaps, gender improvements to the Domestic Violence Act and Sexual Offences Act | Submissions have not been made to DOJCD |  | Submissions will be made in the next quarter |

| Strategic Objective 1: To ensure the creation and implementation of an enabling legislative framework that promotes the attainment of gender equality |
| --- |
| Sub-Strategy 3. To conduct periodic performance assessments of Government departments, political parties, state institutions, CSOs, and any private sector organisations, on the implementation of legislation and policies that impact on gender equality |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Assessment Reports prepared & tabled in Parliament | 1 Report on the effective implementation of the 365 days NAP and the GBV Council | 1 Report on the effective implementation of 365 days NAP | Compile background reports, publications and official documents on the 365 days NAP | Project plan was developed. background review of relevant documents/publications are underway. letter of request to secure access to GBV council proceedings has been written. | No variance | No corrective action |
| 1 report on the Assessment of Women in Political Participation and Representation | 1 report and findings on the Assessment of Women in Political Participation and Representation | 1 report on the assessment of women in political parties | Compile assessment report on Women in Political Parties Engagement with the IEC on party lists and 50/50 | Letters were written to political parties, namely, ANC, COPE, IFP, UDM and DA requesting meetings to discuss the objectives of the study. Meetings were held with ANC, COPE, IFP and UDM. The DA has not responded. One focus group meeting was held in the WC Engagement with IEC on party lists have not taken place | Party lists are not yet available | Meetings will be held with the IEC once the party lists have become available |

| Strategic Objective 1: To ensure the creation and implementation of an enabling legislative framework that promotes the attainment of gender equality |
| --- |
| Sub-Strategy 4. To evaluate the functioning of the national justice facilities promoting gender equality |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| 1 Consolidated Evaluation Report on the Maintenance, Equality and Family Courts | 1 Consolidated Evaluation Report on the Maintenance, Equality and Family Courts | 1 Consolidated Evaluation Report on the Maintenance, Equality and Family Courts tabled at Parliament | Evaluation of the functioning of Equality Courts against predetermined criteria | The monitoring tool has been developed, but awaits approval. Court monitoring as commenced | No variation | No corrective action |

| Strategic Objective 1: To ensure the creation and implementation of an enabling legislative framework that promotes the attainment of gender equality |
| --- |
| Sub-Strategy 5. To convene policy dialogues with identified policy makers on findings and recommendations contained in CGE reports |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Record of the 3 National policy dialogues on Education, Victims Charter and Gender Barometer | 3 National policy dialogues | 3 National policy dialogues on Education, Victims Charter and Gender Barometer | Preparation of Policy Dialogue material | Policy briefs have been drafted, but not finalised on Victims’ charter and Gender barometer | Delays experienced in the processing and completion of draft policy briefs | The policy briefs will be finalised in the next quarter |
| Record of the Provincial policy dialogues on Education, Victims Charter and Gender Barometer | 33 Provincial policy dialogues | 27 Provincial policy dialogues on Education, Victims Charter and Gender barometer | Preparation of Policy Dialogue material | Policy briefs have been drafted, but not finalised on Victims’ charter and Gender barometer Four policy dialogues were conducted that were rolled over from the previous financial year | Delays experienced in the processing and completion of draft policy briefs | The policy briefs will be finalised in the next quarter MP Education Policy brief will be conducted in the next quarter |

| Strategic Objective 2: To protect and promote gender equality by engaging with relevant stakeholders to educate and raise awareness of issues of gender equality. Challenge patriarchal perceptions and stereotypes and take action against infringements of gender rights through the implementation of appropriate redress |
| --- |
| Sub-Strategy 1. To investigate complaints of gender rights violations and identify appropriate redress per Sect. 11(1)(e)of the CGE Act |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Report on complaints handled presented to Commissioners | Complaints received and considered | 1620 Complaints received and considered | 405 complaints received and considered | 245 complaints were received, 131 files were closed | Gender discrimination toll free line has not been popularised sufficiently | Toll free gender discrimination line will be |
| Conduct 108 Legal Clinics to generate complaints | New focus area- Legal clinics | Conduct 108 Legal Clinics to generate complaints | Conduct 3 Legal Clinics per province totalling 27 | 21 legal clinics were held this quarter. 6 legal clinics are outstanding this quarter | NC only conducted 2 legal clinics, GP only conducted 1 legal clinic, NW did not conducted any legal clinics | The outstanding 6 legal clinics will be conducted in the next quarter |

| Strategic Objective 2: To protect and promote gender equality by engaging with relevant stakeholders to educate and raise awareness of issues of gender equality; challenge patriarchal perceptions and stereotypes; and take action against infringements of gender rights through the implementation of appropriate redress |
| --- |
| Sub-Strategy 3. To develop and implement coordinated programmes to promote gender equality |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Campaigns & programmes to promote gender equality implemented | 2 coordinated programmes to promote gender equality per year | 4 coordinated programmes to promote gender equality per year | Conduct a GBV schools education programme during the Youth month | Provinces have implemented with the exception of KZN and NC. KZN only visited one school | NC does not have an Education Officer. Mid year exams have also impacted on implementation | KZN and NC will implement in the next quarter |

| Strategic Objective 2: To protect and promote gender equality by engaging with relevant stakeholders to educate and raise awareness of issues of gender equality; challenge patriarchal perceptions and stereotypes; and take action against infringements of gender rights through the implementation of appropriate redress |
| --- |
| Sub-Strategy 4. To initiate interventions for sustainable development and promotion of gender equality in cultural and religious organisations |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective Action |
| Cultural and religious intervention programme developed and implemented | 1 cultural and 1religious intervention programme implemented per year | 1 cultural and 1 religious intervention programme implemented per year | Develop and sign 1 MOU with the national and provincial Houses of Traditional Leaders and 1 MOU Religious sector | WC has signed an MOU with Religious sector. NC is reviewing current MOU with PHTL and have conducted 3 interventions on initiation schools MP held a meeting with PHTL and is in the process of reviewing MOU. Other provinces have not implemented with PHTLs. Provinces have not developed MOUs with Religious sector | Provinces were slow in rolling-out the APP. | Facilitating the signing of MOUs will take place in the next quarter |
| Community Radio station advocacy intervention programme | New focus are- community radio presentations on gender education | 54 community radio (3 per radio station) presentations on gender education | Develop a media advocacy programme on gender education for community radio | Concept paper was developed and themes for radio programme have been identified. Meetings were held with NCRF to facilitating signing of an MOU | No variance | No corrective action |

| Strategic Objective 2: To protect and promote gender equality by engaging with relevant stakeholders to educate and raise awareness of issues of gender equality; challenge patriarchal perceptions and stereotypes; and take action against infringements of gender rights through the implementation of appropriate redress |
| --- |
| Sub-Strategy 5. To collaborate with Chapter 9 Constitutional entities supporting democracy, organs of state, civil society and other institutions to develop, protect, promote and attain gender equality |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Report Joint programmes conducted to develop, protect, promote and attain gender equality | 2 Reports | 2 Joint programmes conducted to develop, protect, promote and attain gender equality | Development of 2 Concept papers | Concept paper on LGBTIs has been developed. Concept paper on GBV in Higher institutions of learning as not been developed | No correspondence that relates to funding of the project was received from minister of Higher Education and learning. | Follow-up will be made wit the minster. concept paper will be finalised in the next quarter |
| Partnership programme with SALGA on gender equality | New focus area | 1 High level MOU with SALGA at national sphere | Not applicable this quarter |  |  |  |

| Strategic Objective 3. To monitor state compliance with regional and international conventions, covenants and charters which have been acceded to or ratified by the Republic, relating to the object of the Commission for Gender Equality |
| --- |
| Sub-Strategy 1. To conduct periodic reviews of state compliance with obligations under the conventions, covenants and charters and to report on a regular basis to Parliament |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Baseline Reports produced and submitted to Parliament on CEDAW, BEIJING and MDGs | 3 Compliance Reports i.t.o. CEDAW, BEIJING and MDG's per year submitted to Parliament as per parliamentary schedule | 3 Compliance Reports i.t.o. CEDAW, BEIJING and MDG's per year submitted to Parliament as per parliamentary schedule | Engagement with Parliament on content of CEDAW report | Engagement with Parliament has not taken place | Report has not been finalised | Finalisation of the report will take place in the next quarter |
| Complete Data collection on the Africa Gender Development Index (AGDI) | New focus area- 1 AGDI Report | Implementation of the AGDI South African report | Engagement with stakeholders and establish an advisory committee on the AGDI | Meeting with stakeholders has not taken place | Project plan has not been finalised | Project plan will be finalised in the next quarter |

| Strategic Objective 3. To monitor state compliance with regional and international conventions, covenants and charters which have been acceded to or ratified by the Republic, relating to the object of the Commission for Gender Equality |
| --- |
| Sub-Strategy 2. To engage national, regional and international bodies on state compliance with conventions, covenants and charters acceded to or ratified and to make recommendations for improvements |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Report on conventions attended | 2 Reports on Regional and/ or International conventions attended | 2 Reports on conventions attended | CSW report | Report has been finalised and tabled at Plenary held in May 2013 | No variance | No corrective action |
| Final report presented to Parliament on CEDAW committees concluding remarks | 1 Presentation to Parliament on CEDAW Committee concluding remarks | 1 Presentation to Parliament on CEDAW Committee concluding remarks | 1 Presentation to Parliament on CEDAW Committee concluding remarks | Presentation ahs not taken place. a funding proposal was drafted for attention of UN Women to fund this intervention. No favourable |  |  |

| Strategic Objective 4. To build an effective, efficient, visible and sustainable institution that will fulfil its constitutional mandate on gender equality |
| --- |
| Sub-Strategy 1. To establish and maintain a well-defined Commissioners oversight governance structure for execution of the mandate delegated to the Chief Executive Officer, with clear roles, and responsibilities |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Approved Governance Structure | Approved Governance Structure and Commissioners' handbook | Approved Roles and Responsibilities of Secretariat | Assessment of Roles and Responsibilities against King 3 checklist | Roles and responsibilities for the secretariat have not been developed. Meetings to discuss roles and responsibilities still need to take place | Meeting dates have not been set | Meetings will take place in the next quarter |

| Strategic Objective 4. To build an effective, efficient, visible and sustainable institution that will fulfil its constitutional mandate on gender equality |
| --- |
| Sub-Strategy 2. To develop a financial management strategy that promotes effective, efficient and economic utilisation of resources as well as accountability |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Financial Management Strategy Document | Financial Management policies and procedure documents | Revised Financial Management Strategy Document | Approved financial management strategy based on delegation of authority and revised and approved policies and procedures | A strategy document entitled “Operation Clean Audit” has been drafted and was adopted by Finance Committee. A request was further done through the Chair of Finance committee for the document to be presented to plenary | No variance | No corrective action |
| Electronic Asset management system | Manual Asset Management System | An optimal and effective electronic Asset Management System | Migration of the Fixed Assets management system to an electronic platform | This project will be effected once the IT Infrastructure refresh is completed. The migration is dependent on IT Infrastructure following action points that were identified in the PPE investigation report |  |  |
| Approved funding policy | Draft Donor Funding policy | Approved Donor funding policy | Approved Donor funding policy | Donor funding policy has been approved | No variance | No corrective action |

| Strategic Objective 4. To build an effective, efficient, visible and sustainable institution that will fulfil its constitutional mandate on gender equality |
| --- |
| Sub-Strategy 3. To improve, align and maintain innovative ICT infrastructure & systems that support the CGE organisational objectives |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Progress |
| 4 revised approved ICT policies | Framework ICT policy | 4 ICT Policies | Revise and approve IT, Security, Disaster recovery, Business Continuity Policies | IT policy has been approved. IT Change Control has been approved by ITC Committee, still needs to be tabled at plenary. IT Security, Disaster Recovery and Business Continuity Policies have been drafted. Still needs to be tabled with Manco | Plenary is scheduled for July 2013 to adopt change management policy. Policies still need to be discussed at Manco | Policy will be tabled with Manco and ITC Committee in the next quarter |
| ICT Infrastructure upgrade | Analysis report on current Infrastructure | 4 Phases of Infrastructure upgrades | Server upgrade | Engagement with SITA took place to assist with the development Master Systems Plan. The costing was very high. Management advised that an RFQ needs to go out to obtain service provider to draft MSP. SCM process is underway | No variance | No corrective action |
| Business Application Software Improvements | Legacy Systems software | 4 Phases of Business Application Software Improvements | Enterprise Resource Planning Application (ERP) | Currently finalising the electronic gender barometer tool. ERP review is dependant on finalisation MSP | No variance | No corrective action |

| Strategic Objective 4. To build an effective, efficient, visible and sustainable institution that will fulfil its constitutional mandate on gender equality |
| --- |
| Sub-Strategy 4. To develop a comprehensive HR Strategy that creates an enabling environment for employee wellbeing, talent attraction, development & retention |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Revised and Approved HR Strategy, policies & procedures | HR Policies and PPRR | Approval of 10 HR Policies developed & reviewed | Five HR policies developed & reviewed approved | 5 policies have been reviewed. Manco still needs to engage on the polices | Approval of policies still needs to take place | Polices will be approved at the next plenary |
| Developed and implemented Employee Assistance Programmes | Ad hoc Employee assistance | Employee Assistance Programme in implemented | Development and Implement Employee Assistant Programme and Procurement of Service Provider for the programme | Quotations for EAP have been sourced. Process still needs to go through SCM | Procurement process has not been finalised | Procurement will take place next quarter |
| Improve Compliance to the relevant labour legislation | Occupational Health and Safety programme in place and Employment Equity Plan implemented | Health and Safety programme implemented Employment Equity plan implemented | Appointment of the OHS Committee Implement the Employment Equity Plan | Committee has not been established Employment Equity plan is in place and employment equity targets are adhered to | Time constraints No variance | Committee will be established in the next quarter No corrective action |
| Implemented performance management system | Performance Appraisals for all staff | Performance Appraisals for all staff | Signed performance agreements for current year; and Appraisals for preceding financial year | Performance agreements have been signed. Appraisals for preceding year has not commenced | Appraisals still outstanding | Appraisals will commence in the next quarter |
| Training and Development Plan submitted to relevant SETA and implemented | Training & Development programme developed | Training & Development Plan developed and implemented | Training & Development Plan developed and submitted to relevant SETA | Training and development plan was developed and submitted to ETDP SETA | No variance | No corrective action |
| VIP leave administration system implemented | Manual Leave Administration system | Electronic Leave Administration implemented | Electronic Leave Administration | Electronic leave administration is in place | No variance | No corrective action |
| New & Revised Job Profiles | Old Job design/profiles | New & Revised Job Profiles developed | New & Revised Job Profiles developed | Job profiles for new post have been developed- ADS Finance and COO | No variance | No corrective action |
| All staff vacant posts filled in 3 Months | 80% of staff complement filled | 100% staff complement filled | Advertisement of critical vacant posts | Advertisements were published in City Press. Interviews for vacant posts. PC positions need to be finalised. Candidates for positions have been identified and will be appointed in next quarter | No variance | No corrective action |

| Strategic Objective 4. To build an effective, efficient, visible and sustainable institution that will fulfil its constitutional mandate on gender equality |
| --- |
| Sub-Strategy 5. To develop a long term funding model for the CGE that includes funding from the donor agencies |
| Performance Measure/ Indicator | Baseline | Annual Target 2013-2014 | April 2013 to June 2013 | Progress | Reason for variance | Corrective action |
| Communication programmes run to promote gender equality per year | 4 Communication programmes to promote gender equality per year | 4 Communication programmes to promote gender equality per year | Campaign for “1 Woman 1 Hectare” advancing land ownership Youth month programme | 2 media interviews were held Four press releases were drafted and sent to the media | No variance | No corrective action |
| Improvement of communications tools approved | 2 communication protocols developed Target (2000 Followers) | Social media policy approved Internal communication protocol approved | Facebook and Twitter campaign for youth month (2000 Followers) | CGE twitter and Facebook accounts have been created. | Communications officer was on maternity leave. only returned in June | Communications officer will manage accounts on a daily basis |
| Communication policies approved | 2 communication policies approved | Communication policy Branding policy | Communications policy approved | Communications Policy has been approved | No variance | No corrective action |
| Enhanced Website | Restructure content management and maintenance of website | Content management and maintenance of website | Identify content for website | Content for website has been identified | No variance | No corrective action |