REPORT PRESENTED TO THE AD HOC COMMITTEE FOR THE OVERSIGHT ON THE IMPLEMENTATION OF THE REVERSAL OF THE LEGACY OF THE 1913 NATIVES LAND ACT

Prepared by the

Commission on the Restitution of Land Rights

19 August 2013

OBJECTIVES OF THE REPORT

- To update statistics of restitution to illustrate provincial breakdown of total number of claims lodged by 31 December 1998

- To report on the financial performance of restitution to date and implications for finalisation of outstanding land claims

- To report on the State of readiness of the CRLR to reopen the lodgement of land claims

- To report on the legislative amendments to allow for the reopening of the lodgement of land claims.

- Background to restitution

- The land restitution programme is implemented through the Restitution of Land Rights Act 22 of 1994 (“the Restitution Act”), as amended. The Restitution Act establishes the Commission on Restitution of Land Rights and the Land Claims Court as the institutions that are responsible for processing land claims.

- The Commission consists of a Chief Land Claims Commissioner (“CLCC”), a Deputy Land Claims Commissioner (“DLCC”) and as many Regional Land Claims Commissioners (“RLCC”) as may be appointed by the Minister. Presently only RLCC has been appointed. The Commission is supported by Chief Directors: Restitution Support who head Commission Offices, which are in all 9 Provinces.

- The Commission is mandated to solicit land claims (which include receiving them), investigating them and attempting to resolve them through negotiation and mediation. Where an agreement is reached claims are referred to the Minister of Rural Development and Land Reform for administrative settlement. Where there is a dispute, such disputes are adjudicated by the Land Claims Court

- Constitutional and legislative framework governing restitution and the Commission on Restitution of Land Rights

- Section 25 (3) of the Constitution of the Republic of South Africa, 1996 provides that “a person or community dispossessed of a right in land after 19 June 1913 is entitled, to an extent provided for in an act of Parliament, to restitution or equitable redress”.

- The Restitution of Land Rights Act 22 of 1994 gives effect to section 25 (3) and provides procedures to be followed in the restitution process.

- The Public Finance Management Act 1 of 1999 provides the framework through which funds allocated for restitution are used.

- Restitution status update

Financial performance (cumulative) vs the amount of ha acquired and beneficiaries (households)

  - Cumulative statistics on restitution (nationally)

| Province | Claims | Dismissed | HHs | FHHs | Ha |
| --- | --- | --- | --- | --- | --- |
|  | rural | Urban |  |  |  |  |
| Eastern Cape | 419 | 16207 | 291 | 65139 | 25295 | 136753 |
| Free State | 41 | 2858 | 209 | 7614 | 2716 | 55747 |
| Gauteng | 1717 | 11866 | 702 | 14320 | 5448 | 16964 |
| KwaZulu-Natal | 2196 | 13641 | 141 | 85421 | 26503 | 764358 |
| Limpopo | 2294 | 1326 | 438 | 48492 | 18206 | 603641 |
| Mpumalanga | 1611 | 1235 | 202 | 53525 | 17362 | 460964 |
| Northern Cape | 133 | 3593 | 255 | 21900 | 9097 | 569341 |
| North West | 626 | 2924 | 319 | 44268 | 18408 | 399407 |
| Western Cape | 1426 | 15469 | 633 | 27411 | 11838 | 4140 |
| TOTAL | 10483 | 69119 | 3190 | 368090 | 134873 | 3011315 |

| Province | Land cost | Financial compensation | Grant |  |
| --- | --- | --- | --- | --- |
|  |  |  | Development | RDG | SPG | RSG | Total Award |
| EC | 67,250,053.29 | 1,644,201,185.00 | 315,382,294.76 | 85,509,000.00 | 40,963,680.00 | 50,972,735.00 | 2,204,278,948.05 |
| FS | 36,932,702.95 | 265,046,110.26 | 29,907,913.64 | 9,180,000.00 | 4,406,400.00 | 2,756,710.00 | 348,229,836.85 |
| GP | 117,189,227.57 | 674,381,918.29 | 76,215,311.38 | 6,663,000.00 | 2,197,440.00 | 4,161,445.00 | 880,808,342.24 |
| KZN | 5,226,281,658.54 | 1,871,176,249.20 | 1,109,815,238.95 | 103,761,000.00 | 46,640,880.00 | 52,621,210.00 | 8,416,838,236.69 |
| LP | 3,377,869,474.93 | 486,827,620.34 | 612,704,478.69 | 97,206,457.75 | 42,603,000.00 | 24,786,200.00 | 4,641,997,231.71 |
| MP | 4,299,838,890.63 | 453,174,795.13 | 225,362,193.13 | 100,289,640.00 | 48,319,950.00 | 21,934,970.00 | 5,148,920,438.89 |
| NC | 467,743,629.50 | 867,667,471.53 | 163,669,153.79 | 16,118,890.00 | 12,327,315.48 | 13,018,530.00 | 1,540,544,990.30 |
| NW | 1,728,569,064.38 | 374,195,368.43 | 357,557,533.76 | 83,112,000.00 | 39,632,280.00 | 8,899,830.00 | 2,591,966,076.57 |
| WC | 57,663,294.92 | 954,449,479.03 | 319,784,715.92 | 15,612,290.00 | 4,729,692.00 | 2,453,795.00 | 1,354,734,266.87 |
| TOTAL | 15,379,337,996.71 | 7,591,120,197.21 | 3,210,398,834.02 | 517,452,277.75 | 241,820,637.48 | 181,605,425.00 | 27,128,318,368.17 |

  - Status of land claims nationally

| Status of claims | Number of claims | Number of projects | Number of claimants |
| --- | --- | --- | --- |
| Ungazetted | 7226 | - | - |
| Gazetted but not yet settled | 1507 | - | - |
| Settled (claims as lodged) – claim forms | 59415 | - | - |
| Settled (claims as settled) – combination of claim forms and rights | 79582 | - | - |
| In process of being implemented | 20592 | - | - |
| Implementation finalised | 58990 | - | - |

  - Status of land claims per province

| Province | Number of ungazetted claims | Number of gazetted but not yet settled claims | Number of claims partially settled (in phases) | Number of fully settled claims (but not finalised) | Number of finalised |
| --- | --- | --- | --- | --- | --- |
| Eastern Cape | 844 | 164 | 213 | 1885 | 14528 |
| Free State | 0 | 14 | 8 | 148 | 2743 |
| Gauteng | 227 | 43 | 1929 | 1747 | 9907 |
| KwaZulu-Natal | 1463 | 665 | 1244 | 3053 | 11540 |
| Limpopo | 580 | 176 | 849 | 447 | 2324 |
| Mpumalanga | 2396 | 289 | 578 | 374 | 1894 |
| North West | 5 | 82 | 303 | 914 | 2730 |
| Northern Cape | 99 | 37 | 82 | 562 | 2685 |
| Western Cape | 1612 | 37 | 2802 | 3454 | 10639 |
| TOTAL | 7226 | 1507 | 8008 | 12584 | 58990 |

3.4	Number of outstanding claims

| Province | Outstanding due to partial settlement (projects) | Outstanding (Not yet settled at all) | Total |
| --- | --- | --- | --- |
| Eastern Cape | 22 | 1008 | 1030 |
| Free State | 12 | 14 | 26 |
| Gauteng | 3 | 270 | 273 |
| KwaZulu-Natal | 92 | 2128 | 2220 |
| Limpopo | 94 | 756 | 850 |
| Mpumalanga | 85 | 2685 | 2770 |
| North West | 60 | 87 | 147 |
| Northern Cape | 22 | 136 | 158 |
| Western Cape | 26 | 1649 | 1675 |
| TOTAL | 416 | 8733 | 9149 |

- National and provincial statistics for restitution on military, forestry and other state land

- Legal support (claims in court)

| PROVINCE | REFERRAL | REVIEW | DIRECT ACCESS | MATTERS TO COMPEL | OTHER (DECLATORY, INTERDICT, ETC) | TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
| Eastern Cape | 3 | 1 | 0 | 1 | 9 | 14 |
| Free State | 5 | 2 |  | 1 | 1 | 9 |
| Gauteng | 2 | 8 | 0 | 2 | 2 | 14 |
| KwaZulu-Natal | 41 | 21 | 0 | 16 | 32 | 110 |
| Limpopo | 14 | 9 | 2 | 8 | 6 | 39 |
| Mpumalanga | 42 | 35 | 3 | 4 | 13 | 97 |
| Northern Cape | 4 | 2 | 0 | 0 | 9 | 15 |
| North West | 13 | 4 | 0 | 0 | 2 | 19 |
| Western Cape | 0 | 2 | 0 | 2 | 4 | 8 |
| TOTAL | 124 | 84 | 5 | 34 | 78 | 325 |

- Backlog claims

- Claims that have been lodged and that adheres to the requirements for a valid claim will go through a pre-settlement phase which includes research, verification, validation, negotiation and the preparation of the S42D submission to the Minister for approval.

- Once the Minister is satisfied with the settlement options and restitution for the claimants, the S42D submission will be considered for approval.

- The claim is thus indicated as settled.  The settlement amount will create a commitment for the state.  The implementation of the settlement will then commence in order to finalise the claim.

- Implementation includes the acquiring of land and transferring it to the claimants’ entity or payment of financial compensation award to the claimants.

- If the claim is not finalised within the financial year which it was approved – all funds paid and all land purchased and transferred- the claim is indicated as a backlog claim.

- These are settled claims that have not been finalised and forms part of the commitments of Restitution.  It creates a liability that is due to claimants and must still be paid in future.

- Achievements

- Restitution managed to spend 100% of the allocated budget in 2012/13 and received an unqualified audit report for the financial year in question.

- The branch also managed to meet its performance targets as set out in the APP.

- Challenges

The lack of proper database / IT system that is current and interactive continues to be a barrier to our information management systems and makes it difficult to access information on lodged claims, settled claims and finalised claims.

Financial information often required to reconcile and verify beneficiaries is   also not readily available as all reporting is done manually.  This makes the creation of specified reports very difficult as information is locked in the format that it is captured in.

The dynamics that are found in any society often create an environment such that the officials who have been tasked to settle claims find it very difficult to complete the tasks.

The failure of Communities who have already received their land to manage the Community Property association means very often that Land that was restored in good condition end up neglected with the land laying fallow.

We have to make sure that we work very closely with Recapitalisation and development unit and other branches to ensure the sustainability of our project and also the Recapitalization of those farms that need it.

The fact that as the Commission is allocated a specific limited budget each year means that there is always pressure for us to settle more claims by both the land owners and claimant communities.

- Financial performance (cumulative) vs the amount of ha acquired and beneficiaries (households)

POINT 9 ABOVE IS ALREADY COVERED IN POINT 3 ABOVE.

- State of readiness for the reopening of land claims

  - Strategic plans for the reopening of the lodgement of land claims

The re-opening programme is in final planning stages of phase 2 to roll down to district offices while finalising the implementation for phase 1.   It should be noted that this phased approach was adopted at the point when the target date of re-opening was set for 20 June 2013 and a comprehensive roll-out could not be done due to short lead times.  As such an initial Phase 1 followed a minimalist approach but has subsequently been amended to roll-out the full complement of actions through Phase 2.  Most of the activities that are outstanding for phase 1 are reworks (i.e. IT system errors) and things that were not originally planned for, however they were included to improve the quality of work.  A consolidated revised baseline programme plan was developed and is targeted to be finalised by mid August once all streams and provinces have submitted implementation plans.

Task teams have been developed in each province to roll down to districts. Each task team has a representative from IT, Facilities, HR, Communications, Security, OHS, Procurement, NARYSEC and any other official that each individual province may see fit. In a nutshell this mimics the national reopening task team structure. These people will assist restitution officials that represent provinces in the national task team. Each national work-stream leader is still accountable to ensure that their respective stream objectives are achieved through provinces.

  - Capacity to implement restitution re-opening

In the assessment of the capacity, the following sub-categories are dealt with:

- Legislative progress

- Preparation of facilities

- Information technology

- Business Processes and Standards

- Communication

- Human resourcing

- General matters

- Financial overview

- Status overview

Legislative progress

Public comments on the Bill closed on the 24th of June 2013.Comments have been evaluated and amended Bill has been finalised.A memorandum to Cabinet requesting approval for tabling of the Bill has been routed to Minister for approval. The next Cabinet Committee meeting which the Bill can be considered is 28 August 2013 and full Cabinet on the 4th of September 2013.The Bill is also being processed through NEDLAC where there are weekly NEDLAC Task Team meetings. NEDLAC shall finalise its process on the 21st of September 2013.

Planned and outstanding matters

  - Cabinet approval for tabling the Bill to Parliament.

  - Approval of the Bill by Parliament.

  - Enactment of the Amendment Act.

Preparation of facilities

A total of 54 lodgement sites have been identified for lodgement across the country.14 of the 54 offices are existing DRDLR/ Restitution offices were identified checked for space availability, security and OHS. A consolidated list or report of all things that needed to be fixed wasdone and forwarded to DPW (Department of Public Works) and offices (land lords). The offices are in the process of implementing corrective actions.

A service provider was appointed to develop offices layouts (data captures cubicles, filing, back office, waiting area, furniture etc.)  for all 14 offices. All the offices are in the process of implementing the layout i.e. acquire and install cubicles and all other furniture.  (This will ensure that offices have the same or standard feel and look).A task team has been formed to define a prototype of how new buildings that will be acquired should have and look like in terms of security, OHS, area and IT. This process required the involvement and interactive planning from respective directorates; a service provider was engaged to assist drawing the plans that would be necessary.The DPW has been engaged to assist to acquire buildings required in other identified lodgement sites. All required information has been submitted i.e. the list of lodgement sites (towns), space requirement and a prototype of how the office layout is envisaged taking into consideration staff complement, filing requirement, claimant waiting area etc.

DPW has been engaged to provide a project manager that will assist to acquire extra buildings after all internal processes have been followed.

A provisional report was submitted by Security and OHS on the findings in the 14 identified offices. This was incorporated to facilities and office layout reports and issued to provinces to implement.

A total 9 mobile units will be bought across the country (1 per province), thereafter might be increased to as requestedby provinces only after a further needs analysis or customer requirements will be conducted and finalised to create or tailor make mobile units that will suit lodgement needs.

Initiate the procurement process to procure the units.

Planned and outstanding matters

- Finish implementation of corrective actions that were identified by security, OHS and facilities directorate.

- Finalise implementation of layout plans for 14 offices i.e. install cubicles and all other furniture.

- Acquire or appoint a project manager from DPW to assist in acquiring new building for identified lodgement site.

- Acquire buildings for identified lodgement sites; prepare the buildings to mimic the prototype.

Information technology

The system has been developed. URL was given to various officials to test the system. Gaps were identified and communicated to IT to repair. IT has completed fixing these and have commenced with re-testing the system.  We have engaged with the Deeds office and Branch SPLUMB to ensure that you systems are integrated order to enable us to quickly access required information of the land that is under claim and whether the claimed land has been claimed by any other community. It will also allow us to locate and therefore map the claims as they are lodged.  We are also engaging the Department of Home Affairs so that we are allowed access to ID numbers data base so that ID numbers can be immediately validated during the lodgement to prevent fraud.  An MOU (or implementation protocol) has been routed to the DG to request this service or integration with the Department of home affairs.We have also Initiated engagements with Telkom to source a comprehensive IT infrastructure solution that will enable the branch to host its lodgement information and ensure that the network is of good standard with enough bandwidth for the system to be fast. The planning is such that we have also had to take into consideration rolling out to all district offices.

Computers for the 14 phase 1 offices were procured and delivered to the National office and these will be delivered to provinces once offices have been set up to meet the minimum standard and have been furnished. The Procurement of furniture and scanners has been delegated to provincial task teams so that these are procured provincially as we were unable to procure nationally due to procurement process constraints. The work stream leaderwill oversee the procurement process.

Planned and outstanding matters

- Finalise integration of Deeds and SPLUM information into the system.

- Finalise integration of the system with the Department of Home Affairs (This may delay as authorisation lies with Home Affairs).

- Conduct a formal UAT to formally test the system with end users and finalised development or rework there off.

- Finalise the development of the user manual in collaboration with SOP work-stream.

- Train officials on the system.

- Deploy the system in provinces.

- Finalise and implement IT infrastructure solution by Telkom.

Business Processes and Standards

We have drafted processes and standard operating procedures (SOPs) for the front office, manual data capturing and back office support have been drafted. The processes have increased from 1 page to 4 pages to cater for all activities and control measures that need to be in place for lodgement offices.SOPs for manual capturing are being reviewed by the stream and they will be issued to DLCC and task team to sign off.The manual claim form has been amended to incorporate questions that were suggested by the Minister:question on Juristic persons, back office requirements, acknowledgement letter and ease of use. The form has been given to Communications Directorate to improve its looks, feel and security features.

Planned and outstanding matters

- Finalise processes and SOPs once the “Front End User” of IT system has been finalised. The stream will work with IT to develop SOPs that will be used to guide capturing.

- Finalise back-office SOPs.

- Train and implement SOPs.

Communication

The citizens’ manual has been developed and translated in all 11 languages. The manual will provide the necessary information to a potential claimant on how to lodge a claim, the required documents as well as the places where claims can be lodged. A first run printing has been done. During the time we were holding consultation workshop for the Bill advertisements were successfully plighted on various media space. This includes bill boards, radio stations, AgriTV, newspapers and posters. Anti-Fraud Campaigns have started in Limpopo and North West on community radio stations, and the Eastern Cape have commenced with a campaign called  “We are Ready Campaign”.

257 NARYSEC young people havebeen trained on Restitution across the country so that they conduct a “knock and drop” campaign where they will be required to go house to house with the Citizen’s Manual delivering the manual to potential claimants. They have been equipped further so that they can assist at the lodgement sites and general restitution process. A consolidated plan is being developed for implementation of the campaign by restitution, communications and NARYSEC Team.

Planned and outstanding matters

- Collaborate with NARYSEC to finalise a comprehensive plan for “knock and drop”

- Print citizens’ manual once we get the green light so that it can be given to NARYSEC to distribute.

- Repackage the manual claim form to improve security, looks and feel

Human resourcing

The organisational structure created for lodgement offices has been approved, and furthermore 275 NARYSEC youth have also been trained of Restitution processes so that they are ready an available to provide necessary support. They have also been trained to do a “Knock and Drop” which is a campaign that we have planned to ensure that the Citizens’ manual which explains the lodgement process and where the claimants can lodge their claims.

  - Financial implications

The breakdown below shows the breakdown per cost item.  It shows the initial start-up and once off costs as included in year 1 to amount to just under R480m whereas the outer years only reflect the recurrent costs in the amount of just over R200million per year.

| Activity | # | Year 1 | Year 2 etc (yr 3,4&5) | Total |
| --- | --- | --- | --- | --- |
| Procurement: Desktop | 416 | 6 240 000 |  | 6 240 000 |
| Procurement: Scanners/Photocopier/fax | 52 | 2 720 000 |  | 2 720 000 |
| Procurement :Furniture | 52 | 6 825 000 |  | 6 825 000 |
| Procurement : Water coolers | 52 | 182 000 |  | 182 000 |
| Procurement :Network Points | 468 | 468 000 |  | 468 000 |
| Procurement :SWITCHES | 52 | 4 160 000 |  | 4 160 000 |
| Procurement Laptop | 88 | 1 936 000 |  | 1 936 000 |
| Procurement Printer | 113 | 678 000 |  | 678 000 |
| Stationery & Consumables | 61 | 12 200 000 | 12 200 000 | 61 000 000 |
| ID Buddy | 61 | 427 000 |  | 427 000 |
| Numbering system | 52 | 1 625 000 |  | 1 625 000 |
| IT - Network points, Switches, WAN, Telkom Servers | 52 | 104 485 544 | 8 400 000 | 138 085 544 |
| IT infrastructure upgrade |  | 150 000 000 | 0 | 150 000 000 |
| Communication: print, radio, newspapers, branding |  | 16 078 015 | 5 000 000 | 36 078 015 |
| Additional compensation of employees |  | 102 315 483 | 108 454 412 | 576 761 889 |
| Upgrading of office sites | 52 | 7 800 000 | 0 | 7 800 000 |
| Operational cost | 61 | 61 000 000 | 67 100 000 | 372 411 100 |
| Rental of buildings | 52 | 1 430 000 | 1 573 000 | 8 730 293 |
| Total |  | 479 140 042 | 201 154 412 | 1 367 397 547 |