| Performance Reporting | Q1 2013/14 |
| --- | --- |

TABLE OF CONTENTS

OVERVIEW	1

PROGRAMME 1: ADMINISTRATION	2

PERFORMANCE AGAINST QUARTERLY TARGETS	3

Branch: Corporate Services	3

Sub-programme: Human Resources Management	3

Sub-programme: Chief Information Office	14

Branch: Policy, Planning, Monitoring and Evaluation	16

Sub-programme: Policy Planning and Development	16

Branch: Stakeholder Relations, Communication and Legal Services	18

Sub-programme: Legal Services	18

Sub-programme: Stakeholder Relations & Communications	Error! Bookmark not defined.

Branch: Chief Financial Office	23

Sub-programme: Financial Management	23

PROGRAMME 2: AGRICULTURAL PRODUCTION, HEALTH AND FOOD SAFETY	24

PERFORMANCE AGAINST QUARTERLY TARGETS	26

Sub-programme: Animal Production and Health	26

Sub-programme: Plant Production and Health	27

Sub-programme: Quarantine and Inspection Services	30

PROGRAMME 3: FOOD SECURITY AND AGRARIAN REFORM	31

PERFORMANCE AGAINST QUARTERLY TARGETS	32

Sub-programme: Food Security	32

Sub-programme: Sector Capacity Development	35

PROGRAMME 4: ECONOMIC DEVELOPMENT, TRADE AND MARKETING	36

PERFORMANCE AGAINST QUARTERLY TARGETS	37

Sub-programme: Agro-Processing and Marketing	37

Sub-programme: Cooperatives and Rural Enterprise Development	38

Sub-programme: International Relations and Trade	39

PROGRAMME 5: FORESTRY AND NATURAL RESOURCES MANAGEMENT PROGRAMME	42

PERFORMANCE AGAINST QUARTERLY TARGETS	44

Sub-programme: Forestry Operations	44

Sub-programme: Forestry Development and Regulations	44

Sub-programme: Natural Resources Management	45

PROGRAMME 6:  FISHERIES MANAGEMENT	47

Sub-programme: Aquaculture Management	48

Sub-programme: Monitoring, Control and Surveillance	50

Sub-programme: Marine Resources Management	52

ADDITIONAL INDICATORS AT SUB-PROGRAMME LEVEL	54

CONCLUSION	55

ACRONYMS

ABET 		Adult Basic Education and Training

ABP 		Annual Business Plan

ACP 		Aquaculture Certification Plan

ADF 		Agricultural Development Finance

ADZ 		Aquaculture Development Zone

AGIS 		Agricultural Geo-referenced Information System

AgriBEE	Agricultural Broad-Based Black Economic

Empowerment

APA 		Agricultural Produce Agents

API 		Agricultural production input

APP 		Annual Performance Plan

ARC		Agricultural Research Council

ATF 		Agricultural Trade Forum

ATI 		Agricultural Training Institute

ATPR		Agricultural Trade Progress Report

BCC		Benguela Current Commission

BEE		Black Economic Empowerment

CAADP 	Comprehensive African Agricultural Development      Programme

CAF		Consultative Advisory Forum

CASP 		Comprehensive Agricultural Support Programme

CC 		Climate change

CCS 		Compulsory community service

CD 		Chief Director

CMDB 		Configuration management database

COMESA 	Common Market for Eastern and Southern Africa

CPI 		Consumer price index

CRDP 		Comprehensive Rural Development Programme

DAFF 		Department of Agriculture, Forestry and Fisheries

DBSA 		Development Bank of Southern Africa

DDG 		Deputy Director-General

DEA 		Department of Environmental Affairs

DEXCO		Departmental Executive Management Committee

DFQF 		Duty free and quota free

DG		Director-General

DHET 		Department of Higher Education and Training

DPSA 		Department of Public Service and Administration

DPW 		Department of Public Works

DRDLR 		Department of Rural Development of Land Reform

DRP 		Disaster Recovery Plan

EAC		East African Cooperation

EAF 		Ecosystems Approach to Fisheries

EAF 		Ecological Approach to Fisheries

EC		European Countries

EE		Employment equity

EFTA 		European Free Trade Association

EH&W 		Employee Health and Wellness

EPA 		Economic Partnership Agreement

EPDM              	 Employee Performance Development Management

EPWP                  Expanded Public Works Programme

ER A 		Ecological Risk Assessment

ER P 		Enterprise Resource Planning

EU		European Union

FAnGR		Farm animal genetic resources

FARM		Framework for Aquaculture Research Management

FAO		Food and Agriculture Organization

FET 		Further Education and Training

FMD 		Foot-and-mouth disease

FMP 		Fisheries Management Plan

FPE		Fish processing establishment

FS 		Food security

FTE		Full-time equivalent

GADI 		Grootfontein Agricultural Development Institute

GDP 		Gross domestic product

GEP 		Gauteng Enterprise Propeller

GFI 		Gross farm sector income

GHG 		Greenhouse Gases

GMO		Genetically Modified Organism

HE		Higher Education

HIV 		Human Immunodeficiency Virus

HoD 		Head of Department

HR 		Human Resources

HRD 		Human Resources Development

HRM		Human Resources Management

IBSA 		India, Brazil and South Africa

ICT 		Information and Communication Technology

IFSNP 		Integrated Food Security and Nutrition Programme

IFSS 		Integrated Fisheries Security Strategy

IGDP 		Integrated Growth and Development Plan

ILM		Industry liaison meeting

IPAP 		Industrial Policy Action Plan

IT 		Information Technology

ITCAFF 	            	Intergovernmental Technical Committee for Agriculture,

Forestry and Fisheries

ITSC		International Trade and Security Cluster

KIM		Knowledge and Information Management

LR 		Labour Relations

LTRAMP 	Long-term Rights Allocation Management Process

Mafisa 		Micro-agricultural Financial Institutions of South Africa

MAP 		Marketing of Agricultural Products

MAST 		Marine Administration System

MCM		Marine and Coastal Management

MCS		Monitoring, Control and Surveillance

MDG 		Millennium development goals

M&E		Monitoring and Evaluation

MER		Monitoring, Evaluation and Reporting

MERCO SUR	Mercado Commún del Sur

MIS 		Marketing Information System

MLRA 		Marine Living Resources Act

MoA 		Memorandum of Agreement

MoU 		Memorandum of Understanding

MSP 		Master Systems Plan

MTEF 		Medium Term Expenditure Framework

MTSF 		Medium Term Strategic Framework

NAC		National Agro-meteorological Committee

NAFU		National African Farmers’ Union

NAMC		National Agricultural Marketing Council

NARMCO	National Agricultural Risk Management Committee

NAS 		National Aquaculture Strategy

NDTT 		National Disaster Task Team

NERPO		National Emergent Red Meat Producers’ Organisation

NFA 		National Forests Act

NGP 		New Growth Path

NPoA 		National Programme of Action

OIE 		Office International des Epizooties

OHS 		Occupational Health and Safety

PBR		Plant breeders’ rights

PDA 		Provincial Department of Agriculture

PDI 		Previously disadvantaged individual

PFMA 		Public Finance Management Act

PGRFA 		Plant Genetic Resources for Food and Agriculture

PMDS 		Performance Management and Development System

QPR		Quarterly performance report

R&D 		Research and development

RSA 		Republic of South Africa

SADC		Southern African Development Community

SALA 		Subdivision of Agricultural Land Act

SAQA 		South African Qualifications Authority

SASSA 		South African Social Security Agency

SDIP 		Service Delivery Improvement Plan

SETA 		Sector Education and Training Authority

SMME		small, medium and micro enterprises

SMS 		Senior Management Services

SOE		state-owned entities

SPS 		sanitary and phytosanitary

SRPP 		social responsibility programmes and projects

TAC		total allowable catch

TAE		total allowable estimate

the dti 		The Department of Trade and Industry

TIDCA 		Trade, Investment and Development Cooperation

Agreement

ToR		Terms of Reference

UN 		United Nations

VOIP 		Voice over Internet Protocol

WCR L 		West Coast rock lobster

WFFP 		Working for Fisheries Programme

WSCD 		White Shark Cage Diving

WSP 		Work Skills Programme

WTO		World Trade Organization

# OVERVIEW

In this organisational report, the Department presents its Quarter 1 Performance Report for the period April to June 2013, against the planned deliverables as reflected in Part B and Annexure 1 of Part C of its Strategic Plan. This Report has been compiled in accordance with the requirements of sections 92 and 114 of the Constitution and other government legislative prescripts that guide performance management in the public sector to display and promote transparency and accountability to stakeholders and the general public concerning matters under their control. This reported information will also be utilised to respond to the Department`s commitments in the achievement of Government Outcomes 4, 7 and 10. This report and other forthcoming quarterly reports will form the basis of the of Department`s Annual Report, to be compiled at the end of the current financial year.

# PROGRAMME 1: ADMINISTRATION

Purpose

Provide strategic leadership, management and support services to the Department. The aim of the programme is to lead, support and promote agricultural, forestry and fisheries resources management through policies, strategies and programmes to enhance sustainable use, and to achieve economic growth, job creation, food security, rural development and transformation.

The programme comprises the Ministry, Office of the Director-General, Chief Financial Office, Internal Audit, Corporate

Services, Stakeholder Relations and Legal Services, Policy Planning, Monitoring and Evaluation and Office Accommodation.

Strategic goals and objectives:

- SG 6: Effective and efficient governance

SO 2:  Strengthen policy, planning, monitoring, evaluation, reporting and sector information.

SO 3:	Provide effective audit, investigative and legal, human resources and financial risk

management.

SO 5:	Provide leadership and manage communication and information.

### PERFORMANCE AGAINST QUARTERLY TARGETS

### Branch: Corporate Services

### Sub-programme: Human Resources Management

| Sub-programme: Human Resources Management |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 6 | 3 | Integrated Human Resource Management Plan submitted to DPSA and implemented. | Identify units with a high vacancy rate and advise. | Agriculture & Forestry: During the reporting period units with a high vacancy rate were identified and visits were undertaken to these Directorates to advise on recruitment and selection processes. Submissions were also made to the Minister and Oversight to inform them of the vacancy rate per respective branch and DDGs were required to ensure that the vacancy rate is decreased in their respective Branches. |  | Line managers delay the filling of vacant posts by not submitting the Application to Fill a Post form timeously. A further challenge in the filling of vacancies is when line managers do not commit themselves to identified shortlisting and interview dates. |
|  |  |  |  | Fisheries: The Branch continues to experience challenges in filling of posts due to 8% [i.e. 66] of the total post establishment [i.e. 777] being unfunded. Of the 50 appointments made, 41 were FCOs whose contracts ended and they were appointed permanently & 2 internal promotions. This did not have any impact on the vacancy rate as only 7 of 50 were newly appointed. |  |  |
|  |  |  |  | DAFF: The vacancy rate was 13% at the end of Quarter 1. |  |  |
|  |  |  | Approved jobs evaluated. | Agriculture & Forestry: During the reporting period the job evaluation results of 1028 posts were approved by the relevant delegated authorities. |  | The availability of line managers to provide relevant information for the job evaluation process. Misperceptions of employees on the purpose of job evaluation. |
|  |  |  |  | Fisheries: No jobs were evaluated during the period under review. Focus has been on Phase 1 of the implementation of Resolution 1 of 2012. |  | No jobs evaluated during the period under review. Focus has been on Phase 1 of the implementation of Resolution 1 of 2012. |
|  |  |  | Improve turn-around times on verification process. | Agriculture & Forestry: The average turnaround time for SAQA to verify qualifications before an appointment could be made was reduced from 4 months to 38 working days. The average turnaround time for SSA to verify criminal and citizenship verifications through the Director: Security Services were also reduced from 4 months to 29 working days. The reduction in the turnaround times was as a result of regular interaction and follow-ups with the service providers. |  | The verification processes still takes almost 2 months to be finalised. The processes are not within the control of the D:HRM as it is dependent on the two service providers and the availability of the Director: Security Services. |
|  |  |  |  | Fisheries: On average, SAQA verifications are taking 6-weeks to be returned. SSA (Criminal & Citizenship Record) takes approximately 8 weeks. |  | Employment offers tend to be delayed due to the time-lag taken to receive verification reports. |
| 6 | 3 | Integrated Human Resource Management Plan submitted to DPSA and implemented. | Work Place Skills Plan developed. | Agriculture & Forestry: Work Place Skills Plan was developed and approved. A total of 28 employees were awarded bursaries in various fields of study. A total of 58 employees were registered for ABET. A total of 99 employees (level 1-12) attended induction programme. A total of 178 employees attended generic programmes and 91 workshops, conferences and seminars as part of skills programmes. |  |  |
|  |  |  |  | Fisheries: Branch WSP approved and 10% of Q1 identified training interventions completed. |  |  |
|  |  |  | 100% submission of Performance Agreements. | Agriculture & Forestry: 58% of Performance Workplans (levels 1-12) submitted. 75% of Performance Agreements (SMS members) submitted. |  | Non-compliance by managers and employees to the EPMDS timelines. |
|  |  |  |  | Fisheries: 443 employees have submitted their Work- plans in respect of the 2013/14 financial year cycle. This translates to a 70% compliance rate. |  | It is now three months into the new financial year and in spite of several reminders sent out to both employees and their Senior Managers, 188 employees have still not complied. |
|  |  |  | 100% submission of moderated annual assessment reports monitored. | Agriculture & Forestry: 88% submission of bi-annual reports. |  | Non – compliance by moderation committees. Incomplete documents submitted by the moderation committees. Employees refusing to sign the assessment reports. |
|  |  |  |  | Fisheries: 18 employees have failed to submit their second bi-annual performance documentation to HR. |  | Strong consideration should be given towards initiating corrective measures against those who are non-compliant in accordance with the departmental EPMDS policy. |
| 6 | 3 | Integrated Human Resource Management Plan submitted to DPSA and implemented. | Conduct management intervention implemented in Mpumalanga Region. | Skills Audit for SMS members was conducted and a draft employee handbook was also developed as these will assist in preparation and prioritisation of implementing management intervention in identified provinces going forward. |  |  |
|  |  |  | Review Strategic HRP Submission to DPSA via the DG and the Minister. | The HRP was submitted to the Minister for approval. | The target was not met as approval is awaited from the Minister for the HRP to be submitted to the DPSA. | The late submission by task team members also hampered/delayed the process of approval. |

### Sub-programme: Chief Information Office

| Sub-programme: Chief Information Office |  |
| --- | --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 6 | 5 | MSP implemented. | Secure DEXCO approval for MSP Phase 1 (Business articulation report and current ICT assessment report). | Fisheries: MSP Phase 1 and 2 (Business articulation report and current ICT assessment report): Completed and accepted by the Chief Directorates. |  | Only the final MSP (Phases 1 to 5) will be approved by DEXCO. All phases need to be completed to have a complete MSP document that can be approved by DEXCO. |
|  |  |  | ICT strategy context document (phase 3) developed and approved by Chief Director. | Fisheries: MSP Phase 3 (Business ICT alignment): Completed. - ICT Strategy context document developed and approved by Chief Director. |  |  |
| 6 | 5 | KIM Strategy implemented. | EDMS software options testing phase. | Various service providers were invited to demonstrate software capabilities and another demonstration on the suitable workflow was presented to senior management. . |  |  |

### Branch: Policy, Planning, Monitoring and Evaluation

### Sub-programme: Policy Planning and Development

| Sub-programme: Policy Planning and Development |
| --- |
| SG | SO | Performance Indicator | Quarter 1Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 6 | 2 | Programme/project decision support management system implemented. | Programme/project decision support management system approved by DEXCO. | A proposed project management methodology was devised and tabled at a meeting (14th June 2013) of DAFF directorates. Amendments to the methodology were recommended. The amended project management methodology by DAFF directorates was workshoped with provinces on the 26-27 June 2013. Amendments were recommended and resolutions taken to incorporate amendments, set up a national project management working group, and have the methodology go through DEXCO approval. Amendments were made as recommended by provinces and further discussed at the 1st meeting of the project management working group held 25 July 2013. ToR for a project management working group was also discussed. Resolutions include a joint meeting between the working group and CASP office. |  |  |
| 6 | 2 | 2014-2019 MTSF plan approved. | Draft MTSF plan compiled. | Workshops and meetings have been held with key national departments, in particular DRDLR and Environmental Affairs, to get same understanding. Inputs have also been sourced from PDAs. Draft MTSF for Outcomes 7 and 10 will be discussed further for approval in the coming QRM. |  |  |

### Sub-programme: Monitoring and Evaluation

| Sub-programme: Monitoring and Evaluation |
| --- |
| SG | SO | Performance Indicator | Quarter 1Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 6 | 2 | CASP and MAFISA evaluated. | CASP and MAFISA ToRs for evaluation approved by Steering Committee. | The Terms of References for both CASP and MAFISA have been approved by Steering Committee. These evaluation studies will be carried through the National Evaluation Plan coordinated by the Presidency. |  |  |

### Branch: Stakeholder Relations, Communication and Legal Services

### Sub-programme: Legal Services

| Sub-programme: Legal Services |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 6 | 3 | Legislation review project completed. | Advertisement of 9 Bills for public comment and public consultations with stakeholders on legislation. | The following bills were published for public comments: Plant Breeders Rights' Amendment Bill National Animal Pounds Bill Marketing of Agricultural Products Amendment Bill National Forest Amendment Bill National Veld and Forest Fire Amendment Bill Agricultural Produce Marketing Agency Bill Plant Improvement Bill Marine Living Resource Amendment Bill Conservation of Agricultural Resources Amendment Bill. |  |  |
|  |  |  | NEDLAC and government cluster process followed and 11 Bills forwarded to State Law Advisor for pre- certification. | The following Bills are currently being finalised by the directorate concerned and/or with the State Law Advisor and/or on their way to Parliament: Marine Living Resources Amendment Bill. Conservation of Agricultural Resources Amendment Bill. Liquor Products Amendment Bill. Agricultural Products Standards Amendment Bill. Agricultural Research Council Amendment Bill. Perishable Products Export Control Bill. Protection and Development of Agricultural Land Framework Bill. National Forest Amendment Bill. National Veld and Forest Fire Amendment Bill. Plant Breeders Rights Bill. Plant Improvement Bill. |  |  |
|  |  |  | Submit 7 Bills to relevant unit for submission to Minister and Cabinet for approval. | 7 Bills could not be submitted to the relevant Directorate for submission to the Minister. |  |  |

### Branch: Chief Financial Office

### Sub-programme: Financial Management

| Programme / Sub-programme: Chief Financial Office |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 6 | 3 | Improved financial management control. | Submit unaudited annual financial statements to National Treasury (NT) and Auditor- General (AG) by 31 May 2013. | Submitted unaudited annual financial statements to National Treasury and Auditor- General by 31 May 2013. |  |  |

# PROGRAMME 2: AGRICULTURAL PRODUCTION, HEALTH AND FOOD SAFETY

Purpose

Manage the risks associated with animal diseases, plant pests, genetically modified organisms (GMOs) and registration of products used in agriculture; promote food safety and create an enabling environment for increased and sustainable agricultural production.

The programme comprises three sub-programmes, namely Plant Production and Health; Animal Production and Health; and Inspection and Laboratory Services.

Strategic goals and strategic objectives:

- SG 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 1: Promote efficient production, handling and processing of food, fibre and timber.

- SG 2: Sustained management of natural resources

SO 1: Ensure protection of indigenous genetic resources.

- SG 3: Effective national regulatory services and risk management systems

SO 2: Establish and maintain effective early-warning and mitigation systems.

### PERFORMANCE AGAINST QUARTERLY TARGETS

### Sub-programme: Animal Production and Health

| Sub-programme: Animal Production and Health |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 1 | 1 | Number of producers benefiting from animal improvement schemes. | 325 | 179 | 146 | Demand driven service, therefore the target achieved is affected by the interest from farmers to be part of the scheme. |
| 3 | 2 | Planned surveillance conducted. | Plant and animal disease surveillance programmes as required. | Avian Influenza Surveillance is continuing. Preparations for distribution of 878 sampling boxes for the national survey on pig diseases completed. |  |  |

### Sub-programme: Plant Production and Health

| Sub-programme: Plant Production and Health |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 2 | 1 | Number of indigenous agricultural genetic resources conserved. | Consult ARC, Breeders’ Societies and Universities. | Officials from ARC-Animal Improvement Institute have been consulted and briefed about the project. Officials from KZNDAE (Directors, DDs and Animal Scientists) who work with farmers in Zululand and uMkhanyakude and officials from the University of Zululand were also consulted during May 2013. Constructive inputs were noted and a dual programme of action was developed. A meeting with Managers of Livestock Development Centres and subsistence Afrikaner cattle farmers from Dr. Ruth Segomotsi Mompati District was convened. A meeting with officials from EmbyoPlus Ex Situ centre was successfully convened. |  |  |
|  |  |  | Initiate project with Provincial Departments. | The KZNDAE and NWDARD was formally notified about the programme on in situ conservation of Zulu sheep in KZN. SLA between DAFF and ARC has been signed that addresses the in situ conservation of Afrikaner cattle and Zulu sheep. |  |  |
| 3 | 2 | Planned surveillance conducted. | Document and analyse surveillance results. | Official notification and media release regarding the status of the fruit fly in South Africa surveillance and control actions was amended. The Vhembe district was declared as an area where B. invadens is present and R110 will be amended to indicate the status of this district. The rest of South Africa is considered to be free from this pest and movement control actions were implemented through D: Inspection Services for produce from this district. However, surveillance results have indicated several other areas in the country where B. invadens was recorded. These areas were evaluated and control has been implemented with the objective to eradicate this pest from these areas. |  |  |

### Sub-programme: Quarantine and Inspection Services

| Sub-programme: Quarantine and Inspection Services |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 3 | 1 | Number of regulatory compliance and monitoring interventions implemented. | Conduct inspections, surveys, investigations, take appropriate action and compile report. | An inspection report on the regulatory compliance and monitoring interventions was compiled. |  |  |

# PROGRAMME 3: FOOD SECURITY AND AGRARIAN REFORM

PURPOSE

The programme facilitates and promotes household food security and agrarian reform programmes and initiatives targeting subsistence and smallholder producers. It comprises three sub-programmes, namely, Food Security, Sector Capacity Development and Extension Support Services.

Strategic goals and strategic objectives:

- SG 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 1: 	Promote efficient production, handling and processing of food, fibre and timber.

- SG 4: A transformed and united sector

SO 4:	Provide leadership and support to research, training and extension in the sector.

### PERFORMANCE AGAINST QUARTERLY TARGETS

### Sub-programme: Food Security

| Sub-programme: Food Security |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 1 | 1 | Number of subsistence farmers supported. | 20 000 | 792 subsistence farmers supported (Q1) Distribution of subsistence farmers supported per province: Free State: 89 household gardens and 26 community gardens. Limpopo: 30 household gardens and 4 community gardens. Mpumalanga: 4 community gardens. KZN: 59 households gardens and 11 community gardens. Western Cape: 7 household gardens and 1 community garden. Eastern Cape: 49 household gardens. North West: 450 household gardens. Northern Cape: 23 household gardens and 16 community gardens. Gauteng: 23 household gardens. | 19 208 | Provinces are preparing for the implementation of the approved projects. Procurement needs take first priority during this Quarter. Winter production season requires irrigation if any production has to happen. |
| 1 | 1 | Number of smallholder producers supported. | 3 000 | A total of 3 009 smallholder producers received support in the form of advisory services and the details are as follows: Mpumalanga: 847 Limpopo: 70 KwaZulu-Natal: 555 Western Cape: 0 (reported number of projects only) Eastern Cape: 802 Gauteng: 23 Northern Cape: 0 Free State: 276 North West: 436. |  |  |
| 1 | 1 | Number of infrastructure anchor projects established. | Collecting existing planning criteria and compare to international best practices. | Existing planning documents collected from the provinces involved. Attended meetings held regarding the anchor projects. |  | The engineering staff in the Directorate could not interrogate the material effectively due to the commitment to complete the Lesotho border road specification. |

### Sub-programme: Sector Capacity Development

| Sub-programme: Sector Capacity Development |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 4 | 4 | Number of Colleges of Agriculture accredited by CHE. | Conduct needs analysis for Tsolo and Potchefstroom Colleges. | Conducted needs analysis for Tsolo and Potchefstroom Colleges. |  |  |

# PROGRAMME 4: ECONOMIC DEVELOPMENT, TRADE AND MARKETING

Purpose

Ensure value chain integration; facilitation of market access for agriculture, forestry and fisheries products in support of economic growth, job creation and development.

The programme comprises the following three sub-programmes, namely International Relations and Trade; Agro-processing and Marketing; and Cooperatives and Rural Enterprises Development.

Strategic goals and objectives:

SG 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 2: 	Coordinate government food security initiative.

SG 5: Increased contribution of the sector to economic growth and development

SO 1:	Increase growth, income and sustainable job opportunities in the value chain.

SO 3:	Increase domestic and international market access for South African and African agricultural, forestry and fisheries products.

### PERFORMANCE AGAINST QUARTERLY TARGETS

### Sub-programme: Agro-Processing and Marketing

| Sub-programme: Agro-Processing and Marketing |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 5 | 1 | Agro-processing Strategy implemented. | Undertake feasibility studies for two agro-processing projects. | Project number 1. The feasibility study for establishing Wool processing plant at Elundini municipality has been completed and it will be tabled to stakeholders for their comments/input. Project number 2. The undertaking of a feasibility study to establish fresh produce (fruit and vegetables) processing plant in Greater Letaba Municipality could not be completed as planned. |  |  |
| 5 | 1 | Marketing Strategy Implemented. | Meetings of the network and its working groups; report on the outcomes of the network facilitated. | One meeting of the Aquaculture Intergovernmental ad hoc working group on aquaculture legislation was held. |  |  |

### Sub-programme: Cooperatives and Rural Enterprise Development

| Sub-programme: Cooperatives and Rural Enterprise Development |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 1 | 2 | Number of commodity based cooperatives established and supported. | 1 | One Commodity Based Cooperative has been established in the Western Cape to process fish harvested by primary cooperatives in the area (Houtbay Community Fishers Secondary Cooperative Limited (Registration number 2013/009029/25). |  |  |

### Sub-programme: International Relations and Trade

| Sub-programme: International Relations and Trade |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 5 | 3 | International Relations Strategy implemented. | Implementation of bilateral and multilateral engagements and new agreements facilitated (capacity building, market access and technical assistance. | BRICS: Concept notes for both the Climate Change seminar and Agricultural Economics Working Group meetings have been developed and sent to DIRCO. DIRCO has been requested to invite the members and they have subsequently invited the BRICS members. IBSA: In line with the implementation of the IBSA Action Plan, DAFF succesfully facilitated Plant Health, Inspection Services, Forestry and Climate Change, to attend a Workshop on Harmonisation of Methodologies on Pest Risk Analysis, which took place on 5-7 June 2013 in India. PROTOCOLS TO BE SIGNED: As a result of the signed overarching agreement with China, DAFF is currently working on two protocols to facilitate market access: (a) Wool protocol (b) Maize protocol TAIWAN (Arrangement signed in April 2013). MEXICO (draft agreement). ARGENTINA (signed agreement 6 June 2013). Coordinated the signing of an agreement between SA and Argentina on the 6 June 2013. MULTILATERAL ENGAGEMENTS FAO: Facilitated and attended a meeting with FAO, DAFF and DIRCO to discuss Country Programming Framework and Partnership Agreement, 8-10 May 2013. IFAD: Facilitated a meeting between the Minister and IFAD President to discuss issues of mutual interest May 2013. OECD: Solicited advice from DIRCO and DAFF Legal Advisor on the proposed MoU on capacity building. |  |  |
| 5 | 1 | Trade Development Strategy implemented. | Negotiating mandate approved. | A progress report on the negotiations for the quarter has been written and will be forwarded to Minister and Management on 23 July 2013. |  |  |

# PROGRAMME 5: FORESTRY AND NATURAL RESOURCES MANAGEMENT PROGRAMME

PURPOSE

Develop and facilitate the implementation of policies and targeted programmes to ensure management of forests, sustainable use and protection of land and water as well as managing agricultural risks and disasters.

There are three sub-programmes in the Forestry Programme, namely Forestry Operations; Forestry Development and Regulations; and Natural Resources Management.

Strategic goals and objectives:

- SG 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 2: Coordinate government food security initiative.

- SG 2: Sustained management of natural resources

SO 1: Ensure the sustainable management and efficient use of natural resources.

- SG 3: Effective national regulatory services and risk management systems

SO 2: Establish and maintain effective early-warning and mitigation systems.

- SG 5: Increased contribution of the sector to economic growth and development

SO 2: Increase the level of public and private investment in the sector.

### PERFORMANCE AGAINST QUARTERLY TARGETS

### Sub-programme: Forestry Operations

| Sub-programme: Forestry Operations |
| --- |
| SG | SO | Performance Indicator | Quarter 1Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 1 | 2 | Number of smallholder producers supported. | 350 | 307 small growers supported (KZN =14, MP&L=60, EC=91, other regions 142). | 43 |  |
| 2 | 1 | Increased number of hectares rehabilitated. | 150 ha | 15 ha planted at Sokhulu plantation. | 135 | The planting in KZN and other regions will take place in Quarters 3 & 4 as this is in the rainy season. |

### Sub-programme: Forestry Development and Regulations

| Sub-programme: Forestry Development and Regulations |
| --- |
| SG | SO | Performance Indicator | Quarter 1Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 2 | 1 | Charter undertakings implemented. | Appoint service provider to develop toolkits to enhance the potential of the SMMES and rolling out pilot training programmes in the forestry sector. | The service provider was appointed to develop toolkits. |  |  |
|  |  |  | Develop implementation plan in consultation with regions. | Workshops were held in all the forestry regions and draft implementation plans were developed. |  | Time constraints to schedule the national workshop. |

### Sub-programme: Natural Resources Management

| Sub-programme: Natural Resources Management |
| --- |
| SG | SO | Performance Indicator | Quarter 1Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 1 | 2 | Number of hectares (agricultural land, woodlands and indigenous forests) rehabilitated. | 2 125 ha | Total of 1139.92 hectares we rehabilitated of which 856 ha is agricultural land and 283, 92 ha is state indigenous forests. |  | Due date for Provinces to submit their quarterly reports is 31 July 2013; therefore the status reported will be updated as soon as all reports are available. |
| 1 | 2 | Increase the number of hectares of irrigation schemes revitalised. | 10 ha | 10 ha revitalized at Vaalharts irrigation scheme. | - | Hectares could not be been revitalized at Makhathini due to provincial processes. |
| 1 | 2 | CC adaptation and mitigation plans implemented. | Collate proposals for the implementation plans. | Project proposals for the implementation of the plans have been collated. Call for project proposals were issued and expression of interest was received from a potential service provider. Process of appointing the service provider underway. |  |  |

# PROGRAMME 6:  FISHERIES MANAGEMENT

PURPOSE

Promote the development, management, monitoring and sustainable uses of marine living resources and the development of South Africa’s fisheries sectors. Sustainable livelihoods will be achieved through aquaculture growth and fisheries economic development.

The programme comprises four sub-programmes, namely Aquaculture and Economic Development; Fisheries Research and Development; Marine Resource Management; and Monitoring, Control and Surveillance.

STRATEGIC INTERVENTION:

- Facilitate investment in the production and support of infrastructure for aquaculture and fisheries

- Support the development of small-scale fisheries

- Advance transformation of fisheries

- Maintain the productivity of fish stocks and ecosystems; and rebuild depleted fish stocks

Strategic goals and objectives:

- SG 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 2: Coordinate government food security initiative.

- SG 2: Sustained management of natural resources

SO 1: Ensure the sustainable management and efficient use of natural resources.

- SG 5: Increased contribution of the sector to economic growth and development

SO 1: Increased growth, income and sustained job opportunities in the value chain.

### Sub-programme: Aquaculture Management

| Sub-programme: Aquaculture Management |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 1 | 2 | Number of fish farms supported. | Technical assessment of 5 business plans and compliance assessments conducted on 5 fish farms. | Technical assessments conducted for 6 business plans. 5 business plans were assessed for support through the Aquaculture and Enhancement Development Programme (ADEP) and one for CASP support for a proposed catfish project in Pixley Ka Seme District Municipality in the Northern Cape. The business plans assessed for ADEP applications were: - Abagold (Pty) Ltd: Abalone farm expansion, Hermanus, Western Cape. - Blue Cap General Trading (Pty) Ltd: Dusky kob farm expansion, Paternoster, Western Cape. - Aloe Creek Aquaculture CC: Tilapia farm expansion, Cullinan, Gauteng. - Gapwedge Properties 63 (Pty) Ltd: Concept for finfish farm, Pearly Beach, Western Cape. - Malmesbury fishmeal: agro-processing. |  |  |

### Sub-programme: Monitoring, Control and Surveillance

| Sub-programme: Monitoring, Control and Surveillance |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 2 | 1 | Enforcement and compliance measures to combat poaching improved. | 160 sea-based inspections of vessels conducted in 4 priority fisheries. | Sea-based inspections of vessels conducted in 4 priority sectors: 154 Hake: 0 Abalone: 27 Rocklobster: 93 Linefish: 34 Other sectors where sea based inspections were carried out: 106 | Under achievement of 6 sea-based inspections. | Vessels were handed over from the South African Navy on 7 May 2013, and work commenced to prepare the vessels for sea. Inclement weather was a challenge. Small crafts are restricted in their distance out to sea. |
| 2 | 1 | Enforcement and compliance measures to combat poaching improved. | 73 investigations conducted on rights holders in 4 key fisheries sectors. | Rights holders investigated in 4 priority sectors: 76 Hake: 14 Abalone: 12 Rock lobster: 34 Line fish: 16 Other sectors where right holders were investigated: 4 A total of infringing 45 non rights holders were also investigated |  |  |
| 2 | 1 | Enforcement and compliance measures to combat poaching improved. | Conduct 157 inspections on vessel landings in 4 key fisheries sectors. | Total number of vessels inspected in 4 priority sectors: 374 Hake: 79 Abalone: 59 Rock lobster: 97 Line fish: 139 Other sectors where investigations on vessel landings were carried out: 591 | Overachievement of 217 vessels inspected. | Line fish vessels increased the number of sea going vessels due to Easter Holidays and good weather permitting for fishing activities. Also Abalone sector fishing season started from December 2012 to July 2013. Abalone vessels start to increase their fishing activities from March to July pushing to finish their quota before 31 July. Number of vessels increased during April to June 2013. Also Foreign vessels that are visiting South African ports increased during April and June period and these vessels they bring large pelagic fish such as Tuna. |

### Sub-programme: Marine Resources Management

| Sub-programme: Marine Resources Management |
| --- |
| SG | SO | Performance Indicator | Quarter 1 Planned Target | Quarter 1 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations |
| 2 | 1 | Depleted fish stocks rebuilt (abalone, West Coast rock lobster and Line fish). | Formulate TAE recommendations for Line fish. | Line fish TAE approved. |  |  |
|  |  |  | Review permit conditions for Line fish. | Line fish permit conditions revised and approved. |  |  |
| 5 | 1 | Increased support to SMMEs within the sector. | Revise the general fishing policy and 8 sector specific fishing policies in the inshore and high seas fisheries sectors. | Draft revised General and sector specific policies published in the Government Gazette. |  |  |
| 2 | 1 | Depleted fish stocks rebuilt (abalone, West Coast rock lobster and Line fish). | Reconciliation of allocations and landings. | Preliminary catch data received from one (1) rights holder in the deep-sea hake sector and from one (1) rights holder in the hake longline sector. All rights holders in the hake (deep-sea, inshore trawl, longline and handline) sector must submit their summary of landings for the period 1 January 2013 to 30 June 2013 on 31 July 2013. | The hake fishing season is from 1/1/2013 to 31/12/2013. Rights holders will submit their summary of landings for the period 1/1/2013 to 30/6/2013 on 31 July 2013, after which the bi-annual reconciliation for the hake sector can be finalised. | The due date for the submission of the rights holders’ summary of landings falls within Q2 and as such reconciliation can only be finalised after 31/7/2013. |
|  |  |  | Update the capacity management models. | Models updated for hake sector (deep-sea, inshore trawl and longline). No capacity management model kept for hake handline as it is managed as a total applied effort (TAE) fishery. |  |  |
| 5 | 1 | Increased support to SMMEs within the sector. | Revise the general fishing policy and 8 sector specific fishing policies in the offshore and high seas fisheries sectors. | Draft revised general and sector specific policies published in the Government Gazette. |  |  |

### ADDITIONAL INDICATORS AT SUB-PROGRAMME LEVEL

| Sub-programme: Monitoring, Control and Surveillance |
| --- |
| Strategic Goal | Strategic Objective | Performance Indicator | Actual Performance against Target | Reason for Variance |
|  |  |  | Annual Target | Actual against Target |  |
| Sustained management of natural resources. | Ensure the sustainable management and efficient use of natural resources. | Enforcement and compliance efforts to combat poaching increased. | Facilitate approval and implementation of the Integrated Fisheries Security Strategy (IFSS). | Facilitate Approval of IFSS: The draft IFSS is available with inputs from relevant stakeholders including Branch management. It is now being refined for presentation to DEXCO for approval. Implementation of Integrated Fisheries Security Strategy: During this Quarter, 76 rights holders were investigated in addition to 154 sea-based vessels inspected as well as 374 land based vessel inspection were conducted. | Due to repairs on the big patrol vessels of the Department the target for sea-based inspections could not be achieved for this Quarter. |

# CONCLUSION

The development of Branch monitoring and evaluation plans will go a long way in improving the quality of reporting and verification of performance information, which is critical in order to present credible reports that satisfy audit requirements. The annual targets have been broken down into quarterly targets and this will surely assist with the measurability of performance and the timeous need for corrective actions.

Generally, progress has been made during the quarter under review and as the trend indicates, the momentum will increase from Quarter 2, when it will be possible to make a fairly balanced assessment of the departmental state of performance. The submission of evidence and administratively assessing all reported information by Programme Managers to enhance the credibility of the reports cannot be over-emphasized. This is one of the important features in the reviewing of monitoring, evaluation and reporting guidelines that is currently in progress.