Directorate: Strategic Management, Monitoring and Evaluation,

Private Bag X 896,

Regent Place, 66 Queen Street,

Pretoria: Tel: 012 304 5175

ORGANISATIONAL PERFORMANCE REVIEW REPORT

QUARTER 1: 2013/14 FINANCIAL YEAR

April–June 2013

TABLE OF CONTENT

1.	INTRODUCTION	3

2.	LIST OF PROGRAMMES AND PEFORMANCE INFORMATION	4

2.1	PROGRAMME 1: ADMINISTRATION	4

2.1.2	PERFORMANCE INFORMATION	6

2.1.3	LIST OF COMPLIMENTARY DOCUMENTS	14

2.1.4	STRATEGIC CHALLENGES	16

2.2	PROGRAMME 2: SPORT SUPPORT SERVICES	18

2.2.1	SERVICE DELIVERY MAIN ACHIEVEMENTS	19

2.2.2	PERFORMANCE INFORMATION	20

2.2.3	LIST OF COMPLEMENTARY DOCUMENTS	23

2.3	PROGRAMME 3: MASS PARTICIPATION	24

2.3.1	SERVICE DELIVERY ACHIEVEMENTS	25

2.3.2	PERFORMANCE INFORMATION	26

2.3.3	LIST OF COMPLIMENTARY DOCUMENTS	29

2.4	PROGRAMME 4: INTERNATIONAL LIAISON AND EVENTS	30

2.4.1	SERVICE DELIVERY MAIN ACHIEVEMENTS	31

2.4.2	PERFORMANCE INFORMATION	32

2.5.1	LIST OF COMPLIMENTARY DOCUMENTS	34

2.6	PROGRAMME 5: FACILITIES COORDINATION	35

2.6.1	SERVICE DELIVERY ACHIEVEMENTS	36

2.6.2	PERFORMANCE INFORMATION	37

2.6.3	LIST OF COMPLIMENTARY DOCUMENTS	38

3. OVERALL ORGANISATIONAL PERFORMANCE	39

4.	PROBLEM AREAS	40

5.	CONCLUSION	41

# INTRODUCTION

Government legislation requires that Cabinet members provide Parliament with full and regular reports concerning matters under their control and to also be transparent and accountable to the public in accordance with Section 195 of the Constitution of the Republic of South Africa, Act 108 of 1996. As a response to these requirements, the Department through the Directorate: Strategic Management, Monitoring and Evaluation, has compiled the organisational performance report for quarter 1 of the 2013/14 financial year.

The purpose of the report is to give an overview of what transpired in the first quarter of the 2013/14 financial year.

The report reflects performance against key strategic objectives and annual performance indicators as reflected in the Department’s Annual Performance Plan for 2013/14.

It further provides a reflection on additional services rendered in the period under review and also highlights achievements and key challenges experienced.

# 2.	LIST OF PROGRAMMES AND PEFORMANCE INFORMATION

## PROGRAMME 1: ADMINISTRATION

The purpose of the programme is to provide management, strategic and administrative support services. It comprises of 7 sub-programmes namely Ministry; Management; Strategic & Executive Support; Corporate Services; Chief Financial Officer; Internal Audit; and Office Accommodation.

Performance Graph

There were 19 targets to be achieved by the programme during the quarter under review;

Sixteen (16) achievements were reached with one (1) of them exceeded. One of the achievements made (in Marketing & Communication) was not targeted for in this quarter. Three (3) targets were not achieved; and one (1) is reported as ‘not applicable’ because it is dependent on lodging of grievances.

    - SERVICE DELIVERY MAIN ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| Ministry | 3 community outreach programmes (Mitchell’s Plain, Carolina, and Mabopane) were initiated and attended instead of 2 |  |  |  |
| Management | Published 2010 World Cup Report Managed and provided support to the Minister's budget vote programme Managed and provided support to the Minister's NCOP budget statement programme Provided assistance to sports entities to finalise Lottery Applications Consulted on and completed the Grant submission to National Treasury for MIG funding. Collaborative Agreements were signed by the DG with the provincial HoDs to assist integration of key elements of the sport and recreation service delivery plans of SRSA into those of provinces. |  |  |  |
| Strategic Executive Support | A very comprehensive mapping exercise was undertaken to clarify what funds are available for project allocation in 2013/14. The National Development Plan was scrutinised for areas where sport and recreation can possibly be used as a vehicle to achieve some of the key objectives of the NDP. A concise document was compiled highlighting these areas and it was distributed to all staff to alert them to the priorities of Government. The budget programme structure for 2014/15 was aligned with the NSRP and approved by National Treasury for implementation in the MTEF. The fourth quarter Outcome 12 b progress report was submitted with SRSA achievements. Service Delivery Improvement Plan (SDIP) annual progress report for 2012/13 was compiled and submitted to the EA. The 4th quarter performance summary and consolidated performance report for the 4th quarter of 2012/13 were finalised, presented to QSRM, and submitted to the EA. The first draft of the 2012/13 Annual Performance Report was compiled and submitted to the Auditor-General and Treasury by end of May 2013 as required. |  |  |  |
| Corporate Services | Marketing & Communication The unit Launched Sport in the Struggle Exhibition and supported the: - Seminar on the World Cup Close-Up Report and the related TNA Breakfast - Budget Vote (National Assembly & NCOP) activities in the Western Cape (school visits, the Gym handover at Mitchell’s Plain, Budget Vote Lunch Cocktail and the Gala Dinner) - Soweto Open. |  |  |  |
| Chief Financial Officer | Met all the set targets for quarter 1: 6 service provider databases operational; 1 asset reconciliation report signed off; and 3 financial reports submitted in line with prescripts. |  |  |  |
| Internal Audit | None |  |  |  |
| Office Accommodation | None |  |  |  |

### PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan.

| Performance indicator | Reporting period | Target for 2012/13 as per Annual Performance Plan (APP) | 1st Quarter Planned target as per APP | Actual | Status On Achievements | Cumulative Information | Reasons For Deviation | Corrective Actions And Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-programme: Ministry |
| Political and legislative mandate delivered. |
| Number of Collaborative Agreements signed with Provinces. community outreach | Annual | 9 | No target | N/A | N/A | N/A | None | None |
| Number of community outreach and sport promotion activities attended. | Quarterly | 8 | 2 | 3 Mabopane Carolina Mitchell’s Plain | Exceeded | 3 | A need to engage with 1 more community in view of the Minister’s availability, was identified. | None |
| Sub-programme: Management |
| Sub-programme: Management: Strategic guidance, administrative support and financial accountability imparted |
| Management Performance Assessment Tool (MPAT) rating. | Annual | 4 | No target | N/A | N/A | N/A | None | None |
| Institutional performance managed. |
| Number of Institutional performances reports overseen. | Quarterly | 34 | 8 | 8 | Achieved | 8 | None | None |
| Sub-programme: Strategic and Executive Support |
| Strategy managed |
| Number of strategic documents completed. | Bi-annual | 5 | 1 | 1 (Programme of Action – Outcome 12(b) 2010-2014 (SRSA input) | Achieved | 1 | None | None |
| Electronic Monitoring and Evaluation systems developed and implemented. |
| Number of electronic monitoring and evaluation systems implemented. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Number of institutional performance reports produced. | Quarterly | 7 | 1 | 1 The consolidated and executive summary performance information reports for quarter 4 of the 2012/13 financial year were compiled, presented to QSRM and submitted to EA. | Achieved | 1 | None | None |
| Number of annual NSRP implementation progress reports produced. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Sub-programme: Corporate Services |
| SRSA promoted through marketing and communication |
| Number of sport and recreation promotion campaigns launched. | Quarterly | 3 | No target | 3 National Assembly Budget Vote NCOP Budget Vote 2010 WC Seminar & related breakfast | Achieved | 3 | Campaigns were not planned; they only came ad hoc | Plan future campaigns |
| Number of client satisfaction surveys conducted (external). | Annually | 1 | No target | N/A | N/A | N/A | None | None |
| Number of Sports Awards hosted. | Quarterly | 1 | No target | N/A | N/A | N/A | None | None |
| Number of Little Green Books published. | Annually | 1 | No target | N/A | N/A | N/A | None | None |
| Legal advice services provided. |
| Number of legal services status reports signed off. | Quarterly | 4 | 1 | 1 | Achieved | 1 | None | None |
| Human Resources effectively utilized. |
| Turnaround time on posts filled. | Quarterly | 6 months | 6 months | 6 months One of the 40 positions that were advertised during the last quarter of 2012/13 was filled in this quarter (within the 6 months period). | Achieved | 6 months | None | None |
| Number of employees trained | Quarterly | 100 | 25 | 5 | Not achieved | 5 | The plan was to train new recruits in view of the existing vacancies. However, a decision was taken later to advertise the posts internally. The posts were thus filled with people, who did not require induction. | Training will be conducted during the 2nd quarter |
| Number of Health & Wellness programmes conducted with SRSA staff. | Quarterly | 12 | 3 | 0 | Not achieved | 0 | The review of the strategy to have a creative way to conduct EHWP. | Wellness programmes plan to be reviewed and costed for implementation in the 2nd quarter |
| Number of staff satisfaction surveys conducted (internal). | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Reliable and efficient ICT and knowledge management systems provided. |
| Number of Master System Plans developed, approved and maintained. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Number of status reports on the upgrading of the ICT system signed off. | Quarterly | 4 | 1 | 1 out of the 5 reports that have to inform the said status report, approved. The reports are: Microsoft vs Novel Anti virus package – licensing & upgrading SITA SLA Network Printing Audio-visuals | Not Achieved | - | Four ITC issues as listed under ‘actual’ awaits management decision | Finalisation of the outstanding ITC issues |
| Number of Information Management Systems developed, approved and maintained. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Sound labour relations created and promoted. |
| Turnaround time to resolve grievances | Quarterly | 30 days | 30 days | N/A | N/A | - | No grievance was received | None |
| Infrastructure, logistical, security and office support service rendered |
| Number of reports on active Service Level Agreements overseen and signed off. | Quarterly | 12 | 3 | 3 | Achieved | 3 | None | None |
| Sub-programme: Chief Financial Officer |
| Sound financial and management accountability ensured |
| Number of financial reports submitted in line with prescripts. | Quarterly | 31 | 6 | 6 | Achieved | 6 | None | None |
| A transparent procurement and asset management system compliant with regulations implemented. |
| Number of service provider databases operational. | Quarterly | 1 | 1 | 1 | Achieved | 1 | None | None |
| Number of asset reconciliation reports signed off. | Quarterly | 12 | 3 | 3 | Achieved | 3 | None | None |
| Sup-programme: Internal Audit. |
| Effective governance, risk management and control evaluated and improved. |
| Number of Internal Audit, Audit Committee and Risk Management Committee Charters reviewed and approved. | Annually | 3 | 3 | 3 a. Internal Audit Charter was reviewed and approved by the AC and endorsed by the DG. b. Risk Management Committee Charter was reviewed and approved by the DG. c. Audit Committee Charter has been reviewed and is still on the process of approval by the Minister. | Achieved | 3 | None | None |
| Number of Internal Audit and Risk Management Plans approved and implemented. | Quarterly | 2 | 2 | 2 a. Internal Audit plan has been developed and approved by the Audit Committee. b. Risk Management Implementation plan has been developed and the Risk Management Committee has recommended for approval by DG. | Achieved | 2 | None | None |
| Number of reports presented to the Audit Committee & Risk Management Committee. | Quarterly | 8 | 2 | 2 a. Internal Audit quarterly report and Risk Management quarterly reports have been prepared however will only be presented to the Risk Management Committee Meeting and Audit Committee to be held on the 07 August and 13 August 2013 respectively. | Achieved | 2 | None | None |
| Sub-programme: Office Accommodation. |
| Office accommodation managed. |
| Turnaround time for payments for rental and rates and taxes | Quarterly | 30 days | 30 days | 30 days | Achieved | N/A | None | None |
| Number of office relocation progress reports signed off. | Quarterly | 4 | 1 | 1 | Achieved | N/A | None | None |

### LIST OF COMPLIMENTARY DOCUMENTS

| Unit | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| Ministry | Reports on the community outreaches in Mabopane; Carolina; and Mitchell’s Plain |  |  |  |
| Management | Strategic Risk Assessment Report Executive Summary of Performance Review Task teams report X 3 DG’s executive summary X 3 Budget Vote and NCOP Report 2010 World Cup Report Assistance to sports entities to finalise Lottery Applications Completion of Grant submission to National Treasury for MIG funding 9 collaborative agreements signed with provinces. |  |  |  |
| Strategic Executive Support | Project-Budget map. NDP alignment document. Approved new budget programme structure 4th Quarter Outcome 12 b progress report. SDIP Report for 2012/13 2012/13 4th quarter performance summary 4th quarter consolidated performance report 2012/13 Annual Performance Report |  |  |  |
| Corporate Services | Legal: Legal services status report M&C: Media invites & statements Branding of events Programme and invites designed Promotional items procured Adverts placed in the print media HR: Proof of training for the 5 trained employees Proof of the post filled in the quarter under review. Auxiliary: Report on active Service Level Agreements overseen and signed off. Service Level agreements x 3 |  |  |  |
| Chief Financial Officer | Finance: IYM Data File for June April Dora report May Dora report June Dora report 2014 MTEF & MIG Submission Annual Report incl. performance information |  |  |  |
|  | SCM: Proof of operational service provider database. Asset reconciliation reports signed off |  |  |  |
| Internal Audit | Number of asset reconciliation reports signed off. |  |  |  |
| Office Accommodation | Executive summary for April 2013 Executive summary for May 2013 Executive summary for June 2013. |  |  |  |

### STRATEGIC CHALLENGES

| Programme | Challenge | Corrective Action | By whom | By When |
| --- | --- | --- | --- | --- |
| Strategic and Executive Support | General disregard of deadlines for submission of strategic inputs. | Implementation of disciplinary measures. | Top Management | Ongoing |
| Management | Monthly reports not tabled in time. | Follow up with Chief Directors | COO | Immediately after due dates |
| Marketing & Communication | Ad hoc events that happen and take place during the weekend without overtime compensation taken into account. | Overtime policy approval process should be finalised as this has an effect on the working and insurance of people's lives. Verbal instructions over weekend events endanger staff as anything could happen and without proper paperwork done, it brings up a lot of issues that may have been prevented. | HR |  |
|  | Filling of vacancies-The unavailability of selection committees to conduct recruitment processes are problematic and may result in HR not meeting the 6 month target. | The constitution of the selection committees should be reviewed and not have the same members serving on too many different committees. | DG | As soon as possible |

| 2.1.5. SUPPLEMENTARY PROJECTS |
| --- |
| Project name | Assigned by | Progress Report | Target Dates | Why not captured in APP? | Source of funding |
| Quarter 1 | CD: CS | 273 Subsistence and travel claims to the value of R 591 930.49 processed for reimbursement to staff |  | Not Auxiliary Services responsibility | All units |
|  |  | Minister’s Bursary signing ceremony |  | Ad hoc event |  |
|  |  | Sent-off of the USSA athletes to Russia |  | Ad hoc event |  |

| 2.1.6. PREVIOUS CORRECTIVE ACTIONS CLEARED |
| --- |
| ISSUES / CORRECTIVE ACTIONS RELATING TO THE PREVIOUS QSRM | TARGET DATE SET | ACTUAL |
| LEGAL: 1. Combat Sport Bill had to be redrafted via the instructions received from the DG. Legal Services have now completed a 1st draft of the Bill which in volume encompasses around 80 pages and will now embark on a process to refine the said draft Bill further in order to constitute a 2nd draft in the above regard. 2. Fitness Industry Bill need to be redrafted via the instructions received from the DG. Legal Services are now initiating actions to draft a 1st draft of the Bill. | 31-Jul-13 | Bill was redrafted completely |
|  | 30-Aug-13 | Bill will be redrafted completely |
| HR: Change the target for the filling of posts to 6 months in line with operational requirements. | 1 –April-13 | The APP has been adjusted to indicate the turnaround time on the filling of posts as 6 months |
| Filling of vacancies |  | 40 positions were advertised during the last quarter of 2012. Of the 40 positions in question, only one position was filled during the current quarter in a period of less than six months. Recruitment processes for the other positions are ongoing and will be reported on during the second quarter as it is still within the 6 month period. |

## PROGRAMME 2: SPORT SUPPORT SERVICES

The programme comprises of four sub-programmes which are Sport and Recreation Service Providers, Club Development, Education & Training and Scientific Support. The purpose of the programme is to support recognized sport and recreation bodies and public entities, and monitor and report on their performance.

Performance Graph

There were six (6) targets to be achieved by the programme during the quarter under review. Four (4) of the targets were achieved and 1 target exceeded. One (1) target was not achieved.

### SERVICE DELIVERY MAIN ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| Sport and recreation service providers | None |  |  |  |
| Scientific Support | None |  |  |  |

    - PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan

| Performance indicator | Reporting period | Target for 2012/13 as per Annual Performance Plan (APP) | 1st Quarter Planned target as per APP | Actual | Status On Achievements | Cumulative Information | Reasons For Deviation | Corrective Actions And Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SPORT AND RECREATION SERVICE PROVIDERS |
| Number of programme performance reports signed off. | Quarterly | 16 | 4 | 4 | Achieved | 4 | None | None |
| Sup-programme: Programme Management: Sport Support Services |
| Governance and sports development monitored |
| Number of sport and recreation bodies receiving financial support per year. | Quarterly | 60 | 2 | 3 | Exceeded | 3 | In addition to the entities, a transfer was made to Tennis SA | None |
| Number of national federation grading frameworks developed and implemented. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Number of national federation support service needs analysis conducted. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Transformation programmes implemented and monitored. |
| Number of consolidated National Federation Transformation Progress Reports produced. | Bi-annual | 2 | No target | N/A | N/A | N/A | None | None |
| Sub-programme: Club Development and Support |
| Clubs developed |
| Number of club systems developed and implemented | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Mass Participation and Sport Development Grant outputs centralized at the end of document from 2013 – sub-programme provides oversight and guidance for 5 indicators. |  |  |  |  |  |  |  |  |
| Sub-programme: Education and Training |
| Education and training of coaches, administrators and technical officials coordinated. |
| Number of national federations supported to develop training programmes. | Quarterly | 8 | No target | N/A | N/A | N/A | None | None |
| Number of sector skill plan and strategies developed in conjunction with CATHSSETA | Quarterly | 1 | No target | N/A | N/A | N/A | None | None |
| Sup-programme: Scientific Support |
| Scientific support services coordinated for development athletes and their coaches. |
| Number of talent identification and development strategies developed and implemented. | Quarterly | 1 | 1 | 1 | Achieved | 1 | None | None |
| Number of athletes & coaches assisted by means of scientific support programmes. | Quarterly | 71 | 71 | 70 | Achieved | 70 | 1 Athlete was removed from the programme | For the other quarters, the maximum achievement will be 70. |
| Number of knowledge management systems implemented and maintained. | Quarterly | 1 | 1 | 0 | Not Achieved | 0 | One official was transferred from the scientific support unit, thus lessening capacity within the unit. | Fill the vacancy and prioritise the implementation of the system. |
| Number of scientific conferences organised and publications produced. | Quarterly | 4 | No target | N/A | N/A | N/A | None | None |
| Mass Participation and Sport Development Grant outputs centralised at end of document from 2013 – sub-programme provides oversight and guidance for 5 indicators. |  |  |  |  |  |  |  |  |
| Government responsibility towards anti-doping supported. |
| % Compliance with international anti-doping regulations. | Quarterly | 100% | 100% | 100% | Achieved | 100% | None | None |
| Team South Africa preparation and delivery supported. |
| Number of reports on the services delivered by SASCOC. | Biannual | 2 | No target | N/A | N/A | N/A | None | None |

### LIST OF COMPLEMENTARY DOCUMENTS

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| Sport and recreation service providers | Allocation agreements with SAIDS, BSA and Tennis SA. Programme performance reports signed off x 4 |  |  |  |
|  | Proof of sport and recreation bodies receiving financial support per year. |  |  |  |
| Club Development | Not target in quarter 1 |  |  |  |
| Education and Training | Not target in quarter 1 |  |  |  |
| Scientific Support | School Sport Athlete Support Framework Removal letter of 1 athlete from the programme List of athletes & coaches assisted WADA Compliance [Agenda Item 7.1 ] |  |  |  |

## PROGRAMME 3: MASS PARTICIPATION

The programme comprises of two sub-programmes which are Community Sport and School Sport. The purpose of the programme is to create an enabling environment and provide support to increase the number of participants in sport and recreation in South Africa.

Performance Graph

There were five (5) targets to be achieved by the programme during the quarter under review. Three (3) targets were achieved, with 1 of them exceeded. Two (2) targets were not achieved.

### SERVICE DELIVERY ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| Community Mass Participation | Grant Framework : All the Grant Agreements have been received from the Provinces Annual Evaluation Reports have been received from 7 provinces and two reports are outstanding. 8 Provinces have submitted their Annual Evaluation Plan which will be consolidated and sent to National Treasury. |  |  |  |
| School Sport | Community Mass Participation: Capacity Building of Teachers has been hindered by NFs Accreditation Status with the SETA. We have since agreed that all International Federation-Accredited Programmes will be conducted. |  |  |  |

### PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan

| Performance Information | Reporting Period | Target for 2012/13 as per Annual Performance Plan (APP) | 1st Quarter Planned target as per APP | 1st Quarter Actual - validated | Status for Achievements | Cumulative Information | Reason for deviation | Corrective Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-programme: Programme Management: Mass Participation |
| Number of Mass Participation and Sport Development Grant evaluation reports submitted. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Number of Mass Participation and Sport Development Grant performance reports submitted. | Quarterly | 4 | 1 | 1 | Achieved | 1 | None | None |
| Sub-programme: Community Mass Participation |
| Sport participation opportunities provided. |
| Number of participants in sport promotion projects managed by Sport and Recreation South Africa per year. | Quarterly | 25 000 | 5 000 | 398 | Not Achieved | 398 | Most of the projects undertaken were focused more at institutions rather than individual participants. | Whenever there is a sport promotion project, the project manager will ensure that the lists of participants form part of the annexure of the Project report |
| Number of focus group status reports signed off. | Quarterly | 4 | 1 | 1 | Achieved | 1 | None | None |
| Community structures supported |
| Mass Participation and Sport Development Grant outputs centralised at end of document from 2013 – sub-programme provides oversight and guidance for 8 indicators. |  |  |  |  |  |  |  |  |
| Capacity building to deliver community sport |
| Number of volunteers registered in the National Sport Volunteer Corps Programme. | Quarterly | 200 | 50 | 70 | Exceeded | 70 | Increased interest from sport legends | None |
| Sub-programme: School Sport |
| Access to sport, recreation and physical education in every school in South Africa maximised. |
| Number of South African School National Championships hosted. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Capacity building to deliver school sport. |
| Number of schools supported to participate in school sport leagues | Quarterly | 4 000 | 500 | 0 | Not achieved | 0 | Due to delayed Accreditation of National Federations | Delivery will be done in 2nd and 3rd quarters. |
| Mass Participation and Sport Development Grant outputs centralised at end of document from 2013 – sub-programme provides oversight and guidance for 8 indicators. |  |  |  |  |  |  |  |  |

### LIST OF COMPLIMENTARY DOCUMENTS

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| Community Mass Participation | Registered Volunteer Corps for quarter 1 Participants’ numbers for the Mabopane and Mpumalanga Ministerial Outreach Program Focus groups status report Mass participation and sport development Grant performance report |  |  |  |
| School Sport | N/a |  |  |  |

## PROGRAMME 4: INTERNATIONAL LIAISON AND EVENTS

The programme comprises of two sub-programmes which are International Liaison and Major Events. The purpose of the programme is to coordinate an intra-government sport and recreation relations and support the hosting of identified major events.

Performance Graph

There were three (3) targets to be achieved by the programme during the quarter under review. Three (3) targets were achieved in addition to one (1) achievement that was not targeted for in this quarter.

### SERVICE DELIVERY MAIN ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| International Liaison and Events | Successful hosting and support of the 2013 Soweto Open. Active participation in multilateral engagements. Bilateral consultations conducted with Lesotho; New Zealand; Burundi and Australia. Financial support to SA students in Cuba |  |  |  |

### PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan

| Performance indicator | Reporting period | Target for 2012/13 as per Annual Performance Plan (APP) | 1st Quarter Planned target as per APP | Actual | Status On Achievements | Cumulative Information | Reasons For Deviation | Corrective Actions And Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-programme: International Liaison |
| Strategic bilateral relations initiated and strengthened. |
| Number of bilateral relations exchanges implemented. | Quarterly | 5 | 1 | 1 Exchange with Germany. In addition, Bilateral consultation processes were conducted with Burundi; Lesotho; Australia and New Zealand. South African sport students in Cuba continued to receive financial support from SRSA. | Achieved | 1 | None | None |
| Number of multilateral engagements supported. | Quarterly | 3 | No target | 6 | Achieved | 6 | A number of multilateral organizations that South Africa affiliate to convened their international meetings during the first quarter, namely; SCSA EXco, CABOS, MINEPS 5, WADA, WIPO and UN International Forum on Sport for peace and development. | None |
| Sub-programme: Major Events |
| Major event bidding and hosting support services provided. |
| Number of major international events receiving intra-governmental support per year. | Quarterly | 5 | 1 | 1 (2013 Soweto Open) | Achieved | 1 | None | None |
| Sports tourism promoted |
| Number of national & international sporting events, exhibitions or conferences used to showcase SA as a sports tourist destination. | Annually | 1 | No target | N/A | N/A | N/A | None | None |
| International travel documentation service provided. |
| Percentage of requests met for facilitating the provision of visas. | Quarterly | 100% | 100% | 100% | Achieved | 100% | None | None |

### LIST OF COMPLIMENTARY DOCUMENTS

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| International Liaison and Events | 2013 Soweto Open Report. Active participation in multilateral engagements. Bilateral consultations conducted with Lesotho; New Zealand; Burundi and Australia. Financial support to SA students in Cuba Exchange with Germany. |  |  |  |
|  | Proof of international meetings: SCSA EXco, CABOS, MINEPS 5, WADA, WIPO and UN International Forum on Sport for peace and development. |  |  |  |
|  | Register of visa requests and management thereof. |  |  |  |

## PROGRAMME 5: FACILITIES COORDINATION

The programme comprises of two sub-programmes which are Planning and Advocacy and Technical Support. The purpose of the programme is to facilitate the provision and management of sustainable sport and recreation facilities.

PERFORMANCE GRAPH

There were 2 targets to be achieved by the programme during the quarter under review. One (1) target was achieved (exceeded). One (1) target was not achieved.

### SERVICE DELIVERY ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| Facilities | Completed 5 projects (sites) in George Installed an outdoor gym in Mitchell's plain and received positive feedback regarding the usage of the gym by the community Sports Trust erected a multi purpose facility in Carolina The agreement between SRSA, Wide Open Space and the City of Gauteng completed and ready for signature |  |  |  |

### PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan

| Performance indicator | Reporting period | Target for 2012/13 as per Annual Performance Plan (APP) | 1st Quarter Planned target as per APP | Actual | Status On Achievements | Cumulative Information | Reasons For Deviation | Corrective Actions And Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-programme: Planning and Advocacy |
| Access to sport and recreation facilities optimized. |
| Number of facility audit reports published. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Number of facility plans published. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Number of status reports regarding the maintenance and usage of the stadia built or refurbished for the 2010 FIFA World Cup. | Biannual | 2 | No target | N/A | N/A | N/A | None | None |
| Number of national facilities database reports generated. | Quarterly | 4 | 1 | 0 | Not Achieved | 0 | Still working towards the next milestone following the approval of the classification framework. | Report on next milestone to be in the 2nd quarter |
| Sub-programme: Technical Support |  |  |  |  |  |  |  |  |
| Technical support provided. |  |  |  |  |  |  |  |  |
| Number of Norms and Standards for Sport and Recreation Infrastructure gazetted. | Annual | 1 | No target | N/A | N/A | N/A | None | None |
| Number of sport for social change projects assisted with facilities technical support | Quarterly | 16 | 4 | 5 (3 projects in Thembalethu, and 2 projects in Pacaltsdorp. The projects are: 2 grass surface soccer/rugby field, one children’s play area, 2 multi purpose courts | Exceeded | 5 | Following the timeous transfer of funds, the 5th project was started early and SRSA was then able to provide technical support to an additional project. | None |

### LIST OF COMPLIMENTARY DOCUMENTS

| Sub-programme | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- |
| Facilities | George report for the 5 projects (3 in Thembalethu, and 2 in Pacaltsdorp) Mitchell’s Plain Outdoor gym report Report on the Sports Trust multi purpose facility in Carolina The agreement between SRSA, Wide Open Space and the City of Gauteng. Facilities database report. |  |  |  |

# 3. OVERALL ORGANISATIONAL PERFORMANCE

The graph below indicates the overall performance of SRSA.

Overall,

SRSA has registered a 77, 1% achievement in the quarter under review.

There were 35 targets to be achieved by the Department during the quarter under review.

      - 29 targets were achieved with 4 of them exceeded. Two of the achievements were not targeted for in this quarter.

      - 7 targets were not achieved.

1 is reported as Not Applicable [dependent on grievances lodged].

# PROBLEM AREAS

| Finding | Action steps |
| --- | --- |
| Late submission of performance information reports remains a challenge. Most programmes do not adhere to the deadlines. | Late reports will be mentioned in the consolidated report to the EA and relevant managers will be reported to the DG. Negative impact on performance assessment of manager. |
| Unit reports not consolidated and signed-off by the Chief Directors despite the request | Raise the matter at QSRM and Chief Directors’ meetings |
| Most programmes submitted reports with gaps, i.e. no reasons for deviation where there is no achievement, no corrective actions or corrective actions with implementation dates, etc. | Reports will be sent back and if not corrected within the specified time it will be mentioned in the executive summary. Negative impact on performance assessment of manager. |
| Failure to submit source of evidence when targets are achieved. This is also prevalent on supplementary projects. | If evidence is not provided for both APP indicators and supplementary projects and claimed achievements, the report of the programme will be regarded as incomplete. Managers need to get into the culture of preparing evidence each month. Negative impact on performance assessment of manager. |
| None or very sketchy reporting on service delivery achievements. | The QSRM report must be a consolidated quarterly report of the DG monthly reports. Four quarterly reports must be consolidated as input to the Annual report. |
| Supplementary projects are named but in most cases, it is not clear what they are about. | Managers need to provide a short description of what the supplementary project entails. |
| Reasons for not capturing a supplementary project in the APP are not provided. | Managers must ensure that they provide this information. |
| Impact of incomplete reporting on Department. | Management to take responsibility as a whole for performance information. |
| It is a struggle to get quarterly performance reports from Ministry. | Relevant sections need to assist in providing information. |

# CONCLUSION

The performance of the Department during the quarter under review indicates that line functions have to improve on implementing their core indicators, more especially, those that have direct impact to the Department’s beneficiaries.

The majority of the 27 achieved targets can be attributed to the achievement of the support function units (16, which amounts to 84.2%) and not the line function (11 which amounts to 68.8%).

All units still have to improve on their submission deadlines and on submission of relevant performance evidence. The overarching principle remains: if it is reported as achieved, it must be proven.

SRSA’s ORGANISATIONAL PERFORMANCE REPORT FOR QUARTER 1: 2013/14 FINANCIAL YEAR

Signed and approved by:

Chief Director: Strategic and Executive Support

Name: Bernadus van der Spuy

_______________				_________________

Signature:					Date:

Chief Operating Officer:

Name: Summaya Khan

_______________				_______________

Signature:					Date:

Director-General:

Name: Alec Moemi

_________________				______________

Signature: 					Date: