| SIPs REPORT QUARTER ONE | CONTRIBUTORS: HUMAN SETTLEMENTS PLANNING UNIT PROGRAMME AND PROJECT PLANNING UNIT AUGUST 2013 |
| --- | --- |

Contents

Executive Summary	3

SIP 1: Unlocking the Northern Mineral Belt: MPUMALANGA	4

SIP 1: Unlocking the Northern Mineral Belt: LIMPOPO	6

SIP 2: Durban – Free State- Gauteng Logistics Corridor CORNUBIA: PROGRAMME AND PROJECT PLANNING	12

SIP 3: South Eastern Node and Corridor Development: EASTERN CAPE	19

SIP 4: Unlocking economic opportunities in NORTH WEST	24

SIP 5: Saldanha – Northern Cape Development Corridor: KATHU SISHEN: - NORTHERN CAPE	28

SIP 6: Integrated Municipal Infrastructure (DCOG) KEITH GOVENDER	33

SIP 7: Integrated Urban Space and Public Transport Programme:  Mangaung	34

SIP 7: Integrated Urban Space and Public Transport Programme:   City of Cape Town	37

SIP 18: WATER AND SANITATION:	78

CROSS CUTTING SIPS: SIP SKILLS DEVELOPMENT: TECHNICAL CAPACITY UNIT	79

# Executive Summary

According to the Presidential Infrastructure Coordinating Commission (PICC), the SIPs quarterly reports are due 6 weeks after the end of a quarter. This serves as an attempt to the Quarter One report.

The National Department of Human Settlements has had correspondence with Provinces in order to ensure that the Projects funded by the Human Settlements Development Grant (HSDG) and the Urban Settlements Development Grant (USDG) are projects that are under implementation in 2013/14 financial year.This process continues.

The main challenge that has been faced is the need for the criteria for SIP projects to be explained to Provinces. Free State and Gauteng province have suggested that the PICC have workshops with them in order to explain the SIP projects criteria and funding implications.  In addition, metropolitan cities have raised concern that there was assumption that placing projects under the SIP umbrella suggested additional funding. Metropolitan cities have requested that this be clarified by the PICC.

Concern has been raised by other SIP coordinators for the overlap function with the Department. With emphasis, the projects indicated in this report are those solely funded by Grants administered by the National Department of Human Settlements. These are merely a subset of what a complete SIP entails.

This report has a collection of six (6) SIPs summarized as follows.

- 13 running projects in SIP 1, in Mpumalanga,

- 2 running projects under SIP 2, Cornubia,

- 8 running projects under SIP 3 form the Eastern Cape,

- 35  projects under SIP 4 from the North West,

- 7 running projects under SIP 5 from the Northern Cape,

- 12 running projects from Mangaung metro under SIP 7

- 347 running projects from the city of Cape Town Metro under SIP 7.

These are unpacked in the detailed report that follows. An annexure with the PICC template will also be forwarded in due course.

# SIP 1: Unlocking the Northern Mineral Belt: MPUMALANGA

Mpumalanga is part of the Northern Mineral belt because the Nkangala region is where “gold, platinum group metals, silica, chromite, vanadiferousmagnetite, argentiferouszinc, antimony, cobalt, copper, iron, manganese, tin, coal, andalusite, chrysotileasbestos, kieselguhr, limestone, magnesite, talc and shale” are mined some in Nkangala and some in GertSibanda. Mpumalanga boasts of 83% of South Africa's coal production.

While according to the PICC, SIP 1, “rail capacity is to be extended to Mpumalanga power stations…and additional rail capacity will shft from road to rail …with social benefits..and supportive logistics corridors to strengthen Mpumalanga’s economic development,” the Mpumalanga Department of Human settlements is implementing projects to a handsome R122,304,588.75 of the Human Settlements Development Grant as seen in the list below which is the report for this quarter.

| Project Name | Project Phase | Project Name on HSS | Budget | Amount Paid | Municipality |
| --- | --- | --- | --- | --- | --- |
| IRDP Phase 1 informal | E12010015/1 | IRDP PH1/NKOMAZI BUS ENTER/EMPUMELELWENI/EMALAHLENI MUN (1000) | R 18,411,430.00 | R 5,232,400.74 | EMALAHLENI |
| CRU | E12010014/1 | INST/ORGANIC ARCHITECTS/KLARINET/EMALAHLENI MUN (500) | R 2,071,664.71 | R 2,071,664.71 | EMALAHLENI |
| IRDP Phase 2 | E12110005/1 | IRDP PH2/KLARINET INTEGRATED HOUSING DEVELOPMENT/2012-2013/EMALAHLENI MUN (620) | R 55,692,225.00 | R 55,692,225.00 | EMALAHLENI |
| IRDP Phase 2 | E10040001/1 | IRDP/KLARINET INTEGRATED HOUSING DEVELOPMENT/EMALAHLENI MUN | R 34,425,412.30 | R 34,425,412.30 | EMALAHLENI |
| Accreditation | E10030010/1 | OPSCAP/LEVEL ONE ACCREDITATION/EMALAHLENI MUN | R 3,400,000.00 | R 2,800,000.00 | EMALAHLENI |
| Social Economic Facilities Hall | E08040006/1 | SH/ARTECH ARCHITECTS/PHOLA COMMUNITY HALL/EMALAHLENI MUN | R 631 949.21 | R 535 100.21 | EMALAHLENI |
| Social Economic Facilities Hall | E08040004/1 | SH/ARTECH ARCHITECTS/COMMUNITY HALL/EMALAHLENI MUN | R 685 005.37 | R 685 005.37 | EMALAHLENI |
| Social Economic Facilities Hall | E09020019/1 | SH/MGUGWANA INVEST JV MEONDO TRAD/COMMUNITY HALL/EMALAHLENI MUN | R 4,025,154.18 | R 3,408,154.20 | EMALAHLENI |
| Social Economic Facilities Hall | E08120004/1 | SH/HARRIET CONSTRUCTION/COMMUNITY HALL/EMALAHLENI MUN | R 4,363,091.54 | R 4,363,091.54 | EMALAHLENI |
| Social Economic Facilities Child Day Care | E08040005/1 | SH/ARTECH ARCHITECTS/CHILD CARE CENTRE/EMALAHLENI MUN | R 235 343.00 | R 235 343.00 | EMALAHLENI |
| Social Economic Facilities Child Day Care | E08120005/1 | SH/PHETLOKUHLE BUS ENTER/CHILD CARE CENTRE/EMALAHLENI MUN | R 1,539,237.64 | R 1,536,867.04 | EMALAHLENI |
| Rental Stock | E10030011/1 | HOSTEL/F AND A CONSULTING/PHOLA(OGIES)/EMALAHLENI MUN | R 11,071,185.65 | R 6,642,711.43 | EMALAHLENI |
| Rental Stock | E09110017/1 | HOSTEL/SHUMA CONSTR/KWAGUQA HOSTEL PH3/EMALAHLENI MUN | R 46,923,095.82 | R 4,676,613.21 | EMALAHLENI |

# SIP 1: Unlocking the Northern Mineral Belt:LIMPOPO

The Platinum mining cluster located in Dikolong corridor between Polokwane and Bugersfort, and, the simultaneous coal mining and petrochemical cluster in Lephalale serve as economic drivers for Limpopo and the Northern Mineral belt indicated by the PICC in SIP 1.

While new platinum and chrome mines are some of the mushrooming developments, the Provincial Department of Human Settlements  hasa planned spend on Bulk connections and Community residential units in Lephalale. Implementation is yet to happen but cognizance should be given to the project pipe line.

With the background of the 2013 State of the Nation Address that gave emphasis to the need for development, implementation and planning for people in mining towns, the Province is yet to make good on the implementation of Projects for the 2013/14 financial year.

| INTERVENTION & PROJECT NAME | DELIVERABLES | Fun-ding Source | FINANCIALS |
| --- | --- | --- | --- |
|  | Planned Q1 | Actual Q1 | Q2 Target |  | Budget Q1 (‘000) | Actual Exp | Budget Q2 (‘000) |
| Lephalale bulk connector |  |  |  | Conditional grant | R16,576 | 0 | R0 |
| Lephalale CRU | 100 services | 0 | 426 | Conditional grant | R6,400 | 0 | R27,264 |

  - LEPHALALE DETAILED NOTES

    - Location and Project Description

The Lephalale Local Municipality (LLM) is situated in the Waterberg District Municipal Area in the western part of the Limpopo Province and borders Botswana on its north-west and western international boundaries.

500 hectares of land was purchased by COGHSTA to develop an integrated human settlement with an estimated yield of 4 000 residential sites which will comprise fully subsidised and affordable housing units.

1.1.2	Altoodtyd Human Settlement Development

The following progress is reported in the Altoostyd Human Settlement Development (Altoodtyd) component of the Lephalale Project area.

Table 9: Progress achieved at Altoostyd

| Component of Project | 31 March 2013 | 30 April 2013 |
| --- | --- | --- |
| Pre-planning |  |  |
| Scoping report | Done | Completed |
| Investment report | Done | Completed |
| Town planning |  |  |
| Township layout plan | Floodline being re-determined | Flood line Report received. Department is evaluating all floodline reports |
| General Plan | Done | Completed |
| Township registration | In progress | Awaiting finalisation of the Flood line Report & Services Agreement |
| Land |  |  |
| Request for exchange of part of Ext 102 for Marapong Ext 5 by Eskom | Application now with Coghsta | In progress at CoGHSTA |
| 500 ha land for mixed income development in Lephalale including Altoostyd | Done | Completed |

1.1.3	OTHER PROGRESS ACHIEVED

Progress achieved in the other aspects of Lephalale is indicated in the table below.

Table 10: progress achieved in the other aspects of Lephalale

| Process | Aspect of work | 30 Sept 2012 | 31 March 2013 | 30 April 2013 |
| --- | --- | --- | --- | --- |
| Land related issues | Servitude : Private | Negotiations - ongoing with the private land owners. Eskom applied to Coghsta to register servitude over a stand in Altoostyd. More land for servitude is required and Eskom is negotiating with the private land owners | All six (6) land owners have given permission for construction to go ahead on those land parcels. ABSA has also signed the final servitude contract. | Three servitude negotiations are underway as land owners are making counter offers for higher compensation. |
|  | Environ-mental Impact Assess-ment (EIA) | The Record of Decision was received on 25 July 2012. Environmental monitoring will be undertaken by a dedicated official as stipulated in the RoD requirements. | On Target | No findings to date. ECO on site and no findings. |
| Bulk Infrastructure | Water designs | Preliminary | 100% complete | Done | Completed |
|  |  | Detailed | 100% complete Finalisation of the pipe route has been reached | Done | 100% |
|  |  | Inter-changes (pipes) | 70% complete | Done | Completed |
|  |  | Drawings | 100% complete | Done | Completed |
|  | Sewer designs | Preliminary | Altoostyd sewer pump station to be linked with the existing Paarl sewer treatment works. Awaiting the costing of the design | Done | Completed |
|  |  | Pipe route | 100% complete | Done | Completed |
|  | Electricity designs Altoostyd Sub Station | Preliminary | 80% complete | Done | Completed |
|  |  | Detailed | 65% complete | Done | Completed |
|  |  | Drawings | 50% complete | Done | Completed |
|  | Electricity designs : Lephalale Sub Station | Preliminary | 100% complete | Done | Completed |
|  |  | Detailed | 90% complete | Budget quote was accepted by Coghsta and payment made. | Completed |
|  |  | Drawings | 90% complete | Done | Completed |
|  |  | Design | To be Conducted | In process | Completed |
|  | Construc-tion | Water | Work on the 350mm diameter pipe has commenced | Resolved. 100% access achieved | Completed |
|  |  | Electricity | Awaiting long lead material which was ordered in April 2012 | Construction delayed due to the delay in the approval of the budget quote. An expenditure report was due from Eskom after which Eskom will go out on tender. | Procurement due to commence |

1.1.4 	 Expenditure on Altoostyd

The financial information for this component of the project, as at 30 April 2013, is as follows:

Table 11:  Expenditure of the HSDG

| Fin year | Funding source | Received | Committed | Expenditure to date: 31 March 2013 | Expenditure to date: 30 April 2013 |
| --- | --- | --- | --- | --- | --- |
| 2011-2012 | Ring-fenced | R318 841 000 |  |  |  |
|  | Committed for bulk services |  | R234 015 663 |  |  |
|  | Paid for bulk services |  |  | 166 742 606,19 | R 217 437 912.39 |
|  | Paid to Eskom based on Feasibility Quote for purchases of long lead materials – 65% assurance |  | R 84 856 285,75 | R41 755 445,75 | R 209 188 384.13 |
| 2012-2013 | Ring-fenced | R274 888 000 |  |  |  |
| 2013-2014 | Ring-fenced | R291 651 000 |  |  |  |
| TOTAL |  | R593 729,000 | R318 871 948,75 | 208 498 051,94 | R426 626 296.52 |

1.1.5  	Challenges

Challenges being experienced in the implementation process are indicated in the table below.

Table 12: Challenges being experienced in the implementation process

| Challenges | Progress achieved in solving the problem: 31 March 2013 | Progress achieved in solving the problem: 30 April 2013 |
| --- | --- | --- |
| The access to the private properties not achieved. | A meeting was held with the MEC and the land owners on the 13th November 2012 and the Land owners have promised to co-operate. This matter was resolved for construction access. One (1) landowner has signed the final contract and Coghsta is now in process of negotiation of compensation with 5 land owners. | No change reported |
| Approval of the VOs is affecting the finalization of the Sewer Designs. | VOs 1 & 3 were subsequently approved by Coghsta and contractor given go ahead on these VOs. VO 2 is the responsibility of the municipality and is prioritized for 2013/14 budget. The Municipality is awaiting approval of the Council. | No change reported |
| There was a delay caused by Eskom’s reluctance to quote for the Switching stations at the new Sub-Stations. | Eskom is in the process of approving the switching station quotes and it is due to be with Coghsta by April 2013. | A special request will be made to the procurement manager to seek a way of fast tracking the procurement process at the meeting of the Task Team |

# SIP 2: Durban – Free State- Gauteng Logistics CorridorCORNUBIA:PROGRAMME AND PROJECT PLANNING

| HSS No. | Responsible Organisation, Person and Contact Detials | Sub-Programme name ie PHP | Project Name | Project Status (eg. Concept, Design, Execution) as of December 2012 |  |  | Project Timeframe |  | (‘000) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Municipality (District) | GPS Coordinates | Start Date | End Date | 2013/14 |
| K10050005 | Mr. Winston Oakes 082 375 8460 (Project Management) | 2.2a Integrated Residential Development Programme: Phase 1 Planning and Services (excluding Informal Settlements) | Cornubia (Phoenix East) | construction | eThekwini Metropolitan Municipality | 31.02932 | 2011/10/11 | 2012/10/01 | R 44,562 |
| K10050005 | Mr. Winston Oakes 082 375 8460 (Project Management) | 2.2d Integrated Residential Development Programme :Phase 2:Top Structure Construction INFORMAL SETTLEMENTS | Cornubia (Phoenix East) | construction | eThekwini Metropolitan Municipality | 31.02932 | 2011/10/11 | 2012/10/01 | R 76,181 |

  - CORNUBIA PROJECT DETAILS

    - Location and Project description

The Cornubia Development is a public-private partnership between the eThekwini Municipality and TongaatHulett (TH) which boarders the surrounding Ottawa, Mount Edgecombe and Umhlanga suburbs which are established residential human settlements and are in very close proximity to the central business districts of Phoenix, Ottawa and Verulam and the King Shaka International Airport.

The subsidised housing component will be is to be funded from the HSDG. One thousand  two hundred (1 200) hectares of land have been set aside for this mixed-use, mixed income development which will incorporate industrial, commercial, social and residential sites within ecologically sensitive open spaces. It is envisaged that the housing component product mix will yield about 24 400 units.

    - Project progress

Project Progress on Phases 1 A and Phase 1 B are indicated below.

Table 5: Progress achieved as at 31 March 2013 is indicated in the table below.

| Aspect | 30 September 2012 | 31 March 2013 | 31 May 2013 |
| --- | --- | --- | --- |
| Access Rd | 80% complete | 85 % | 95% |
| Bulk water | Progress delayed due to inclement weather | 30 % | 55% |
| Phase 1 A (482 units) |
| Layout Plan | Approved | Amendments being finalized | Awaiting approval from COGTA |
| RoD | In place | Done | Done |
| NHBRC | Enrolment approved on 31 August 2010 | Ongoing monitoring | Ongoing Monitoring |
| Township | Proclaimed | Done | Done |
| Bulk Sewer | In progress | In Progress | In Progress |
| Bulk Electricity | In progress | In Progress | In Progress |
| Water reticulation | Commenced | In progress | In Progress |
| Electricity | Commenced | In progress | Internal reticulation in progress |
| Top structure construction | Foundations / slabs | 451 | 480 |
|  | 1st Floor slab | 444 | 478 |
|  | Roofs | 444 | 475 |
|  | Finishes | 207 | 275 |
| Phase 1 B (Number reduced from 2263 to 2186 units due to topography) |
| Layout Plan | Approved | Approved | Approved |
| RoD | In place | Done | Done |
| NHBRC | Project Enrolment approved | Done | Done |
| Phase 1 B (1) |
| Appointment of contractor for civil engineering services, serviced sites and first 623 houses | Stalled due to appeal lodged by one of the unsuccessful bidders | Report submitted to the Bid Committee regarding the results of the Appeals Authority decision | Committee required complete re-evaluation. Re-evaluation report completed and submitted for approval |
| Phase 1 B (2 & 3) | Tender documentation for the infrastructure ready is now to be advertised | The Tender was advertised on 25 January 2013 and is now at the tender evaluation stage | Negotiations with the two most responsive tenderers has been completed, report being finalised |

    - Beneficiary Administration

The Beneficiary Allocation Guidelines document has been accepted as a working document but has yet to be endorsed by the Human Settlements Committee. Settlements have been identified and included in report to Council for approval. Report has been on agenda twice, but has always been removed at the last minute. Due to majority support of guideline, Snr Manager Human Settlements has instructed the allocations teams to proceed with signing up of beneficiaries.

    - Labour issues and job opportunities

- The MEC appointed an independent facilitator to resolve the ongoing labour issues and a Report on the outcome of the process was in the process of being discussed with the Developer and the contractor; and

- It is estimated that 42 800 permanent jobs and 387 000 temporary construction jobs will be created, sustained over the 8 – 20 year period and 35 jobs have been created for Women  and 165 for the Youth.

    - Quality

The NHBRC's Provincial Assessor together with the structural engineer are on site on a daily basis to undertake quality checks and eliminate the incidents of shoddy workmanship. This process is ongoing and, to date, the NHBRC has not issued a notice of non-compliance for inferior work.

    - Amenities

The three spheres of Government are developing a project description document for the construction of a multipurpose centre and to make the application for the necessary funding. In addition, the implementation team has met with the Provincial Department of Education to push for the first school to be ready for use by 2015. Bussing is being discussed for those children whose families will be relocated to the first 482 houses.

1.1.7	Financial information

The financial information for the project is unchanged. The expenditure on this project, together with the funding flows, are indicated in the following two (2) tables.

Table 6: Expenditure to 31 May 2013 (No change as is indicated below)

| Aspect |  | 31 March 2013 | 31 May 2013 |
| --- | --- | --- | --- |
| Land | Ethekwini Municipality acquired 659 ha of land | R336,777,190.00 | No Change |
| Phase 1 A | Services and house construction underway. | R43,284,851.28 | No Change |
| Phase 1 B | Process delayed due to Appeal Process | R34,537,019.00 | No Change |
| Ring fenced funds received | 2011 – 2012 | R 132,000,000.00 |  |
|  | 2012 – 2013 | R 113,800,000.00 |  |
|  | 2013 – 2014 | R 120,743,000.00 |  |
| TOTAL |  | R 245,800,000.00 | R414 599 060.28 | R414 599 060.28 |

Table 7: Funding flows

|  | R-FF | USDG | Approved by Province | Received by eThekwini |
| --- | --- | --- | --- | --- |
| Ring-fenced funding (R-FF) 2011-2012 | R132 mil |  |  |  |
| Ring-fenced funding (R-FF) 2012-2013 | R113,8 mil |  |  |  |
| Ring-fenced funding (R-FF) 2013-2014 | R120,743mil |  |  |  |
| Cumulative expenditure to date |  | R395,8 mil |  |  |
|  |  |  | Ph 1 A | R44,8 mil | R43,3 million |
|  |  | Ph 1 B | R209,2 mil | R34,5 million |
| TOTALS | R245,8 mil | R395,8 mil |  | R254 mil | R77,8 million |

1.1.8	Conubia Industrial and Business Estate (CIBE)

Construction of the internal roads has commenced and is targeted for completion by the end 	of August 2013.

1.1.9	Cost Sharing between TH and Ethekweni Municipality

As part of the exercise to fund the construction of the road, an application to the Jobs Fund 	was made.  While the application was considered to be of a very high standard and very 	well 	motivated, it was not considered for the second tranche due to the fact that Ethekwini had 	underspent its budget.  The funding for the third tranche has not been finalised as yet.

1.1.10 Socio Economic Development (SED)

A workshop to discuss the manner in which SED will be managed between Ethekweni and TH was held. Further interactions have been planned for.

1.1.11 	matters that require attention

The under-mentioned issues require attention.

Table 8: Issues that require attention

| Issues that Require Attention | Responsibility | Time Frames |
| --- | --- | --- |
| Reconciliation of R77mill to be completed for the Ph 1 A and a part of the Ph 1B. | eThekwini | August 2013 (When Phase 1A and 1B are complete). |
| Adjudication of Tenders for Ph 1B2 and Ph1B3. | eThekwini’s Legal Services and Supply Chain Management Units | Dependent on the municipality's processes |
| Labour disputes | Local political leadership | In process |
| Community dynamics/social facilitation | Three spheres of Government, TH, Ward Councilors and CLOs | Ongoing |
| Name change | Province and Ethekwini | Corporate GIS Department has been tasked to manage this process of name change. |
| Signing of the Cooperative Agreement | 3 spheres of government | Dependent on agreement by the City and Province on the name change |
| Finalisation of the Allocations Policy | Ethekwini | Dependent on the approval of EXCO |
| Revised Cash flows from the municipality | Ethekwini | Done |
| Appointment of the Programme Manager | Ethekwini | About October 2013 |

1.1.12Assessment

The top-structure construction is slow, but production is as per the Project Plan agreed upon between the Contractor and Ethekweni.

# SIP 3: South Eastern Node and Corridor Development: EASTERN CAPE

| Project name and Description | No of units | Implementation Phase | Timeframe for implementation | Location (where originate from) |
| --- | --- | --- | --- | --- |
|  | How many |  | Actual Start Date | Planned End Date | Province(s) | District Municipality(ies) | Local Municipality(ies) | GPS Longitude (East) Coordinate | GPS Latitude (South) Coordinates |
| Ngangelizwe BNG200 | 200 | Construction | 2010-11-01 | 2013-06-01 | Eastern Cape | OR Tambo | King SabataDalindyebo | 28.807724 | -31.607223 |
| Siyanda BNG 407 | 407 | Construction | 2011-02-01 | 31-03-2014 | Eastern Cape | Amathole | Mnquma | 28.158456 | -32.321226 |
| Elliotdate 4000 | 4000 | Construction | 2009-08-01 | 31-03-2014 | Eastern Cape | Amathole | Mbhashe | 28.896000 | -31.959000 |
| Joe Slovo 500 | 500 | Construction | 2013-08-31 | 2012-10-30 | Eastern Cape | Nelson Mandela Metropolitan | Nelson Mandela Metro | 25.513600 | -33.832210 |
| Chatty 1398 | 1398 | Construction | 2011-04-01 | 31-03-2013 | Eastern Cape | Nelson Mandela Metropolitan | Nelson Mandela Metro | 25.461538 | -33.854747 |
| Downtown 1000 | 1000 | Construction | 2011-04-01 | 2013-03-31 | Esatern Cape | Alfred Nzo | Mbizana | 29.866390 | -30.848738 |
| Mzamomhle 512 | 512 | Construction | 2009-08-01 | 2014-03-01 | Eastern Cape | Buffalo City Metro | Buffalo City Metro | 27.983080 | -32.955813 |
| Tombo 200 | 200 |  | 2012-06-01 | 31-082013 | Eastern Cape | OR Tambo | Port St. Johns | 29.392000 | -31.624000 |

ii) Budget information of the Projects:

| Project Name | Medium Term Budget Requirement R | Funding Secured/Medium Term Allocations R | Funding to be secured/allocated |
| --- | --- | --- | --- |
|  | Up to March 2013 | 2013/14 | 2014/15 | 2015/16 | Up to March 2013 | 2013/14 | 2014/15 | 2015/16 | Total Project |
| Ngangelizwe BNG 200 | R 380 000 | R4 380 000 | R 3 750 000 | R 5 508 790 | R 380 000 | R4 380 000 | R 3 750 000 | R 5 508 790 | R 9 258 790.00 |
| Siyanda BNG 407 | R7 347 738 | R 25 197 038 | R15 833 088 | 0 | R7 347 738 | R 25 197 038 | R15 833 088 | 0 | R 41 030 126 |
| Elliotdate 4000 | R4 290 000 | R 61 185 670 | 0 | R 8 500 000 | R4 290 000 | R 61 185 670 | 0 | R 8 500 000 | R 84 645 240 |
| Joe Slovo West 4000 | R4 600 000 | R 41 200 000 | R 62 000 000 | R 85 000 000 | R4 600 000 | R 41 200 000 | R 62 000 000 | R 85 000 000 | R 391 003 920 |
| Chatty 1398 | R19 543 338 | R 50 300 000 | R 42 000 000.00 | R 15 000 000 | R19 543 338 | R 50 300 000 | R 42 000 000.00 | R 15 000 000 | R 47 698 263 |
| Downtown | R 550 000 | R1 177 804 | R 3 578 040 | R 9 839 610 | R 550 000 | R1 177 804 | R 3 578 040 | R 9 839 610 | R 30 469 900 |
| Mzamomhle | R 7 065 552 | R 6 480 000 | R 8 500 000 | R 6 800 000 | R 7 065 552 | R 3 000 000 | R 7 500 000 | R 13 500 000 | R 15 234 400 |
| Tombo | R 637 124 | R10 200 000 | R 7280 000 | 0 | R 637 124 | R10 200 000 | R 7280 000 | 0 | 0 |

iii) Time Frames for the Projects:

| Project Name | Project Construction Timeframe | Direct Jobs | Project Cost |
| --- | --- | --- | --- |
|  | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Total Jobs Planned (entire project) | 2013/14 | 2014/15 | 2016/2020 | 2021/2030 | Total Cost of Project Planned (Cost at completion excl IDC) |
| Ngangelizwe BNG 200 | 2010-10-01 | 2010-11-01 | 2013-06-01 | Not applicable at the moment | The information is not available of hand | 51 | 54 |  |  | R 15 258 790.00 |
| Siyanda BNG 407 | 01-05-2013 | 2011-02-01 | 31-03-2014 | Not applicable at the moment | The information is not available of hand | 492 | 517 | 0 | 0 | R 12 134 229.00 |
| Elliotdate 4000 | 01-05-2013 | 2009-08-01 | 31-032014 | Not applicable at the moment | The information is not available of hand | 1530 | 1607 | 0 | 0 | R 84 645 240 |
| Joe Slovo West 4000 | 2012-04-16 | 2013-08-31 | 2012-10-30 | Not applicable at the moment | The information is not available of hand | 1425 | 1496 |  |  | R 391 003 920 |
| Chatty 1398 | 2011-02-01 | 2011-04-01 | 31-03-2013 | Not applicable at the moment | The information is not available of hand | 597 | 627 |  |  | R 47 895 632 |
| Down Town | 2010-05-01 | 2011-04-01 | 2013-03-31 | Not applicable at the moment | The information is not available of hand | 400 | 450 | 0 | 0 | R 30 469 900 |
| Mzamomhle | 2009-08-01 | 2009-08-01 | 2014-03-01 | Not applicable at the moment | The information is not available of hand | 257 | 270 | 0 | 0 | R 15 234 400 |
| Tombo | 2012-05-01 | 2012-06-01 | 31-082013 | Not applicable at the moment | The information is not available of hand | 51 | 54 | 0 | 0 | R18 872 283.44 |

iv) Progress of the projects

| Total Progress to Date ( Start - March 2013) |
| --- |
| PROJECT NAME | Total Actual Spend to date (R) | Total Actual Local Spend to date R | Total Actual Foreign Spend to date R | % Progress (Spend) | % Progress (Construction) | Total Direct Jobs Planned (to date) | Total Actual Direct Jobs (to date) | % Youth of Actual Direct Jobs (to date) | % Women of Actual Direct Jobs (to date) | % Disabled of Actual Direct jobs (to date) | Additional info / Key Challenges |
| Ngangelizwe BNG 200 | R 909 456 | n/a | n/a | 10% | 10% | 238 | 95 | 5% | 5% | 5% | All these projects are having a general poor performance on site due to poor contractor performance. |
| Siyanda BNG 407 | R 0 | n/a | n/a | 0% | 0% | 1009 | 0 | 5% | 5% | 5% |  |
| Elliotdale 4000 | R 28 884 000 | n/a | n/a | 34% | 34% | 3137 | 1255 | 5% | 5% | 5% |  |
| Joe Slovo West 4000 | R 356 026 168 | n/a | n/a | 91% | 91% | 2921 | 1168 | 5% | 5% | 5% |  |
| Chatty 1398 | 0 | n/a | n/a | 0% | 0% | 1224 | 0 | 5% | 5% | 5% |  |
| Down Town | 0 | n/a | n/a | 0% | 0% | 512 | 0 | 5% | 5% | 5% |  |
| Mzamomhle | R 13 315 167 | n/a | n/a | 87% | 87% | 527 | 211 | 5% | 5% | 5% |  |
| Tombo | R980 155.66 | n/a | n/a | 5% | 5% | 105 | 42 | 5% | 5% | 5% |  |

# SIP 4: Unlocking economic opportunities in NORTH WEST

| INTERVENTION & | DELIVERABLES | Funding Source | EXPENDITURE |
| --- | --- | --- | --- |
| PROJECT NAME | Planned Q1 | Actual Q1 | Q2 Target |  | Planned Q1 (R’100) | Actual Q1 (R’100) | Q2 Target (R’100) |
| Matlosana Jouberton Ext 20 Tigane | 13 | 336 | 19 | HSDG | 1 118 | 26 055 | 1 588 |
| Rustenburg CRU 100 Rigid | 30 |  | 30 | HSDG | 9 600 | 13 264 | 9 600 |
| Rustenburg CRU 100 Toro | 30 |  | 30 | HSDG | 9 600 | 9 796 | 9 600 |
| Madibeng 1000 Sunset Bay Trading | 25 | 0 | 65 | HSDG | 1 691 | 28054 | 4 397 |
| Matlosana Khuma ext 6 500 units |  | 29 |  | HSDG | 0 | 6476 | 0 |
| Matlosana Jouberton Ext 19 (150 Units) | 6 | 0 | 9 | HSDG | 559 | 5861 | 794 |
| Matlosana Jouberton Ext 16 (429 Units) | 6 | 55 | 9 | HSDG | 559 | 9238 | 794 |
| MatlosanaJouberton Ext 10 Trans Gariep | 26 | 45 | 37 | HSDG | 2 235 | 4619 | 3 177 |

| INTERVENTION & | DELIVERABLES | Fun-ding Source | EXPENDITURE |
| --- | --- | --- | --- |
| PROJECT NAME | Planned Q1 | Actual Q1 | Q2 Target |  | Planned Q1 (R’100) | Actual Q1 (R’100) | Q2 Target (R’100) |
| MOSES KOTANE- SAULSPOORT RURAL HOUSING | 77 |  | 105 | HSDG | 5 209 | 0 | 7 103 |
| Madibeng - Lethabong (2100 Subs) B01030001 Sn 176 | 45 |  | 90 | HSDG | 3 044 | 0 | 6 088 |
| Matlosane L.M Khuma Ext 1,3,4 & 5 (168 subs) | 13.16987957 |  | 18.71509203 | HSDG | 1 118 | 0 | 1 588 |
| Matlosane L M- Jouberton Ext 3 (50 Subs) |  |  |  | HSDG | 2 061 | 0 | 724 |
| Madibeng L M Bokfontein Housing Project (529 Subs) | 0 |  | 0 | HSDG | 3 510 | 0 | 4 096 |
| Rustenburg (4000) Boitekongext 8 1759 | 152.3809524 |  | 228.5714286 | HSDG | 6 148 | 0 | 9 221 |
| RustenbuegSeraleng Anglo-platinum Flisp | 26.08695652 |  | 26.08695652 | HSDG | 1 765 | 0 | 1 765 |
| Madibeng Mamba | 0 |  | 0 | HSDG | 3 510 | 0 | 3 510 |
| Rustenburg Meriting Ext 4 & 5 Makole | 119.6531792 |  | 190.7514451 | HSDG | 8 094 | 0 | 12 904 |
| MatlosanaNkagisang Village 143 Kgantso | 9.877409681 | 0 | 14.03631902 | HSDG | 838 | 0 | 1 191 |

| INTERVENTION & | DELIVERABLES | BENEFICIARIES | Funding Source | EXPENDITURE |
| --- | --- | --- | --- | --- |
| PROJECT NAME | Planned Q1 | Actual Q1 | Q2 Target | Planned Q1 | Actual Q1 | Q2 Target |  | Planned Q1 (R’100) | Actual Q1 (R’100) | Q2 Target (R’100) |
| Matlosana Cru 100 Proplan |  |  |  |  |  |  | HSDG | 0 | 0 | 0 |
| MATLOSANE - KHUMA HOSTEL | 0 |  | 0 |  |  |  | HSDG | 0 | 0 | 0 |
| Matlosane- Jouberton Ext. 3 Letsema (149 Subs) Sn 001 |  |  |  |  |  |  | HSDG | 2 061 | 0 | 724 |
| Matlosana Emergency Storm Damaged 200 units |  |  |  |  |  |  | HSDG | 0 | 0 | 0 |
| Madibeng CRU | 15 |  | 25 |  |  |  | HSDG | 8 000 | 0 | 9 600 |
| Madibeng Sunway FLISP | 19 |  | 77 |  |  |  | HSDG | 8 859 | 0 | 5 237 |
| MadibengDekroon | 0 |  | 0 |  |  |  | HSDG | 0 | 0 | 0 |
| wonderkop informal |  |  |  |  |  |  | HSDG | 5 500 | 0 | 5 500 |
| Matlosana Jouberton ext 17 906 units | 24 |  | 34 |  |  |  | HSDG | 2 045 | 0 | 2 907 |
| Matlosana Jouberton ext 21 741 units | 20 |  | 28 |  |  |  | HSDG | 1 677 | 0 | 2 382 |
| Matlosana Jouberton ext 23 1164 units | 20 |  | 28 |  |  |  | HSDG | 1 677 | 0 | 2 382 |
| Matlosana Kanana ext 11 772 units | 20 |  | 28 |  |  |  | HSDG | 1 677 | 0 | 2 382 |
| Matlosana Kanana ext 13 2757units | 20 |  | 28 |  |  |  | HSDG | 1 677 | 0 | 2 382 |
| Moses Kotane Mogwase Urban | 21 |  | 35 |  |  |  | HSDG | 1 416 | 0 | 2 360 |
| Moses Kotane Rural 1200 | 25 |  | 65 |  |  |  | HSDG | 1 691 | 0 | 4 397 |
| Rustenburg Boitekong Ext 16 | 277 |  | 303 |  |  |  | HSDG | 18 760 | 0 | 20 465 |
| Rustenburg Seraleng | 68 |  | 146 |  |  |  | HSDG | 3 960 | 0 | 9 900 |

# SIP 5: Saldanha – Northern Cape Development Corridor: KATHU SISHEN: - NORTHERN CAPE

  - PROJECTs PROFILE

Sesheng is a residential area located 2 kilometres west of Khatu. The area was planned as a high density residential area for mine workers, which excluded families. In the northern part of Sesheng are hostels and few houses to serve middle management at the time. In the years later, the mine workers started to move out of the hostels to build family units. The Municipality formalised the area and this is the fastest growing residential area outside Khathu.

  - PROJECTs RESPONSE TO SIP 5

Taking into consideration the objective of SIP 5 which is: Integrated rail and port expansion, expanding iron ore mining and strengthening maritime capacity, it can be said that the Provincial plans to construct 1,920 units as seen in the tables below in this financial year (2013/2014) will yield a platform in making SIP 5 effective in terms of positive impact on residents should the construction of the projected units and participation of relevant sector Department come into fruition.

The sizes of the projects means more people will reside in the area and they will have access to transport and economic opportunities. This responds squarely to the government initiative of creating jobs utilising, among other tools, infrastructure or housing.

Given the fact that the area was earmarked for high density, the implementation of the rental housing programme would be appropriate. This may lead to a high impact transformation of the space with effects that may favourably spill over surrounding beneficiary societies.

The existence of the primary sector of the economy – that is, mining within a reasonable radius, can also aid in creating positive spatial related spill-over effects that can benefit the people.  This is the case as this may, to a certain extent, create economic opportunities for the beneficiaries of the project.

  - IMPLICATION ON THE DEPARTMENT’S HUMAN SETTLEMENT PLANNING UNIT

Based on what is raised in this submission, the Human Settlement Planning Unit has to provide support and assistance in the form of ensuring the development of credible Housing Chapters for both John GaetseweTaolo (JGT) and Gamagara Municipalities taking into consideration the developmental agenda outlined in SIP 5. Sustainability socially, economically and environmentally should be ensured in the content including integration.

Below is the current conjuncture of SIP 5 Projects in Northern Cape.

- Background information to the SIP 5 projects

| Project Name | Project Description | No of units | Implementation Phase | Timeframe for implementation | Location (where originate from) |
| --- | --- | --- | --- | --- | --- |
|  |  | How many |  | Actual Start Date | Planned End Date | Province(s) | District Municipality(ies) | Local Municipality(ies) | GPS Longitude (East) Longitude | GPS Latitude (South) Coordinates |
| OLIFANTSHOEK | TOWN PLANNING | 1000 | 1 | JULY 2014 | MARCH 2017 | NC | JTG | GAMAGARA | 22.733 | -27.933 |
| SESHENG 490 | TOP STRUCTURES | 70 | 2 | NOV 2013 | MAR 2014 | NC | JTG | GAMAGARA | 23.0020 | -27.6933 |
| KATHU 1600 | SERVICES | 200 | 2 | OCT 2013 | JUNE 2014 | NC | JTG | GAMAGARA | 23.0469 | -27.6973 |
| GA-SEGONYANA 1000 | TOP STRUCTURES | 200 | 4 | APRIL 2013 | DEC 2013 | NC | JTG | GA-SEGONYANA | 23.4906 | -27.3947 |
| JOE MOROLONG 1000 | TOP STRUCTURES | 200 | 2 | APRIL 2013 | JAN 2014 | NC | JTG | JOE MOROLONG | 23.6452 | -26.9938 |
| UPINGTON 200 | TOP STRUCTURES | 200 | 1 | OCT 2013 | JULY 2014 | NC | ZFM | //KHARA HAIS | 21.24264900 | -28.45746000 |
| DANIELSKUIL 50 | TOP STRUCTURES | 50 | 2 | APRIL 2013 | DEC 2013 | NC | ZFM | KGATELOPELE | 23.53 | -28..18 |

- Budget information for the Projects

| Project Name | Medium Term Budget Requirement R | Long Term Budget Requirement (5 Years) R | Long Term Budget Requirement (10 Years) R | Funding Secured/Medium Term Allocations R | Funding to be secured/ allocated |
| --- | --- | --- | --- | --- | --- |
|  | Up to March 2013 | 2013/14 | 2014/15 | 2015/16 | 2016/2020 | 2021/2030 | Up to March 2013 | 2013/14 | 2014/15 | 2015/16 | Total Project |
| OLIFANTSHOEK 200 | 11,681,448 | 4,464,000 |  |  |  |  | 11,681,448 | 4,464,000 | 0 | 0 | 16,145,448 |
| SESHENG 490 | 12,698,663 | 5,040,000 | 0 | 0 | 0 | 0 | 12,698,663 | 5,040,000 | 0 | 0 | 17,738,663 |
| KATHU 1600 | 4,008,448 | 6,400,000 | 24,000,000 | 17,500,000 | 48,000,000 | 168,000,000 | 4,008,448 | 6,400,000 | 0 | 0 | 257,500,000 |
| GA-SEGONYANA 1000 | 70,669,844.24 | 14,400,000 | 14,400,000 | 0 | 0 | 0 | 70,669,844.24 | 14,400,000 | 14,400,000 | 0 | 70,669,844.24 |
| JOE MOROLONG 1000 | 73,672,773 | 14,400,000 | 23,040,000 | 0 | 0 | 0 | 73,672,773 | 14,400,000 | 0 | 0 | 73,672,773 |
| UPINGTON 200 |  | 10,800,000 | 3,600,000 | 0 | 0 | 0 |  | 10,800,000 | 3,600,000 | 0 | 14,400,000 |
| DANIELSKUIL 50 | 23,464,660 | 3,600,000 | 3,600,000 | 3,600,000 | 34,000,000 | 0 | 23,464,660 | 3,600,000 | 0 | 0 | 41,200,000 |

- Time Frames of Projects

| Project Name | Project Construction Timeframe | Direct Jobs | Project Cost |
| --- | --- | --- | --- |
|  | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Total Jobs Planned (entire project) | 2013/14 | 2014/15 | 2016/2020 | 2021/2030 | Total Cost of Project Planned (Cost at completion excl IDC) |
| OLIFANTSHOEK | JULY 2014 | N/A | APRIL 2015 | N/A | 25 | 0 | 25 | 25 | 0 | 136,400,000 |
| SESHENG 490 | NOVEMBER 2013 | N/A | MARCH 2014 | N/A | 10 | 10 | 0 | 0 | 0 | 10,080,000 |
| KATHU 1600 | OCTOBER 2013 | N/A | JUNE 2014 | N/A | 80 | 20 | 20 | 20 | 0 | 257,500,000 |
| GA-SEGONYANA 1000 | APRIL 2013 | MAY 2013 | DECEMBER 2013 | N/A | 20 | 20 | 20 | 0 | 0 | 70,669,844.24 |
| JOE MOROLONG 1000 | APRIL 2013 | JUNE 2013 | JANUARY 2014 | N/A | 20 | 20 | 20 | 0 | 0 | 73,672,773.90 |
| UPINGTON 200 | OCTOBER 2013 | N/A | JULY 2014 | N/A | 40 | 40 | 0 | 0 | 0 | 24,000,000 |
| DANIELSKUIL 50 | APRIL 2013 | JUNE 2013 | DECEMBER 2013 | N/A | 20 | 20 | 0 | 0 | 0 | 3,950,000 |

- Progress to date of the Projects

| Total Progress to Date ( Start - March 2013) |
| --- |
| PROJECT NAME | Total Actual Spend to date (R) | Total Actual Local Spend to date R | Total Actual Foreign Spend to date R | % Progress (Spend) | % Progress (Construction) | Total Direct Jobs Planned (to date) | Total Actual Direct Jobs (to date) | % Youth of Actual Direct Jobs (to date) | % Women of Actual Direct Jobs (to date) | % Disabled of Actual Direct jobs (to date) | Additional info / Key Challenges |
| OLIFANTSHOEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The first phase of town planning will be funded by the Mines |
| SESHENG 490 | 12,485,652.00 | 12,485,652.00 | 0 |  | 261 | 10 | 16 | 16 | 0 | 0 | The project will be closed of |
| KATHU 1600 | 4,008,310.85 | 4,008,310.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The first phase was town planning, which does not make use of unskilled labour |
| GA-SEGONYANA 1000 | 47,180,208.20 | 47,180,208.20 | 0 |  | 653 | 20 | 21 | 21 | 0 | 0 | None |
| JOE MOROLONG 1000 | 26,719,273.44 | 26,719,273.44 | 0 |  | 428 | 20 | 22 | 18 | 4 | 0 | Slow progress on the project |
| UPINGTON 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The project is at tender stage |
| DANIELSKUIL 50 | 0 | 0 | 0 |  | 0 | 10 | 20 | 1 | 19 | 0 | The contractor commenced construction in July 2013 |

# SIP 6: Integrated Municipal Infrastructure (DCOG)

This deals with addressing all maintenance backlogs and upgrades required in water, electricity and sanitation bulk infrastructure in the 23 least-resourced municipalities, covering 17-million people.

An excel sheet is attached as an annexure. This SIP is managed by DCOG, though information from the Business Plans has been provided.

# SIP 7: Integrated Urban Space and Public Transport Programme: Mangaung

| Mangaung Metro priorities | Mangaung USDG planned expenditure (final BEPP) | Mangaung HSDG Planned expenditure 2013/14 per Sub-Programme | HSDG % |
| --- | --- | --- | --- |
| PRIORITY 1 | Bulk sanitation R147 065 265.00 | Social and Rental | 12,4% |
| PRIORITY 2 | Bulk water R113 388 347.00 | Incremental housing Programme | 6,4% |
| PRIORITY 3 | Upgrading roads R78 496 388.00 | Financial intervention | 1,1% |
| PRIORITY 4 | Electricity R60 000 000.00 | Total | 19,8% |
| PRIORITY 5 | Social facilities R43 384 000.00 |  |  |

According to the PICC, SIP 7 is about “coordination of planning, implementation or public transport, human settlement, economic and social infrastructure and location decisions into sustainable urban settlements connected by dense transport corridors.”

The higher order transport networks that shape the Built Environment Form of Mangaung are the N1, N3, N5, N6 and the N8 which is the centre of attraction for investment. The N8 links the 3 urban centers in Mangaung and therefore is an economic stimulant. The City’s response is the “airport link” project as seen in the list below with an investment of about 4 Million from the National Department of Human Settlements Urban settlements Development Grant (USDG). The projects listed below are in one way or another linked to the ordering transport lines which are the N1, N3, N5, N6 and the N8.

As a natural urban response urban nodes such as Bloemfontein a metropolitan node has its industrialization boosted by the N8, N6 and N1 intersect.  Supportive nodes where projects are located though not mentioned below but shown under the USDG and HSDG priorities on the table on the right,are Winburg, Ventersburg and Kroonstad. The support nodes to the N5 are Winburg, Senekal, Bethlehem and Harrismith. Harrismith also strengthens the activity strength of the N3. The N8 has activity centers exploding in the Bloemfontein CBD, Botshabelo Industrial, Bitshabelo CBD, Thabanchu CBD, the Race Course, and Transwerke. It is in these nodes that indeed the HSDG and USDG spend is reflected.

The first quarter report for Mangaung metro argues that the list below is the focal point.  More information will be received before the second report.

| SIP No. | Project Name | Location | Project Timeframe | Jobs | Costing R | Medium Term Expenditure Framework (MTEF) Budget R |
| --- | --- | --- | --- | --- | --- | --- |
|  | Municipality (District) | GPS Coordinates | Start Date | End Date | Total Jobs Projected | Total Cost of Project | 2013/14 |
|  | PLANNING |  |  |  |  |  |  |  |
| 7 | SERVICES RETICULATION OF MMM LAND WITHIN | Mangaung Metro |  |  |  |  |  | 42,835,000 |
| 7 | AIRPORT LINK (CONTRIBUTION TO SANRAL) | Mangaung Metro |  |  |  |  |  | 4,715,000 |
| 7 | HEAVY REHABILITATION OF EEUFEES ROAD | Mangaung Metro |  | Mar-14 | Aug-14 |  |  | 2,000,000 |
| 7 | MECHANICAL AND ELECTRICAL WORKS FOR NORT | Mangaung Metro | 29 05,215 26 19,442 | Dec-12 | Aug-14 | 519 | 62,312,027 | 40,100,000 |
| 7 | ADDITION OF 10ML TO STERKWATER WWTW | Mangaung Metro | 29 11,318 26 18,675 | Sep-11 | Nov-13 | 221 | 26,536,118 | 16,285,265 |
| 7 | NAVAL HILL RESERVOIR 35 ML | Mangaung Metro | 29 05,822 26 14,346 | Apr-12 | Nov-13 | 250 | 30,045,264 | 16,388,347 |
| 7 | NAVAL HILL RESERVOIR 35 ML | Mangaung Metro | 30 05,822 26 14,346 | Apr-12 | Nov-13 | 250 | 30,045,264 | 6,000,000 |
| 7 | NAVAL HILL RESERVOIR: 3.5KM SUPL AND DEL | Mangaung Metro | 31 05,822 26 14,346 | Apr-12 | Apr-13 | 349 | 41,939,031 | 26,000,000 |
| 7 | LONGRIDGE RESERVOIR SUPPLY LINE 8.3 KM | Mangaung Metro | 29 10,708 26 12,029 | Aug-13 | Jan-15 | 630 | 75,585,576 | 25,000,000 |
| 7 | CENTLEC | Mangaung Metro |  |  |  |  |  |  |
| 7 | ELECTRIFICATION CONNECTIONS DME | Mangaung Metro |  | Oct-13 | Jun-14 |  |  | 7,000,000 |
| 7 | ELECTRIFICATION CONNECTIONS DME | Mangaung Metro |  | Oct-13 | Jun-14 |  |  | 14,000,000 |
|  |  |  |  |  |  |  |  | 200,323,612 |

# SIP 7:Integrated Urban Space and Public Transport Programme: City of Cape Town

Within the PICC, SIP 7 background which is “coordination of planning, implementation or public transport, human settlement, economic and social infrastructure and location decisions into sustainable urban settlements connected by dense transport corridors:” the City of Cape Town’s built environment structure and density profile is informed by four main lines. These in summary according to the Cape Town Spatial Development Framework are:

- The Western Corridor integratesMain Road, the Simons Town originated railway line to Cape Town CBD and continues to the West Coast; simulteneously reinforced by the M3 and N7 freeways.

- The Southern Corridor between Claremont/Wynberg, South East metro, and Strand/ Somerset West. Its support is the R300 and N2. The support activity magnets are the Khayelitsha CBD, Mitchells Plain Town Centre, Phillipi Node, PhillipiIndutsrial Area, Atlantis Town Centre, Atlantis Industrial, Kaptensklip, Strandfontein and Silverstroom-strand. Indeed the projects highlighted for SIP 7 as seen in the list below are in these activity points especially Khayelitsha.

- Eastwards is the Eastern Corridor which has its people magnetic points as Mitchells Plein, Khayelitsha, Bellville/ Kraaifontein. It integrates the Blue Downs Rail link automatically exploding opportunities between the Urban Core Corridor and the South East and vice versa. As a response the City has USDG and HSDG funded projects in among others Bellville.

- The Urban Core Corridor which is one of the oldest and informant corridors to Built form of the City is a prominent integrator for the Northern and Southern and stretches from the Cape Town CBD to the Bellville CBD. The magnetic points are spread and connected by lower order activity corridors, and are by name: Bellville CBD, Athlone CBD, Gatesville, Kenilworth, Vanguard Drive/ N7, Macassar, Heartlands, and Symphony Way/ Modderdam. The map of the City showing the USDG and HSDG spend shows projects within these corridors and activity points.

In the pipeline for the city is the enhancement of the N1 through a corridor development plan and the crafting of a 15 year growth management plan. These initiatives are all anchored on the City’s strategy 2 which as stated in the CTSDF to “manage urban growth…” and “encouraging a more compact form of Development.

For this quarter the SIP 7 list for Projects funded by the USDG and HSDG is as seen below.

| July 2013 |
| --- |
| Dept_IM | WBS | Project Description | Project # | Project KPA's | Consulting % complete | Construction % complete | AREA |
| A1507 | ? | Fisantekraal TRA establishment and installation of basic services | 11/13 | G5 Sub-base hardened surface; gravel access tracks; earthworks | 100% | 90% | Fisantekraal |
| A0904 | C06.00280-F4 | Develop Cemetery: Wallacedene |  | Construct 0.4km access road, 1.1km internal gravel road, 1km fencing, space for approx 18,000 graves and 8 public toilets | 0% | 100% | Wallacedene |
| A1304 | C06.01025-F3 | New Facility Eerste River | 24/11 | 1 clinic; 1250m² | 100% | 90% | Eerste River |
| A1505 | C06.01622-F2 | Rondevlei Housing Project | 59/11 | stormwater platform for 225 erven | 0% | 100% | Rondevlei |
| A0806 | C06.01639-F3 | Retreat Rising Main - Rehab | 101/11 | Construction of 700diameter, 1900m long sewer pipeline. | 100% | 100% | Retreat |
| A0806 | C06.30148-F3 | Mitchells Plain WWTW (USDG) | 18/13 | Modification and improvement of treatment works: construction of extended dewatering building; roadworks; construction of sludge hoppers; linear screens for improved sludge dewatering; replacement of all aeration blowers; inlet works upgrade (screens/ degritting and ancillary equipment); complete electrical upgrade to all sections above to bring plant up to current electrical code | 85% | 15% |  |
| A0806 | C06.30170-F3 | Bellville WWTW-USDG | 84/12 | Civil contract for 20Ml/d extension | 85% | 70% | Bellville |
| A0806 | C06.30201-F3 | Athlone WWTW (USDG) | 149/12 | Design - Build of Mechanical & Electrical Works for Additional Primary Settling Tanks | 70% | 10% | Athlone |
| A1505 | C06.30881-F2 | Wallacedene Phase 10A (PLS) | 116/11 | Provide services to 300 houses | 0% | 0% | Wallacedene |
| A1505 | C06.41496-F2 | Nonqubela Site C Housing Proj (USDG) |  | Provision of professional services | 100% | 0% | Khayelitsha |
| A1505 | C06.41500-F2 | WitsandHsgProj Ph2 Atlantis |  | Bulk Earthworks, Roads and services. | 0% | 50% | Atlantis |
| A1505 | C06.41502-F2 | Nyanga Upgrading Project(PLF&UISP) |  | Providing services 349 Erven | 0% | 25% | Nyanga |
| A1505 | C06.41518-F2 | Belhar/Pentech Strip: 350 Units | 15/13 | Pre-planning | 0% | 0% | Belhar |
| A1505 | C06.41525-F2 | Site C : Survey & Su |  | Survey & Subdivision | 20% | 0% | Khayelitsha |
| A1505 | C06.41531-F2 | The Downs : Housing Project |  | Develop 587 medium density units | 0% | 70% | Manenberg |
| A1505 | C06.41540-F2 | Bardale / Fairdale:Develop4000Units |  | Providing services 4040 Erven | 0% | 70% | Bluedowns |
| A1505 | C06.41565-F1 | Kalkfontein Phase 3 Housing Project |  | Kpa's to be ascertained | 0% | 0% |  |
| A1505 | C06.41568-F2 | Happy Valley Phase 2 - 1000 Units | 122/11 | Providing servises to 1460 units | 0% | 100% | Blackheath |
| A1505 | C06.41570-F2 | Ocean View - Mountain View HsgProj | 88/12 | Bulk earth works, provided services | 0% | 100% | Ocean View |
| A1505 | C06.42371-F3 | 10 Ha Somerset West Hsg Project |  | Provide servises to 216 houses | 0% | 70% | Somerset West |
| A1505 | C07.00027-F2 | Wallacedene Phase 10B (UISP) |  | Serving282 houses | 0% | 40% | Wallacedene |
| A1505 | C07.00246-F2 | Valhalla Park infill 777 units | 41/12 | Provision of civil services | 0% | 0% | Valhalla Park |
| A1505 | C07.00437-F2 | Hazendal Housing Project | 134/12 | Construct 2 X Retention ponds 520m³, construct tarred side walks and erect 750m of fencing. | 0% | 50% | Hazendal |
| A1505 | C07.00438-F2 | Driftsands Housing Project |  | Professional services: consultant | 0% | 0% | Driftsands |
| A0904 | C07.00674-F2 | Maitland Cemetery Upgrade Roads &Infras | 97/11&127/12 | 1km access road; 1km internal road; 3km fencing; Refurbishment of 3 ablutions and 3 office blocks | 0% | 75% | Maitland |
| A1003 | C08.10325-F3 | Pelican Park: Strandfontein Rd Upgr_USDG | 9/11 | Installation of 160 street lights | 0% | 80% | Pelican Park |
| A1505 | C08.15507-F2 | Morkel's Cottage Strand Housing Project |  | Turn key Development | 0% | 0% | Somerset West |
| A1505 | C08.15508-F2 | Delft - The Hague Housing Project | 29/11 | Provision of services to houses | 0% | 70% | Delft |
| A1505 | C08.15509-F2 | Kanonkop (Atlantis Ext12)Housing Project | 51/12 | 78 streetlights; 1.23km + 1.8m wide tarred sidewalk; 1.12km + 900mm wide tarred sidewalk; 500m fencing 2.4m high; 32735 m³ bulk earthworks | 0% | 95% | Atlantis |
| A1505 | C09.15513-F1 | Sir Lowry's Pass (Pinetown &Balestra) | 125/12 | Pre-planning: consultant | 50% | 0% | Somerset West |
| A1505 | C09.15515-F1 | Gugulethu Infill Project Erf 8448/Mau Mau |  | Professional services | 100% | 0% | Gugulethu |
| A0806 | C09.86014-F2 | Pump Station & Rising Main Du Noon | 184/12 | New sewerage pump station & new rising main from pump station to Potsdam WWTW inlet works | 100% | 35% | Du Noon |
| A0904 | C09.94001-F4 | Welmoed Cemetery Development | 114/12 | construct 360m internal roads | 0% | 10% | Eerste River |
| A0904 | C09.94007-F3 | Develop Districtpark: Jack Muller,Bellvi | 120/12 | 100m of stormwater channel rehabilitation; 1383m²stormwater retention pond; park to be built | 0% | 100% | Bellville |
| A0904 | C09.94008-F3 | Khayelitsha Wetlands Park Upgrade | 121/12 | 1 X park (3 park types); 2 X solid waste removal site | 0% | 85% | Khayelitsha |
| A0904 | C09.94009-F3 | Athlone Nantes Upgrade | 126/12 | 1 X park: parking; NMT route; skate park; trim park; footbridge; small amphitheatre; benches; lights; playground equipment; climbing wall; public toilets/ security office | 0% | 100% | Athlone |
| A0904 | C09.94011-F3 | ModderdamCem: Upgrade Roads |  | Tarring of roads | 0% | 0% |  |
| A0904 | C09.94013-F2 | Rusthof Cemetery Upgrade | 114/12 | 360m internal roads | 0% | 80% | Strand |
| A0904 | C09.94014-F2 | Atlantis Cemetery Upgrade | 96/11 | 1km access road, 10km internal road, 5km fencing, space for 52,500 graves and 1 storeroom | 0% | 80% | Atlantis |
| A0904 | C09.94018-F2 | GugulethuCem: Implement Lscape Plans |  | Construction of 320m paved pedestrian precinct and landscaping of the main service route at Gugulethu cemetery. | 0% | 0% |  |
| A0905 | C09.95016-F3 | ImizamaYethu - Develop Sports Complex | 37/11 |  | 100% | 100% | ImizamoYethu |
| A1505 | C10.15503-F1 | Eureka &Leonsdale Housing Project |  | Construct 177 low cost housing | 0% | 0% | Elsies River |
| A1505 | C10.15504-F1 | Green Point Phase 3 Housing Project |  | Kpa's to be ascertained | 0% | 0% |  |
| A1505 | C10.15509-F1 | Hangberg CRU 70 Units | 70/12 & 69/12 | Develop 142 residential units | 30% | 0% | Hangberg |
| A1505 | C10.15510-F2 | HeideveldDuinefontein Housing Project | 2/12 | 6 retention ponds, fencing and road works | 0% | 90% | Heideveld |
| A1505 | C10.15511-F1 | Mitchell's Plain KapteinsklipHousingDev | 2/12 | 6 retention ponds, fencing and road works | 0% | 90% |  |
| A0806 | C10.86033-F3 | Zandvliet WWTW-Extension (USDG) | ? | Design work – rehabilitation of black mac sewer 18 ml upgrade | 15% | 0% |  |
| A0806 | C10.86066-F2 | KhayelitshaDriftsands Site C | 87/11 | 2950m new outflow line; 355mm Ø | 100% | 85% | Khayelitsha |
| A0906 | C10.96010-F2 | New Regional Library KuyasaKhayalitsha | 129/12 | construction of library | 100% | 0% | Khayelitsha |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | PRIMARY | PRIMARY |  |  |  |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation |  | Rehabilitate 1.5km road | 0% | 35% | Bonteheuwel |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation |  | 3.2km tarred road 3.2km paved sidewalks; 2.15km tarred sidewalk & 1.65km tarred sidewalk rehabilitation | 0% | 50% | Gugulethu |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 102/12 | 1.726km tarred road0.74km pipeline; 3.2km paved sidewalks; 2.15km tarred sidewalk & 1.65km tarred sidewalk rehabilitation | 0% | 95% | Gugulethu |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation |  | Professional services: consultant | 40% | 0% | Gugulethu |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 47/11 | Upgrading of 1km road and the installation of 2km curbing, 1km storm water drainage and 1km tarred side walks. | 0% | 100% | Khayelitsha |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 10/11 | 3.5km of roads including 3,5km footways | 0% | 90% | Heideveld |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 43/11 | Construct a 70m X 2.5 high retaining wall | 0% | 100% | ImizamoYethu |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 52/12 | Construction of man holes and 0.3km pipeline 600mm Ø | 0% | 100% | Joe Slovo |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 18/11 | Install 26 - 1.5m X 2m Box culverts across road intersection. Construction of a 500m tarred foot path. | 0% | 70% | Gugulethu |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 18/12 | Widen Lotus canal 40m X 400m, Lay 400m X 30m bidim and pave with erosion concrete blocks. | 0% | 60% | Gugulethu |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 104/12&150/12 | 3km paved road rehabilitation; 3km tarred sidewalks & 2km tarred sidewalks rehabilitation | 0% | 80% | Manenberg |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 19/12 | Rehabilitate 2.7km road | 0% | 100% | Eerste River |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 144/12 | 500m Construct Road and stormwater drainage | 0% | 100% | Strand |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 23/11 | Upgrade canal | 0% | 80% | Lwandle |
| A1003 | C11.10332-F1 | Roads &Stormwater Rehabilitation | 18/12 | Rehab of 5.6km road | 0% | 100% | Kuilsriver |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | PRIMARY | PRIMARY |  |  |  |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 51/12 | Install Bulk services | 0% | 100% | Atlantis |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 54/11 | installation of servises | 0% | 100% | Bluedowns |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj |  | Professional services | 0% | 0% | Bluedowns |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 70/12 | 0.391km new tarred road; 1590m² new paved access collector; 146m² new stormwater channel; 120m stormwater pipeline (450mmØ) | 0% | 0% | Hangberg |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 2/12 | Construct 4 X retention ponds 1226 m³ | 0% | 100% | Heideveld |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj |  | Provide services | 0% | 60% | Blackheath |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 98/11& 99/11 | Construct 1300m tarred roads and provide 1300m storm water drainage. | 0% | 80% | Blackheath |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj |  | Provide services, Construct roads, curbing and side walks |  | 50% | Hazendal |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 85/12 & 98/12 | Develop 587 medium density units | 0% | 0% | Manenberg |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 53/11 | 60,000m³ retention pond; 4km paved sidewalks | 0% | 100% | Ocean View |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 60/12 | Bulk Earthworks | 0% | 100% | Phillipi |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj | 28/12&29/12 | 2.44km new paved access collectors | 0% | 90% | Pelican Park |
| A1003 | C11.10334-F1 | Bulk Roads &Stormwater for Housing Proj |  | Provide proffesional services and bulk earth works | 100% | 70% | Wallacedene |
| A1304 | C11.13106-F3 | Luvuyo clinic extensions for ARV service | 25/11 | Extension of existing clinic. | 100% | 95% | Khayelitsha |
| A1504 | C11.15418-F1 | Langa Hostels CRU Project (461 units) | 4/13. 5/13. 6/13& 7/13 | Provide water and sanitation to 463 units, Roads and storm water and refurbishing. | 0% | 0% |  |
| A1504 | C11.15440-F2 | Scottsdene MIG Project Phase 1 | MIG | Refurbish CRU's | 0% | 100% | Scottsdene |
| A1504 | C11.15442-F1 | Uitsig MIG Project | MIG | Refurbish CRU's | 0% | 100% | Elsies River |
| A1504 | C11.15443-F2 | Woodlands MIG Project | MIG | Refurbish CRU's | 0% | 100% | Mitchells Plain |
| A1504 | C11.15444-F2 | Connaught MIG Project | MIG | Refurbish CRU's | 0% | 100% | Elsies River |
| A1504 | C11.15445-F2 | Manenberg USDG Project |  | zzzz | 0% | 0% |  |
| A1504 | C11.15447-F2 | The Range MIG Project | MIG | stormwater, water reticulation and Fencing | 0% | 80% | Elsies River |
| A1504 | C11.15448-F2 | Hanover Park MIG Project | MIG | stormwater, water reticulation and Fencing | 0% | 40% | Hanover Park |
| A1504 | C11.15449-F2 | Heideveld MIG Project | MIG | stormwater, water reticulation and Fencing | 0% | 60% | Heideveld |
| A1504 | C11.15450-F2 | Marble Flats MIG Project | MIG | stormwater, water reticulation and Fencing | 0% | 20% | Ottery |
| A1505 | C11.15504-F1 | ImizamoYethu - Hout Bay Housing Project |  | land acquisition. | 0% | 0% | ImizamoYethu |
| A1505 | C11.15505-F1 | Scottsdene New CRU Project - 200 unit | 14/12 | Provide services to 200 units | 0% | 100% | Scottsdene |
| A2405 | C11.17518-F2 | Construction of ECD Centre - Leonsdale | 45/11 | Construction of early childhood development centre | 50% | 5% | Elsies River |
| A0806 | C11.86059-F3 | Sandtrap Bridgetown Sewer Pump Station | 19/11 | Construction of sandtrap linked to 1400l/s pumpstation | 100% | 65% | Athlone |
| A0806 | C11.86060-F3 | Philippi Collector Sewer | ? | Planning: Surveying, geotechnical - consultant | 5% | 0% |  |
| A0806 | C11.86063-F3 | Potsdam WWTW - Extension (USDG) | 162/12 | Expand to a 100Ml/d | 100% | 40% | Milnerton |
| A0806 | C11.86077-F4 | Bulk Water Augmentation Scheme (USDG) | ? | Design and land acquisition only | 15% | 0% |  |
| A0904 | C11.94074-F1 | Park Upgrades and Developments | PRIMARY | PRIMARY |  |  |  |
| A0904 | C11.94074-F1 | Park Upgrades and Developments |  | Skate board park, Amp theatre, new bridge, trim park and new play area. | 0% | 0% | Athlone |
| A0904 | C11.94074-F1 | Park Upgrades and Developments | 158/12 | Installation of play equipment, multipurpose ball section, benches, grass, trees, irrigation system. | 0% | 60% | Azalea |
| A0904 | C11.94074-F1 | Park Upgrades and Developments | 36/12 | construct Interactive skateboard park, installation of fencing, land scaping and tree planting | 0% | 50% | Hanover Park |
| A0904 | C11.94074-F1 | Park Upgrades and Developments | 159/12 | Installation of play equipment, benches, drainage system, grass, trees, irrigation system. | 0% | 40% | Elsies River |
| A0904 | C11.94074-F1 | Park Upgrades and Developments | 36/11 | Installation of play equipment, drainage system, grass, trees, irrigation system. | 0% | 20% | Valhalla Park |
| A0904 | C11.94075-F1 | Delft Cemetery Development | 32/12 | 4km internal roads; 1.3km palisade fencing; space for 10750 graves; 10 additional ablutions | 0% | 0% | Delft |
| A1005 | C12.00039-F1 | Wallacedene Public Transport Int:USDG |  | Kpa's to be ascertained | 0% | 0% |  |
| A1005 | C12.09427-F1 | Embayments-Scottsdene-Eon Drive:USDG | 91/11 | 12 embayments (1080m² area to be paved) | 100% | 95% | Scottsdene |
| A1003 | C12.10369-F1 | Scottsdene Housing Project | PRIMARY | PRIMARY |  | PRIMARY | Scottsdene |
| A1003 | C12.10369-F1 | Scottsdene Housing Project | 94/11 | Upgrade 72000m3 to 142 000m3 Detention Pond | 100% | 80% | Scottsdene |
| A1003 | C12.10369-F1 | Scottsdene Housing Project | 92/11 | provision of link and bulk services | 100% | 95% | Scottsdene |
| A1003 | C12.10369-F1 | Scottsdene Housing Project | 89/11 | Develop 12 pockets of open infill land, upgrading of Link and bulk services. 850m of 300mm Ø and 320m of 400mm Ø connector services, 1600m of 160m Ø reticulatio pipe lines. Upgrading of existing 165 L/s to 165 L/s and a new 25L/s. various 160mm Ø to 315mm Ø 2850m Sanitation Main outflow lines. Tarred 1.52 Roads and 0.550km intersections. 185 Street lights. new 1km storm water and .450km rehabilitated. Taxi rank 1080m2(12 embayments) 60m2 2 at each embayment. 7.5km Paved sidewalks. | 100% | 95% | Scottsdene |
| A1304 | C12.13119-F2 | Seawinds Clinic Upgrade &Extentions | 112/12 | extension to existing clinic by 550m² | 100% | 95% | Seawinds |
| A1301 | C12.13120-F2 | Mzamomhle clinic upgrade &ext TB/ARV | ? | Extension to clinic by 366m² | 15% | 0% |  |
| A1304 | C12.13121-F1 | Tafelsig clinic Upgrade &Extentions | 71/12 | professional services for the extension of 1 clinic of 190m² | 20% | 5% | Mitchells Plain |
| A1301 | C12.13122-F1 | Hout Bay/ImizamoYethu - upgrade | ? | Pre-planning for extension of clinic by about 50 to 60m² | 5% | 0% |  |
| A1304 | C12.13125-F1 | Site B youth clinic - replacement | 22/11 | demolish and rebuild the clinic | 100% | 85% | Khayelitsha |
| A1505 | C12.15505-F1 | Masiphumelele Housing Project - Phase 4 | 24/13 | Professional Fees | 0% | 0% |  |
| A1505 | C12.15506-F1 | Edward Street: Grassy Park Development |  | Provide services to 104 houses | 0% | 0% | Grassy Park |
| A1505 | C12.15507-F1 | Pelican Park Phase 1 Housing Project | 61/12 | infrastructure for 2000 subsidy housing units: Water, sewerage, roads & access, stormwater, electricity | 0% | 70% | Pelican Park |
| A1505 | C12.15509-F1 | Dido Valley Housing Development | 25/13 | Professional Fees | 0% | 0% |  |
| A1505 | C12.15510-F1 | Morningstar Durbanville Housing Project | 163/12 | Pre-planning | 0% | 0% | Morningstar |
| A1505 | C12.15512-F1 | Fisantekraal Garden Cities Hsg Project |  | Construct 400 | 0% | 0% | Fisantekraal |
| A1506 | C12.15601-F1 | Scottsdene Housing Project (internal services) | 14/12 | 1.52km + 0.55km new tarred roads | 100% | 95% | Scottsdene |
| A1507 | C12.15702-F1 | Tambo Square |  | UISP 143 units | 70% | 0% |  |
| A1507 | C12.15703-F1 | 8ste Laan Valhalla |  | Budget zeroed | 0% | 0% |  |
| A1507 | C12.15705-F1 | Enkanini |  | UISP 2000 units; construction of access roads | 100% | 40% |  |
| A1507 | C12.15706-F1 | Phola Park Gugulethu |  | UISP project planning and development; viability study | 40% | 0% |  |
| A1507 | C13.15704-F1 | Doornbach | 60/13 | Construction of access roads & related infrastructure | 100% | 85% |  |
| A1507 | C13.15708-F1 | Re-Blocking | PRIMARY | PRIMARY | PRIMARY | PRIMARY |  |
| A1507 | C13.15708-F1 | Re-Blocking | 93/13 | Informal Settlement Re-Blocking - Rebuilding of existing informal structures | 100% | 50% |  |
| A0804 | C12.84261-F2 | High Mast Lighting | PRIMARY | PRIMARY |  |  |  |
| A0804 | C12.84261-F2 | High Mast Lighting | Ex MIG | 3X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 95% |  |
| A0804 | C12.84261-F2 | High Mast Lighting | 87/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 90% | Bluedowns |
| A0804 | C12.84261-F2 | High Mast Lighting | 53/12 | 3X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 100% | Khayelitsha |
| A0804 | C12.84261-F2 | High Mast Lighting | 43/12 | 3X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 100% | Gugulethu |
| A0804 | C12.84261-F2 | High Mast Lighting | 46/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 90% | Phillipi |
| A0804 | C12.84261-F2 | High Mast Lighting | 57/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 90% | Strand |
| A0804 | C12.84261-F2 | High Mast Lighting | 55/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 90% | Mfuleni |
| A0804 | C12.84388-F2 | Electricity - Formal Settlements | N/A | N/A | 100% | 55% | Gugulethu |
| A0806 | C12.86008-F2 | Infrastructure Replace/Refurbish - WWT | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0806 | C12.86008-F2 | Infrastructure Replace/Refurbish - WWT | 103/11 | Aerator being repaired | 0% | 0% | Klipheuwel |
| A0806 | C12.86008-F2 | Infrastructure Replace/Refurbish - WWT | 18/13 | Replacement or refurbishment of aging mechanical and electrical equipment needed for the efficient treatment of the sewerage. | 100% | 95% | Mitchells Plain |
| A0806 | C12.86008-F2 | Infrastructure Replace/Refurbish - WWT | 103/11 | Replacement or refurbishment of aging mechanical and electrical equipment needed for the efficient treatment of the sewerage. | 100% | 95% | Fisantekraal |
| A0806 | C12.86008-F2 | Infrastructure Replace/Refurbish - WWT | 103/11 | Replacement or refurbishment of aging mechanical and electrical equipment needed for the efficient treatment of the sewerage. | 100% | 95% | Kommetjie |
| A0806 | C12.86008-F2 | Infrastructure Replace/Refurbish - WWT | 103/11 | Replacement or refurbishment of aging mechanical and electrical equipment needed for the efficient treatment of the sewerage. | 100% | 95% | Atlantis |
| A0806 | C12.86008-F2 | Infrastructure Replace/Refurbish - WWT | 103/11 | Replacement or refurbishment of aging mechanical and electrical equipment needed for the efficient treatment of the sewerage. | 0% | 0% |  |
| A0806 | C12.86082-F1 | Water Supply at Baden Powell Dr to Khaye | 68/11 | EIA for new main supply line | 40% | 0% | Khayelitsha |
| A0806 | C12.86083-F1 | New Rest Reticulation Rectification | 68/12 | Upgrade sewer mains from 200mm to 300mm (gravity main2) 200mm to 250mm (gravity main 3) and various point repairs (+-88 identified faults)/ Rising main upsized from 150mm to 250mm; pumpstation capacity increased from 49L/s to 57L/s | 55% | 10% | Gugulethu |
| A0806 | C12.86084-F1 | Completion of Langa Collector Sewer | 119/11 | Investigate on the current internal condition of the collector sewer conduit and recommendations | 100% | 5% | Langa |
| A0806 | C12.86091-F1 | Borchards Quarry WWTW | 60/11 | Odour control, security fencing &stercus handling facility upgrade | 60% | 0% | Matroosfontein |
| A0806 | C12.86092-F1 | Cape Flats WWTW | 104/11 | Structural refurbishment of anaerobic digestor (6000m³); sludge regionalisation | 100% | 90% | Zeekoevlei |
| A0806 | C12.86096-F1 | Macassar WWTW Extention (USDG) | 105/11 | provide a standby electricity generator, additional 16ml/d treatment capacity; INSTALLATION OF COMPLETE INFRASTRUCTURE FOR IP CCTV SYSTEM | 100% | 10% | Macassar |
| A0806 | C12.86103-F1 | Scottsdene: Water & Sewerage | 93/11 | new pipelines (850m of 300mm Ø; 320m of 400mm Ø), 1600m pipeline to be reticulated (160mm Ø), upgrade of existing (140L/s to 165L/s) and new (25L/s), 2580m connector service - main outflow lines (from 160mm Ø to 315mm Ø) | 100% | 80% | Scottsdene |
| A0904 | C12.94002-F1 | Klip Road Cemetery Extension | 35/12 | 1km internal road; 855m metal palisade fencing; 15,000 graves | 40% | 0% | Grassy Park |
| A0904 | C12.94010-F1 | Wesbank POS system development |  | Develop Bigstone Park and Putman Park in Wesbank | 0% | 0% |  |
| A0904 | C12.94012-F1 | Macassar POS system development | 123/12 | 1 X recreational park; fencing; pathways; landscaping; mini golf course; skateboard park; multi purpose court; water features and ablution facilities | 0% | 0% | Macassar |
| A0904 | C12.94013-F1 | Upgrade of Watsonia Park |  | Construction of pathways, Landscaping, Supply and installation of park equipment. | 0% | 0% |  |
| A0904 | C12.94015-F1 | Upgrade of Parks in Mfuleni |  | Construction of pathways, Landscaping, Supply and installation of park equipment. | 0% | 0% |  |
| A0904 | C12.94017-F1 | Fencing of Parks (Strand service Area) |  | Kpa's to be ascertained | 0% | 0% |  |
| A0904 | C12.94028-F1 | Cemetery Upgrades & Extensions |  | PRIMARY |  |  |  |
| A0904 | C12.94028-F1 | Cemetery Upgrades & Extensions | 184/12 & 1/13 | Delft Cemetery extension- 500m fencing and new burial blocks. | 0% | 0% | Delft |
| A0904 | C12.94028-F1 | Cemetery Upgrades & Extensions | 119/12 | Acquiring of Landscape Architect Professional services for Eikendal Cemetery. | 0% | 0% | Kraaifontein |
| A0904 | C12.94028-F1 | Cemetery Upgrades & Extensions | 119/12 | Eikendal Cemetery- Erect 280m concrete palisade fence 70m Metal fence | 0% | 100% | Kraaifontein |
| A0904 | C12.94028-F1 | Cemetery Upgrades & Extensions | 110/11 | Provide Surveying services | 0% | 0% | Hout Bay |
| A0904 | C12.94028-F1 | Cemetery Upgrades & Extensions | 22/13 | Professional services for rezoning of land | 0% | 100% | Mfuleni |
| A0904 | C12.94028-F1 | Cemetery Upgrades & Extensions | 23/13 | Welmoed Cemetery- 729 concrete palisade fencing. | 0% | 100% | Eerste River |
| A0904 | C12.94028-F1 | Cemetery Upgrades & Extensions | 22/13 | Wallacedene Cemetery- 42m metal fence. | 0% | 0 | Wallacedene |
| A0904 | C12.94029-F1 | Cemetery Upgrades & Extensions |  | Kpa's to be ascertained | 0% | 0% |  |
| A0904 | C12.94137-F1 | Park Dev. & Upgrades - Informal Settlements |  |  | 0% | 0 |  |
| A0905 | C12.94137-F1 | Park Dev. & Upgrades - Informal Settlements | 36/12 | 1 X skateboard park | 100% | 90% | Hanover Park |
| A0905 | C12.95013-F1 | Sport and Recreation Facilities Upgrade | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0905 | C12.95013-F1 | Sport and Recreation Facilities Upgrade | 36/11 | 1.2m spray park, double storey change room, ablution and community facility, pavements and pathways, street & area lighting, playground equipment,landscaping& sundry works | 95% | 40% | Valhalla Park |
| A0905 | C12.95078-F1 | Valhalla Park - Functional Rec Area | 36/11 | 1.2m spray park, double storey change room, ablution and community facility, pavements and pathways, street & area lighting, playground equipment,landscaping& sundry works | 100% | 40% | Valhalla Park |
| A0905 | C12.95079-F1 | Du Noon SF - Design & Develop Districts | 33/11 | Additional clubhouse and changeroomfacilities.Installation of 2 floodlights. | 100% | 90% | Du Noon |
| A0906 | C12.96037-F1 | Extensions to Libraries | PRIMARY | PRIMARY | PRIMARY | PRIMARY |  |
| A0906 | C12.96037-F1 | Extensions to Libraries |  | Extend existing building; study area, children's section, hall, and some renovations | 60% | 0% |  |
| A1005 | C13.01592-F1 | Wallacedene(Scottsdene) PTF:USDG | 95/11 | Development of 1080m² Taxi Rank | 100% | 0% | Scottsdene |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | PRIMARY | PRIMARY |  |  |  |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 48/11 | 3km new paved side walks, rehabilitate 600m paved side walk, 7km new tarred sidewalks, refurbish 25km tarred side walks, accommodate 1 park | 0% | 70% | Wallacedene |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 24/12 | 0.5km of paved sidewalks and 2.16km of tarred sidewalks | 0% | 100% | Steenberg |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 50/11 | 1km new paved sidewalks, rehabilitate 2.5km paved sidewalks ; 2km new tarred sidewalks, rehabilitate 1km tarred sidewalks | 0% | 99% | Delft |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 34/12 | 10.5km new tarred sidewalks | 0% | 90% | Blackheath |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 22/12 | widening of 0.5km paved sidewalk, 3km new tarred sidewalk, rehab of 1km of tarred sidewalk | 0% | 99% | Bonteheuwel |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide |  | 1.2 km new paved sidewalks; 3km new tarred sidewalk | 0% | 100% | Mitchells Plain |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 38/12 | 1km new paved sidewalks; 3km new tarred sidewalk | 0% | 75% | Steenberg |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 80/11 | widening of 0.5km paved sidewalk, 3km new tarred sidewalk, rehab of 1km of tarred sidewalk | 0% | 100% | Gugulethu |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 81/11 | widening of 0.5km paved sidewalk, 3km new tarred sidewalk, rehab of 1km of tarred sidewalk | 0% | 100% | Gugulethu |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide |  | construct side walks 3km | 0% | 40% | Retreat |
| A1003 | C13.10314-F1 | Non Motorised Transport: City Wide | 23/12 | widening of 0.2km +rehab of 0.2km of paved sidewalk] and [widening of 3km +rehab of 0.5km of tarred sidewalk] | 0% | 70% | Mitchells Plain |
| A1003 | C13.10518-F1 | Construct:Broadway Blvd, Nomzamo/Lwandle |  | Kpa's to be ascertained | 0% | 40% | Lwandle |
| A1301 | C13.13108-F2 | Replacement Clinic Fisantekraal |  | Purchase containers | 100% | 90% |  |
| A1507 | C13.15101-F1 | Urbanisation: Backyards/ Informal Settlements | PRIMARY | PRIMARY |  |  |  |
| A1507 | C13.15101-F1 | Urbanisation: Backyards/ Informal Settlements | 123/11 | 156 new toilets | 0% | 80% | Factreton |
| A1507 | C13.15101-F1 | Urbanisation: Backyards/ Informal Settlements | 152/12&21/13 | Construction of 1.5km access roads | 0% | 100% | Khayelitsha |
| A1507 | C13.15101-F1 | Urbanisation: Backyards/ Informal Settlements | 13/13 | Provision of services to 1115 erven | 0% | 65% | Mfuleni |
| A1507 | C13.15101-F1 | Urbanisation: Backyards/ Informal Settlements |  | Flood calming measures | 0% | 100% | Du Noon |
| A1507 | C13.15101-F1 | Urbanisation: Backyards/ Informal Settlements | 124/12 | 2km access road, gravel | 0% | 100% | Khayelitsha |
| A1507 | C13.15101-F1 | Urbanisation: Backyards/ Informal Settlements | 183/12 | 80 retic standpipes; 90mm Ø; main outflow sanitation connector; 89 new toilets | 0% | 100% | Mfuleni |
| A1505 | C13.15501-F1 | USDG Project Governance |  | Kpa's to be ascertained | 0% | 0% |  |
| A1505 | C13.15502-F1 | USDG Project Governance |  | Kpa's to be ascertained | 0% | 0% |  |
| A1505 | C13.15503-F1 | Khayelitsha CBD Housing Project 402 Units | 44/11&120/11 | Provide Bulk infrastructure for 402 units | 0% | 50% | Khayelitsha |
| A1505 | C13.15507-F1 | Morgans Village B5 / B6 |  | Provide services, roads, stormwater and sewer | 0% | 85% | Mitchells Plain |
| A1506 | C13.15601-F2 | Land Acquisition (USDG) | To be approved by City Council | Land purchases: Gugulethu, Kraaifontein, Phillipi, Strand | 50% | 50% | Strand |
| A1507 | C13.15703-F1 | Hazeldene Housing Project Services | 165/12 | Professional services: consultant | 35% | 5% | Kraaifontein |
| A1507 | C13.15705-F1 | Vissershok (Site Establishment) | 12/13 | The design and construction of civil services for 320 households | 45% | 5% | Milnerton |
| A1507 | C13.15706-F1 | Masonwabe (Site Establishment) | 122/12 | Earthworks and 0.407km fencing; EHP funding also used | 100% | 70% | Kuilsriver |
| A1507 | C13.15707-F1 | Re-Blocking | PRIMARY | PRIMARY |  | PRIMARY |  |
| A1507 | C13.15707-F1 | Re-Blocking | 20/13? | Plumbing supply & installation; clear rubble | 45% | 0% | Hanover Park |
| A1507 | C13.15707-F1 | Re-Blocking | 56/13 | provide hardened gravel platform, gravel access tracks, overland stormwater drainage, water reticulation for tap stands, and chemical toilets | 100% | 5% |  |
| A1507 | C13.15707-F1 | Re-Blocking |  | Masonwabe entrance | 1% | 0% | Kuilsriver |
| A1507 | C13.15707-F1 | Re-Blocking | 21/13 | BM Section - Informal Settlement | 100% | 85% | Khayelitsha |
| A1509 | C13.15901-F1 | Upgr Recreational Facilities Khayelitsha | 141/12 | Pre-planning: Development of Lindela Open Space | 0% | 5% | Khayelitsha |
| A1509 | C13.15902-F1 | Prov. of Multi purpose hall Heinz Park | 142/12&37/13 | Pre-planning: Multi-purpose facility in Heinz Park | 0% | 5% | Phillipi |
| A1509 | C13.15903-F1 | Uprading of C-Hall in Mfuleni | 143/12 | Pre-planning: upgrading of Mfuleni Beer Hall (D Hall) into a multi-purpose community centre | 0% | 5% | Mfuleni |
| A1509 | C13.15904-F1 | Constr pathways existing Informal Settl. | 144/12 | Pre-planning: Pathways in Mfuleni Main Rd &Onverwacht Rd in Strand (informal settlements) | 0% | 5% | Mfuleni |
| A0804 | C13.84081-F2 | Athlone- Philipi: OH Line Undergrounding | 105/12 | Phillipi overhead 132kV powerline replacement with underground cabling | 15% | 5% | Phillipi |
| A0804 | C13.84260-F1 | Street Lighting: City Wide MIG Funding | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0804 | C13.84260-F1 | Street Lighting: City Wide MIG Funding | 30/12 | installation of 171 street lights | 100% | 10% | Pelican Park |
| A0804 | C13.84260-F1 | Street Lighting: City Wide MIG Funding | 90/11 | installation of 185 street lights | 100% | 65% | Scottsdene |
| A0804 | C13.84260-F1 | Street Lighting: City Wide MIG Funding | 42/11 | Istallation of street lights. Eskom designing and implementing. | 100% | 100% | Wallacedene |
| A0804 | C13.84261-F2 | High Mast Lighting | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0804 | C13.84261-F2 | High Mast Lighting | 172/12 | 2X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 100% | Belhar |
| A0804 | C13.84261-F2 | High Mast Lighting | 169/12 | 2X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 95% | Khayelitsha |
| A0804 | C13.84261-F2 | High Mast Lighting | 147/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 15% | Strand |
| A0804 | C13.84261-F2 | High Mast Lighting | 32/13 | 2X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 95% | Crossroads |
| A0804 | C13.84261-F2 | High Mast Lighting | 180/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 5% | Khayelitsha |
| A0804 | C13.84261-F2 | High Mast Lighting | 167/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 60% | Khayelitsha |
| A0804 | C13.84261-F2 | High Mast Lighting | 168/12 | 2X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 5% | Monwabisi |
| A0804 | C13.84261-F2 | High Mast Lighting | 100/12 | 3X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 5% | Milnerton |
| A0804 | C13.84261-F2 | High Mast Lighting | 137/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 95% | Khayelitsha |
| A0804 | C13.84261-F2 | High Mast Lighting | 132/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 95% | Nyanga |
| A0804 | C13.84261-F2 | High Mast Lighting | 116/12 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 95% | Gugulethu |
| A0804 | C13.84261-F2 | High Mast Lighting | 131/12 | 3X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) | 100% | 95% | Mfuleni |
| A0804 | C13.84389-F2 | Electricity - Backyarders | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0804 | C13.84389-F2 | Electricity - Backyarders | 182/12 | Electrification: 954 new connections | 100% | 30% | Hanover Park |
| A0804 | C13.84390-F2 | Electricity - Formal & Informal | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0804 | C13.84390-F2 | Electricity - Formal & Informal | 49/13 | Electrification of 1115 TRA dwellings; construction of NV & LV cabling. | 100% | 100% | Mfuleni |
| A0804 | C13.84390-F2 | Electricity - Formal & Informal | 95/12 | Electrification of 2935 connections; Joe Slovo Ph3 | 100% | 30% | Joe Slovo |
| A0804 | C13.84390-F2 | Electricity - Formal & Informal | 2/13 | service connections for 2989 households (2150 poor) | 100% | 75% | Scottsdene |
| A0804 | C13.84390-F2 | Electricity - Formal & Informal | ? | Relocate 124 service connections | 100% | 90% | IlingeLabahlahli |
| A0804 | C13.84390-F2 | Electricity - Formal & Informal |  |  | 100% | 100% | Khayelitsha |
| A0805 | C13.85000-F2 | Development of Landfill Infrastructure | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0805 | C13.85000-F2 | Development of Landfill Infrastructure | 174/12 | Design and build of 2 X 1500ton portal cranes | 100% | 60% | Athlone |
| A0805 | C13.85000-F2 | Development of Landfill Infrastructure | 175/12 | Design & construction of refuse transfer station and public drop off | 100% | 71% | Bellville |
| A0805 | C13.85000-F2 | Development of Landfill Infrastructure | 50/13 | construction of civil engineering works and installation of geosynthetic membranes | 100% | 90% | Milnerton |
| A0806 | C13.86048-F2 | Replace &Upgr Water Network (USDG) | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0806 | C13.86048-F2 | Replace &Upgr Water Network (USDG) | 73/12 | PRIMARY: Repairing of valves, isolating & fire hydrants in Khayelitsha. | 100% | 70% | Khayelitsha |
| A0806 | C13.86053-F1 | Cape Flats III | 104/11&19/13 | Digester rehabilitation, Dewatered sludge drying facility | 75% | 20% | Strandfontein |
| A0806 | C13.86074-F1 | Pump Stn Rehab ( Citywide) | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0806 | C13.86074-F1 | Pump Stn Rehab ( Citywide) | 78/11 | PRIMARY: Upgrade of Three Foul Sewer Pump Station; Additional pump station and upgrading the existing pump station (400mm diameter, 2000m long bulk water) | 90% | 5% | Fish Hoek |
| A0806 | C13.86074-F1 | Pump Stn Rehab ( Citywide) | 85/11 | Bulk earthworks, construction of a formal access road and Bulk infrastructure. | 100% | 70% | Khayelitsha |
| A0806 | C13.86075-F1 | Rehab of Sewer Network (Citywide) | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0806 | C13.86075-F1 | Rehab of Sewer Network (Citywide) | 72/12 (86/11?) | 20 X New Sewer Connections of Various Lengths and Depths; rehabilitation of 75 manholes (5000m pipeline); repair of various damaged and collapsed sewer pipelines | 100% | 40% | Khayelitsha |
| A0806 | C13.86077-F1 | Bulk Sewer (Housing Projects) | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0806 | C13.86077-F1 | Bulk Sewer (Housing Projects) | 33/12 | 20.37l/s capacity main outflow lines; 250mm diameter | 100% | 60% | Blackheath |
| A0806 | C13.86077-F1 | Bulk Sewer (Housing Projects) | 7/12 | outfall bulk sewer lines; 14l/s - 25l/s capacity; Ø160mm (800m) and Ø200m (350m); total length 1150m | 85% | 10% | Gugulethu |
| A0806 | C13.86077-F1 | Bulk Sewer (Housing Projects) | 114/11 | PRIMARY: Provide 99l/s to the dido valley system and provide 200/250mm diameter, 2200m long water pipeline | 0% | 0% | Dido Valley |
| A0806 | C13.86077-F1 | Bulk Sewer (Housing Projects) | 69/12&91/12 | 17m outflow line; 0.85l/s; 160mmØ | 100% | 5% | Hangberg |
| A0806 | C13.86077-F1 | Bulk Sewer (Housing Projects) | N/A | N/A | 5% | 5% |  |
| A0806 | C13.86077-F1 | Bulk Sewer (Housing Projects) | N/A | N/A | 0% | 5% | Langa |
| A0806 | C13.86078-F1 | Bulk Water ( Housing Projects) | PRIMARY | PRIMARY |  | PRIMARY |  |
| A0806 | C13.86078-F1 | Bulk Water ( Housing Projects) | 10/12 | 186m link bulk water line (connect internal water lines); 12 l/s capacity; Ø160mm | 85% | 10% | Gugulethu |
| A0806 | C13.86078-F1 | Bulk Water ( Housing Projects) | 69/12&91/12 | 260m new main supply line; 0.74l/s/ 110mm Ø | 85% | 10% | Hangberg |
| A0806 | C13.86078-F1 | Bulk Water ( Housing Projects) | N/A | N/A | 5% | 5% |  |
| A0806 | C13.86078-F1 | Bulk Water ( Housing Projects) | 100/11 | Bulk water provision, 1570m X 250mm pipeline | 100% | 90% | Blackheath |
| A0806 | C13.86078-F1 | Bulk Water ( Housing Projects) | 31/12 | 12500m pipe for reticulation; 30l/s capacity; 150mm to 250mm diameter | 100% | 75% | Pelican Park |
| A0904 | C13.94001-F1 | Park Upgrades and Developments | PRIMARY | PRIMARY |  |  |  |
| A0904 | C13.94001-F1 | Park Upgrades and Developments |  | Development and construction of Smart Park in NY 110 Gugulethu. | 0% | 0% |  |
| A0904 | C13.94001-F1 | Park Upgrades and Developments |  | Kpa's to be ascertained | 0% | 0% |  |
| A0904 | C13.94001-F1 | Park Upgrades and Developments |  | To construct ablution facilities and office space. To supply and install gym play equipment ,wooden play equipment. To construct spray fountain and develop the proteace garden and lastly planting and landscaping. Laying of kikuyi roll-on lawn. | 0% | 0% |  |
| A0904 | C13.94001-F1 | Park Upgrades and Developments |  | Kpa's to be ascertained | 0% | 0% |  |
| A0904 | C13.94001-F1 | Park Upgrades and Developments |  | Request for Professional services | 0% | 0% |  |
| A0904 | C13.94001-F1 | Park Upgrades and Developments |  | Kpa's to be ascertained | 0% | 0% |  |
| A0904 | C13.94001-F1 | Park Upgrades and Developments |  | Develop community gardening projects | 0% | 0% |  |
| A0905 | C13.95019-F2 | Synthetic Pitch-Nyanga | 80/12 | Installation of an artificial synthetic turf | 0% | 0% | Nyanga |
| A0905 | C13.95022-F2 | Synthetic Pitch Gugulethu | 81/12 | Installation of an artificial synthetic turf to existing field | 0% | 0% | Gugulethu |
| A0905 | C13.95025-F1 | Westridge Artificial Turf Mitchells Plain | 77/12 | Construction of a full synthetic size soccer pitch (9400m2), drainage system, lighting and ancillary soccer equipment | 0% | 0% | Mitchells Plain |
| A0905 | C13.95026-F1 | Langa Artificial Hockey Pitch | 82/12 | Installation of an artificial synthetic turf (100X60m) formal hockey field | 0% | 0% | Langa |
| A0905 | C13.95027-F1 | Ocean View Spray Pool | 75/12 | installation of an artificial hockey pitch | 0% | 0% | Ocean View |
| A0905 | C13.95040-F1 | ImizamoYethu SC Upgrade (Club house) | 37/11 | Upgrade clubhouse | 0% | 0% | ImizamoYethu |
| A0905 | C13.95072-F1 | Scottsville-Bloekombos Node - Spraypark | 76/12 | Develop spray park | 0% | 0% | Kraaifontein |
| A0905 | C13.95073-F1 | Du Noon Node - Spraypark | 33/11 | Modification of Hall | 0% | 0% | Du Noon |
| A0905 | C13.95074-F1 | Nyanga / Cross Roads Node - Spraypark | 80/12 | Spray park | 0% | 0% | Nyanga |
| A0905 | C13.95075-F1 | Khayelitsha Node - Spraypark | 83/12 | spray park, clubhouse | 0% | 0% | Khayelitsha |
| A0905 | C13.95076-F1 | Synthetic Pitch - Scottsdene | 78/12 | Installation of an artificial synthetic turf to existing field | 0% | 0% | Scottsdene |
| A0905 | C13.95077-F1 | Solomon Mahlangu Hall Modification | 129/12 | Modification of Hall | 0% | 0% | Khayelitsha |
| A0216 | C14.00078-F1 | Preliminary Design for MURP |  |  | 0% | 0% |  |
| A1003 | C14.10313-F1 | Pedestrian Network & Universal Access |  | The project scope comprised of the construction of a combined pedestrian & cycling (Non-Motorised Transport - NMT) facilities, together with hard and soft landscaping. The works include design of 560m of Military Road widening, new street lighting and upgrade of two intersections. The NMT facilities forms an integral part of the City of Cape Town’s Transport Master Planning Strategy | 100% | 65% |  |
| A1003 | C14.10316-F1 | Roads &Stormwater Rehabilitation |  | kpa's to be ascertained | 0% | 0% |  |
| A1003 | C14.10321-F1 | Bulk Roads &Stormwater for Housing Proj | PRIMARY | PRIMARY | 0% | 0% |  |
| A1003 | C14.10321-F1 | Bulk Roads &Stormwater for Housing Proj | 82/13 | Provision of bulk roads &stormwater services with its associated stormwater pipelines | 0% | 0% |  |
| A1003 | C14.10321-F1 | Bulk Roads &Stormwater for Housing Proj |  | Kpa's to be ascertained | 0% | 0% |  |
| A1003 | C14.10321-F1 | Bulk Roads &Stormwater for Housing Proj | 64/13 | Provision of Sewer infastructure. Construct a 150m 50Ø water pipeline, construct a 150m sewer pipeline, | 0% | 0% |  |
| A1003 | C14.10321-F1 | Bulk Roads &Stormwater for Housing Proj |  | Kpa's to be ascertained | 0% | 0% |  |
| A1003 | C14.10359-F1 | Nomzamo Access Bridge & PTI |  | Construction of NMT bridge across railway line. | 5% | 0% |  |
| A1510 | C14.15101-F1 | Urbanisation: Informal Settlements Upgrd |  |  |  |  |  |
| A1506 | C14.15601-F2 | Land Acquisition (USDG) |  | Stage: Planning |  |  |  |
| A1507 | C14.15701-F1 | Monwood - UISP Project |  | Name of Consultant: FaiselMoosa (Knight Piesold) |  |  |  |
| A1507 | C14.15702-F1 | Shukushukuma - UISP Project |  |  |  |  |  |
| A1507 | C14.15703-F1 | Burundi Mfuleni - UISP Project |  |  |  |  |  |
| A1507 | C14.15704-F1 | Sweet homes - UISP Project |  |  |  |  |  |
| A1507 | C14.15705-F1 | Strandfontein - UISP Project |  |  |  |  |  |
| A0216 | C14.15904-F1 | Construction of pathways in existing informal settlements |  |  |  |  |  |
| A1803 | C14.18303-F1 | Quality Public Spaces - Citywide | PRIMARY | PRIMARY | PRIMARY | PRIMARY |  |
| A1803 | C14.18303-F1 | Quality Public Spaces - Citywide |  | Upgrade to Langa Station Precinct South | 100% |  |  |
| A0804 | C14.84260-F1 | Street Lighting: City Wide USDG Funding | PRIMARY | PRIMARY | PRIMARY | PRIMARY |  |
| A0804 | C14.84260-F1 | Street Lighting: City Wide USDG Funding |  | Kpa's to be ascertained | ? | ? |  |
| A0804 | ? | High Mast Lighting | PRIMARY | PRIMARY |  |  |  |
| A0804 | C13.84261-F2 | High Mast Lighting | 8/13 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) floodlights | 0% | 0% | Du Noon |
| A0804 | C13.84261-F2 | High Mast Lighting | 9/13 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) floodlights | 0% | 0% | Du Noon |
| A0804 | C13.84261-F2 | High Mast Lighting | 32/13 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) floodlights | 0% | 0% |  |
| A0804 | C13.84261-F2 | High Mast Lighting | 10/13 | 1X40m high mast pole with 6X1000W High Pressure Sodium (HPS/T) floodlights | 0% | 0% | Du Noon |
| A0804 | C14.84389-F2 | Electrification- Backyarders | PRIMARY | PRIMARY | - | - |  |
| A0804 | C14.84389-F2 | Electrification- Backyarders | ? | service connections for backyarders | 100 | 40 |  |
| A0804 | C14.84390-F2 | Electrification- Formal & Informal | PRIMARY | PRIMARY | - | - |  |
| A0804 | C14.84390-F2 | Electrification- Formal & Informal | 86/13 | Medium and low voltage; and service connections | 80 | 20 |  |
| A0804 | C14.84390-F2 | Electrification- Formal & Informal | 33/13 | Medium and low voltage; and service connections | 100 | 60 |  |
| A0805 | C14.85001-F2 | Solid Waste Management Infrastructure | PRIMARY | PRIMARY | PRIMARY | PRIMARY |  |
| A0805 | C14.85001-F2 | Solid Waste Management Infrastructure |  |  |  |  |  |
| A0806 | C14.86020-F1 | Pump Stn Rehab ( Citywide) | ? | Pumpstation rehabilitation - city wide | 100 | 0 |  |
| A0806 | C14.86022-F1 | Rehab of Sewer Network (Citywide) | 35/13 | Rehabilitation of sewers and pipelines | 70 | 30 |  |
| A0806 | C14.86023-F1 | Rehab of Water Network (Citywide) | ? | City wide rehab of bulk water network | 5 | 0 |  |
| A0806 | C14.86038-F1 | Bulk Sewer (Housing Projects) | ? | KPAs to be established | ? | ? |  |
| A0806 | C14.86039-F1 | Bulk Water ( Housing Projects) | PRIMARY | PRIMARY | - | - |  |
| A0806 | C14.86039-F1 | Bulk Water ( Housing Projects) | ? | bulk connections (greenfields) | 100 | 20 |  |
| A0806 | C14.86055-F3 | Development of Additional Infrastructure | PRIMARY | PRIMARY | - | - |  |
| A0806 | C14.86055-F3 | Development of Additional Infrastructure | ? | 11kv upgrade | ? | ? |  |
| A0806 | C14.86056-F1 | Spes Bona Reservoir 35 Ml | ? | EIA / design only | 10 | 0 |  |
| A0806 | C14.86073-F1 | Fisantekraal Housing Project (Garden Cities)- Water | 72/13 | Water connection services - 7150m; diameters 400mm for 5010m; 500mm for 210m; 200mm for 1930m | 100 | 10 |  |
| A0806 | C14.86074-F1 | Fisantekraal Housing Project (Garden Cities)- Sewer | 75/13 | Sewer connection services - 4102m; diameters 600mm for 1259m; 450mm for 62m; 400mm for 26m; 355mm for 585m; 315mm for 680m; 250mm for 620m; 200mm for 870m | 100 | 10 |  |
| A0904 | C14.94059-F1 | Park Upgrade: Uitsig |  | Installation of play equipment, multipurpose ball section, benches, grass, trees, irrigation system. | 0% | 0% |  |
| A0904 | C14.94060-F1 | Park Upgrade: Netreg |  | Installation of play equipment, multipurpose ball section, benches, grass, trees, irrigation system. | 0% | 0% |  |
| A0904 | C14.94061-F1 | Park Upgrade: Ravensmead |  | Installation of play equipment, multipurpose ball section, benches, grass, trees, irrigation system. | 0% | 0% |  |
| A0904 | C14.94106-F1 | Installation of Playground Equipment |  | Installation of alternative play equipment in Wards 19, 14 and 11 | 0% | 0% |  |
| A0904 | C14.94123-F1 | Nomzamo Park Suburb POS Development |  | ########################## | 0% | 0% |  |
| A0904 | C14.94126-F1 | District Park Atlantis |  | 1.) Appointment of Landscape Architect to complete Public Participation processes & Master Plan. 2.) Outcome of Landscape Architect will determine next phase; Appointment of Architect, Implementation of Phase 1 | 0% | 0% |  |
| A0904 | C14.94127-F1 | District Park NY10 |  | Appointment of professional services –Landscape architect, for developing a Master plan for NY 10 District Park. | 0% | 0% |  |
| A0904 | C14.94128-F1 | Park Upgrades Hanover Park |  | Upgrade of Surran road Park | 0% | 60% |  |
| A0904 | C14.94129-F1 | Parks Upgrades Manenberg |  | Construction of a Park in Manenburg (site still to be chosen) | 0% | 0% |  |
| A0904 | C14.94132-F1 | Park Upgrades in Browns Farm |  | Erect fencing, Installing benches and tables, Lay lawns, Planting trees and installation of play items | 0% | 0% |  |
| A0904 | C14.94133-F1 | Park Upgrades in SamoraMachel |  | Erect fencing, Installing benches and tables, Lay lawns, Planting trees and installation of play items | 0% | 0% |  |
| A0904 | C14.94134-F1 | Park Upgrades in Vrygrond |  | Kpa's to be ascertained | 0% | 0% |  |
| A0904 | C14.94135-F1 | Valhalla Park Family Park (irrigation) |  | Provision of irrigation for the Valhalla Park Family Park | 0% | 0% |  |
| A0905 | C14.95005-F2 | Sport & Recreation Facilities Upgrade |  | completion of structural, civil, mechanical and electrical engineering works required for the installation of the construction of container architecture and a spray park at Du Noon sportsfield. The building and services is to be constructed using refurbished shipping containers erected in a layout as designed and supported by structural steel and reinforced concrete works. | 100% | 40% |  |
| A0905 | C14.95022-F1 | Synthetic Pitch - Steenberg | 51/13 | Provision of a FIFA 1Star standard soccer pitch with synthetic grass which includes the construction of sub-surface drainage system to accommodate the synthetic turf surfacing, provision of soccer goal and set of flags and maintenance equipment and the installation of irrigation system for watering the pitch. The size of the pitch including run off is 110m x 85m. | 50% | 0% |  |
| A0905 | C14.95023-F1 | Synthetic Pitch - Heideveld | 54/13 | Provision of a FIFA 1Star standard soccer pitch with synthetic grass which includes the construction of sub-surface drainage system to accommodate the synthetic turf surfacing, provision of soccer goal and set of flags and maintenance equipment and the installation of irrigation system for watering the pitch. The size of the pitch including run off is 110m x 85m. |  |  |  |
| A0905 | C14.95024-F1 | Synthetic Pitch - Cross Roads | 55/13 | Provision of a FIFA 1Star standard soccer pitch with synthetic grass which includes the construction of sub-surface drainage system to accommodate the synthetic turf surfacing, provision of soccer goal and set of flags and maintenance equipment and the installation of irrigation system for watering the pitch. The size of the pitch including run off is 110m x 85m. | 50% | 0% |  |
| A0905 | C14.95025-F1 | Synthetic Pitch - Kewtown | 53/13 | Provision of a FIFA 1Star standard soccer pitch with synthetic grass which includes the construction of sub-surface drainage system to accommodate the synthetic turf surfacing, provision of soccer goal and set of flags and maintenance equipment and the installation of irrigation system for watering the pitch. The size of the pitch including run off is 110m x 85m. | 50% | 0% |  |

SIP 18: WATER AND SANITATION:Addressing backlogs in water and sanitation; maintenance of water and sanitation infrastructure, which are “near collapse” in some municipalities; construction of sewerage plants

# CROSS CUTTING SIPS: SIP SKILLS DEVELOPMENT: TECHNICAL CAPACITY UNIT

No report received yet though there is ongoing work.