These three months have seen the provisional selection of the 2014/15 evaluations, and most evaluations for 2013/14 underway. The major problem is delays on evaluations funded by Human Settlements (due to their very slow procurement system), and also a delay in reporting on their improvement plan for ECD by Social Development. A very significant Guideline has been produced with Treasury on Planning Implementation Programmes, providing minimum standards for these programme plans. A lot of work has been undertaken to help ensure effective demand for evaluations including work with the Appropriations Committee (study tour to E Africa), planning a course for DGs, and co-organising the SAMEA Conference. An evaluation repository on the DPME website has been launched with 70 evaluations, which is available to the public.

Evaluations being taken forward

Four evaluations have now been completed including the pilot evaluation of Early Childhood Development (ECD) and three of the 2012/13 evaluations (Grade R, Business Process Outsourcing Scheme, Land Recapitalisation) and these three reports are on their way to the clusters and then Cabinet. 3 others from 2012/13 are close to completion while two DHS evaluations are delayed. Of the 15 2013/14 evaluations, 7 were underway by 30 September, two started the first week of October, five evaluations are in final contracting processes (three of them DHS evaluations), and DBE has requested to drop the evaluation of the National School Curriculum as a Ministerial Review is looking at this. Annex 1 has the status on each of these.

Development of policies and guidelines

- Guidelines now available - TORs for Evaluations, Guideline for Peer Reviews, Template for Evaluation Project Plan, TORs for Evaluation Steering Committees and Guideline for Inception Phase, Management Response, Improvement Plan, Communication, Provincial Evaluation Plans. In addition a very significant Guideline has been produced on Planning Implementation Programmes. This will be taken to Cabinet.

- 5 draft guidelines have been produced on Diagnostic Evaluation, Implementation Evaluations, Impact Evaluations, Economic Evaluations and Evaluation Synthesis. These will be finalised in November.

Capacity development

- A major contract around training started in August with the Centre for Learning on Evaluation and Results (CLEAR) with support from DFID. This will include Course 1 for evaluations selected for the 2014/15 Plan, Course 2 for evaluations selected in 2012/13 and 2013/14. In addition Course 3 on Methodology will be developed and piloted, as well as Course 4 on Planning Implementation Programmes and Design Evaluation. A training on logframes using the logframe in the Guideline on Planning Implementation Programmes was held with National Treasury in August. 156 people have been trained to date (50% of target).

- A course with UCT for Director Generals on evidence-based policy-making and implementation will be held 18-20 November 2013 with funding from DFID. This will aim to build support from senior management for evidence-based policy-making and implementation including the use of M&E.

- A successful study tour was organised to Uganda and Kenya with Parliament’s Appropriations Committee from 29 June to 6 July 2013. This included meeting with Parliaments as well as government M&E staff. A report is available.

Quality assurance

- A repository of evaluations conducted for government since 2006 was launched on 18 September at the SAMEA Conference. This can be accessed at http://evaluations.dpme.gov.za/sites/EvaluationsHome/SitePages/Home.aspx

- A design clinic was held 12-13 September to critique the emerging TORs for the 2014/15 evaluations. Top international and national evaluators participated.

Research

- Work will start in October on commissioning a diagnostic and research strategy identifying the role of DPME within the research-policy-practice nexus, specifically in the use of evidence for policy-making and implementation.

- DPME is asking CLEAR to manage some research grants for doctoral or post-doctoral research on elements of DPME’s work. The research should start in 2014.

- Two research assignments are underway – one on use of time by DGs, and on evaluation Norms and Standards.

Evaluation and research evidence shared

- Paper written for the inaugural edition of the African Journal of Evaluation with Stephen Porter of CLEAR, based on the African M&E workshop held in March 2012.

- Paper written for African Development Bank Publication, Evaluation Matters for September 2013.

- DPME cofunded and co-organised the SAMEA Conference in 2013 on Meaningful Evaluation: Improving Use and Results from 18-20 September. A number of papers were submitted by DPME and partners around the government evaluation system, and we are organising training prior, including on the national evaluation system.

- Article written for Canadian Journal of Evaluation on the development of evaluation competences.

- DPME is co-organising a South-South Roundtable in November with countries from Latin America, Africa and Asia on the demand & use of evidence in policy-making and implementation

Management

- National Evaluation Plan 2014/15 to 2016/17 – 15 evaluations have been selected (see Annex 2).

- Departmental Evaluation Plans – three departments now have departmental plans: Trade and Industry; Science and Technology; and Rural Development.

- Provincial Evaluation Plans – Western Cape Plan for 2013/14 and Gauteng have provincial evaluation plans. Free State and North West are in the process of developing one and discussions have been held with Limpopo.

- Panel of service providers – other government departments and provinces are now seeking to use the panel. Our procurement system is proving to be far faster and more efficient than most departmental systems. However there are weaknesses in the panel and training of the panel will be encouraged. A big weaknesses is only one university is actively bidding for evaluations so we are missing a major source of expertise.

- Staff – two Directors and a Deputy Director Programme Administration started in August/September.

Issues arising

- We are seeing a variety of gaming responses by departments as challenging evaluations emerge. This year is going to be very interesting as we see how to deal with this.

- A challenge as we move forward is the balance between work on specific evaluations in the National Evaluation Plan, and support to evaluations across government. Discussions at the DPME strategic planning suggest we are likely to reduce from 15 to 10 evaluations in the NEP while more effort goes on supporting evaluations across government.

Priorities for the next three months

- The first evaluations from the 2012/13 plan are completing and the processes of management response, improvement plans, and submission to cluster and Cabinet will be happening. All the 2013/14 evaluations are starting, except DHS evaluations which are delayed.

- Starting development of a research strategy which will involve consultations within and outside DPME.

Annex 1:	Evaluation Status Report 30 September 2013

| NEP | Reference | Name of Evaluation | Department(s) responsible for the programme being evaluated | Date of contract & Service Provider to carry out evaluation | Current Stage | Anticipated or actual date of receipt of final report | Anticipated or actual date of Cabinet approval or presentation to Parliament |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2011/12 | 11/11033 | Diagnostic Review of Early Childhood Development (ECD) | Social Development Basic Education Health | 27 October 2011- HSRC | Evaluation completed in June 2012. Improvement Plan completed in October 2012. First progress report on improvement plan awaited from DSD. Report has taken over 3 months to produce. A second letter has been written to DSD requesting the report. | Final report approved by Steering Committee 15 June 2012 and report on DPME website. | Presented to Basic Education Portfolio Committee in June 2013 |
| NEP 2012/13 | 12/0288 | Evaluation of Business Process Services Programme | Trade and Industry | 3 October 2012 - Genesis Analytics | Evaluation report completed. Management response received from Department. Workshop for Improvement Plan scheduled for 2 September 2013 | May 2013 | October 2013 |
|  | 12/428 | Impact Evaluation of Grade R (reception year of schooling) | Basic Education | 12 December 2012 -Stellenbosch University | Evaluation report completed. Management response requested (DG DPME & DBE to meet); cab memo drafted; discussion around a implementation evaluation for 2014/15 | 28 May 2013 | November 2013 |
|  | 12/0287 | Implementation Evaluation of Nutrition Programmes addressing under 5s | Health Rural Development Social Development Agriculture | 06 November 2012- Khulisa Management Services | Draft final report received and discussed at workshop with stakeholders | December 2013 | February 2014 |
|  | 12/410 | Implementation Evaluation of Land Recapitalisation and Development (RECAP) programme | Rural Development | 11 December 2012- University of Pretoria | Final report approved by Steering Committee 27 Sept ‘13 | 27 September 2013 | January 2014 |
|  | 12/409 | Implementation Evaluation of Comprehensive Rural Development Programme (CRDP) | Rural Development | 11 December 2012- Impact Economix | Final draft report received and comments from Steering Committee forwarded to SP. Final report due 1st week of Oct. Approval date to be set for week of 7-11 Oct | 11 October 2013 | January 2014 |
|  | Procured by DHS | Implementation Evaluation of Integrated Residential Development Programme (IRDP) | Human Settlements | Call for proposals have been made and recommendation for service provider with DG DHS for approval. | ToR approved, tender issued. Awaiting bid assessment outcome, bid sat on the 26th September. Extensive delays due to DHS procurement process. | April 2014 | July 2014 |
|  | Procured by DHS | Implementation Evaluation of Urban Settlements Development Grant (USDG) | Human Settlements | PDG. SLA waiting for DG DHS signature. | Design evaluation report submitted and validation workshop held 26th, PDG will soon begin the implementation evaluation phase. Extensive delays due to DHS procurement process. | March 2014 | June 2014 |
|  | 12/427 | Impact evaluation of National School Nutrition Programme | Basic Education | The evaluation started & it was stopped due to poor quality | First evaluation stopped. DBE have indicated they wish to proceed with revised concept. Awaiting concept from DBE. | N/A | N/A |
| Other | 12/0468 | Formative Evaluation of the Presidential Intervention within the King Sabata Dalindyebo Municipality (KSD). | DPME | 1 March 2013 - Impact Economix | Field work report submitted | November 2013 | February 2014 |
| NEP 2013/14 | 12/0536 | Implementation Evaluation of Government Coordination System (clusters/MinMECs and Implementation Forums) | Presidency | 20 March 2013 - Impact Economix | Research work completed. Draft report received. Findings discussed at FOSAD Manco. | November 2013 | March 2014 |
|  | 13/0836 | Implementation Evaluation of the Export Marketing Investment Assistance Incentive Incentive Programme (EMIA) | Trade and Industry | 14 August 2013: DNA Economics (Pty) Ltd | TORs developed and agreed with dept. Call for proposals issued and service provider selected. Service Provider submitted 1st draft literature review. The document sent to ST members and peer reviewers for comments | 6 December 2013 | March 2014 |
|  | 13/0934 | Evaluation of the Support Programme for Industrial Innovation (SPII) | Trade and Industry | Genesis Analytics | TORs developed and agreed with dept. Call for proposals issued, service provider appointed and steering committee made comments to update the final inception report | March 2014 | June 2014 |
|  | 13/0933 | Evaluation of Technology and Human Resources for Industry Programme (THRIP) | Trade and Industry | Business Enterprises and University of Pretoria | TORs developed and agreed with dept. Call for proposals issued, service provider appointed and steering committee made comments to update the final inception report | March 2014 | June 2014 |
|  | 13/0856 | Evaluation of Military Veterans Economic Empowerment and Skills Transferability and Recognition Programme | Military Veterans | Singizi Consulting | TORs developed and agreed with dept. Call for proposals issued, Service Provider contract signed and evaluation has started. | March 2014 | June 2014 |
|  | 6 | Evaluation of Advanced Manufacturing Technology Strategy (AMTS) | Science and Technology | Not yet appointed | TORs finalised. Initial delay with Call for Proposals in September – too little interest from service providers. Rescheduled for October 2013. | April 2014 | June 2014 |
|  | 13/0926 | Evaluation of Tax compliance cost of small businesses | SA Revenue Service | Genesis Analytics | TORs finalised, service provider appointed, 2 steering committee meetings held. Evaluation started 30 August 2013. Inception Report accepted by SC 23/09/2013. Instrument development and data-collection preparation underway. | March 2014 | June 2014 |
|  | 8 | Evaluation of Community Work Programme (CWP) | Cooperative Governance | Not yet appointed | TORs developed but currently being revised. SC met 19/09/2013. | June 2014 | September 2014 |
|  | 13/0766 | Evaluation of Land Restitution Programme | Rural Development and Land Reform | Genesis Analytics 28 June 2013 | TORs developed and agreed with dept. Call for proposals issued. Service Provider Contract Signed. Evaluation plan, literature view and instrument design complete | January 2014 | April 2014 |
|  | 13/0958 | Evaluation of Comprehensive Agricultural Support Programme | Agriculture, Forestry and Fisheries | Business Enterprises at University of Pretoria. 6 September 2013. | TORs developed and agreed with dept. Call for proposals issued. Service Provider Contract Signed Work underway. | March 2014 | June 2014 |
|  | 11 | Evaluation of Upgrading of informal Settlement | Human Settlements | Not yet appointed | Call was made, Proposals were assessed and winning tender was double the budgeted amount. Bid Advisory Committee recommended that the tender be re-advertised. Tender was re-advertised. Extensive delays due to DHS procurement process. | June 2014 | September 2014 |
|  | 12 | Evaluation of Access to the City | Human Settlements | Not yet appointed | Final comments have been made on the ToRs and waiting go ahead to advertise from DHS. Extensive delays due to DHS procurement process. | June 2014 | September 2014 |
|  | 13 | Evaluation of Provision of State Subsidised Housing (Assets) | Human Settlements | University of Free State | University of Free State has been appointed to do the work. In the process of finalising SLA and inception meeting will happen on the 10th Oct 13. Extensive delays due to DHS procurement process. | April 2014 | July 2014 |
|  | 14 | Evaluation of Impact Evaluation of the Outcomes Approach | DPME | Not yet appointed | TORs developed and agreed by Steering Committee. Call for proposals issued. Negotiating with service provider. | May 2014 | August 2014 |
|  | 13/0812 | An Impact Assessment of the Micro Agricultural Financial Institution of South Africa (MAFISA) | Agriculture | Business Enterprise-University of Pretoria 5 August 2013 | Work started but SLA not signed. To be signed by 4 Oct. inception phase is now complete. | March 2014 | June 2014 |
|  |  | Evaluation of quality of National Senior Certificate (Matric) | Basic Education | Not yet appointed | DBE has requested not to take forward the evaluation. May be replaced by Implementation Evaluation of Grade R |  |  |
| NEP 2014/15 |  | 15 evaluations selected. NEP be submitted to Cabinet for approval in November 2013. |  |  |  |  |  |

Annex 2: Evaluations selected for 2014/15 by Evaluation Technical Working Group and being worked on prior to submission to Cabinet in November 2013

| Dept | Evaluation |
| --- | --- |
| Cooperative Governance | Evaluation of the Free Basic Service Programme (FBS) |
| Environmental Affairs | Evaluation of the Effectiveness of Environmental Governance in the Mining Sector (EEGM) |
| Health | Evaluation of Roll-out of Integrated Chronic Disease Management (Non-communicable diseases) |
| Higher Education and Training | Design Evaluation of the Policy on Community Education and Training Colleges (PCETC) |
| Human Settlements | Impact Evaluation of the Social Housing Programme (SHP) |
| Science and Technology | Evaluation of the Indigenous Knowledge Systems Policy (IKSP) |
| Social Development | Diagnostic Evaluation/Programme Audit for Violence Against Women and Children (AVAWC) |
| Social Development | Diagnostic Review of Coordination of the Social Sector Expanded Public Works Programme |
| SAPS | Economic Assessment of the CJS Review Process: SAPS Forensic Service Capability (Modernisation) (Forensic Labs) |
| Agriculture, Forestry and Fisheries | Impact Evaluation of the Ilima Letsema Programme |
| Agriculture, Forestry and Fisheries | Impact Evaluation of MAFISA (funded and implemented through 3ie – International Initiative for Impact Evaluation, subject to successful scoping exercise) |
| Agriculture, Forestry and Fisheries /Rural Development and Land Reform | Policy Evaluation of Small Farmer Support |
| Rural Development and Land Reform | Impact evaluation of Land Restitution Programme (funded and implemented through 3ie, subject to successful scoping exercise) |
| Rural Development and Land Reform | Cost benefit analysis of the Revitalization of existing irrigation schemes (possibly combining with Ilima Letsema evaluation) |
| Basic Education | Evaluation of the Funza-Lushaka Bursary Scheme |

Annex 3: Process to get to Parliament after an approved final evaluation report

Note that once the evaluation report is approved as factually correct and methodologically sound by the Evaluation Steering Committee, the DG of DPME writes officially to the relevant DGs requesting a management response on the evaluation report within one month, and that work should start on the Improvement Plan. In the Management Response the departments(s) involved indicate whether they agree with the recommendations and if not why not. After this month a presentation on the evaluation findings is made to the relevant cluster, and then on to Cabinet Committee and Cabinet. Once Cabinet has approved a letter is written to the relevant portfolio committee indicating that the evaluation has completed and they may want the department to present on the findings. The Improvement Plan addressing the findings should be completed within a maximum of 4 months of the approval of the report by the Steering Committee. 6 monthly reports are requested on the Improvement Plan.

Annex 4:	Work flow for undertaking an evaluation in the National Evaluation Plan

Key principles underlying the process:

- It is essential to have departmental ownership of the evaluation to ensure evaluation does not stay as a report but is implemented. Hence the department submits the proposal for the evaluation, and DPME makes great efforts to ensure that the department owns the TORs, the reports etc. This is sometimes causing delays but is likely to mean much greater impact of the findings. The work prior to contracting also takes a long time to get real clarity on what should be evaluated, to draw up good TORs, which are owned by the department, and to complete the procurement process.

- Where there is joint funding by DPME and the custodian department, DPME procures and the department transfers its proportion of the funding to DPME. Where the custodian department is fully funding the evaluation they procure. This is leading to extensive delays in the case of DHS where their procurement system takes 6-12 months while DPME’s takes 6 weeks.

- Standard guidelines and training are used to help ensure minimum standards during the evaluation process.

- There is andependent panel of service providers which is used for procurement.

| Activity /Deliverable | Responsible | Duration/approx date for 2014/15 evaluation cycle |
| --- | --- | --- |
| Workshop to develop the TORs for evaluation, TORs for Steering Committee, the Project Plan and the proposals for potential Peer Reviewers. | Technical Working Group (dept+ERU) | 1 day (October) |
| Workshop to develop the the Project Plan and the proposals for potential Peer Reviewers. |  | 0.5 day (January) |
| Circulation of draft TORs for Evaluation, TORs for Steering Committee, the Project Plan, and the Proposals for Peer reviewers to nominated steering committee members for comments. | Secretariat (usually DPME ERU members) | 1 day (January) A day after the workshop |
| Second draft TORs produced and circulated to potential Steering Committee members | Technical Working Group | A week after the workshop (late March ) |
| Steering Committee established and a first meeting held to approve TORs for evaluation, TORs for Steering Committee, Project Plan, and Proposed Peer Reviewers | Steering Committee | A week after receiving TORs (January) |
| Call for proposals | Commissioning Department | Within a week after approval of TORs (Early February) |
| Compulsory briefing session | Selected Steering Committee members /Bid evaluation Committee | 1 Week after issuing of a call (February) |
| Proposals received | Commissioning Department | 2 weeks after compulsory briefing (end of February) |
| Presentations by shortlisted service providers | Service providers | 1 week after receiving proposals. (Early March) |
| Decision on the successful bidder by the Bid Evaluation Committee (Steering Committee) and SCM | Bid Evaluation Committee (Steering Committee)/ SCM | Same day as above (Early March) |
| Successful bidder notified | Commissioning Department | 2 days after decision on successful bidder (appointment letter issued) (mid-March) |
| Submission of the review of the proposal (submitted by successful bidder) (possibly by peer reviewers) & comments by the Steering Committee | Service provider | 1 week (1st Week of April) |
| Inception meeting with the successful Service Provider | Steering Committee and service provider | 1 week after appointment letter (beginning of April) |
| Submission of the inception report incorporating comments from Peer Review and Steering Committee | Service providers | 1 week (mid-April) |
| Approval of Inception Report | Steering Committee | 1 week (April) |
| Service provider contract signed | Commissioning Department & Service provider | Within a week after approval of inception report (end April) |
| Literature review submitted with analytical framework for evaluation | Service provider | 2 weeks (End of May) |
| Development of initial logic model & theory of change | Service provider | 1 week (End of May) |
| Report outline produced bringing together analytical framework and key questions and guiding methodology | Service provider | 1 week (Early June) |
| Analytical framework, report outline, theory of change agreed | Steering Committee | (Early June) |
| Final data collection instruments, analysis plan and other tools after piloting | Service provider | 1 week (after report outline and analytical framework approved) ( Mid -June) |
| Research work undertaken | Service provider | 2-6 months depending on complexity (Aug-Dec) |
| Field work report produced | Service provider | 5 weeks (Early Sept-Dec) |
| Analysis of findings | Service provider | 1 month (Early Oct to January) |
| Draft consolidated full evaluation report produced for review | Service provider | 3 weeks (October to end January) |
| Workshop with stakeholders to discuss the draft report | Secretariat (usually DPME ERU members) | 1 week (after receiving draft report) (early November to early Feb) |
| Peer review of the report & comments from Steering Committee | Peer reviewers & Steering Commitee | 1 week after workshop (mid November to mid-Feb) |
| Final full report with comments from stakeholders incorporated | Service provider | 2 weeks (after incorporating comments from stakeholders, peer reviewers and Steering Committee) (end November to end Feb) |
| Submission of the draft final report in 1/3/25 format | Service provider | 1 week (1st week of December to 1st week of March) |
| Comment on the 1/3/25 report to the service provider | Steering Committee/Peer Reviewers | Early January to 2nd week of March |
| Approval of the Final Report | Steering Committee | 2 weeks (Mid-Jan- mid-April) |
| Power-point or audio-visual presentation of the results and provision of all datasets, metadata & transcripts | Service provider | With final report (Mid-January- mid-April) |
| Letter from DG of DPME to DG of custodian department requesting management response | DPME | 1 week (end January to end April) |
| Management Response | Custodian department | 1 month (end February to end May) |
| Evaluation Report submitted to cluster | Custodian department/ DPME | 2-4 weeks (March to June) |
| Evaluation Report submitted to Cabinet Committee | Custodian department/ DPME | 2 weeks (mid-April to mid-July) |
| Report submitted to Cabinet for approval | Custodian department/ DPME | 2 weeks (end-April to end-July) |
| Report on the custodian department & DPME website | Custodian department & DPME | Within a week after approval of Report by Cabinet (May to August) |
| Presentation to portfolio committee | Custodian department & DPME | June to September |
| Improvement Plan finalised | Steering Committee | 4 months after approval of final report (mid-May to mid-Aug ) |
| Communication to stakeholders | Custodian department & DPME | Within a week after approval of Report by Cabinet (during July) |
| Improvement plan progress reports requested from custodian departments | DPME | 5/11/17/23 months after improvement plan produced |
| Improvement plan progress reports developed and submitted to DPME | Custodian departments | 1 month (6/12/18/24 months |

# Text boxes

# Evaluation Report	July-September  2013

Box 1: progress with W Cape Provincial Evaluation Plan

The draft Terms of Reference for the 10 evaluations contained in the 2013/14 Provincial Evaluation Plan has been completed by the relevant departments, and are being edited.

Departments who are conducting internal evaluations are currently compiling their Inception reports and those departments who are outsourcing their evaluations are busy with the procurement of their service providers.

A call for evaluations for 2014/15 was sent out on 8 August 2013 and to date responses were received from four provincial departments (Agriculture, Community Safety, Local Government and Human Settlements).  The due date for this call is 31 August 2013.

A Dictionary (catalogue) of Evaluation Studies for the Western Cape Government is currently being substantiated for finalisation during September 2013.