Limpopo Provincial Government

S100(1)(b) Intervention

Departmental Progress reports

October 2013

Department:	 Roads and Transport

| Education | Health | Public Works | Provincial Treasury | Roads & Transport |
| --- | --- | --- | --- | --- |

BRIEF GUIDANCE

The template below must be completed and submitted to Mr. Tom’s office by no later than Thursday, 10 October 2013. The information will be used to complete a report to be issued to Parliament.

The information provided must speak to:

- What has the intervention done to date and how will we ensure that what has been done will be sustained

- What must the intervention still do (picked up now) and how do we ensure that these future actions will be sustained

- What are the gaps that the departments must close (leadership, ownership, skills, IT etc)

| Project name | Date started | Issues / Challenges | Deliverables | Progress to date | Risk of failure | Action to mitigate risk | Driver |
| --- | --- | --- | --- | --- | --- | --- | --- |
| “AG” Project / FY14 AFS | January 2013 | Qualified audit opinion for 2011/12 as result of asset register inaccuracies and irregular expenditure | Clear audit queries Assist in the compilation of AFS Assist in the resolution of 2012/13 audit queries Improve the asset register Capacitate SCM staff | All audit queries for 2011/12 were cleared Obtained unqualified audit opinion for 2012/13 Staff capacitated especially in asset management | Sustainability of the gains made Capacity challenges | Gradual hand over and performance monitoring | Fully capacitated SCM unit led by the CFO |
| Head count |  |  |  |  |  |  |  |
| Boilers |  |  |  |  |  |  |  |
| LTSM |  |  |  |  |  |  |  |
| Procurement – transversal (Health pilot) |  |  |  |  |  |  |  |
| Organisational structure / key posts | April 2012 | Revising organograms for the department and RAL for alignment with core functions Vacancies in key positions at RAL | Revise the organizational structure Fill key vacant positions at RAL Appoint a new Board for RAL | Department’s organogram has been revised and sent to DPSA for approval The study to determine the appropriate model to deliver roads insfrastrcture is underway The position of CEO, CFO, 2 Executive Managers, Legal manger and Internal Auditor have been advertised and shall be filled once the new Board is place (before December 2013 | Delay in service delivery Low staff morale | Provide support to hardworking staff Appoint appropriately qualified people in key positions | Accelerated but legal recruitment process |
| Pharmaceutical depot |  |  |  |  |  |  |  |
| Infrastructure |  |  |  |  |  |  |  |
| DC & criminal cases | January 2013 | Following up on findings and recommendations of the various investigations | Processing matters through the criminal and disciplinary processes | 5 cases have been opened with SAPS 1 official and 1 ex-official of the department have been arrested with 9 service providers for alleged fraud and corruption with regard to pothole patching contract 1 former employee and 1 former Board member of GAAL also arrested The former CEO and an employee of RAL also arrested Other criminal cases are being investigated Financial Manager at GAAL is on suspension for financial irregularities An Executive Manager at RAL is on suspension for performance related matters | Perpetuation of maladministration and irregular conduct. | Swift action by law enforcers Quick finalization of DC cases | Collaboration among stakeholders within the ACTT Cooperation with the investigation |
| Project based learning |  |  |  |  |  |  |  |
| Revised operation plan | June 2012 | Alignment of the intervention recovery plan with the APP’s of the department | Revised APP | The 2012/13 contains intervention recovery plan | N/A | N/A | Combined management committee |

# Comments

To be completed by all departments

To be completed by Health, Education and Treasury

Health

Education

Health

Treasury, Education, Health, Public Works

Health

This is covered in the sustainability plan, however Education, Health and Public Works must indicate how disclosure issues have been dealt with (i.e) Section 42 transfers and accounting for work in progress, contract management etc

To be done by DPSA and SIU

All departments – must update status of this plan and activities therein. A report from DaVinci will be included to supplement departmental input