ANNEXURE B: 2014/15 THIRDQUARTER REPORT

DEPARTMENT OF ENVIRONMENTAL AFFAIRS

| PERFORMANCE INDICATORS | 2014/15 TARGET AS PER ANNUAL PERFORMANCE PLAN (APP) | 3RD QUARTER TARGET AS PER APP | 3RD QUARTER ACTUAL OUTPUT | CHALLENGES | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- |
| PROGRAMME 1 : ADMINISTRATION |
| Percentage vacancy rate | 9.5 % | Q3: 10% | 10.6% (196 /1841) -V=Vacant (196) -F=Filled (1645) -T=Total posts (1841 | Moratorium on the filling of vacancies has had an impact on the efforts to reduce vacancy rate during the reporting period | Moratorium has been lifted and filling will be expedited |
| Percentage turnover rate | 10% | Q3: 7,5% | 4.9% (78/1588) L=Left (78) F=Filled posts (1588) at the beginning of 2014/15 financial year | None | None |
| Percentage implementation of PMDS policy framework | 95 % Compliance with contracting and assessment requirements | Q3 – 95 %of 1st biannual assessment reports received | 79% (1333 /1 691) 1st bi annual assessment received | Unavailability of officials and supervisors to finalise assessment reports | Constant follow ups and engagement of the branch heads for interventions |
| Number of HRD strategy initiatives implemented | 3 Interventions: • 100 interns recruited, • 70 bursaries issued • 80 % of WSP implemented | Q3: Implement 60% of WSP Issue 30 external full time bursaries and 40 part time bursaries | 78%(726/925) of WSP implemented. 49 part-time bursaries approved Part time bursaries not dealt with due to post office strike | Full time bursaries were not dealt with due to post office strike | Re advertisement of the full time bursaries student |
| Percentage of Women, Blacks and People with disabilities at DEA | Women 50% | Q1-Q4: 50% | 56% (927/1646) | None | None |
|  | Blacks 90% | Q3-Q4: 90% | 91% (1493/1646 ) | None | None |
|  | People with disabilities 2% | Q1-Q4: 2% | 2.7% (45/1646) | None | None |
| Average number of days taken to resolve disciplinary cases | 90 days misconduct cases | Q1-Q4: 90 days | Misconduct cases addressed in average of 54.6 working days (819 days/15 cases) | None | None |
|  | 30 days grievance cases | Q1-Q4: 30 days | Grievances cases addressed in average of 33 working days(394 days/12 cases) | Unavailability of managers and grievants who are out of office, eg on Antarctica | Continued efforts to be made to reduce solution time |
| Phased implementation of DEA New Head-Office Building PPP project | Phase I of the operation implemented (service commenced as per project plan)plan) | Q1-Q4: Implementation of the operations of the project ( as per the activities in the project plan) | Unitary report analysed and monthly invoices processed as planned Operational Project Committee monthly held Inspection conducted to ensure compliance to service level standards on hard and soft services facilities management OHS service standards as outlines in the schedule monitored and implemented | None | None |
| Percentage implementation of security risk assessment recommendations | 90% Implementation | Q3: 80% | 96% ( 67% for Q2 + 29% for Q3) 2 of 7 targets as reflected on the action plan has been achieved and 5 not achieved | Procurement of the alternative buildings by DPW, which results in recommendations not been implemented | The assessment in the newly procured building to be conducted |
| Number of funded Master System Plan (MSP) implemented (as per schedule) | 9 funded Master System Plan initiatives implemented (per schedule) | Q1-Q4: 9 funded MSP initiatives implemented per schedule | 2 of 9 projects achieved, 2 projects partially achieved and 5 projects off targets | 1 Project was cancelled by project manager due to change in requirements and 1 donor funded project was cancelled as a decision by DAC | Fast track the project implementation on all initiatives that are behind the schedule |
| Percentage availability of IT services | 97% availability IT service | Q1-Q4: 97% availability of IT services | 99.3% | None | None |
| Percentage compliance with statutory tabling and prescripts | 100% compliance with statutory tabling and prescripts(All MPAT Standards with moderated score of 3 and above | Q1-Q4: 100% per quarter | 100% - The following key requirements were complied with within the stipulated timeframes : Submitted DEA 2nddraft Strategic Plan and APP to National Treasury in November 2014. Submitted the 2nd quarter ENE report to National Treasury in October 2014 Submitted the DEA 2nd quarter performance reports to DPME in October 2014 (preliminary report) and November 2014 ( final report) Draft DEA ENE Chapter prepared and submitted to National Treasury in December 2014. | None | None |
| Unqualified Audit report | Unqualified Audit Report | Q1 - Q4: Implementation, review and continuous enhancement of control measures | DEA received an unqualified external audit opinion from the Auditor General of SA for the 2013/14 financial year. Systems of Internal control ( financial, risk management and performance information) are implemented on an continuous basis (each quarter) to ensure proper accountability and attainment of an unqualified audit opinion | None | None |
| Percentage adherence to cabinet and cluster schedule as per approved protocol | 100% | Q1-Q4: 100% | 100% adherence to the Scheduled : ESEID: 03 meetings scheduled 100% ICTS: 03 meetings scheduled 100% SPCHD: 03 meetings scheduled 100% G&A: 03 meetings scheduled 100% ESEID 2 ad-hoc meetings - 100% | None | None |
| Percentage expenditure | 98 % | Q3: 72% | 73%-R4,132 381 billion expenditure out of R5,680 386 billion budget allocation | None | None |
| Percentage of expenditure on affirmative procurement | 65 % | Q1-Q4: 65% | 89% expenditure on BEE in December 2014 | None | None |
| Number of media statements/ speeches issued and opinion pieces published | 120 statements/speeches | Q1–Q4: 30 statements/ speeches issued per quarter | 44 media statements/ speeches issued | None | None |
|  | 6 opinion pieces | Q3: 2 | 2 opinion pieces published Equity in climate financials Stopping the greedy depleting the Rhino | None | None |
| Number of communication events including Ministerial Public Participation programme (PPP) | 20 Public Participation events hosted | Q2-Q3: 6 events | 7) events were facilitated National Marine Week Global march for elephant and rhino Official opening of the DEA Green Building Opening of Masibekela Park in Malelani, Nkomazi Local Municipality Non-Motorised Transport. Handover and opening of a cycling facility in Soweto and at Ditsong Museum in City of Tshwane The EPIP 15 Year Review and the launch of Andover Game Reserve project near Acornhoek in Mpumalanga and -BASIC ministerial climate change meeting | None | None |
| Number of publications produced and distributed | 4 editions stakeholder publications | Q1-Q4: 1 stakeholder publication per quarter | 1 Environmental Quarterly publication printed and distributed | None | None |
| Number of website hits per annum | 450 000 website hits | Q3: 150 000 hits (less activities this time of year) | 164, 055 website hits | None | None |
| Number of Environmental Awareness activities conducted (Leanerships, CAPS training and Campaigns) | 100 teachers trained | Q3: Needs assessment conducted | Need assessment tool developed and circulated to stakeholders to complete | None | None |
|  | 100 unemployed youths recruited and learnership programme implemented | Q2-Q4: 100 learners trained | 99 learners trained and one was hospitalised due to the illness and could not make it | None | None |
|  | 8 Environmental awareness campaigns implemented | Q1- Q4 2: campaigns per quarter | 4 awareness campaigns conducted Rhino campaigns Clean-up campaign Climate Change Waste Management campaign | None | None |
| Number of SETA sector skills plans with environmental focus | 6 Sector Skills Plans with environmental focus confirmed | Q2-Q4: Review of the Sector Skills Plans | Six SSPs were reviewed and evaluation reports prepared for each of the SETAs | None | None |
| Number of officials undergoing/completed Environmental Management training and (EMI/IEM) | 400 officials trained in IEM | Q1-Q4: 100 official trained per quarter | IEM training session for Government Officials was conducted in 8 provinces. 900 officials have been trained, including EAPS, government officials, and all stakeholders | None | None |
|  | 240 EMIs trained | Q1-Q3: 70 per quarter | 178 EMIS trained as follows: EMI Basic Training Course (63) DNA Barcode of Wildlife Training(12) SARS Senior Manager Training (15) EMI Specialised Training on Biodiversity Crime Scene Management (47) Justice College Prosecutors Training on Environmental Crime (12) Free State BCOCC Training on the Illicit Trade in Endangered Species | None | None |
| Number of accredited training person days created | 139 915 | Q3: 35 265 | 42 829. (Cumulative performance is 129 260) | None | None |
| Outcome 10 Delivery Agreement developed and implementation facilitated | Approved Outcome 10 Delivery Agreement for sector on new priorities (2014 -2019) | Q3: Approval of the Outcome 10 Delivery Agreement | Outcome 10 Delivery Agreement approved by Mintech and Minmec | None | None |
| Number of environmental knowledge and information management systems/tools developed, refined and/or operational (EGIS, NEAS, O&C Online system, CC M&E system etc) | Technical development of the system continued (specifications defined) | Q3: Continue development of system | Procurement options have been determined A submission (SCM 139553) for the appointment of CSIR as a sole provider for O&C Information Management System) approved SLA currently being finalized | None | None |
|  | GIS internet developed | Q3: Develop Internet based GIS Screening tools interface and deploy on Internet | Started with the compilation of data sets for the screening tool as well as methodology sheets Appointment of contractor to conduct the deployment on internet has been delayed | Appointment of the contractor to conduct the deployment on internet has been delayed | The project will be finalised in the next financial year |
|  | Phase 1 of the South African National Environmental Information Meta-database finalised | Q3: Meta-Database project Output A.5: Draft Status Quo chapter/s for Final Project Report are approved Key stakeholder workshop held on the development of a new set of environmental / sustainable development indicators as envisaged by the NDP 2030 | DG approval to initiate the SANEIM Phase I - Scoping Project was received on 2 September 2014 | Delays as result of a process to be undertaken to ensure that the scope of the project does not duplicate the Business Intelligence and Analytics Strategy Project Tender for the SA National Environmental Information Metadata (SANEIM) Project: Phase I – Scoping, advertised with a bid closing date of 5 December 2014 | Tenders for this highly delayed project will only be evaluated in mid-January 2015. However, even with this delay, it is possible that the annual target of the project being well underway will be met |
|  | 2 components of the NEMA Chapter 5 Environmental Regulatory Authorization system monitored (EIA amended timeframes module and the appeals module) | Q1-Q4: Coordination of NEAS implementation Reporting of EIA statistics from NEAS for 10 competent authorities | Facilitated the NEAS quarterly Task team meeting Produced the quarterly outcome 10 report | None | NEAS Appeal module will be implemented following receipt of feedback of process to be followed for S24 applications from Compliance Section |
|  |  | Q3: Develop a plan of action to implement the NEAS Appeal module for two additional competent authorities |  |  |  |
|  | Design of Climate Change response M&E system approved | Q3: Initiate approval process for the M&E System Road-shows to provinces & metros to discuss the M&E system | The M&E system framework presented and approved at MINTECH and MINMEC Preparations for road-shows completed as follows: Road-shows concept note and plan completed Training materials for the road-shows completed Invitation letters for the first two road-show meetings sent and dates set for Q4 | All road –show meetings have re-scheduled for Q4 due to: unavailability of suitable times for the stakeholders in Q3; Delays in securing key external partners to hold the road-shows | The implementation plan of the road-shows has been designed such that the annual target will still be achieved |
|  | 50% of facilities with AELs reporting to the NAEIS | Q3: 50% of facilities in the Master list report to NAEIS | The list updated and currently there are 657 facilities in the NAEIS New facilities uploaded into NAEIS in September | None | None |
| Number of Environmental knowledge and information management, monitoring and evaluation reports/publications and response options produced | State of the Oceans Report compiled | Q3: Chapter Outline of State of the Oceans Report produced | Chapter Outline of the Chapters of the completed | None | None |
|  | 18 peer-reviewed scientific publications (including theses) | Q3-Q4: 4 Scientific researches published in peer-reviewed journals per quarter | 3 Scientific publications published | None | None |
|  | 1 South Africa Environment Outlook (2nd SAEO) completed and published 1 reviewed (NSSD1 M&E Report finalised) | Q3:Design and layout of the NSSD1 M&E Report | Comments on the final NSSD1 M&E draft report were submitted to the CSIR for final incorporation. NSSD1 M&E final report in place | Communication Unit still to confirm if they have internal capacity to carry out the design and layout of the report | Finalise the design and layout of the report will be prioritised in the quarter 4 |
| Local Government SupportProgramme implemented | Annual action plan implemented (100 % implementation) | Q3: 75% | 64% implementation of planned action for the quarter ( 27/42 planned actions for quarter 3 are on target) | Unavailability of high level delegation to proceed with the launch of the planned events for the quarter. With regard to the initiatives related to the ecosystems that are sustained and natural resources used efficiently; constraints are related the environmental management plans that are not published | New dates have been negotiated and committed for the high level delegation to launch the capacity building and environmental awareness projects in Q4 Measures are put in place to fast the implementation of projects that are behind schedule in the focus are of Green Economy |
| Percentage of Sector conflict management tools implemented | 50 % of received conflict cases dealt with (in line with NEMA Chapter 4 provisions) | Q2-Q4: Management of cases referrals (50%Cases dealt with in line with NEMA Chapter 4 provisions) | 1 case in progress and the submission for implementation awaiting Minister's approval | The 2 cases reported in the 2nd quarter were consolidated into 1 case as it is dealing with one area and the stakeholders are the same | Continuous engagement with programme managers for proper of processing cases |
| Number of South African positions on Chemical and Waste, Biodiversity, Sustainable Development (SD), African and bilateral South-South, South-North and International Environmental Governance (IEG) processes prepared, negotiated and reported | 13 Bilateral/Pleurilateral (Africa, IBSA, S-S, S-N) approved | Q3: AMCEN, Botswana, Namibia | Positions prepared, negotiated and reported -Botswana BNC 17-20 November). SA-Botswana RES (21 November 2014) AMCEN Consultative meeting ( 07 December 2014) - SADC (3-5 November 2014) | Emerging issues in other countries have an impact on the proceeding of bilateral and beyond the department's control | Follow up with DIRCO for the next session |
|  | 3 Multilateral position (SD and IEG) approved | Q3 1 Post-Rio+20 Regime • negotiating positions researched, developed, consulted and approved | Positions researched & developed: Group of Friends of Paragraph 47 on corporate sustainability - position 10 - Year Framework of Programmes (10YFP) on Sustainable Consumption and Production (SCP) - position SDG Youth – position Post 2015 Development Agenda- Environment Cluster - position | None | None |
|  | 3 chemicals and waste positions approved | Q1–Q4: Positions researched, developed and approved | Developed and presented the position paper for the Vienna COP 10/MOP26, (17-21 November 2014) to ICTS Cluster, Cabinet Committee & Full Cabinet. Developed the Position Paper for the Mercury INC6, 3-7 November 201. Developed the Position Paper for SAICM 2nd OEWG, 15-17 December 2014. Drafted the Basel 9TH OEWG Report & presented to the MCCM. Drafted the Mercury INC6 Report & presented to the MCCM. Drafted the CRC10 & POPRC10 Report & presented to the MCCM | None | None |
|  | 10 Biodiversity positions approved | Q1-Q4: Positions researched, developed and approved | Position papers for the CITES Animals and Plants Committee meetings prepared and negotiated Draft position paper for the Standing Committee developed and approved Position papers for the fifth meeting of the Working Group on Review of Implementation (WGRI 5) of the Convention on Biological Diversity (CBD) which was held in Montreal, Canada from the 16th to the 20th of June 2014 were prepared, negotiated and reported on The eighteenth meeting of the Subsidiary Body on Scientific, Technical and Technological Advice (SBSTTA 18) to the Convention on Biological Diversity (CBD) took place in Montreal, Canada, from 23-28 June 2014 and its position papers were prepared, presented in the meeting and reported on | None | None |
|  | 2 Climate change positions for formal international engagements (UNFCCC) developed and approved | Q3: Position researched, approved and negotiated for the following meetings: UNFCCC (ADP 3-4, SBI 41, SBSTA 41, COP 20, CMP10) IPCC 40 | Position paper researched, approved and negotiated for the following meetings: UNFCCC (ADP 2-7, SBI 41, SBSTA 41, COP 20, CMP10) IPCC 40 | None | None |
| The financial value of resources raised from multilateral and bilateral donors to support the department, SA and Africa’s programmes | US$30 million from all sources (Multilateral: US$20 million; Bilateral: US$10 million) | Q3: US$15 million | The total amount for Quarter 3 is therefore US$ 10,4 million (cumulatively US$35 798 957/US$30m) Building Resilience in the Greater uMngeni Catchment (South African National Biodiversity Institute (SANBI) US$ 7,495,055 | None | None |
| Mandatory international and national reports prepared and submitted within timeframe (in terms of relevant legislation and/or international obligations/conventions) | 2013/14 NEMA S26 report tabled to Parliament within timeframe | Q3: No target | No planned milestone for the reporting period | None | None |
|  | First Biennial Update Report completed and submitted to UNFCCC | Q3: BUR submitted to the UNFCCC | Cabinet approval to submit South Africa’s 1st BUR granted on the 12th of November 2014. BUR submitted to the UNFCCC BUR submitted to the UNFCCC (available at: http://unfccc.int/national_reports/non-annex_i_natcom/reporting_on_climate_change/items/8722.php) | None | None |
|  | Principles and procedures for compilation of TNC finalized | Q1-4: Principles and procedures for compilation of TNC finalised | Submission seeking approval to appoint authors for the TNC approved by the DG (EDMS 138955) Request to approve bid specification committee and bid evaluation committee has been approved by the DDG (EDMS 140236) DEA is about to advertise the call for TNC Authors | None | None |
|  | Draft GHG Inventory 2000-2012 compiled | Q3: Contracting service provider to compile the GHG inventory finalised | This project forms part of the DEA-DFID (Department for International Development-UK) and the funding is being facilitated by a Company called Cardno North West University (NWU) has been appointed to undertake this work. A contract signed between Cardno and NWU is provided as evidence | None | None |
| PROGRAMME 2 : LEGAL ,AUTHORISATIONS ,COMPLIANCE AND ENFORCEMENT |
| Number of environmental authorisations inspected | 135 | Q1-Q3: 34 per quarter | 41 Authorisations were inspected | None | None |
| Percentage of administrative enforcement actions resulting incompliance | 75% | Q1-Q4: 75 % | The overall percentage compliance with administrative enforcement actions will be calculated and report in the 4th quarter. The following administrative actions were issued during the reporting quarter: 31H Notices:6 Compliance Notices and Directives: 4 PCN: 9 SAWIS PCN: 25 NEBA PD: 1 Variations:5 CNs:1 | None | None |
| Compliance and Enforcement Strategy for the Environmental Management Inspectorate developed and implemented | Final strategy approved for implementation across all EMI institutions | Q3:Presentation of strategy at WG forums; approval process through Mintech and Minmec | The draft strategy was taken to MINTECH on 14 November where it was referred to MINMEC for approval. On 28 November 2014 MINMEC approved the strategy, with a proviso that we need to strengthen what is said in the strategy in relation to compliance and enforcement within the context of sustainable development | None | None |
| Number of criminal investigations finalised and dockets handed over for prosecution | 26 | Q2-3: 7 per quarter | 4 investigation were finalized and dockets handed over to NPA: Delmas 62/07/2013 – 28-11-2014 Bosveld Phosphates 05/01/2013 – 17-11-2014 Xstrata 01-10-2014 Advidata 78/03/2014 – 22-12-2014 | None | None |
| Number of interventions implemented for Safety and Security of wildlife including rhinoceros populations in South Africa | Review of the national strategy for the safety and security of rhinoceros population in SA Africa | Q3: Report reflecting Stakeholder comments produced | Comments Consolidated and gaps identified through the integrated management strategy. The report reflecting stakeholder comments produced | None | None |
|  | MoUs with strategic government departments (Justice and Constitutional Development, Home Affairs, Correctional services and police) on safety and security of wildlife including rhino management | Q3: Consultation with two stakeholder and develop draft MOU’s | Stakeholder consultation conducted with Departments of Transport in June 2014. Draft MOUs developed with Department of Home affairs and Transport | None | None |
|  | Implementation of corrective actions relating to the implementation of TOPS regulations monitored in two provinces | Q3: TOPS Compliance inspection to monitor implementation of corrective action in one province conducted | An inspection was conducted in North West to monitor the implementation of corrective actions | None | None |
|  | Compliance assessments on the implementation of CITES regulations conducted in two provinces | Q3: CITES Compliance inspection in one province conducted | CITES compliance inspection conducted in North West | None | None |
|  | 1100 environmental monitors trained and deployed | Q1- Q4: 1 100 environmental monitors trained and deployed | 1 307 | None | None |
| Number of tools for mitigation of negative impacts of development developed and implemented | Minimum requirements for biodiversity in land use planning and IEM finalised | Q3: Incorporation of comments | Comments incorporated into and Documents approved by Minister for designation of False Bay NR and submitted to the Ramsar Convention for designation | None | None |
| PROGRAMME 3 : OCEAN AND COASTS |
| Ocean management regime developed | Report on the analysis of legislative framework with implication on ocean governance in SA finalised | Q2-Q3: Draft report on the analysis of legislative framework of ocean governance in South Africa | Final report on the analysis of legislative and institutional framework of ocean governance in South Africa finalised | None | None |
|  | Implementation plan for the Ocean Management policy developed | Q3:Consultation and consideration of the draft implementation plan with focal points of key departments on draft implementation plan | The necessary interactions between affected parties and initiative leaders as well as supportive organisation taking place in efforts to initiate implementation Interactions at different sector departments and delivery units to implement the plans being established | Role clarification as well as, the establishment of delivery units need to gain speed | Meetings are being held between stakeholders to establish necessary structures and set up procedures and systems -E.g. Norwegian Workshop to discuss the Marine Spatial Plan |
| Strategies and plans for management of ocean and coastal environment developed and implemented | National framework implemented | Q2-Q3: Consult stakeholders on implementation plan and identify first ocean area for development of first ocean spatial plan | The draft Implementation plan developed as part of the Marine Protection and Governance sector implementation plan as devised in the Oceans LABS process Area for 1 subordinate spatial plan identified during Oceans LABS process | None | None |
|  | NCMP launched and implementation plan developed | Q3: Development of second draft NCMP implementation plan Development of performance indicators for the NCMP Implementation plan | Final draft NCMP developed (post the comments period) and sent to the Minister for adoption The Performance Indicators developed as part of the Implementation Plan and Chapter 6 of the NCMP itself | None | None |
|  | Additional 1 plan updated | Q3:Update Margate Zone oil spill contingency plan | The Knysna LOSCP plan was revised taking into account comments made and received | None | None |
|  | 1 oil spill readiness exercise and 1training session held | Q3: Conduct the training workshop and exercise | Training workshop and exercise for West Coast and Northern Cape region successfully undertaken on 21-23 October 2014 in Veldrift | None | None |
|  | 5 estuary management plansdeveloped | Q3: Facilitate compilation of one draft estuarine management plan | Orange River Mouth EMP Revised ORM EMP has been presented to ORMIMC, NC PCC and WG8’s Estuary Sub-Committee | None | None |
|  | One new draft protected Marine Species Plan developed (Turtle) | Q3: Draft Turtle Management plan | Draft Turtle Management plan in place | None | None |
| Percentage of coastline with formal protection | Full Protection of 9.5% (342/3 600km), and partial protection of13.5 % (486/3 600km) | Q3: Continue and conclude consultation process with stakeholders Develop Declaration Notices and/or regulations for MPAs to be expanded and summit to legal services for vetting | Operation Phakisa launch on 15 October 2014 in KZN affirmed a 5% protection in 2019. Interaction on Operation Phakisa’s undertaken with Offshore Environmental Forum. Addo MPA has been approved by the Minister. Robberg, Goukamma and Betty’s Bay Submission for gazetting are with the Minister for approval. Dwesa-Cwebe MPA – Ccommunities consultation facilitated. MPA resonation was gazetted for public comments, which closed on the 04 December 2014. Namaqualand, Isimangaliso, Aliwal Shoal MPA has been identified as part of Operation Phakisa | Stakeholder engagement is taking place for Operation Phakisa quite earnestly currently as initiatives are shaping up | Continue with Stakeholder engagement |
| Percentage increase of total area of EEZ under protection and managed | Draft monitoring proposal for Prince Edward Island developed | Q3:Draft proposal developed | Draft Letter of Intent submitted to Dept. of International Relations and Cooperation (DIRCO) for consideration and advice Consultation facilitated: SA officials met France’s officials at the World Parks Congress in Australia discussing management of PEI MPA and the Crozet Island France presented at the MPAAP summit about South Africa and French MOU on management of the PEI MPA and Crozet Island | Delays in engagement between DEA and DIRCO Submission of the verified Letter of Intent on the PEI Monitoring to be submitted to Minister for signature and delivery by DIRCO | The draft letter of intent from DIRCO has been received, amended and sent for final copy (hard copy to be produced for signature by Minister) |
| Number of relief voyages to remote stations (Antarctica and Islands)undertaken | 3 relief voyages undertaken (SANAE, Gough and Marion Islands) | Q3:Relief voyage to Antarctica | The SA Agulhas II returned from Gough Island on 09th October 2014 The SANAE Voyage departed on 4 December 2014 | None | None |
| Oceans and coastal research projects, surveys completed and monitoring projects undertaken | 4 Surveys of priority habitats | Q3-Q4: 1 inshore priority habitat re-surveyed | De Hoop MPA long-term monitoring survey undertaken | None | None |
|  | Seabird population estimates for: • 12 species around SA • 2 Southern Ocean species | Q3: Population estimates for White Pelican, Roseate Tern, Cape Cormorant, Crowned Cormorant, White-breasted Cormorant and Kelp Gull | Population estimates for six species of seabirds (White Pelican, Roseate Tern, Cape Cormorant, Crowned Cormorant, White -breasted cormorant and Kelp Gull) | None | None |
|  | 2 Coastal research projects completed | Q3-Q4: Phase 3 of Coastal Vulnerability study 50% completed | Phase 3 TOR reviewed and request for additional information submitted to service providers Updated and edited Phase 3 Coastal Vulnerability Proposal received and put on EDMS to request DDG approval | None | None |
| Number of interventions aimed at advancing the biodiversity science policy interface | Biodiversity Research strategy finalised | Q3: Draft Research strategy prepared for publication | Draft research Strategy developed | None | None |
|  | National IPBES hub established | Q3: IPBES hub trial site running | IPBES Hub site updated and operational | None | None |
|  | Elephant research strategy approved | Q3: Final draft Elephant research strategy process in progress | Elephant Research Strategy approved by the Minister on 12 September 2014. The approved strategy was submitted to the Departmental Communications section for the design and Layout for printing | None | None |
|  | Phase 1: UNCCD DLDD land cover mapping impact indicator research finalised | Q3: Draft report developed | Draft report developed | None | None |
|  | Report on the extent of MON810 insect resistance finalised | Q3: Report on MON 810 resistance development study finalised | Draft report on MON 810 resistance development reviewed, analysed and input incorporated to the draft report | Busseola fusca moth which is a targeted pest on this study only flights during the middle to end of November so this has delayed the service provider in terms of collecting field data to be in-cooperated on the final report | None |
|  | 2 Science/policy input Reports compiled on Risk Analysis for intensive breeding in the wildlife sector; and State of play report on Predator control and conservation | Q3: Progress report on Predator control stud Draft risk analysis of intensive breeding | TOR for Predator Control study not yet approved. Symposium round table convened at the annual KZN symposium. Draft risk analysis of intensive breeding developed | TOR for Predator Control study not yet approved. Predator control study has not begun due to procurement challenges | None |
| Number of observational platforms contributing to an ocean and coastal observation and monitoring network | 6 Observational platforms deployed | Q3: Servicing and calibration of UTRs (Underwater Temperature Recorders) to be deployed along KZN shelf (eddy system) concluded Servicing of deployed platforms (buoys, moorings and UTRs) concluded | Surface Buoy for Algoa Bay prepared, serviced and sent to NMMU for deployment in January/ February 2015 4 SAMBA moorings retrieved and not redeployed Algoa Bay moorings retrieved and not redeployed Port St Johns sharks cruise undertaken | None | Efforts will be made to undertake Procurement Processes so as to procure spares and consumables for the moorings, data buoys and UTRs |
| Number of ecosystem process studies undertaken | 2 Multidisciplinary ocean functioning projects undertaken (in Benguela and Agulhas currents) | Q3: Planning of multidisciplinary project in Agulhas current Scientific proposal drafted | The multidisciplinary cruise was undertaken in the Agulhas Current | None | None |
| PROGRAMME 4 : CLIMATE CHANGE AND AIR QUALITY |
| Number of sectors for which Long Term Adaptation Scenarios have been developed | Reports of phase 2 Long-term Adaptation Scenarios finalised for Human Settlement (Urban/Rural/Coastal) and Disaster Management sectors | Q3:Printing of the LTAS Phase 2 reports | Outstanding Disaster Risk Reduction report has been finalised after high level intervention and Phase 2 fact sheets internally drafted for engagement with ‘journalistic communicator ‘ for final editing prior to printing | DRR report delayed | Process instituted to finalise after delay due to DRR Report |
| Number of climate change adaptation studies conducted | Draft report of the Situational analysis and needs assessments (SANAs) of provincial CC response planning & adaptive capacity completed | Q2.-Q3: Conducting the SANAs Stakeholder consultation | Adaptation thematic issues addressed as part of the National Climate Change Conference which incorporated regional dynamics | None | None |
| Number of sector adaptation plans aligned with the National climate change response policy | Recommendations for 4 sectors on mainstreaming climate change adaptation response measures into sector plans and policies: • Human settlement (Urban, Rural and Coastal) •Disaster managements | Q3: Conduct the gap analysis and policy alignment review | Contract being finalised for the appointment of the Technical expert | None | Report to be finalised in the 4th quarter |
| National adaptation strategy developed and implementation facilitated | Framework for the National Climate Change Adaptation Strategy for South Africa developed. | Q3: Conduct study Stakeholder consultation | Draft Framework for the National Adaptation Strategy developed considering input received from stakeholder consultations conducted | None | None |
| National Framework for Climate Services developed and implemented | Draft Framework for National Climate Services developed | Q3: Stakeholder engagement on the NFCS | Stakeholder engagement on NFCS done at the National Climate Change Conference | None | None |
| Number of sector mitigation potential and impact studies conducted | Draft National Carbon Sinks Atlas | Q2-Q3: Stakeholder engagements Data collection and analysis | The funding for the project was approved by the GIZ and they agreed on a financial agreement | Project is delayed and the Q3 deliverables not met due to delays in the implementation of the DFID fund Proposal was sent back to CSIR to capture DEA concerns and comments, because some of the deliverables in the TORs were not included in the proposal The CSIR was also requested by the GIZ to reduce costs by 20%. GIZ and DEA still awaiting CSIR’s response to the issues raised above | Corrective measure: Project moved to GIZ, in the process of finalising procurement under the GIZ fund |
| Number of Climate Change Response Policy interventions implemented | My 2050 Pathways Calculator developed | Q3: Draft my 2050 calculator | My 2050 Pathways Calculator developed Draft My 2050 calculator finalised. The calculator will be migrated to the Departmental website once completed | None | None |
|  | Draft DEROs (Desired Emission Reduction Outcomes) for 5 Sectors developed | Q2-Q3: Stakeholder engagements | Business stakeholder meeting held on the 24 November 2014 | None | None |
|  | Draft Mix of measures for 5 sectors developed | Q2-Q3: Stakeholder engagements | Draft Mix of measures framework circulated for stakeholder comments. | None | None |
|  | Flagship Framework coordinated and facilitated for 2sectors (Energy Efficiency and Transport) | Q1-4: Flagship Framework coordinated and facilitated for 2 sectors | Draft frameworks of energy efficiency and transport flagships have been developed. The comments were solicited during the Climate Change Conference at the Exhibition Stand dedicated to the climate change flagships | None | None |
| Number of sector mitigation plans aligned with the National Climate Change Response policy | Guidelines for mitigation plans finalised | Q3:Final mitigation plan guidelines document | Awaiting clarification of few elements on the Carbon budgets in order to finalise the guideline document | None | None |
| The National Air Quality Indicator (NAQI) | 1.135 | Q3 :Lekgotla Presentation | The National Air Quality Indicator presented with the 2014 State of Air Report at the Lekgotla. The National air quality index will be reported in the fourth quarter | None | None |
| Number of air quality monitoring stations reporting to SAAQIS | 90 | Q1-Q3: Facilitate and finalise contracts with station owners | Consultation is currently underway as following Saldanah Bay District Municipality for data sharing agreement North West Province for the reporting of six stations to SAAQIS | None | None |
| AQA Regulatory Framework Developed and Implemented | Emissions Offset Policy for AQM published | Q2-Q3: Offset policy published for public comments Comments and draft response database compiled | A decision was taken to publish this as a guideline and not a policy – this means that the document produced will not go through cabinet and public consultations | None | The initial comments received during stakeholder consultations will be used to finalise the guideline document before publishing on SAAQIS |
|  | Draft S23 – Small Scale Charcoal Plants Declared as Controlled Emitters | Q3: Comments response database compiled and the final draft submitted to legal service | Draft S.23 Notice recommended to the Minister by the DG (EDMS137941) in quarter 2 | Awaiting Minister’s approval | Upon Ministerial approval, the draft declaration will be published for comments within a week |
|  | 2 Priority Area AQMPs under implementation (Vaal and Highveld) | Q3: Two AQMP interventions implemented. Two awareness campaign programmes conducted to address domestic fuel burning in two priority areas & quarterly progress reports compiled | An air quality fun run to raise awareness on domestic fuel burning and other air quality issues was planned to take place in October. However the event was postponed A multi Stakeholder Reference Group meeting was held on the 26 November 2014 in VTAPA The meeting allows for communication and reporting to monitor progress with implementation of the AQMP by all stakeholders | None | None |
|  | Waterberg-Bojanala Priority Area AQMP and Threat Assessment Gazetted | Q3: Draft AQMP published for comments | The draft AQMP was finalised and a submission to request Minister approval for publishing the AQMP for public comment was loaded on EDMS with no 140409 | Delays were due to the shiftingof the MSRG date. | None |
| PROGRAMME 5 : BIODIVERSITY AND CONSERVATION |
| Percentage of land under conservation | 11.2% (13 660 1014/ 121 991 200 ha) | Q3:Transfer of funds to SANParks facilitated | A submission for the transfer of funds to SANParks has been drafted and is on route for approval | None | None |
| NPAES Reviewed and implemented | NPAES Reviewed | Q3: Stakeholder consultation | Stakeholders consulted and service provider appointed | None | None |
| Number of additional stewardship sites established | 1 additional stewardship site established | Q3: Consultation process for Ingula NR finalised | Consultations process undertaken. Further negotiations with KwaZulu-Natal Wildlife and Free State Province held to take over declaration process | None | None |
| Percentage of area of state managed protected areas assessed with a METT score above 67 % | 86 % of area of state managed protected areas assessed with a METT score above 67 % | Q3: 2013/14 METT data audits undertaken | Training for METT data audits undertaken. Field audits to begin in quarter 4 | None | None |
| Number of conservation andlegislative tools to ensurethe protection of species andecosystems developed and implemented | 14 legislative and conservation tools: Regulations for the registration of Professional Hunters, trainers and Hunting Outfitters published for implementation | Q3: Regulations for the registration of professional hunters, hunting outfitters and trainers published in the Gazette for implementation | Signed notice received from Minister but not yet published | The signed notice was received from Minister’s office in November. Publication in the Gazette could only have been done by middle November, which would have resulted in the comment period extending into the December holiday, which may lead to possible challenges regarding unfair opportunity to comment | None |
|  | Review of the norms and standards for the management of elephants in South Africa initiated and amendments drafted | Q3: Report reflecting stakeholder comments produced | Report reflecting stakeholder comments compiled | None | None |
|  | TOPS regulations published for implementation and draft guideline for implementation developed | Q3: Revised TOPS Regulations published in the Gazette for implementation Stakeholders consulted on implementation guidelines | Revised TOPS Regulations not published in the Gazette for implementation | MINMEC was consulted on 31 October 2014 and referred the draft revised TOPS Regulations back to MINTECH for comments MINMEC was consulted again on 28 November 2014. The re-publication for public participation of the draft revised TOPS Regulations was approved, with an instruction that measures be developed to address canned hunting | A letter addressed to the Minister of DAFF to request a bilateral with DAFF to discuss this matter, has been drafted and submitted for Minister’s signature |
|  | BABS Amendments Regulations approved by Inter-governmental structures | Q2-Q3: Revised Draft BABS amendments presented to Intergovernmental structure/s Inputs incorporated in to the draft document | Revised Draft BABS Amendment Regulations recommended to MINTECH by WG1 Revised Draft BABS Amendment Regulations recommended to MINMEC by MINTECH Final BABS Amendment Regulations approved by MINMEC | None | None |
|  | NEMBA review completed | Q3: Engagement with stakeholders to resolve areas of conflict or concern conducted | Stakeholder engagement at NBSAP workshop conducted | None | None |
|  | Amendment Bill to incorporate MPAs into NEMPAA finalised | Q1-Q4: Support NCOP process | NCOP process completed | None | None |
|  | A draft Amendment Bill incorporating provisions relating to TFCAs and WHS reserves into NEMPAA developed | Q3: Consultation of proposed provisions for WHS and TFCAs | Consultations on proposed provisions for WHS and TFCAs conducted | None | None |
|  | Norms and Standards for the management of protected areas finalised | Q3: Finalise norms and standards including relevant comment | Norms and standards have been revised | None | None |
|  | Draft Norms and standards for declaration and inclusion of private nature reserves completed | Q2-Q3: Stakeholder Consultation | Stakeholder Consultation undertaken in the first quarter | None | None |
|  | Amendment of regulations for Special Nature Reserves, World Heritage Sites and National Parks published for implementation | Q3: No target | No planned milestone for the period under review | None | None |
|  | Draft BMP for 1 ecosystem developed | Q3: Stakeholder consultation | Stakeholder workshop convened on 1 November 2014 for the development of the Colbyn Valley Wetland BMP and workshop report compiled | None | None |
|  | 2 Biodiversity Management Plans for species finalised for public participation (African Lion, White Rhino) ,and one BMP-S finalised for implementation (BeardedVulture) | Q3: BMP for draft African Lion and White Rhino approval for public participation through corporate governance structures initiated Final BMP for Bearded Vulture published for implementation | African Lion: Draft BMP for African Lion approved by WG1 for public participation White Rhino: Comments received are being incorporated by the RMG Bearded Vulture: The final Bearded Vulture BMP was published for implementation in July 2014 | None | None |
|  | National Cycad Management Strategy and Action Plan approved for implementation | Q3: Draft National Cycad Management Strategy and Action Plan submitted for approval | Draft National Cycad Management Strategy and Action Plan presented to WG1(28 October 2014), MINTECH (14 November 2014)and MINMEC (28 November 2014) | None | None |
|  | NBSAP Review conducted | Q1-Q3: Stakeholder consultation | National stakeholder workshop was conducted resulting in a draft National Biodiversity Strategy | None | None |
| Number of tools to mitigate threats to biodiversity | NAP review and alignment with the UNCCD 10 year Strategy and Framework finalised | Q3: Draft National Action Programme reviewed and analysed | The process of reviewing and analysing the existing NAP document to identify gaps in accordance with the UNCCD operational objectives as contained in the 10 Year Strategy and Framework conducted | None | None |
|  | Draft Biodiversity climate change adaptation plans for 9 biomes developed | Q3: Stakeholder consultation conducted | Stakeholder consultation workshop conducted on 25th of November 2014 | None | None |
| Tools for the implementation of the Ramsar Convention developed and implemented | One Ramsar site designated | Q3: Submission of the designation for Minister approval | Documents approved and submitted to the Ramsar Convention for designation | None | None |
|  | Draft strategy to remove sites from the Montreux record developed | Q3: Draft strategy developed | Draft Strategy developed | None | None |
| Biodiversity Sector transformation framework developed and implemented | Biodiversity sector transformation framework finalised | Q3: Biodiversity sector transformation framework developed | Biodiversity sector transformation framework developed | None | None |
| Number of sustainable natural resource based interventions and instruments identified, developed and implementation facilitated | National Biodiversity Economy Development Strategy finalised | Q3: Components of the draft National Biodiversity Economy Development Strategy proposed | Components of the draft National Biodiversity Economy Development Strategy proposed to the sector | None | None |
|  | 2 Biodiversity Economy development projects supported for implementation | Q3:. • Supported projects monitored and evaluated • 2 new biodiversity economy development projects identified according to the approved criteria | Projectswhich are at funding level have been monitored and evaluated as follows: Balepye and Tyhefu Communities received funding from EPIP on the Rhino Ranching Project. Convened two meetings with Tyhefu Community and Malebye for possible funding 2 new biodiversity economy development projects identified according to the criteria established, namely: Devil’s claw cultivation project Wildlife farming project | None | None |
|  | 1 cross border trail operationalised | Q3: Immigration and tax exemption approvals for participants obtained | Approvals obtained and the Desert Kayak cross border trail operationalized (during the Desert Knights event from the 7th to 13 September 2014 | None | None |
|  | One Project from the TFCA Catalogue implemented | Q3: Investment leads identified and negotiations facilitated | Investment promotion sustained through publication and distribution of e-newsletters. | None | None |
|  | 3 natural resource based projects implemented (People &Parks, Bushbuckridge, Awelani) One TFCA Natural Resource based project Implemented (Awelani) | Q3: Implementation of priority activities facilitated | Implementation of priority activities facilitated | None | None |
|  | Implementation of the Bushbuckridge Master Plan (5projects) facilitated | Q3: Source funding | Seda; Anglo American and Resource Africa identified as possible funders | None | None |
| PROGRAMME 6 : ENVIRONMENTAL PROGRAMMES |
| Number of Full Time Equivalents (FTEs) created | 35 936 | Q3: 9 855 | 8 695 FTEs created in the 3rd quarter. A total of 19 942 FTEs created to date (April to December 2014) | None | Ensure submission of all outstanding reports early in Q4 for capturing |
| Number of SMMEs utilised (empowerment) | 2 210 | Q3: 719 | 1 068. No challenges (Cumulatively, the Branch achieved 3 061) | None | None |
| Number of Work Opportunities created | 69 158 (Women- 55%) | Q3: 19 334 | 16 943 work opportunities and 53% of work opportunities created to date are women. (Cumulative performance is ahead at 56 270). Currently not attracting participants from designated groups. | Currently not attracting participants from designated groups | To ensure that new projects prioritise individuals from designated groups |
|  | 69 158 (Youth – 60%) | Q3: 19 334 | 16 943 work opportunities and 70% of work opportunities created to date are Youth. Cumulative performance is ahead at 56 270 and 70% of these are Youth | None | None |
|  | (People with Disabilities – 2%) | Q3: 19 334 | 16 943 work opportunities and 1.84% of work opportunities created to date are people with disabilities. (Cumulative performance is ahead at 56 270 and 1.84% of these are People with Disabilities). Seems to be incorrect extraction of reports between systems | There is incorrect extraction of reports between systems | The incorrect extraction of the reports will be corrected in quarter 4 |
| Number of youths benefiting from the youth Environmental Services | 900 | Q1-Q4: 900 | 1 192 | None | None |
| Percentage of young people placed in exit opportunities (YES) | 75% | Q1- Q4:75% | 77%. (A total of 858 youth were exited and 644 is targeted for placement and 496 were placed) | None | None |
| Number of overnight visitor and staff accommodation units established and/or renovated | 22 | Q3: 8 | No progress for the reporting period | None | Progress towards the annual target is on track as 16 accommodation units were established in quarter 1 |
| Number of school desk equivalent | 120 000 | Q3: 30 078 | 33 393. (Cumulatively progress is 114 198) | None | None |
| Number of wetlands under rehabilitation | 115 | Q3: 16 | 81 wetlands were under rehabilitation | Delays by the IA to consider the agreement thereby delaying commencement of work in the field | implementing Agent agreement is in place and will start in Q4 |
| Number of hectares of land where invasive alien plants treated/cleared (Initial Treatment) | 169 045 | Q3: 50 019 | 112 751. (Cumulative performance is 141 309) | None | None |
| Number of hectares of land where follow up invasive alien plants treated/cleared (Follow up Treatment) | 560 339 | Q3: 163 397 | 204 598 h/a were cleared. (Cumulative performance is 363 744) | None | None |
| Number of hectares of degraded land under repair | 31 262 | Q3: 9 379 | 9 510. (Cumulative performance is 22 675) | None | None |
| Number of kilometres of accessible coastline cleaned | 2 113 | Q1-Q4: 2 113 | 2 113 | None | None |
| Percentage of wild fires suppressed (provided there are not more than 2000) | 90% | Q1 – Q4: 90% | 111% (100%, i.e. 420, of fires reported were all suppressed) | None | None |
| Number of sustainable development,tools/instruments developed and implemented | Concept document for NSSD2 developed | Q3: NSSD2 concept document researched and formulated | Beyond NSSD Concept Document researched and formulated. Consultations undertaken with the Mintech working group members and DEA management. Requests for multi-stakeholders interviews or written input initiated | None | None |
| Number of Green Fund projects approved and implemented | 38 Green Fund projects approved for implementation | Q1-Q4: 38 Green Fund projects approved for implementation | 48 projects have been approved through the Green Fund, against the Investment Projects | None | None |
| Number of high-level environmental and sustainable development threat, weakness or opportunity early warning and/or response options researched and developed | Quarterly early warning and/or issue scanning reports | Q1-Q4: Compilation and presentation of the Quarterly Environmental Threat, Weakness and Opportunity Scan report to management | The Quarterly Environmental Threat, Weakness and Opportunity Scan (QETWOS), 2nd Quarter 2014/15 Report compiled for presentation to the DepartmentalRisk Management Committee Meeting on 13 November 2014 | QETWOS report compiled, but not presented due to a diary clash reported to the COO, DDG, etc. Also, no 4D meetings were held in the 3rd quarter. However, the report was submitted to Secretariat Services for presentation at the next available 3/4D meeting | QETWOS report will be presented at the Mintech workshop in February 2015 |
|  | 4 emerging issue response options formally submitted to top management and approved responses initiated | Q1-Q4: Emerging issue response options formally submitted to top management and approved responses initiated where necessary | Ministerial submission compiled and, together with the updated SIP 19 Description, submitted to the Minister via DEA EDMS on 3 November 2014 with a request for the Minister’s approval of the SIP and its submission to the PICC for formal recognition Compile and submit a detailed 3/4D submission entitled “Emerging Issue Response Options: Completed 3R findings in respect of Traffic Congestion, the MFMA and the Green Economy, GHG and Water Treatment Works and Peak Phosphate” on 17 December 2014 | None | None |
| Number of interventions for streamlining environmental authorisations finalised | 1 legal instrument under evaluation and adjustment (adoption of environmental instruments) | Q3: Obtain WG approval on environmental management instruments regulations | First draft Environmental Management Instruments Regulations circulated internally, finalisation moved to 2015/2016 | Priority given to EIA regulations finalisation. Implementation date of 8 Dec 2014 not negotiable. As a result this work had to be delayed | None |
|  | 4 legal instruments gazetted for implementation (EIA, financial provisioning and mine closure regulations and revised listing notices | Q3: Finalise EIA, financial provisioning and mine closure regulations, listing notice amendments and gazette for implementation Hold open days on EIA, financial provisioning and mine closure regulations amendments and listing notice amendments | EIA Regulations finalised and gazetted for implementation on 4 December 2014, implemented from 8 December 2014. Listing Notices finalised and gazetted for implementation on 4 December, implemented from 8 December 2014. Draft Finance Provisioning and Mine Closure Regulations gazetted for comment on 31 October 2014, being finalised. | Target will not be achieved in the 2014/15 and will be prioritised in 2015/16. A first draft has been circulated internally but finalisation occurs in 2015/16. Reason for delay is that the EIA and financial provisioning regulations had to be implemented by 8 Dec 2014 and had to be prioritised Financial Provisioning Regulations Gazetting occurred late (31 Oct 2014), resulting in commenting period ending in Dec 2014. Final regulations could not be finalised in Dec 2014 Financial provision regulations approval obtained late from Minister, thus gazetted for comment late and to be finalised in Q4 only | These regulations will be finalised and gazetted for implementation after obtaining WG/Mintech/Minmec approval Financial Provisioning Regulations Revised regulations will be submitted to WG7 and 11 in April 2015, Mintec and Minmec May 2015. If it can be justified, these regulations will be finalised and gazetted for implementation after obtaining WG/Mintech/Minmec approval |
|  | Readiness plan for the registration of ESPASA developed | Q3: Develop a plan on the readiness of the Department to take EAPASA forward | 24H Regulations have been gazetted for public comment and that DEA and EAPASA has entered into an MoU which paves the way for EAPASA's appointment as registration authority | None | None |
|  | 1 initiative on hydraulic fracturing of shale gas coordinated and supported | Q1-Q4: Attend and provide inputs at the Interdepartmental Hydraulic Fracturing Monitoring Committee | No meetings were scheduled in this quarter. A submission was prepared in response to a query from the WC which included the progress. This was sent to the Minister | None | None |
|  | 6 interventions for streamlining environmental authorisations for SIP and IPAP priorities developed | Q3: SIP 8: Protocol and SEA finalized for consultation SIP 10: Sensitivity map finalized SIP 16(a): Draft sensitivity map available SIP 16(b): Inception meeting for SEA on hydraulic fracturing Held SIP 2 – Port SEA/authorization process •TOR for ports SEA approved | 4 interventions facilitated as follows: SIP 8 Protocol and Strategic Environmental Assessment (SEA) finalised for consultation. To be consulted upon in upcoming MinTech and Minmec meetings) SIP 10 Sensitivity map finalised SIP 16(a) Draft sensitivity map for Shale Gas SEA available SIP16 (b) Square Kilometre Array SEA ToRs approved | None | None |
|  | 1 sector guideline developed (mining review guideline) | Q3: Stakeholder process initiated for the mining review guideline | ToR to outsource the development of the guideline finalised | Reprioritisation of work as the development of financial provisioning and mine closure regulations was a priority | None |
| PROGRAMME 7 : CHEMICALS AND WASTE MANAGEMENT |
| Number of waste management Instruments developed and implemented | HCRW Management Regulations finalised | Q3: No target | Draft regulations developed and recommendation for approval submitted to Minister for consideration | There are pending key issues between DEA and Department of Health and finalisation of the matters has delayed gazetting of the regulations | The matter has been elevated to Ministerial level to be resolved and meeting between the two Ministers is being facilitated |
|  | Norms and Standards for theValidation of the Treatment Efficacy and Operation of Non combustion Technology Used to Treat Health Care Risk Waste finalised | Q3: No target | Draft Norms and Standards developed and recommendation for approval submitted to Minister for consideration | There are pending key issues between DEA and Department of Health and finalisation of the matters has delayed gazetting of the regulations | The matter has been elevated to Ministerial level to be resolved and meeting between the two Ministers is being facilitated |
|  | Draft Import-Export regulations developed | Q3: Revise regulations | Draft regulations are being revised | None | None |
|  | Draft Norms & Standards/ guidelines for preparation of Waste Derived Fuel (WDF) developed | Q3: Review comments and amend N&S/Guidelines | Revised scope for the work approved Revised SLA signed and order number issued for the service provider to continue with the work | The need to amend the scope of the project and approval process thereof affected the project commencement schedule | Work will commence in January 2015 |
|  | Draft of Norms and Standards for the sorting, shredding, grinding or bailing of general waste developed | Q3: Literature review report developed | Literature review report developed | None | None |
| Percentage increase in waste being reused, recycled and recovered | 10 % | Q1-Q4: Monitor the implementation of approved Industry Waste Tyre Management Plans | Monthly reports available. To date 16.5% waste tyres have been recycled/re used or used for energy recovery | None | None |
| Number of Integrated industry waste management plans reviewed | 2 integrated Industry Waste Management Plans reviewed | Q3-Q4: Review the industry WMPs | 2 Industry Management Plans reviewed. a) e-waste plan b) lighting plan | None | None |
| Percentage of unlicensed waste disposal sites authorised per annum | 80 % of unlicensed sites licensed | Q3: Submission of application forms to provinces | Survey to identify current unlicensed waste site undertaken and finalised. List of unlicensed site available Process to appoint service provider is at an advanced stage. Funds secured and tender advertised closing 12 Dec 2014 Bid evaluation process will be conducted in quarter 4 | Financial constraints and delays in securing funding for the projects has effected delivery of planned quarterly milestones | Funding has been secured and appointment of service providers in at an advanced stage. The work will be underway in quarter 4 |
| Number of buy-back centres established | 11 | Q3: 4 | 1buy-back centres established. Cumulatively, 2 buy-back centres was established ( April to December 2014) | The target was set based on the projects that were in the new project applications at the time. Most of the buy-back centre projects will be completed in quarter 4 | Fast-track implementation of buy-back centre projects |
| Number of chemical management instruments developed and implemented | National Implementation Plan for the Stockholm convention updated | Q2-Q3: Data collection | Draft Review summary report for use, consumption, production, import, export and obsolete stock for 10 newly listed POPs developed | None | None |
|  | Draft PCB phase out plan for municipalities developed | Q2-Q3: Data collection | Data Collection Report finalised | None | None |
|  | Study on impact of Minamata Convention on Mercury conducted | Q3: Data collection | DG approved undertaking of the study TORs advertised in the Government Gazette | There was a delay in the processing of the EDMS for ToR’s approval that resulted in the delay of the whole project | The project has been prioritised and we will negotiate with the appointed service provider to shorten the study |
|  | Draft national chemicals profile developed | Q2-Q3 : Data collection | Data collected on use, production, consumption, import and export for: (a chemicals listed in Annex III of Rotterdam Convention; and b) chemicals listed in Stockholm Convention Draft policy discussion paper questions on chemicals management developed | None | None |

PROGRESS ON DEA SERVICE DELIVERY IMPROVEMENT PLAN INDICATORS

| PERFORMANCE INDICATORS | 2014/15 TARGET AS PER ANNUAL PERFORMANCE PLAN (APP) | 3RD QUARTER TARGET AS PER APP | 3RD QUARTER ACTUAL OUTPUT | CHALLENGES | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- |
| PROGRAMME 1: ADMINISTRATION |
| Percentage of reported fraud and corruption allegations dealt with within timeframes | 100% | Q1- Q4: 100% | 36% Compliance. 11 cases received and 4 cases are pending and are within time frame and 7 are pending but are already out of timeframes | Delays in the procurement process of the appointment of the service providers to conduct the forensic investigations | Appointment of the service provider to be prioritised |
| Percentage of legitimate invoices from suppliers paid with prescribed timeframes (30 days) | 100% | Q1- Q4: 100% | 99.9% (R3, 706,594/R3,708,003 x 100) compliance to payment within (30) Days Early warning done from payment request control reports to ensure proper risk management on payments within 30 days (4 invoices to amount of R14 000 exceeded 30 days from total of 7 374 invoices to the amount of R1.4 billion) | None | None |
| Percentage of Presidential Hotline queries processed within timeframes (within 3 working days) | 100% | Q1- Q4: 100% | 100%. 2 queries received and both processed within timeframe | None | None |
| Percentage of parliamentary questions and requirements responded to within the timeframes | 100% | Q1- Q4: 100% | 98% compliance - 100 parliamentary questions were responded to in quarter, 98 of which were responded to within timeframes, and 2 outside timeframes | Nature and complexity of questions leads to delays as some of the questions require extensive search of information and/or consultation with other parties | Enhance business processes and cooperation to ensure all questions are responded to within timeframe |
| PROGRAMME 2 : LEGAL ,AUTHORISATIONS ,COMPLIANCE AND ENFORCEMENT |
| Percentage of all DEA complaints and Incidents responded to through a compliance and/or enforcement action in accordance with the timeframe set in the referral protocol | 92% | Q1 – Q4: 92% | 95%. In the third quarter, a total of 20 complaints received were due according to the Referral Protocol timeframes and 19 were responded to as per timeframes | None | None |
| Percentage of environmental impact assessment (EIA) decisions processed within the prescribed time frames (subject to number of applications received) | 65% | Q1 – Q4: 65% | 58.82% EIA finalized within timeframes. 85 EIA applications finalized in the quarter. 50 within timeframe and 35 outside of timeframes | Human resource capacity constraints | Vacant post and management level have been filled with effect from January 2015. Processes are underway to facilitated filling of all other vacancies |
| Percentage of appeals received, finalised within the timeframes determined for the category of appeal | 85% | Q1- Q4: 85% | 100% of appeals were finalised within the prescribed timeframes. Out of 16 appeals due to be finalised in this quarter, all were finalised in accordance with the timeframes as per the appeals protocol | None | None |
| Percentage of litigation matters dealt with in terms of court rules or by agreement between litigating parties | 95% | Q1- Q4: 95% | 100%. 78 active matters (includes 10 new matters that were received) and 5 were finalised | None | None |
| Percentage compliance with the implementation of PAIA | 95% | Q1- Q4: 95% | 100% ( 10 out of 10 PAIA request processed within timeframes) | None | None |
| Percentage of applications for permits issued within timeframe (Marine Research permits) | 100% | Q1- Q4: 100% | 1 existing permit amended and re-issued (100%) | None | None |
| Percentage of applications for permits issued within timeframe (Off-road Vehicle permits) | 100% | Q1- Q4: 100% | 100% All five permits that were received were issued and processed within timeframe | None | None |
| Percentage of applications for permits issued within timeframe (Dumping permits) | 100% | Q1- Q4: 100% | Two revised dumping at sea permits were issued for the Ports of Mossel Bay and Durban. (100%) | None | None |
| Percentage of applications for permits issued within timeframe (Permits for Activities within Marine Protected areas) | 100% | 100% | 2 permits were issued in this quarter for scuba diving in MPA’s within time frame | None | None |
| Percentage of GMO applications for permits assessed within prescribed timeframe | 100% | Q1- Q4: 100% | 100% (8/8) GMO applications received and reviewed. Recommendation letter submitted for EC meeting of November 2014 | None | None |
| Percentage of CITES applications for permits assessed within prescribed timeframe | 100% | Q1- Q4: 100% | 100% (50/50)CITES permits applications received and evaluated | None | None |
| Percentage of TOPS applications for permits assessed within prescribed timeframe | 100% | Q1- Q4: 100% | 100% (20/20) TOPS permits applications received and 19 evaluated) | None | None |
| Percentage of BABS applications for permits assessed within prescribed timeframe | 100% | Q1- Q4: 100% | 5/5 (100%) received BABS notification assessed for environmental compliance within prescribed timeframe | None | None |
| PROGRAMME 7: CHEMICALS AND WASTE MANAGEMENT |
| Percentage of Waste Licence applications finalised within legislated time frames (provided not more than 200 applications received) | 95% | Q1- Q4: 95% | 85% (11/13) licenses were processed within legislated time frames | None | None |
| Percentage of contaminated land reports reviewed within time frame (subject to number of applications received) | 85% | Q1- Q4: 85% | 100% (4 out of 4) reports received and reviewed within set timeframes | None | None |