| NON-FINANCIAL PERFORMANCE REPORT | Q2 of 2013/14 01 July – 30 September 2013 |
| --- | --- |

TABLE OF CONTENTS

OVERVIEW	1

SUMMARY OF QUARTER 2 PERFORMANCE	2

PROGRAMME1: ADMINISTRATION	4

PERFORMANCE AGAINST QUARTERLY TARGETS	5

Branch: Corporate Services	5

Sub-programme: Human Resources Management	5

Sub-programme: Chief Information Office	9

Branch: Policy, Planning, Monitoring and Evaluation	11

Sub-programme: Policy Planning and Development	11

Branch: Stakeholder Relations, Communication and Legal Services	14

Sub-programme: Legal Services	14

Sub-programme: Stakeholder Relations & Communication	25

Branch: Chief Financial Office	27

Sub-programme: Financial Management	27

SUMMARY OF  PERFORMANCE AGAINST QUARTERLY TARGETS	28

PROGRAMME 2: AGRICULTURAL PRODUCTION, HEALTH AND FOOD SAFETY	29

PERFORMANCE AGAINST QUARTERLY TARGETS	30

SUMMARY OF  PERFORMANCE AGAINST QUARTERLY TARGETS	33

PROGRAMME 3: FOOD SECURITY AND AGRARIAN REFORM	34

PERFORMANCE AGAINST QUARTERLY TARGETS	35

Sub-programme: Food Security	35

Sub-programme: Sector Capacity Development	38

SUMMARY OF  PERFORMANCE AGAINST QUARTERLY TARGETS	39

ECONOMIC DEVELOPMENT, TRADE AND MARKETING	40

PERFORMANCE AGAINST QUARTERLY TARGETS	41

Sub-programme: Agro-Processing and Marketing	41

Sub-programme: Cooperatives and Rural Enterprise Development	42

Sub-programme: International Relations and Trade	42

SUMMARY OF  PERFORMANCE AGAINST QUARTERLY TARGETS	46

PROGRAMME 5: FORESTRY AND NATURAL RESOURCES MANAGEMENT PROGRAMME	47

PERFORMANCE AGAINST QUARTERLY TARGETS	48

SUMMARY OF  PERFORMANCE AGAINST QUARTERLY TARGETS	51

PROGRAMME 6:  FISHERIES MANAGEMENT	52

Sub-programme: Aquaculture Management	53

Sub-programme: Marine Resources Management	57

ADDITIONAL INDICATORS AT SUB-PROGRAMME LEVEL	58

SUMMARY OF  PERFORMANCE AGAINST QUARTERLY TARGETS	58

CONCLUSION	59

ACRONYMS

ABET 		Adult Basic Education and Training

ABP 		Annual Business Plan

ACP 		Aquaculture Certification Plan

ADF 		Agricultural Development Finance

ADZ 		Aquaculture Development Zone

AGIS 		Agricultural Geo-referenced Information System

AgriBEE	Agricultural Broad-Based Black Economic

Empowerment

APA 		Agricultural Produce Agents

API 		Agricultural production input

APP 		Annual Performance Plan

ARC		Agricultural Research Council

ATF 		Agricultural Trade Forum

ATI 		Agricultural Training Institute

ATPR		Agricultural Trade Progress Report

BCC		Benguela Current Commission

BEE		Black Economic Empowerment

CAADP 	Comprehensive African Agricultural Development       .........................Programme

CAF		Consultative Advisory Forum

CASP 		Comprehensive Agricultural Support Programme

CC 		Climate change

CCS 		Compulsory community service

CD 		Chief Director

CMDB 		Configuration management database

COMESA 	Common Market for Eastern and Southern Africa

CPI 		Consumer Price Index

CRDP 		Comprehensive Rural Development Programme

DAFF 		Department of Agriculture, Forestry and Fisheries

DBSA 		Development Bank of Southern Africa

DDG 		Deputy Director-General

DEA 		Department of Environmental Affairs

DEXCO		Departmental Executive Management Committee

DFQF 		Duty free and quota free

DG		Director-General

DHET 		Department of Higher Education and Training

DPSA 		Department of Public Service and Administration

DPW 		Department of Public Works

DRDLR 		Department of Rural Development of Land Reform

DRP 		Disaster Recovery Plan

EAC		East African Cooperation

EAF 		Ecosystems Approach to Fisheries

EAF 		Ecological Approach to Fisheries

EC		European Countries

EE		Employment equity

EFTA 		European Free Trade Association

EH&W 		Employee Health and Wellness

EPA 		Economic Partnership Agreement

EPDM               Employee Performance Development Management

EPWP               Expanded Public Works Programme

ER A 		Ecological Risk Assessment

ER P 		Enterprise Resource Planning

EU		European Union

FAnGR		Farm animal genetic resources

FARM		Framework for Aquaculture Research Management

FAO		Food and Agriculture Organization

FET 		Further Education and Training

FMD 		Foot-and-mouth disease

FMP 		Fisheries Management Plan

FPE		Fish processing establishment

FS 		Food security

FTE		Full-time equivalent

GADI 		Grootfontein Agricultural Development Institute

GDP 		Gross Domestic Product

GEP 		Gauteng Enterprise Propeller

GFI 		Gross farm sector income

GHG 		Greenhouse gases

GMO		Genetically Modified Organism

HE		Higher Education

HIV 		Human Immunodeficiency Virus

HoD 		Head of Department

HR 		Human Resources

HRD 		Human Resources Development

HRM		Human Resources Management

IBSA 		India, Brazil and South Africa

ICT 		Information and Communication Technology

IFSNP 		Integrated Food Security and Nutrition Programme

IFSS 		Integrated Fisheries Security Strategy

IGDP 		Integrated Growth and Development Plan

ILM		Industry liaison meeting

IPAP 		Industrial Policy Action Plan

IT 		Information Technology

ITSC		International Trade and Security Cluster

KIM		Knowledge and Information Management

LR 		Labour Relations

LTRAMP 	Long-term Rights Allocation Management Process

Mafisa 		Micro-agricultural Financial Institutions of South Africa

MAP 		Marketing of Agricultural Products

MAST 		Marine Administration System

MCM		Marine and Coastal Management

MCS		Monitoring, Control and Surveillance

MDG 		Millennium Development Goals

M&E		Monitoring and Evaluation

MER		Monitoring, Evaluation and Reporting

MERCO SUR	Mercado Commún del Sur

MIS 		Marketing Information System

MLRA 		Marine Living Resources Act

MoA 		Memorandum of Agreement

MoU 		Memorandum of Understanding

MSP 		Master Systems Plan

MTEF 		Medium Term Expenditure Framework

MTSF 		Medium Term Strategic Framework

NAC		National Agro-meteorological Committee

NAFU		National African Farmers’ Union

NAMC		National Agricultural Marketing Council

NARMCO	National Agricultural Risk Management Committee

NAS 		National Aquaculture Strategy

NDTT 		National Disaster Task Team

NERPO		National Emergent Red Meat Producers’ Organisation

NFA 		National Forests Act

NGP 		New Growth Path

NPoA 		National Programme of Action

OIE 		Office International des Epizooties

OHS 		Occupational Health and Safety

PBR		Plant breeders’ rights

PDA 		Provincial Department of Agriculture

PDI 		Previously disadvantaged individual

PFMA 		Public Finance Management Act

PGRFA 		Plant Genetic Resources for Food and Agriculture

PMDS 		Performance Management and Development System

QPR		Quarterly performance report

R&D 		Research and development

RSA 		Republic of South Africa

SADC		Southern African Development Community

SALA 		Subdivision of Agricultural Land Act

SAQA 		South African Qualifications Authority

SASSA 		South African Social Security Agency

SDIP 		Service Delivery Improvement Plan

SETA 		Sector Education and Training Authority

SMME		Small, medium and micro enterprises

SMS 		Senior Management Services

SOE		State-owned entities

SPS 		Sanitary and phytosanitary

SRPP 		Social responsibility programmes and projects

TAC		Total allowable catch

TAE		Total allowable estimate

the dti 		The Department of Trade and Industry

TIDCA 		Trade, Investment and Development Cooperation

Agreement

ToR		Terms of Reference

UN 		United Nations

VOIP 		Voice over Internet Protocol

WCR L 		West Coast Rock Lobster

WFFP 		Working for Fisheries Programme

WSCD 		White Shark Cage Diving

WSP 		Work Skills Programme

WTO		World Trade Organization

# OVERVIEW

In this organisational performance report, the Department presents its Quarter 2 Non-Financial Performance Report for the period 1July up to 30 September 2013, compared to the planned deliverables as reflected in Part B and Annexure 1 of Part C of its Strategic Plan. This Report has been compiled in accordance with the requirements of sections 92 and 114 of the Constitution and other government legislative prescripts such as the PFMA and relevant National Treasury Regulations and Frameworks that guide performance management in the public sector to display and promote transparency and accountability to stakeholders and the general public.

The Report is intended to provide an overview of the Department`s operational performance at the end of the second quarter of 2013/14. The information in this Report will also be utilised to respond to the Department`s commitments in the achievement of government Outcomes 4, 7 and 10. This Report, together with the forthcoming reports for quarters 3 and 4, will form the basis of the Department`s Annual Report to be compiled at the end of the current financial year.

As can be seen in the Report, 26 out of 54 Quarter 2 targets have been met resulting in a 48% success rate. Technical Branches had a total of 34 targets for a period under review of which 18 have been achieved (53%). The response for the submission of relevant evidence and the provision of reasons for variance, is generally gaining momentum if the Quarter 2 performance is compared to the previous Quarter 1. The contents of this Report have been verified as factual by Deputy Directors-General of the various Branches, who have attached their signatures to the verification template as required by the approved Monitoring, Evaluation and Reporting (MER) guidelines. Furthermore, the performance information was interrogated at the recent Quarterly Review Meeting (QRM), attended by the entire Senior Management team. The QRM identified several weaknesses in the performance management process and thus several corrective actions were identified.

### SUMMARY OF QUARTER 2 PERFORMANCE FOR 2013/14

| Programme | PERFORMANCE IN QUARTER 2 | % completed in Q2 |
| --- | --- | --- |
|  | Quarter 2 Planned Targets | Quarter 2 Achievements |  |
| POLICY, PLANNING, MONITORING AND EVALUATION | 3 | 0 | 0% |
| CORPORATE SERVICES | 10 | 3 | 30% |
| STAKEHOLDER RELATIONS, COMMUNICATION & LEGAL SERVICES | 3 | 1 | 33% |
| CHIEF FINANCIAL OFFICE | 4 | 4 | 100% |
| TRADE PROMOTION AND MARKET ACCESS | 6 | 3 | 50% |
| FOOD SECURITY AND AGRARIAN REFORM | 3 | 1 | 25% |
| AGRICULTURAL PRODUCTION, HEALTH AND FOOD SAFETY | 6 | 5 | 83% |
| FORESTRY AND NATURAL RESOURCES MANAGEMENT | 12 | 5 | 42% |
| FISHERIES MANAGEMENT | 7 | 4 | 57% |
| TOTAL | 54 | 26 | 48% |

# PROGRAMME1: ADMINISTRATION

Purpose

Provide strategic leadership, management and support services to the Department. The aim of the programme is to lead, support and promote agricultural, forestry and fisheries resources management through policies, strategies and programmes to enhance sustainable use, and to achieve economic growth, job creation, food security, rural development and transformation.

The programme comprises the Ministry, Office of the Director-General, Chief Financial Office, Internal Audit, Corporate

Services, Stakeholder Relations and Legal Services, Policy Planning, Monitoring and Evaluation and Office Accommodation.

Strategic Goals and Strategic objectives

- Strategic Goal 6: Effective and efficient governance

SO 2:  Strengthen policy, monitoring, evaluation, reporting and sector information.

SO 3:	Provide effective audit, investigative and legal, human resources and financial risk management.

SO 5:	Provide leadership and manage communication and information.

### PERFORMANCE AGAINST QUARTERLY TARGETS

### Branch: Corporate Services

### Sub-programme: Human Resources Management

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Human Resources Management | 6 | 3 | Integrated Human Resource Management Plan submitted to DPSA and implemented. | Identify units with a high vacancy rate and advise. | Agriculture & Forestry: During the reporting period units with a high vacancy rate were identified and visits were undertaken to these Directorates to advise on recruitment and selection processes. ODC meetings were also held monthly to monitor the vacancies in the Department and to take action on posts where there were no movement. | Acceptable vacancy rate as per Public Service norms is 11%. However, a number of appointments were recommended, but awaiting clearance finalisation of these appointments that would reduce vacancy rate to below 13%. Vacancy rate as at 30 September 2013 is still at 13% (same as in Q1). | The protracted delays in the verification of criminal and citizenship checks by the State Security Agency through the Directorate: Security Services impacts on the vacancy rate of the Department. Although SAQA has reduced its turnaround time on the verification of qualifications, it still takes an average of 30 days to verify qualifications. Managers are also not committed to short- listing and interview dates and the postponing thereof delays the filling of vacancies. | Amber |
|  |  |  |  |  | Fisheries: Vacancy rate as at 30 September 2013 was 6.24% (43 vacant posts from the total establishment of 705 posts). |  | Branch: Fisheries Management and its support function’s vacancy rate dropped due to the cleaning up of PERSAL and abolishment of all unfunded vacant posts. |  |
|  |  |  |  | Approved jobs evaluated. | During the reporting period the job evaluation results of 132 posts were approved by the relevant delegated authorities. | There was no deviation from the targeted number of jobs that were planned to be evaluated. | The Department of Public Service and Administration delays the verification of vacant posts on salary levels 10 and 12 in Programme 1, in terms of PSCBC Resolution 1 of 12. This process currently causes a delay of more than four months. | Green |
|  |  |  |  | Improve turn-around times on verification process. | The average turnaround time for SAQA to verify qualifications before an appointment can be made was reduced from an average of 38 working days to 30 working days. A verification agreement was signed with SAQA to commit them to turn around times. Regular interactions are held with the Director: Security Services to follow up on the delays in the criminal and citizenship checks by the State Security Agency. |  | Protracted delays were experienced from the State Security Agency (SSA) on the verification of criminal and citizenship checks during this reporting period. | Amber |
| Employee Development and Performance Management | 6 | 3 | Integrated Human Resources Management Plan submitted to DPSA and implemented. | Develop an approved training report submitted to PSETA, HRD Strategy and M&E report submitted to DPSA. | Training report was developed and approved during the period under review. The report was submitted to PSETA. HRD Strategy and M&E report were also submitted to DPSA. | None. | None. | Green |
|  |  |  |  | Analysis report on alignment of Performance Agreements to APP. | A total of 78% of levels 1-12 employees work plans have been received. A total of 85% Performance Agreements have been finalised and filed with Directorate: Employee Development and Performance Management. The analysis on alignment of the SMS members Performance Agreements with the Annual Performance Plans was done in Q2. The recommendations will be implemented in Q3 during the first performance review process. SMS moderation process finalised. |  | Corrective actions or consequences which will be implemented in respect of non-compliance need to be indicated. | Amber |
| Employee Relations | 6 | 3 |  | Conduct management intervention implemented at KZN Region. | No indication of progress | State corrective action. |  | Red |
|  |  |  |  | Communicate the approved plan to DEXCO. | No indication of progress | State corrective action. |  | Red |
|  |  |  |  | Monitoring and Evaluation approved. | No indication of progress | State corrective action. |  | Red |

### Sub-programme: Chief Information Office

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Information and Communication Technology | 6 | 5 | MSP implemented. | ICT strategy plan (phase 4) developed and approved by DDG: Corporate Services. | ICT strategy plan (phase 4) developed and approved by DDG: Corporate Services. |  |  | Green |
| Knowledge and Information Management | 6 | 5 | KIM Strategy implemented. | Implement change management plan. | Drafted change management plan and forwarded it to relevant stakeholders for inputs of which Human Resources Directorate is one of the stakeholders. • The Directorate has decided that the current Core Work Group be tasked with duties relating to change management. • Terms of Reference of the Core Work Group applies. | The KIM Strategy has not been implemented yet. |  | Amber |

##### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

| Sub-programmes | Planned | Completed | In progress |  | Not Done | % completed for Q2 |
| --- | --- | --- | --- | --- | --- | --- |
| CD:CIO | 2 | 1 | 1 | 0 | 50% |
| CD:HRM | 8 | 2 | 3 | 3 | 25% |
| Total: | 10 | 3 | 4 | 3 | 30% |

### Branch: Policy, Planning, Monitoring and Evaluation

### Sub-programme: Policy Development and Planning

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Development Support | 6 | 2 | Programme/project decision support management system implemented. | Implement programme/ project decision support management system. (This is a tool which can support APAP and is necessary to M&E). | D: PDS was given the responsibility for the formulation of the Agricultural Policy Action Plan (APAP), which delayed its work in the design and institutionalization of the programme and project management system. -APAP was presented at several consultation meetings both internally and with sector organisations, but is still to be finalised for approval by Cabinet. | The Directorate is now focusing its attention to the formulation of Agriculture Policy Action Plan (APAP), but the agreed target from the Strategic Plan was to get the approval and implement the programme/project decision support management system. | The formulation and institutionalization of APAP bears implications for the implementation of a programme/project decision support system. APAP processes must be integrated with that of the programme /project management system. | Red |
| Policy Research Support | 6 | 2 | Policy analysis framework implemented. | Review the status of sectoral policies. | The status report on sectoral policies is being finalized for presentation at the GOPC before being presented to DEXCO for approval. | The Directorate found it necessary to also review the status of DAFF internal/corporate policies. The status report on internal policies is still being developed. The line function policy units are providing information with regard to the policies developed, approved, those still in the development stage and those that are in the pipe line. The finalized report will be presented to STC and GOPC upon completion. |  | Amber |
|  |  |  | R&D programme approved. | Monitor the implementation of the targeted R&D programme. | R&D work has been commissioned with the ARC, the Consortium of Universities, and through the National Research Foundation. |  |  | Amber |

##### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

| Sub-programme | Planned | Completed | In progress |  | Not Done | % completed for Q2 |
| --- | --- | --- | --- | --- | --- | --- |
| CD:PDP | 3 | 0 | 2 | 1 | 0 |
| Total: | 3 | 0 | 2 | 1 | 0% |

### Branch: Stakeholder Relations, Communication and Legal Services

### Sub-programme: Legal Services

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Legal Services | 6 | 4 | Legislation review project completed. | NEDLAC and government Cluster process followed and 5 Bills forwarded to SLA for pre-certification. | Marine Living Resources Amendment Bill. On 24 July 2013, the SLA provided Legal Services with the preliminary opinion on the Bill. On 29 August 2013, the SLA certified the Bill. On 12 September 2013, the Bill was formally introduced into Parliament. Liquor Products Amendment Bill The Bill will be presented to the Economic Cluster. Agricultural Research Council Amendment Bill On 2 July 2013, Legal Services received the comments from the SLA. On 15 July 2013, the line function informed Legal Services that the Minister approved the Bill for public comments. On 2 August 2013, the Bill was published for public comments. Protection and Development of Agricultural Land Framework Bill On 23 July 2013, Legal Services received the comments from the SLA. On 2 September 2013, line function informed Legal Services that they are awaiting the Minister's approval to publish the Bill for comments. Agricultural Product Standards Amendment Bill On 16 July 2013, a revised Bill was forwarded to the SLA. On 1 August 2013, received comments from SLA. On 16 August 2013, the Bill was published for comments. | Evidence needs to be provided. |  | Amber |
|  |  |  |  | Submit 9 Bills to the relevant unit for submission to the Minister and to Cabinet for approval. | Plant Breeder Right's Amendment Bill The Bill was published for public comments on 26 April 2013. On 21 June 2013, the signed-off DDG instructions were provided to Legal Services. On 5 July 2013, the Service Provider (SP) provided Legal Services with inputs on the Bill. On 19 July 2013, the State Law Advisers (SLA) informed us that they are busy finalizing the certification. Inputs were received from the SLA and were incorporated. The Bill is not going back to the SLA for certification. Pounds Bill The Bill was published for public comments on 18 April 2013. Line function is busy with consultations. On 16 July 2013, a meeting was scheduled with the South African Police Services. The meeting was cancelled and will take place on 20 August 2013. On 20 August 2013, the House of Traditional Leaders requested extension for comments until end of September 2013. Veterinary and Para-Veterinary Professions Bill, 2012 The President has assented to the Veterinary and Para-Veterinary Professions Amendment Act, 2012. The Regulations are being drafted. Agricultural Produce Marketing Agencies Amendment Bill On 28 March 2013, the Bill was published for comments. Workshops with stakeholders were conducted. All comments are consolidated into the Bill. On 11 July 2013, line function informed Legal Services that they have completed the draft report from the public hearings. On 8 August 2013, a DAFF internal feedback session on the Bill was done. The process was halted as a result of the Ministerial instruction letter. Marketing of Agricultural Products Amendment Bill On 14 June 2013, the Bill was published for comments. By 14 August 2013, the public consultation process including workshops had to be completed. The process was halted as a result of the Ministerial instruction letter. Fertilizers and Feeds Bill The Bill was introduced to the Portfolio Committee in February 2013, and on 14 May 2013, the Portfolio Committee referred the Bill back to the Department for a further consultation process. Line function is currently busy amending the Amendment Bill. Conservation of Agricultural Resources Amendment Bill On 2 July 2013, the Bill was published for comments. By 17 August 2013, the consolidation of all comments had to be completed. A task team meeting was held on 10 September 2013. On 10 October 2013, a provincial workshop was planned in Gauteng. Plant Health Bill On 16 July 2013, line function provided Legal Services with the signed-off instructions. On 21 August 2013, line function informed Legal Services that the comments are being incorporated. Due date for comments from WTO committee was 18 October 2103. Perishable Products Export Control Bill On 24 July 2013, Legal Services received the submission requesting the Minister to approve the publication of the Bill for comments. On 8 August 2013, Legal Services informed the PPECB that the Bill is with line function in order to clarify certain issues regarding the Bill. On 17 September 2013, line function indicated that the consultation process was halted. National Forests Amendment Bill On 18 July 2013, line function provided Legal Services with the consolidation of all comments. On 31 July 2013, Legal Services forwarded the signed-off instructions to the SP. On 15 August 2013, Legal Services received inputs from the SP. On 20 August 2013, Legal Services received the final Bill to be forwarded to the SLA. National Veld and Forest Fire Amendment Bill On 18 July 2013, line function provided Legal Services with the consolidation of all comments. On 31 July 2013, Legal Services forwarded the signed-off instructions to the SP. On 15 August 2013, Legal Services received inputs from the SP. On 20 August 2013, Legal Services received the final Bill to be forwarded to the SLA. |  |  | Amber |

### Sub-programme: Stakeholder Relations & Communication

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Communication Services | 6 | 5 | DAFF Communication Strategy implemented. | Media plans for Female Entrepreneur and Arbor Week implemented. | Media plan for the Female Entrepreneur Awards was developed and implemented and the gala event was held on 23 August 2013 in Pretoria, Gauteng. A media plan for Arbor Week was implemented and Arbor Week was launched on 3 September 2013 at Hammarsdale, KwaZulu-Natal. A media plan for the Integrated Food and Nutrition Security Plan was developed and implemented in Dutywa, Eastern Cape on 17 July and also in Limpopo on 27 July 2013. |  |  | Green |

### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

| Sub-programmes | Planned | Completed | In progress |  | % completed for Q2 |
| --- | --- | --- | --- | --- | --- |
| CD:SRC | 1 | 1 | 0 | 100% |
| CD:LS | 2 | 0 | 2 | 0 |
| Total: | 3 | 1 | 2 | 33 |

### Branch: Chief Financial Office

### Sub-programme: Financial Management

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Financial Accounting | 6 | 3 | Improved financial management control. | Submit audited annual financial report to NT and AG by 31 July 2013. | Submitted audited annual financial statements for the year ended 31 March 2013 to National Treasury and Auditor General by 31 July 2013. |  |  | Green |
|  |  |  |  | Submit annual report to NT by 31 August 2013. | Annual report for the year ended 31 March 2013 was submitted to National Treasury by 31 August 2013. |  |  | Green |
|  |  |  |  | Submit Q1 interim financial statement (IFS) to NT by 31 July 2013. | Submitted interim financial statements for the quarter ended 30 June 2013 to National Treasury by 31 July 2013. |  |  | Green |
|  |  |  |  | Submit the audit matrix to NT and AG by 30 September 2013. | Audit matrix for the audited annual financial statements submitted to National Treasury and Auditor General prior to 30 September 2013. |  |  | Green |

### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

| Sub-programme | Planned | Completed | In progress |  | % completed for Q2 |
| --- | --- | --- | --- | --- | --- |
| CD:FM | 4 | 4 | 0 | 100 |
| Total: | 4 | 4 | 0 | 100% |

# PROGRAMME 2: AGRICULTURAL PRODUCTION, HEALTH AND FOOD SAFETY

Purpose

Manage the risks associated with animal diseases, plant pests, genetically modified organisms (GMOs) and registration of products used in agriculture; promote food safety and create an enabling environment for increased and sustainable agricultural production.

The programme comprises three sub-programmes, namely Plant Production and Health; Animal Production and Health; and Inspection and Laboratory Services.

Strategic Goals and Strategic Objectives

- Strategic Goal 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 1: Promote efficient production, handling and processing of food, fibre and timber.

- Strategic Goal 2: Sustained management of natural resources

SO 2: Ensure protection of indigenous genetic resources.

- Strategic Goal 3: Effective national regulatory services and risk management systems

SO 2: Establish and maintain effective early-warning and mitigation systems

### PERFORMANCE AGAINST QUARTERLY TARGETS

#### Sub-programme: Animal Production and Health

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Animal Production | 1 | 1 | Number of producers benefiting from animal improvement schemes. | 325 | 375 | 50 | Excess is due to the shortfall in Quarter 1. | Green |
| Animal Health | 3 | 2 | Planned surveillance conducted. | Plan animal disease surveillance programmes as required. Coordinate surveillance actions. Collate and analyse surveillance information. Compile surveillance reports. | The national pig survey was completed. | The achievement embraces all of the targets. |  | Green |

#### Sub-programme: Plant Production and Health

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Genetic Resources | 2 | 1 | Number of indigenous agricultural genetic resources conserved. | Select farmers, nucleus flocks and herds of animals that will be conserved. | 19 farmers and flocks of Zulu sheep were selected in KwaZulu- Natal. Seven farmers and herd of Afrikaner sheep were selected in North West. |  | Although the target was met, its not clear what the impact will be for the sector. | Green |
|  |  |  |  | Site visits to identify farmers and crops. | 59 farmers in Mpumalanga were identified and consulted for the identified landrace crops. | Site visits outstanding. | Logistical arrangements with the provincial government were delayed due to required protocols. This target will be completed in Q3. | Amber |
| Plant Health | 3 | 2 | Planned surveillance conducted. | Document and analyse surveillance results, finalise first report. | National surveillance of plant pests – Fruit fly ( Bactocera invadens) has been completed and report prepared. |  | Although the target was met, its not clear what the impact will be for the sector. | Green |

#### Sub-programme: Inspection and Quarantine Service

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inspection Services | 3 | 1 | Number of regulatory compliance and monitoring interventions implemented. | Conduct inspections, surveys, investigations, take appropriate action and compile report. | The following regulatory compliance and monitoring interventions were implemented: Plant and Animal Quarantine Inspections Surveillance Tests Reports compiled. |  | Although the target was met, its not clear what the impact for the sector will be. | Green |

### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

| Sub-programmes | Planned | Completed | In progress | % completed for Q2 |
| --- | --- | --- | --- | --- |
| CD:APH | 2 | 2 | 0 | 100% |
| CD:PPH | 3 | 2 | 1 | 67% |
| CD:IQS | 1 | 1 | 0 | 100 |
| Total: | 6 | 5 | 1 | 83% |

# PROGRAMME 3: FOOD SECURITY AND AGRARIAN REFORM

PURPOSE

The programme facilitates and promotes household food security and agrarian reform programmes and initiatives targeting subsistence and smallholder producers. It comprises three sub-programmes, namely, Food Security, Sector Capacity Development and Extension Support Services.

Strategic Goals and Strategic Objectives

- Strategic Goal 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 1: 	Promote efficient production, handling and processing of food, fibre and timber.

- Strategic Goal 4: A transformed and united sector

SO 4:	Provide leadership and support to research, training and extension in the sector.

### PERFORMANCE AGAINST QUARTERLY TARGETS

### Sub-programme: Food Security

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Subsistence Farming | 1 | 1 | Number of subsistence farmers supported. | 35 000 | Total number of subsistence farmers supported during Q2 is 27 414. NC = 1 836 beneficiaries EC = 11 594 beneficiaries WC = 352 beneficiaries FS = 644 beneficiaries NW = 0 MP = 1 380 beneficiaries LP = 9 224 beneficiaries KZN = 2 368 beneficiaries Gauteng= 16 community project | 7 586 farmers in Q2. Cumulative deviation: 26 794 farmers (Q1 and Q2). This number was not achieved in Q1 and Q2. | The actual target was not achieved because NW and Ilima/Letsema reports are not accounted for. The numbers will be adjusted in Q3. | Amber |
| Smallholder Development | 1 | 1 | Number of smallholder producers supported. | 3 000 | The number of smallholder producers supported during Q2 is 3 179. This resulted in a cumulative number of 6 188 supported, including 3 009 in Q1. Break down per province (Q2) is as follows: KZN – 228 producers, NC – 455 producers, GP – 48 producers, LIM – 431 producers, FS – 531 producers, MP – 329 producers, WC – 129 producers, and NW – 1 028 producers. |  |  | Amber |
| Infrastructure Support | 1 | 1 | Number of infrastructure anchor projects established. | Conduct feasibility study. | The following technical support was given to Makhathini anchor project: Specification on the installation of cattle grids/gates. Drawings on infield water meters. Specification and bill of quantities on the sub-surface drainage. Map of the piezometer. Dam scoping (30 of 40 dams scoping completed). | The feasibility study of the project was done in the previous financial year; currently the projects are being implemented as recommended by the feasibility study. | These projects are implemented by the various provinces and funded from their own budgets or other arrangements. DAFF does not fund these projects, but provides technical advisory support where the capacities in provinces are lacking. | Amber |

### Sub-programme: Sector Capacity Development

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sector Colleges | 4 | 4 | Number of Colleges of Agriculture accredited by CHE. | Financially assist Tsolo College for the development of training programmes. | DAFF conducted ICT infrastructure audit at Tsolo College of Agriculture to investigate whether the institution has the appropriate ICT infrastructure to enhance the development of training programmes. The audit report is currently being finalized and it will reflect on areas of improvement and financial assistance required. 50% of CASP funding has been transferred to Colleges for infrastructure improvement and development. |  |  | Green |

### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

| Sub-programmes | Planned | Completed | In progress | % completed for Q2 |
| --- | --- | --- | --- | --- |
| CD:FS | 3 | 0 | 3 | 0 |
| CD:SCD | 1 | 1 | 0 | 100 |
| Total: | 4 | 1 | 3 | 25% |

# ECONOMIC DEVELOPMENT, TRADE AND MARKETING

Purpose

Ensure value chain integration; facilitation of market access for agriculture, forestry and fisheries products in support of economic growth, job creation and development.

The programme comprises the following three sub-programmes, namely International Relations and Trade; Agro-processing and Marketing; and Cooperatives and Rural Enterprise Development.

Strategic Goals and Strategic Objectives

Strategic Goal 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 2: 	Coordinate government food security initiative.

Strategic Goal 5: Increased contribution of the sector to economic growth and development

SO 1:	Increase growth, income and sustainable job opportunities in the value chain.

SO 3:	Increase domestic and international market access for South African and African agricultural, forestry and fisheries products.

### PERFORMANCE AGAINST QUARTERLY TARGETS

### Sub-programme: Agro-Processing and Marketing

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Agro-processing Support | 5 | 1 | Agro-processing strategy implemented. | Develop business cases. | Development of agro-processing business cases: 1. Wool processing plant at Elundini Municipality - completed. |  |  | Amber |
|  |  |  |  |  | 2. Fresh produce (fruit and vegetables) processing plant at Greater Letaba. Business case was not developed due to lack of funding and feasibility study was also not conducted. | Lack of funding to undertake the feasibility study. | Need to develop partnerships with PDAs, the dti and IDC to fund identified projects |  |
| Marketing | 5 | 1 | Marketing strategy implemented. | Meetings of the network and its working groups; report on the outcomes of the network facilitated. | One meeting of the Aquaculture value chain network was held on 21 August 2013, while no Working Group meeting took place. A report on the outcomes of the network has been developed. |  |  | Green |

### Sub-programme: Cooperatives and Rural Enterprise Development

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cooperatives and Enterprise Development | 1 | 2 | Number of commodity based cooperatives established and supported. | 2 | 4 commodity based cooperatives established to support smallholder producers. |  |  | Green |

### Sub-programme: International Relations and Trade

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Americas, Australasia, Europe, and Middle East Relations | 5 | 3 | International relations strategy implemented. | Implementation of bilateral and multilateral engagements and new agreements facilitated (capacity building, market access and technical assistance). | IMPLEMENT OF BILATERAL AND MULTILATERAL ENGAGEMENTS AND NEW AGREEMENTS FACILITATED. Successfully facilitated the following: BRICS- DAFF’s hosting of Agriculture Cooperation Working Group was held on the 26-27 August. ARGENTINA-DAFF’s participation in Bi-national Commission with Argentina in Buenos Aires, from 1-2 August. SAUDI ARABIA-Facilitated DAFF’s attendance of SA/SAUDI JEC on the 25 June. IRAN-Coordinated a visit by a technical team to Iran from 16 – 20 September. JAPAN- Three year programme on Horticulture was initiated in 2011. During the year 2011, 15 officials participated in a capacity building programme, followed by 11 officials in 2012. For 2013, in partnership with KOICA, we are preparing to capacitate 19 officials. MULTILATERAL ENGAGEMENTS. FAO- Coordinated the attendance of the 40th session of CFS to be held in Rome from 07 – 11 October. | For Q3 the implementation of the existing agreements and the creation of the new agreements will be divided. | This target will remain amber until Q4 when all the activities have been done. | Amber |
| Africa Relations |  |  |  | Alignment of MoUs to CAADP principles and alliance building facilitated. | CAADP implementation in the country: A stakeholder consultation workshop was held in KZN. Budget tracking inception workshop was held and consultants given their mandate and Terms of Reference. Progress report submission on CAADP was prepared for DEXCO and oversight. BILATERAL ENGAGEMENTS/ IMPLEMENTING SIGNED AGREEMENTS - Proposed amendments from DIRCO State Law Advisors are now included in the draft MoU with Malawi. Inauguration of the JMC meeting took place in Tanzania from 11-12 September 2013. Zimbabwe draft MoU was amended and resent to Legal Services for legal opinion. Interdepartmental meeting on Niger, Ghana, Senegal, Angola, Botswana, DRC and Namibia JMC was held at DIRCO. |  |  | Amber |
| International Trade | 5 | 1 | Trade development strategy implemented. | Progress report on negotiations. | Progress report on Tripartite FTA negotiations has been consolidated for the Q2. |  |  | Green |

### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

| Sub-programmes | Planned | Completed | In progress | % completed for Q2 |
| --- | --- | --- | --- | --- |
| CD:AM | 3 | 0 | 3 | 0 |
| CD:SCD | 1 | 1 | 0 | 100 |
| Total: | 4 | 1 | 3 | 25% |

# PROGRAMME 5: FORESTRY AND NATURAL RESOURCES MANAGEMENT PROGRAMME

PURPOSE

Develop and facilitate the implementation of policies and targeted programmes to ensure management of forests, sustainable use and protection of land and water as well as managing agricultural risks and disasters.

There are three sub-programmes in the Forestry Programme, namely Forestry Operations; Forestry Development and Regulations; and Natural Resources Management.

Strategic Goals and Strategic Objectives:

- Strategic Goal 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 2: Coordinate government food security initiative.

- Strategic Goal 2: Sustained management of natural resources

SO 1: Ensure the sustainable management and efficient use of natural resources.

- Strategic Goal 3: Effective national regulatory services and risk management systems

SO 2: Establish and maintain effective early-warning and mitigation systems.

- Strategic Goal 5: Increased contribution of the sector to economic growth and development

SO 2: Increase the level of public and private investment in the sector.

### PERFORMANCE AGAINST QUARTERLY TARGETS

#### Sub-programme: Forestry Operations

| Directorate | SG | SO | Performance Indicator | Quarter 2Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KwaZulu–Natal Forestry Management | 1 | 2 | Number of smallholder producers supported. | 125 | 136 small growers supported. | 11 | 11 more small growers were supported in this quarter due to more people needing assistance with planting permits in the Umzimkulu area. | Green |
|  | 2 | 1 | Increased number of hectares rehabilitated. | 125 ha | 5 ha planted. | 120 | The majority of the planting will take place in the raining season which is in Quarters 3 and 4. | Amber |
| Eastern Cape Forestry Management | 1 | 2 | Number of smallholder producers supported. | 50 | 61 small growers supported. | 11 | The Directorate received requests of support from more small growers than anticipated, but was able to entertain such requests because they never had financial implications for the DAFF. | Green |
| Mpumalanga & Limpopo Forestry Management | 1 | 2 | Number of smallholder producers supported. | 50 | 35 small growers supported. | 15 | The Directorate was focused on Arbor Week and greening. The Q2 target will be achieved in Q3 and Q4. | Red |
| Forestry Management (Other Regions) | 1 | 2 | Number of smallholder producers supported | 125 | 37 small growers supported. | 88 |  | Amber |
|  | 2 | 1 | Increased number of hectares rehabilitated. | 25 | 0 | 0 | Planting Season is in Q3. | Red |

#### Sub-programme: Forestry Development and Regulations

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Small-Scale Forestry | 2 | 1 | Charter undertakings implemented. | First draft: guidelines and toolkits. | Draft guidelines/toolkits for the following sub-sectors have been developed: Growers Charcoal production Beekeeping (Honey production) Sawmilling Business management |  |  | Green |
| Commercial Forestry | 2 | 1 | Charter undertakings implemented. | Training and mentoring of planners in the regions. | Planners workshop held in KZN in Q1, which included a field visit to Richards Bay Minerals and demonstration of the enumeration equipment. Planners meeting and workshop for managers was held in Mthatha in Q2 and a field-day at Ntywenka. Enumeration equipment was also demonstrated. |  |  | Green |

#### Sub-programme: Natural Resources Management

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Land Use & Soil Management | 1 | 2 | Number of hectares (agricultural land, woodlands and indigenous forests) rehabilitated. | 9 000 ha | Total of 15 106 ha rehabilitated in Q2. Eastern Cape = 1 157 ha Free State = 0 Gauteng = 242,6 ha KwaZulu-Natal = 527 ha Limpopo = 9 316 ha Mpumalanga = 1 558 ha Northern Cape = 20 ha North West = 1 740 ha Western Cape = 545 ha | Exceeded target by 6 106 ha. |  | Amber |
| Water Use & Irrigation Development | 1 | 2 | Increase the number of hectares on irrigation schemes revitalised. | 50 ha | 85 ha revitalized at Vaalharts irrigation scheme. | Exceeded target by 35 ha. |  | Amber |
| Woodlands & Indigenous Forest Management | 1 | 2 | Number of hectares (agricultural land, woodlands and indigenous forests) rehabilitated. | 125 ha | 113,65 ha was rehabilitated during Q2. |  | Due to financial constraints some operations were suspended and employees had to do more work on rehabilitation. | Amber |
| Climate Change & Disaster Management | 1 | 2 | Climate change adaptation and mitigation plans implemented. | Appoint service providers for the approved projects. | A service provider was appointed. Inception report, which includes the latest project plan was submitted by the service provider. |  |  | green |

| Sub-programme | Planned | Completed | In progress | No supporting documents | % completed for Q2 |
| --- | --- | --- | --- | --- | --- |
| CD:FO | 6 | 2 | 2 | 2 | 33% |
| CD:NRM | 4 | 1 | 3 | 0 | 25% |
| CD:FDR | 2 | 2 | 0 | 0 | 100% |
| Total: | 12 | 5 | 5 | 2 | 42% |

### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

# PROGRAMME 6:  FISHERIES MANAGEMENT

PURPOSE

Promote the development, management, monitoring and sustainable uses of marine living resources and the development of South Africa’s fisheries sectors. Sustainable livelihoods will be achieved through aquaculture growth and fisheries economic development.

The programme comprises four sub-programmes, namely Aquaculture and Economic Development; Fisheries Research and Development; Marine Resource Management; and Monitoring, Control and Surveillance.

STRATEGIC INTERVENTIONS:

- Facilitate investment in production and support infrastructure for aquaculture and fisheries.

- Support the development of small-scale fisheries.

- Advance transformation of fisheries.

- Maintain the productivity of fish stocks and ecosystems, and rebuild depleted fish stocks.

Strategic Goals and Strategic Objectives

- Strategic Goal 1: Increased profitable production of food, fibre and timber products by all categories of producers

SO 2: Coordinate government food security initiative.

- Strategic Goal 2: Sustained management of natural resources

SO 1: Ensure the sustainable management and efficient use of natural resources.

- Strategic Goal 5: Increased contribution of the sector to economic growth and development

SO 1: Increase growth, income and sustained job opportunities in the value chain

### Sub-programme: Aquaculture Management

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Aquaculture Technical Services | 1 | 2 | Number of fish farms supported. | Technical support and advice provided to 5 fish farms. | Support was provided to 8 fish farms and approval was granted for funding through ADEP. The farms supported financially are: 1.Abagold (Pty) Ltd- abalone farm expansion, Hermanus, Western Cape. 2.Blue Cap General Trading (Pty) Ltd- dusky kob farm expansion, Paternoster, Western Cape. 3.Aloe Creek Aquaculture CC- tilapia farm expansion, Cullinan, Gauteng. 4.Malmesbury fishmeal agro- processing, Malmesbury, Western Cape. 5.HIK abalone (Pty) Ltd- abalone farm expansion, Hermanus, Western Cape. 6.Marine Growers (Pty) Ltd- abalone farm expansion, Gansbaai, Western Cape. 7.Roman Bay Sea Farms (Pty) Ltd- abalone farm expansion, Gansbaai, Western Cape. 8.Davidson Fisheries (Pty) Ltd- tilapia farm, Tierpoort, Gauteng. Technical support and advisory services were provided to 4 farms/aquaculture operations: 1.Macena Fish Farming- Crops and fish farming, Muyexe, Limpopo. 2.Tompi Seleka College- Research farm, Tompi Seleka, Limpopo. 3.Supreme Catfish- Catfish farm, Ventersdorp, North West. 4.Red Ants Farm, Tilapia farm, Eikenhof, Johannesburg. Gauteng site visits were conducted on the farms and technical assessment reports were provided with recommendations. | 3 fish farms | Due to ADEP awareness programmes put in place and the workshops conducted with the dti, increased demand for developing/ supporting farms both financially and technically through assessment of business plans and site visits by Provincial Departments and individuals. | Green |

### Sub-programme: Monitoring, Control and Surveillance

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Fisheries Protection Vessels | 2 | 1 | Enforcement and compliance measures to combat poaching improved. | 155 sea-based inspections of vessels conducted in 4 priority fisheries. | Sea-based inspections of vessels conducted in 4 priority sectors: 146 Inshore Patrol Vessels: Hake: 21 Abalone: 0 West Coast Rock Lobster: 27 Traditional line fish: 39 Small crafts: Abalone: 7 Traditional line fish: 52 | Under achievement of 9 sea-based inspections for Q2. | Vessels undergoing repairs with the inshore patrol vessels, Ruth First and Victoria Mxenge sea readiness expected in August 2013. Abalone season extended to 31 October 2013, limited commercial abalone activities. West Coast Rock Lobster season closed from 1 June 2013 to 15 November 2013. Inshore patrol vessels Ruth First and Victoria Mxenge sea ready and sailed in August 2013. The lillian Ngoyi and Sarah Baartman still under repairs. | Red |
| Monitoring and Surveillance | 2 | 1 | Enforcement and compliance measures to combat poaching improved. | 71 investigations conducted on rights holders in 4 key fisheries sectors. | A total of 77 rights holders investigated in 4 priority sectors. Hake: 14 Abalone: 4 Traditional line fish: 29 West Coast Rock Lobster: 30 | An over- achievement of 6 rights holders investigated. |  | Red |
| Compliance | 2 | 1 | Enforcement and compliance measures to combat poaching improved. | Conduct 168 inspections on vessel landings in 4 key fisheries sectors. | Total number of vessels inspected in 4 priority sectors: 537 Hake: 147 Abalone: 58 Traditional line fish: 119 West Coast Rock Lobster: 213 | An over-achievement of 369 vessel inspections for Q2. |  | Red |

### Sub-programme: Marine Resources Management

| Directorate | SG | SO | Performance Indicator | Quarter 2 Planned Target | Quarter 2 Actual Achievement | Deviation from planned target to Actual Achievement | Comment on deviations | Status Robot |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inshore Fisheries Management | 5 | 1 | Increased support to SMMEs within the sector. | Establish the rights allocation process in the inshore and high seas fisheries sectors. | General policy; 5 sector policies published; application forms published and printed with schedules and explanatory notes. |  |  | Green |
| Offshore Fisheries Management | 2 | 1 | Depleted fish stocks rebuilt (hake). | Update the capacity management models. | Capacity management models updated in the hake deep sea, hake inshore and hake long line sectors. |  |  | Green |
|  | 5 | 1 | Increased support to SMMEs within the sector. | Establish the rights allocation process in the inshore and high seas fisheries sectors. | General policy and 3 sector specific policies published. |  |  | Green |

### Additional indicators at sub-programme level

| Strategic Goal | Strategic Objective | Performance Indicator | Actual Performance against Target | Reason for Variance |
| --- | --- | --- | --- | --- |
|  |  |  | Annual Target | Actual against Target |  |
| Sustained management of natural resources | Ensure the sustainable management and efficient use of natural resources. | Enforcement and compliance efforts to combat poaching increased. | Facilitate approval and implementation of the Integrated Fisheries Security Strategy (IFSS) | The IFSS document has been reverted back to the sub-directorate for further inputs and updates. A process has been initiated to appoint a service provider to manage the document. |  |

### SUMMARY OF PERFORMANCE AGAINST QUARTERLY TARGETS

| Sub-programmes | Planned | Completed | No supporting documents | % completed for Q2 |
| --- | --- | --- | --- | --- |
| CD:AC | 1 | 1 | 0 | 100 |
| CD:MCS | 3 | 0 | 3 | 0 |
| CD:MRM | 3 | 3 | 0 | 100 |
| Total: | 7 | 4 | 3 | 57 |

# CONCLUSION

The approved Monitoring, Evaluation and Reporting (MER) guidelines are currently being revised for the next financial year. One of the critical areas that necessitated the review is the reporting deadlines. Currently, the due date for reporting is the 20th of the month,  and this makes it difficult to comply with Treasury regulations of having quarterly reports being prepared within 30 days from the end of the quarter. This matter has already been raised by the Auditor-General as a finding during the auditing of the 2012/13 Annual Report. The proposed date for review is the 10th   of the month. This may also only be an academic change unless monthly reporting as required is taken serious and complied with. Currently, reporting takes place mostly at the end of the Quarter and this denies the Department the opportunity of being provided with regular and timely advice, in particular where corrective interventions may be needed. Provision of reasons for variance and related evidence still poses a huge challenge. It needs to be emphasized that both the reasons for variance and relevant evidence is applicable in cases of under- and over-achievement of the planned targets.

APPROVED Q2 OF 2013/14 NON-FINANCIAL PERFORMANCE REPORT OF DAFF

________________________								______________

PROF E. V. VRIES										DATE

DIRECTOR-GENERAL: AGRICULTURE, FORESTRY AND FISHERIES