Annexure A

DEPARTMENTAL PERFORMANCE REPORT

JANUARY – MARCH 2014

(BUDGET STRUCTURE)

Department: Human Settlements

Chief Directorate: Enterprise Architecture

National Department of Human Settlements

P/Bag X644, Pretoria, 0001

240 Justice Mahomed Street, Sunnyside, Pretoria

TABLE OF CONTENTS

1. OVERVIEW BY THE ACCOUNTING OFFICER							3

2. COORDINATION, COOPERATION AND OUTSOURCING					7

2.1 Status of Interdepartmental Linkages								10

2.2 Status of Local Government Linkages								11

2.3 Status of Public Private Partnerships and Outsourcing						11

3. MANAGEMENT AND USE OF RESOURCES							14

3.1 Human Resources Management									14

3.1.1 Specific Challenges and Responses

3.1.2 Progress with the Filing of Critical Positions							 14

3.1.3 Summary of disciplines procedures							 	 15

3.1.4 Specific Details on the 10 oldest Unresolved Disciplines Cases that may result in

Dismissal											  	 15

3.2 Financial Management								 	 	 15

4 Departmental Performance Assessment Templates, January to March        2014	 	  20

1. OVERVIEW BY THE ACCOUNTING OFFICER

The end of 2013/14 financial year is marked with major developments and achievements as per organisational mandate and the Constitution of the Republic of South Africa which provides for creation of sustainable human settlements and improved conditions of living. The Department has during the period under review, made tremendous progress as noted below following the implementation of the Turn Around strategy as of April 2012.

Key Policy Developments

During the period under review, the following policy developments were recorded:

The Rental Housing Amendment Bill, 2013 was adopted by the National Assembly and sent to the National Council of Provinces for concurrence. The National Council of Provinces (NCOP): Select Committee on Public Services was briefed about the Rental Housing Amendment Bill and it was successfully passed. Public hearings were also held in all the Provinces.

The Housing Development Agency Regulations developed in terms of the Housing Development Agency Act, 2008 were finalised, tabled, deliberated and adopted by the Portfolio Committee on Human Settlements and in the process of being published in the Government Gazette.

The revised Employment Equity (EE) Plan was consulted at the Departmental Bargaining Council (DBC) on the 12th February 2014 and the Director – General’s approval of the EE Plan was supported.

Two Provincial and Municipal Human Settlement policy workshops were held in the Eastern Cape Province, Nyndeni Local Municipality and Limpopo Province, Lephalale  Municipality.

The training workshop on Community Residential Units was held for the Western Cape Provincial and Municipal officials.

The draft Green Paper on Human Settlements was awaiting finalisation of the signing of Memorandum of Understanding between the Department of Human Settlements and the Department of Science and Technology.

The fourth quarter report on Contract Management Services has noted that the Department has also during the period under review concluded the Implementation Agency Agreements with the Department of Water Affairs, all the Provinces, Water Boards and Human Settlements Entities for the eradication of the bucket system and improved water and sanitation services.

Internal Audit, Risk Management and Special Investigations Unit (SIU)

The Quarter three Status report on the implementation of the Internal Audit Annual Project plan for 2013/14 financial year was presented at the Executive Management Team (EMT) on the 31st March 2014 and Audit Committee on 25 February 2014.

The Quarter three Status Report on the implementation of the approved Risk Management Strategy was presented to the Audit Committee on 25 February 2014 and the Executive Management Team (EMT) on the 31st March 2014. This report was not yet presented to the Executive Management Team (EMT) and Risk Management Committee (RMC) due to postponement of the EMT and RMC meetings.

The draft Anti-fraud and Corruption, Fraud Prevention Plan and Whistle Blowing Policy were presented to the EMT and Audit Committee on 25 February 2014. The drafting of the Anti-fraud and Corruption Strategy was postponed to the first quarter of the next financial year.

Human Resources Management

The Department has during the period under review, assisted Members of the Senior Management Service (SMS) to disclose their financial interests electronically. About forty interns and Contract and temporary workers were appointed.

The development in area of human resources management entails the submission of the fourth Quarterly report on Training and Development interventions and the third Quarter Expenditure report to the Public Service Sector Education and Training Authority (PSETA).

The approved Departmental Employment Equity report was submitted to the Department of Labour on time.

Accreditation

The report on six Metro Municipalities assessed for the readiness to receive level 3 accreditation was prepared by the Capacity and Compliance Accreditation Panel (CCAP) and submitted.

Financial Management

The approved Interim Financial Statement was submitted to the Auditor General and the National Treasury.  The reports on contracts exceeding R100 000 were also submitted to the National Treasury during the period under review.

Performance Management

It was noted in the Enterprise Operations Performance Assessment Framework (EOPAF) quarterly report that six Performance Agreements were received and all were verified and submitted to the Human Resources Management Unit for further processing.

The moderation process for SMS members for 2012/13 cycle was finalised and the outcome executed.

To date the performance of the Department cannot be validated against the performance of programme managers due to delay in submission of completed performance assessment reports for 2013/14 mid-term and 2012/13 financial year by qualifying Programme Managers.

During the period under review, the Department has produced the Third Quarter Human Settlements Entities report.

Records Management

During the period under review, 165 new and 133 temporary files were opened. About 824.25ml of records were stored in the internal records repository brining the repository to 100.5% full capacity. At the moment there is only 820 linear meters of records space is remaining. It was recorded that 108.55lm of ephemeral and transitory records worth 2713.75kg were destroyed under approved NARS General Disposal Authority, AT2, AR2 and AU1.

Sector Empowerment and Capacity Building

In an effort to accelerate transformation across the sector, the Department has during the period under review embarked on various activities such as;

The Govan Mbeki Awards workshop which was held on the 29th January 2014 at Saint Georges Hotel in order to discuss the Govan Mbeki Awards (GMA) reviewed framework and to also plan for the 2014 Provincial and National Awards. Meanwhile the 2012 and 2013 Govan Mbeki Awards prize money was being processed and will be paid in full by the end of financial year.

Three Consumer Education workshops were held, that is, two in Provinces (North West and Limpopo) and one national and overall, 132 Officials were trained.

Four beneficiary training sessions were conducted in two Provinces, that is, North West, Ramotshere-Moiloa Local Municipality on 28 February 2014 and the KwaZulu-Natal, Umhlathuze Local Municipality on 11 – 13 March 2014 and 1079 beneficiaries were trained.

Thirty Councilors were trained in the Councilor training session which was held in the Limpopo Province, Lephalale Local Municipality.

Research, Monitoring and Evaluation

The final draft of the revised Monitoring, Evaluation and Impact Assessment Framework for Human Settlements was submitted for approval to publish.

The department was able to produce the Quarterly report on performance of Human Settlements Programmes.

Furthermore through the Monitoring and Evaluation Unit the Quarterly report on performance of Outcome 8 outputs was produced and the final draft report on Human Settlements Index was submitted for approval.

During the period under review, the Department has produced two research reports, that is, ‘Asbestos Use in South Africa: Related Health Risks and Policies for Risk Management’ and ‘Towards the Development of the Empowerment Strategy for the Designated Groups in the Human Settlements Sector: Legislative, Policy and Document Review’.

The report on, ‘Environmental scanning: Developments in the economy and their impact on Housing Development’ was also submitted.

Management of Human Settlements Priority Projects

The report on slow moving projects has indicated that the number of slow moving projects across nine Provinces is currently sitting at 2 280, from a total number of 2 365 which was reported during the third quarter. The North West Province has moved from 118 back to 115 as in the second quarter, Gauteng from 869 to 898, Free State from 291 to 294, Western Cape 292 to 305, Eastern Cape from138 to 139, Limpopo from 93 to 92, Northern Cape remained at 77, Kwa-Zulu Natal from 264 to 269 and Mpumalanga from 223 to 91, huge difference between quarter three and four. The status of these projects including the prioritisation process is pending confirmation by the Provincial departments.

The Department has also produced the detailed report on Identified Strategic Projects for the period under review and below are projects assessments as at the performance reporting period:

- The status for the Lufhereng Project has not changed since the previous quarter. This project has not performed well during the financial year under review due to challenges relating to land availability and procurement processes. The remaining funds have been transferred to the performing projects.  However the implementation of the Lufhereng Development by the turnkey contractor and CoJ will result into job creation as well.

- Cornubia Project: About 154 beneficiaries were relocated by end of December 2013.

- Lephalale Project: There has been a delay in the supply of electrical material following the commissioning date of all the substations which was on the 28th  February 2015. Heavy rains have also negatively impacted on the progress of the project.

- The completion date for Khutsong Project has been moved further to April /May 2014. Appointed back up contractors have no contract documents.

- Duncan Village Redevelopment Initiative: Implementation has not yet started. There was no funding received by the Buffalo City Municipality from the Province and bulk infrastructural issues are yet to be resolved. Not much was achieved since the previous quarter.

- The Sweetwaters Project still has not been performing as expected. The ring-fenced funds were since transferred to other projects. The challenges of insufficient capacity of the bulk sewer and water treatment infrastructure and are being addressed. Title deeds for land portions P32 and P35 were in place.

- Diepsloot Project: The construction of the pedestrian bridges is on track as per 2013/14 business plan and it was anticipated that the construction will be finished by the 31st December 2013. The Diepsloot North property was purchased and has an approved township. The construction of almost 600 rental units on the site will commence on 2015/16.

- The Drommedaries Project – 1407 which was on track with the delivery of quality houses amidst social dynamics has been delayed by heavy rains. The completion date was therefore extended to the 16th May 2014.

- The Zanemvula Project is in progress and the problem of nonpayment of management fees was being addressed.

- The progress in the N2 Gateway Project is still slow due to beneficiaries’ concerns regarding the type of products offered by the project. This has also led to the stalling of Boys Town and the Joe Slovo.

- Lerato Park Project: About 491 houses were completed and awaiting handover by the Deputy Minister.

- Klarinet Project: Following termination of the ABSA contract by the Province, there has been steady progress in the implementation and development of Phase 2 mainly that the project does not receive ring-fenced funding.

2. COORDINATION, COOPERATION AND OUTSOURCING

# Below is information on Interdepartmental and Local Government linkages and Public Private Partnerships and Outsourcing as noted by the Corporate Services Programme and the Programme and Project Management Unit

# 2.1. Programme 1: Administration (Corporate Services)

# 2.1.1.	Status of Interdepartmental Linkages

| PARTNER | CHALLENGE | PLANNED MEASURE PUT IN PLACE |
| --- | --- | --- |
| State Security Agency (SSA) | Turnaround time in providing feedback for full vetting applications | Engagements with SSA to accelerate vetting processes for timeous response to submitted vetting applications |
|  | SSA withdrawal of infrastructure facilities to secure transmission of sensitive documents | Engagements with SSA to accelerate provision of infrastructure |
| DPW | Delays in response to queries on office accommodation and payments | Engagements for timeous response |
| SITA | Delays in furnishing required specifications for IT installations at 260 Justice Mahommed Street | Engagements with to furnish response |
| DPSA | General Human Resources Lack of communication | Continuous engagement on timeous response Constant communication and follow-ups. |
| Public Service Commission | Referral of all issues of disputes | Continuous engagement on timeous response. |
| Office of the State Attorney Office of the Chief State Law Advisor | Co-ordination of litigation matters across all spheres of Government Certification of Legal opinion | Hold regular meetings and consultations with Office of State Attorney |
| Provincial Human Settlement Departments | Usage of available HSS functionality; Quality, completeness and availability of source documents to HSS Data Captures for capturing on HSS Quality, accuracy and completeness of data captured on HSS influence reporting Reporting from other sources – Excel Spreadsheet | Established and conducting : HSS Steering Committee and HSS User Group Task Team meetings Formal Training Schedule to improve the knowledge and understanding of HSS Data Capturers and relevant role players |
| Provincial Human Settlements Departments through the Communicators Forum | Co-ordination between the National Department and Provinces around issues of communication has improved over time, but has not yet reached a level of perfection. | Regular interaction and following up on resolutions and decisions of the Forum will help close this gap. |
| Government Communication and Information System (GCIS) | Relations with GCIS and their responsiveness to our needs have improved. | Regular meetings and interaction has helped in this regard. |

# 2.1.2.	Status of Local Government Linkages

| PARTNER | CHALLENGE | PLANNED MEASURE PUT IN PLACE |
| --- | --- | --- |
| Relevant Local Authorities | To ensure support and training in the use of HSS Online and National Housing Needs Register | Promoting the usage of HSS Online and the National Housing Needs Register to municipalities through training sessions |
| Accreditation of municipalities and metro’s | To ensure support and training in the use of HSS, HSS Online and the National Housing Need Register Resources to provide support and training to municipalities and metro’s that was accredited | Promoting the usage of HSS, HSS Online and the National Housing Needs Register to municipalities and metro’s through training sessions |

# 2.1.3.	Status of Public Private Partnerships and Outsourcing

| PARTNER | CHALLENGE | PLANNED MEASURE PUT IN PLACE |
| --- | --- | --- |
| Skynet | Late submission and inaccurate billing of invoices | Engagements with Skynet for compliance with RT5 and SLA conditions |
| SITA | Level of services provided by SITA in relations to the signed Service Level Agreement between NDHS & SITA | Bi Monthly meeting with different SITA business units Monthly reports to SITA & NDHS management and identified role players Internal escalation of issues that cannot be resolved |
| State Information and Technology Agency (SITA) | Happy with the service SITA provides around the maintenance of the Department’s website. | Regular interaction on our needs helps address all identified challenges. |

2.2. Programme Delivery Support

| PARTNER | CHALLENGE | PLANNED MEASURE PUT IN PLACE |
| --- | --- | --- |
| Sector Departments, eg. Health Education, Energy, etc. | Sector departments do not make provision for the amenities that they are responsible for as they have their own priorities. In addition, there is no alignment of deliverables and funding allocation by the different departments to human settlements deliverables. | Continuous interventions are made to ensure that sector departments prioritise their involvement in the projects. Provincial departments are requested to coordinate meetings with provincial sector departments to ensure that those departments are informed about the national priority and strategic human settlement projects and the need to provide the requisite amenities. |
| Provincial Departments and Municipalities | The lack of, and or insufficient bulk infrastructure provision in the projects | Approval of the Terms of Reference for technical Assistance by MISA to undertake an in depth study of the infrastructure challenges in indentified areas. Further, Inter-Governmental Relations meetings with the stakeholders e.g. Eskom, Water Entities and the Department of Water Affairs to be convened to facilitate the alignment of project plans and funding requirements for implementation. In a parallel process the DPME have now engaged the DBSA to undertake technical studies and manage certain processes to assist with addressing the issues relation to the lack of bulk infrastructure in the mining towns |
|  | Inability to spend ring-fenced funding due to slow procurement processes and bulk infrastructure challenges | Re-allocation of funds from non performing projects to projects that are delivering are effected to ensure expenditure on ring fenced funding. Continuous monitoring of financial and non-financial deliverables. |
| Provincial Human Settlements Departments | Available updated information | Continuous meetings (One-on-one and through task team) to align information and reporting formats |
| COGTA | Available updated information | Continuous meetings to align information and reporting formats |
| DPME | Available updated information | Continuous meetings to align information and reporting formats |
| Department of Energy | Available updated information | Continuous meetings to align information and reporting formats |
| PSC | Available updated information | Continuous meetings to align information and reporting formats |
| National Treasury | Strict time frames | Continuous interaction to ensure fast tracking of reporting |
| DWA | Available updated information | Continuous meetings to align information and reporting formats |
| Dept of Environmental Affairs | Available updated information | Continuous meetings to align information and reporting formats |
| HDA, NHBRC, RHL, NURCHA, SHRA, NHFC | Available updated information | Continuous meetings to align information and reporting formats |

# 3.	MANAGEMENT AND USE OF RESOURCES

This section outlines the management of human and financial resources for the period under review:

# 3.1.	Human Resources Management

# 3.1.1.	Specific Challenges and Responses

| Challenge Identified | Management Response / Actions the Accounting Officer And Management Have Taken In Response |
| --- | --- |
| None | None |

# 3.1.2.	Progress with the Filling of Critical Positions

| Position | No of Posts | No of Vacancies At Start of Quarter | Length of Time Is Vacant (Where Appropriate) | No of Appointments Made During Quarter |
| --- | --- | --- | --- | --- |
| SMS | 99 | 22 | This differs in terms of when the vacancy commenced | 1 |

# Summary of disciplinary procedures

| Category of Case | No of Cases At Start of Quarter | Total Monthly Personnel Expenditure on these Officials at the Start of Quarter | No of New Cases Opened During Quarter | No of Cases Resolved During Quarter | No of Unresolved Cases Older Than 3 Months |
| --- | --- | --- | --- | --- | --- |
| Cases involving officials with salary packages >R100 000 that may result in dismissal | 3 | 166463.49 | 0 | 1 | 2 |
| Cases involving officials with salary packages <R100 000 that may result in dismissal | 1 | 7433.89 | 0 | 1 | 0 |

# 3.1.4	Specific Details on the 10 Oldest Unresolved Disciplinary Cases that may result in Dismissal

| Case Number | Date Proceedings Started | Salary Paid to Official Since Start of Proceedings | Specific Actions Being Taken to Resolve the Case |
| --- | --- | --- | --- |
| - | - | - | - |

There are no old cases.

# 3.2. Financial Management

## 3.2.1. Specific challenges and responses

| Challenge identified | Management Response/action the Accounting Officer and management have taken in response |
| --- | --- |
| Lack of adequate capacity. | Lack of adequate capacity is resulting in non-performance of crucial duties, delays in accessing and processing of payments, non-compliance to legislation, errors in processing, low staff morale due to extra work and the inadequate segregation of duties. The work-study has been concluded and approval is awaited from the Director-General on the recommendations of the work-study. Approval was obtained from the DG. However, not all the newly created posts were funded. SCM only obtained funding for the Deputy Director, Assistant Director Asset Management and Senior Supply Chain Practitioner posts. The DD and ASD Asset Management positions are filled. The two incumbents will assume duty on 01 April 2014. The Senior Supply Chain Practitioner will be advertised. The delay in advertising this post was caused by the misunderstandings between SCM and HR on the level at which this position should be advertised ( HR directed that it be advertised at level 7 while SCM needs a level 8 position).SCM has no option but the advertise the post at level 7. |
| No adequate capacity for the Urban Settlement Development Grant | No staff provision was made for the new introduced Urban Settlement Development Grant. The work-study has been concluded and approval is awaited from the Director-General on the recommendations of the work-study. |
| Delay in phasing out of the Debtors System. | Lack of co-operation by provinces to compile plans for the phasing out of the Debtors System. Templates were compiled by NDoHS and presented to provinces. Letters that are addressed to the HOD’s and CFO’s of Western Cape, KwaZulu-Natal and Gauteng have been sent to the relevant Provinces. This matter has to be raised at the next CFO-forum. It is anticipated that the amendment of the Housing Act will speed up the data clean-up process. |
| Transfer of assets to Department of Defense and Military Veterans | Lack of co-operation by the Department of Defense and Military Veterans on the finalization of the formal transfer of assets that were taken to the said department when they were transferred is a serious challenge. It is difficult to remove the assets from the Asset Register as the Transfer Certificate is not signed by the Accounting Officer of the receiving department. Several communiqués requesting the dept. of Defense to finalize the transfer had been unsuccessful. It is proposed that the assets be removed from the asset register.A letter was sent to the National Treasury requesting guidance on this matter to no avail. These assets will be removed from the asset register immediately after 31 March 2014. |
| Assets in 260 Walker Street were moved to the parking area in December 2011 to facilitate the refurbishment of the building. The refurbishment process has to date not started. Prolonged exposure of the assets to dust will cause damage. Furthermore, the assets are further exposed to the risk of theft. | A follow-up was done with Facilities Management on the refurbishment of the building and the ultimate move to 260 Walker Street. It was established that a misunderstanding occurred on the nature of the agreement between the Department and the Department of Public Works. However recent development indicated that these matters have been addressed and work is to be undertaken and projected to be completed with 6 months. The Basement Parking in 260 Justice Mohamed Street flooded during the last heavy rains resulting in the office furniture stored in that area was moved to the Ground Parking. These office furniture could not be adequately accommodated in the Basement Parking and therefore, a submission was made to the Director- General to approve the disposal of the excess office furniture ( as the option of off – site storage appeared to be expensive. Ie. Quotations received for a 3 month period are: R 155 268- Elliot; R 167 580 – Joel Transport and R 280 000 – Mmaserufe Trading). The DG approved the disposal request. These affected assets will be disposed immediately after 31 March 2014. |
| Reluctance by financial institutions to fully comply with the HLAMDA Act. | The Office is engaging with auditors of financial institutions to determine the audit standards and norms to be disclosed to the Office in terms of Act (HLAMDA) |
| Slow progress on the finalization of the Mortgage Default Insurance (MDI) | Engagements were held with different stakeholders to identify blockages in regards to the institutional arrangements and Capitalisation of the MDIC and propose appropriate solutions. The stakeholders have agreed to come up with a policy framework that will define the scope of the MDI going forward. |
| Slow progress on the implementation of FLISP by provinces | Oversight visits were conducted in order to establish the challenges with implementing the subsidy. |
| High level of indebtedness and poor credit record of potential FLISP applicants | Engagement with NCR and other Stakeholders to intensify beneficiary, borrower education and awareness on financial literacy |
| Fixed interest rate | The current macroeconomic environment with a low interest rate is not viable for a fixed interest rate. |

## 3.2.2. Summary of Fraud, Theft and Corruption Cases

None

## 3.2.3. Summary of Receipts and Payments

### Summary of Receipts

|  | Audited 2012/13 R’000 | Un audited April to June 2013 R’000 | Un audited July to September 2013 R’000 | Un audited October to December 2013 R’000 | Un audited January to March 2014 R’000 | Total receipts for 2013/14 R`000 |
| --- | --- | --- | --- | --- | --- | --- |
| Sales of goods and services produced by the department | 167 | 35 | 60 | 31 | 63 | 189 |
| Sales of scrap, waste, arms and other used current goods (excl capital assets) | 3 | 1 | 1 | 0 | 1 | 3 |
| Interest, dividends and rent on land | 90 | 7 | 11 | 18 | 22 | 58 |
| Sales of capital assets | 0 | 0 | 0 | 0 |  |  |
| Financial transaction in assets and liabilities | 779 | 170 | 5 992 | 48 | 89 | 6 299 |
| Total | 1 039 | 213 | 6 064 | 97 | 46 | 6 420 |

### Summary of payments

| Category of Payments | >60 days overdue | >90 days overdue | >120 days overdue |
| --- | --- | --- | --- |
| Suppliers | R839 945.91 | R1 083 254.54 | R158 305.10 |
| Professional services | - | - | - |
| Total | R839 945.91 | R1 083 254.54 | R158 305.10 |

## 3.2.4. Summary of major capital acquisitions and disposals (Preliminary figures)

### Capital acquisitions

| Capital Acquisitions |
| --- |
| Item | Value | Transfer Date | Seller/Supplier |
| Buildings and fix structure | 72 987 691 | Various | Various |
| Machinery and Equipment | 601 495 | Various | Various |
| Software & Intangible assets | 116 280 | Various | Various |

### Assets Disposals

No Assets were disposed during this quarter.

## Update on Major contracts approved during the period

| Contract number | Name of Contractor | Service | Date | Value R |
| --- | --- | --- | --- | --- |
| VA 50/179 DH-021339 | Madlanga & Partners Inc | Conduct Regulatory Impact Assessment on the Home Loan and Mortgage Disclosure Amendment Bill | 15 January 2014 | 500 000.00 |
| VA 50/172 DH- 021394 | Trevor Bailey Attorneys | Conduct Regulatory Impact Assessment on the Rental Housing Amendment Bill | 04 February 2014 | 304 578.00 |
| VA 50/163 DH- 021398 | Procurement Dynamics | Development of a new empower strategy for designated groups in Human Settlements | 04 February 2014 | 476 904.99 |
| DH-021316 | Letsohlo Communications | Audio Visual: procurement, repair/ replaced and maintenance of the Video Conference equipment | 9 January 2014 | 386 350.00 |
| DH-021337 | Palama | Training: [Executive] Accelerated Development Programme | 17 January 2014 | 318 510.00 |
| DH-021353 | US Pects Trading Enterprise | Wall Hanging Calendar, Desk Calendar and Wire bound freestanding A frame – 2000 each – Total 6000 | 24 January 2014 | 351 999.60 |
| DH-021357 | SITA CC | HSS Operational System and Assist Provinces | 27 January 2014 | 540 000.00 |
| DH-0211383 | Ubuntu Technologie | Dell PowerEgde R720 Server, Backup Server, software and Tape Library | 31 January 2014 | 771 151.86 |
| DH-021386 | Elda Security Services | Security Services for 260 JM Street building from 1/2/2014 – 31/7/2014 | 31 January 2014 | 340 500.00 |
| DH-021398 [VA50/163] | Procument Dynamics | Develop a new empowerment strategy for designated groups in Human Settlements | 04 February 2014 | 476 904.99 |
| DH-021411 [VA50/157] Refer to DH-020742 | NDB Consulting | Review SCM: Evaluation, Development of policies and procedures, Support and Related Assistance | 04 February 2014 | 67 500.00 (Variation order) |
| DH-021420 [VA49/381] | Alison Wilson Social Housing Cons | Develop a policy as well as Housing Co-operative programme and Legislative framework to integrate, align and develop a Housing Co-operative Policy | 11 February 2014 | 540 360.00 |
| DH-021449 | Esizwe Technology | Audio Visual Equipment for Minister’s Office in Cape Town. | 17 January 2014 | 458 738.00 |
| DH-021453 | Lekgotla Africa Events | Printing of Stickers: DHS Logo with 20 years – 1000; Pens with 20 years logo – 5000 and note books with 20 years logo – 5000. | 17 January 2014 | 181 345.50 |
| DH-021461 | Dogan Exhibitions & Events (Pty) Ltd | Exhibition Space for DHS at the Rand Show 2014 – 18 April 2014 – 28 April 2014 @ Nasrec - Johannesburg | 20 January 2014 | 114 000.00 |
| DH-021510 | ESRI South Africa | Licence for Software to spatial analysis and to produce Human Settlements spatial reports & maps - GIS | 04 March 2014 | 116 280.00 |
| DH-021518 | Vapaza Printers | Printing Booklets: A4 the design and print – English 120 000 booklets | 06 March 2014 | 417 600.00 |
| DH-021521 | MS Exclusive Shuttle and Tours | Hire of Venue: International Woman’s Day – Khayelitsh – 8 March 2014 – Handover of houses in Khayelitsha | 06 March 2014 | 280 900.00 |
| DH-021532 | Masibilu Trading Projects | Printing and Publication: A5 Landscape booklets Text 44pp Print full colour throughout on 200 gsm Neo Act Gloss – 5000 Quantity | 10 March 2014 | 343 416.00 |
| DH-021547 [VA50/160] | SANCIKMKE | Advisory Services | 13 March 2014 | 249 000.00 |
| DH-021552 | Extribyte | Investigation: on SMS members in DHS and to assist with Disciplinary Hearings [Deviation] | 18 March 2014 | 256 000.00 |
| DH-021553 | Letsotzo Communication | Audio Visual Equipment | 18 March 2014 | 386 350.00 |
| DH-021555 | SITA | Mainframe Systems: on Transversal Systems of SITA – LOGIS Mainframe | 19 March 2014 | 109 408.74 |
| DH-021558 | SITA | Mainframe Systems: on Transversal Systems of SITA – Debtors Mainframe | 19 March 2014 | 340 000.01 |
| DH-021559 | SITA | Mainframe Systems: on Transversal Systems of SITA – BAS Mainframe | 19 March 2014 | 372 488.48 |
| DH-021560 | SITA | Transversal Systems of SITA –PERSAL Mainframe Systems | 19 March 2014 | 122 235.43 |
| DH-021565 [VA49/380] | Human Communications | HR Adverts: Advert and Recruitment till 31 March 2014. | 19 March 2014 | 150 000.00 |
| DH -021566 | Masibulu Trading & Projects | Printing Sanitation flyers, posters and pamphlets | 19 March 2014 | 169 500.00 |
| VA 49/420 | Project Preparation Trust | Participatory Based Planning support to the Umhlathuze Municipality | 03 March 2014 | 3 131 249.00 |
| VA 49/421 | Bigen SA | Participatory Based Planning support to the Madibeng Municipality | 03 March 2014 | 2 569 538.00 |
| VA 49/439 | Shisaka Development Services (Pty) Ltd | Upgrading Training Course Roll -Out | 03 March 2014 | 2 387 641.08 |
| TOTAL |  |  |  | 17 230 449.68 |

M D MOERANE:

CHIEF DIRECTOR:  ENTERPRISE ARCHITECTURE

DATE:

S NGXONGO:

CHIEF OPERATIONS OFFICER

NATIONAL DEAPRTMENT OF HUMAN SETTLEMENTS

DATE:

T ZULU:

DIRECTOR-GENERAL

NATIONAL DEPARTMENT OF HUMAN SETTLEMENTS

DATE:

4. DEPARTMENTAL PERFORMANCE ASSESSMENT TEMPLATE, JANUARY TO MARCH 2014

PERFORMANCE CRITERIA

Certainty that the target will not be achieved or was not achieved in the planned timeframes – major remedial action and urgent intervention is required

Moderate risk that some problems exist and as a result the target will not be achieved in the planned timeframes – remedial action is needed to avoid this

On course – no major action needed

PROGRAMME 1:  ADMINISTRATION: OFFICE OF THE DIRECTOR – GENERAL

SUB-PROGRAMME: EXECUTIVE SUPPORT

| Strategic Objective: To provide executive support to the Office of the Director-General on parliamentary, cabinet liaison, Secretariat Support and management of intra departmental structures |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of reports on Administrative and Logistical support developed | 4 reports on administrative and logistical support developed | 1 Report on administrative and logistical support developed | Report on admin and logistical support developed and submitted | N/A | N/A |  | Report |
|  | 4 FOSAD reports submitted | 1 FOSAD report submitted | Report on FOSAD support submitted | N/A | N/A | N/A | Report |
| Number of reports on parliamentary and cabinet liaison | 4 Report on Parliamentary and Cabinet Liaison submitted | 1 Report on parliamentary and cabinet liaison submitted | Report on Parliamentary liaison submitted | N/A | N/A | N/A | Report |
|  | 4 Reports on stakeholders liaison and engagements submitted | 1 Reports on stakeholders liaison and engagements submitted | Report on stakeholder liaison engagement submitted | N/A | N/A | N/A | Report |
| Number of reports on recording of proceedings | 4 reports on recording of proceedings | 1 report on recording of proceedings | Report on record of proceeding produced | N/A | N/A | N/A | Report |

SUB PROGRAMME:  INTERNAL AUDIT, RISK MANAGEMENT AND SPECIAL INVESTIGATIONS

| Strategic Objective: To provide integrated assurance and advice on governance practices to assist the department achieve its objectives |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Reviewed, approved and implemented annual Internal Audit Project Plan | Reviewed, approved Internal Audit Annual Project Plan for 2013/.14 implemented | Q3 status report on the implementation of the Internal Audit Annual project plan tabled at EMT and AC External Quality Assurance Report on the internal audit compliance to the standards | Status report on the implementation the internal audit operational plan presented at EMTon 31 March 2014 and ACon 25 February 2014 External SOR QAR report on the internal audit compliance to the standards has been finalised. | None | None | None | Status report on the implementation of the internal audit operational plan Submission, Minutes and agenda of EMT and AC meeting External QAR Report submitted for presentation Annexure A |
| Reviewed, approved and implemented risk management strategy for 2013/14. | Reviewed, approved and implemented risk management strategy for 2013/14. | Q3 status report on the implementation of the approved risk management strategy 2013/14 tabled at EMT, RMC and AC. | Q3 Status report on the implementation of the approved risk management strategy has been presented to AC on 25 February 2014 and subsequently to EMT 31 March 2014 | The Q3 status report has not yet been presented to EMT and RMC | The EMT and RMC meetings have been postponed. | Q3 report will be tabled at the coming EMT and RMC meeting. | Q3 status report to the audit committee RMC presentation to EMT 31 March 2014. Annexure B |
| Approved and implemented anti-fraud and corruption strategy | Approved and implemented anti-fraud and corruption strategy | Q3 status report on the Implementation of the approved Anti-fraud and corruption Strategy tabled at RMC, EMT and AC. | The draft Anti-fraud and corruption, Fraud Prevention Plan and Whistle Blowing policies were presented to EMT and AC on the 25 February 2014. | The anti-fraud and corruption strategy not yet developed | AC & RMC recommended that the draft Fraud & Corruption Prevention Policy; Fraud Prevention Plan and Whistle Blowing Policy be approved EMT recommended that the draft policies be tabled at MINTOP and Bargaining Council before approval by the Director-General | The drafting of the anti-fraud and corruption strategy will commence in quarter 1of 2014/15 financial year | Report to the AC for the meeting of 25 February 2014 Draft Fraud & Corruption Prevention Policy Draft Fraud Prevention Plan Draft Whistle Blowing Policy Annexure C |

# SUB PROGRAMME: ADVISORY SERVICES

| Strategic Objective: Provide advisory services to the Department and Portfolio Committee on matters relating to project quality assurance and integration |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of reports on the implementation of the national project integration plan | Two reports on the implementation of the national project integration plan | One report on the implementation of the national project integration plan | Groundwork report on project integration developed | One advisory report on project integration not yet developed | Preliminary work towards project integration was carried out and a report compiled | The unit now has a full staff complement and will therefore be able to complete its targets in the next financial year | Report Attached ANNEXURE T |
| Number of reports on the implementation of the national quality assurance plan | Two reports on the implementation of the national quality assurance plan | One report on the implementation of the national quality assurance plan | Groundwork report on quality assurance developed | One advisory report on Quality Assurance not yet developed | Preliminary work towards quality assurance was carried out and a report compiled | The unit now has a full staff complement and will therefore be able to complete its targets in the next financial year | Report Attached ANNEXURE U |
| Approved national quality assurance plan | Approved national quality assurance plan | Approved national quality assurance plan | The target was not achieved | National quality assurance plan was not approved | Capacity constraints due to delays in the recruitment of staff. | The unit now has a full staff complement and will therefore be able to achieve its targets in the next financial year. The target has been carried over to the next financial year, reformulated and reworded to "Approved national quality assurance framework" | None |
| Number of reports on portfolio committee services provided | Four reports on portfolio committee services provided | One quarterly report on portfolio committee services provided | Advisory report on Portfolio Committee | None | None | None | Report on Portfolio Committee Services ANNEXURE V |

# SUB- PROGRAMME: ENTERPRISE ARCHITECTURE

| Strategic Objective: To oversee the enhancement of human settlements operations through effective enterprise architecture services in order to ensure improved service delivery and compliance |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Approved Departmental Annual Performance Plans | 1 Approved Departmental Annual Performance Plans | Approved Departmental Annual Performance Plans 2014/15 | Approved Departmental Annual Performance Plans 2014/15 | None | None | None | Approved Departmental Annual Performance Plans 2014/15 ANNEXURE A |
| Approved Departmental Performance Reports | Departmental Performance Reports | Departmental Third quarter performance reports | Departmental Third quarter performance reports compiled and submitted to the Office of the Director - General | None | None | None | Departmental Third quarter performance reports Submission to the Office of the Director - General ANNEXURE B |
|  |  | Departmental Performance report on Human Settlements Enterprise Operations Performance Assessment Framework (EOPAF) compiled | Departmental Performance report on Human Settlements Enterprise Operations Performance Assessment Framework (EOPAF) compiled | None | None | None | Departmental Performance report on Human Settlements Enterprise Operations Performance Assessment Framework (EOPAF) ANNEXURE C |

# SUB-PROGRAMME:  FINANCIAL MANAGEMENT

| Strategic Objective: To manage and provide financial support services. |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Annual Financial Statements approved | 4 Interim financial Statements and 1 annual financial statements approved and submitted | 1 approved Interim financial statement submitted to Auditor General and National Treasury | 1 approved interim financial statement submitted to Auditor-General and National Treasury | None | None | N/A | Confirmation letter Annexure 1 |
|  | 12 monthly reconciliation certificates submitted | 3 monthly certificates on reconciliations submitted to National Treasury | 3 monthly certificates submitted to National Treasury | None | None | N/A | Certificates Annexure 2 |
|  | 12 monthly reports on system and document reviews submitted | 3 monthly reports on system and document reviews submitted | 3 monthly reports on system and document reviews submitted | None | None | N/A | Reports Annexure 3 |
|  | 4 Workshops on financial policies conducted | 1 Workshop on financial policies conducted | 1 Workshop on financial policies conducted | None | None | N/A | Report Annexure 4 |
|  | 12 monthly reconciliation between LOGID and BAS on fixed asset transactions submitted | Three (3) monthly Reconciliations between LOGIS and BAS on fixed asset transactions submitted | Three (3) monthly Reconciliations between LOGIS and BAS on fixed asset transactions will be submitted | None | None | N/A | Reconciliations Annexure 5 |
|  | 1 asset disposal report submitted | One (1) assets Disposal Report submitted | Memo on Asset Disposal during this quarter. | None | None | N/A | Report Annexure 6 |
|  | 4 quarterly spot checks reports on store items conducted | One(1) Quarterly spot checks report on store items conducted | One(1) Quarterly spot checks report on store items conducted | None | None | N/A | Report Annexure 7 |
|  | 12 monthly reports submitted to National Treasury on contracts above R100 000 | Three (3) Reports submitted to National Treasury on contracts above R100 000 | Three (3) Reports submitted to National Treasury on contracts above R100 000 | None | None | N/A | Report Annexure 8 |
|  | 4 quarterly reports on awarded bids submitted | One (1) Quarterly report on awarded bids submitted | One (1) Quarterly report on awarded bids submitted | None | None | N/A | Report Annexure 9 |
|  | 4 quarterly Corporate travelling reports submitted | One (1) Quarterly corporate travelling report submitted | One (1) Quarterly corporate travelling report submitted | None | None | N/A | Report Annexure 10 |
|  | 12 monthly and 4 quarterly reports on government vehicle fleet management submitted | Three (3) monthly reports on government vehicle fleet management submitted | Three (3) monthly reports on government vehicle fleet management submitted | None | None | N/A | Report Annexure 11 |
|  | 12 monthly progress reports on Debtors System support submitted | 3 Progress reports on Debtors System support submitted | 3 Progress reports on Debtors System support submitted | None | None | N/A | Report Annexure 12 |
|  | 4 quarterly reports on Debtors System management on data cleanup, devolution and transfer of properties submitted | 1 Quarterly Report on Debtors System management submitted | 1 Quarterly Report on Debtors System management submitted | None | None | N/A | Report Annexure 13 |
|  | 4 quarterly BAS reports submitted | 1 BAS reports printed | 1 BAS report printed and submitted to management | None | None | N/A | Bas Report Annexure 14 |
|  | 3 Training Sessions on Basic Accounting System (BAS) conducted | 1 training session coordinated or conducted | Training sessions were arranged for officials | None | None | N/A | Confirmation forms Annexure 15 |
|  | 4 quarterly reports on user activities on BAS submitted | 1 Report on users activities on BAS system submitted | 1 Report on users activities on BAS system submitted | None | None | N/A | Report Annexure 16 |
|  | Estimate of National Expenditure approved | Estimate of National Expenditure (ENE) approved | Estimate of National Expenditure (ENE) was approved and published | None | None | N/A | ENE chapter Annexure 17 |
|  | 12 monthly early warning System reports to ensure compliance to legislation submitted to National Treasury | 3 Reports by the 15th of each month submitted to National Treasury. (1 report per month) | 3 Reports submitted to National Treasury | None | None | N/A | Reports Annexure 18 |
|  | 12 monthly financial reports regarding over/under expenditure submitted | 3 financial reports submitted to the Minister DG and other Management structures. (1 report per month) | 3 financial reports submitted to the Minister DG and other Management structures | None | None | N/A | Reports Annexure 19 |

# SUB PROGRAMME:  CORPORATE SUPPORT

| Strategic Objective :To manage the corporate support services to the Department |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of reports on compliance to all security standards submitted | 4 reports on compliance to all security standards submitted | 1 report on compliance to all security standards submitted | 1 report on compliance to security standards submitted | None | None | None | Annexure A 1 report on compliance to security standards |
| Number of reports on Facilities and Property management submitted | 4 reports on Facilities and Property management submitted | 1 report on Facilities and Property management submitted | 1 report on Facilities and Property Management submitted | None | None | None | Annexure B 1 report on Facilities and Property Management |
| Number of reports on records management submitted | 4 reports on records management submitted | 1 report on management of records submitted | 1 report on management of records submitted | None | None | None | Annexure C 1 report on management of records |
| Number of reports on library and information management services provided | 4 reports on library and information management services provided | 1 report on library and information management services provided | 1 report on library and information management services submitted | None | None | None | Annexure D 1 report on library and information services |

# SUB PROGRAMME:  HUMAN RESOURCES MANAGEMENT

| Strategic Objective To provide Human Resource Management services to the Department |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of reports on co-ordinated Human Resource Management services submitted | 4 reports on co-ordinated Human Resource services submitted | 1 report on co-ordinated Human Resource services submitted | 1 report on co-ordinated Human Resource services submitted | None | None | None | ANNEXURE E 1 report on co-ordinated Human Resource services |
| Number of reports on co-ordinated Human Resource Development initiatives submitted | 1 Annual training Report on co-ordinated Human Resource Development initiatives submitted | 1 report on Human Development Initiatives submitted | 1 report on Human Development Initiatives submitted | None | None | None | ANNEXURE F 1 report on Human Development Initiatives submitted |
| Number of reports on co-ordinated Labour Relation services submitted | 4 reports on co-ordinated Labour Relation services submitted | 1 report on co-ordinated Labour Relation services submitted | 1 report on co-ordinated Labour Relation services submitted | None | None | None | ANNEXURE G 1 report on co-ordinated Labour Relation services submitted |
| Number of reports on Organisational transformation programmes submitted | 4 reports on Organisational transformation programmes submitted | 1 report on Organisational transformation programmes submitted | 1 report on organizational transformation programmes submitted | None | None | None | ANNEXURE H 1 report on organizational transformation programmes submitted |

# SUB PROGRAMME:  LEGAL SERVICES

| Strategic Objective: To manage legal services to the Department. |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of litigation and legal advisory services | 4 reports on litigation and legal advisory services | 1 report on litigation and legal advisory services | 1 report on litigation and legal advisory services produced | None | None | None | Annexure I 1 report on litigation and legal advisory services |
| Number of legislative framework developed | 4 reports on legislative framework developed | 1 report on legislative framework developed | 1 report on legislative framework developed | None | None | None | Annexure J 1 report on legislative framework |
| Number of reports on oversight of contracts in the department developed | 4 reports on oversight of contracts in the department developed | 1 report on oversight of contracts in the department developed | 1 report on oversight of contracts developed | None | None | None | Annexure K 1 report on oversight of contracts |

# SUB PROGRAMME:  MANAGEMENT INFORMATION SYSTEMS AND INFORMATION TECHNOLOGY SYSTEMS

| Strategic Objective:To manage the Department’s Information Communication Technology (ICT) |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of reports on the implementation plan of Management Information Services (MIS) submitted | 4 reports on the implementation plan of MIS submitted | 1 report on the implementation plan of MIS submitted | 1 report on the implementation plan of MIS submitted | None | None | None | Annexure L 1 report on the implementation plan of MIS submitted |
| Number of reports on the implementation plan of Information Technology Services (ITS) submitted | 4 reports on the implementation plan of ITS submitted | 1 report on the implementation plan of ITS submitted | 1 report on the implementation plan of ITS submitted | None | None | None | Annexure M 1 report on the implementation plan of ITS submitted |
| Number of reports on the implementation plan of Information Communication Technology Infrastructure (ICTI) submitted | 4 reports on the implementation plan of ICTI submitted | 1 report on the implementation plan of ICTI submitted | 1 report on the implementation plan of ICTI submitted | None | None | None | Annexure N 1 report on the implementation plan of ICTI submitted |

# SUB PROGRAMME:  COMMUNICATION SERVICES

| Strategic Objective:To ensure the public is informed of Departmental programmes and policies |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Corporate Communication plans approved and implemented | 4 reports on the implementation of approved Corporate Communication plans | 1 report on the implementation of approved corporate communication plans | 1 report on the implementation of approved Corporate Communication Plans submitted | None | None | None | Annexure O 1 report on the implementation of approved Corporate Communication Plans submitted |
| Media Services plans approved and implemented | 4 reports on the implementation of approved Media Services plans | 1 report on the implementation of approved Media Services plans | 1 report on the implementation of approved Media Services Plans submitted | None | None | None | Annexure P 1 report on the implementation of approved Media Services Plans submitted |
| Public Information and Marketing plans approved and implemented | 4 reports on the implementation of approved Public Information and Marketing plans | 1 report on the implementation of approved Public Information and Marketing plans | 1 report on the implementation of approved Public Information and Marketing Plans submitted | None | None | None | Annexure Q 1 report on the implementation of approved Public Information and Marketing Plans submitted |

PROGRAMME 2: HUMAN SETTLEMENT POILICY, STRATEGY AND PLANNING

SUB-PROGRAMME:  OPERATIONAL POLICY FRAMEWORKS

| Strategic Objective : To manage the development of human settlement policy and accreditation frameworks |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Macro human settlement policy approved | New national human settlement macro policy approved | Submit draft densification policy for approval to MINMEC. | Submission forwarded to EMT for decision making. | Submission not yet forwarded to MINMEC. | Delay in receiving comments on the document from Provinces and Municipalities | Individual follow ups were made to solicit inputs on the document. | Submission to EMT and Draft Policy ANNEXURE A |
| Number of provincial and municipal workshops on national human settlement policy conducted | 9 structured policy workshops on Human settlement policies conducted | 2 provincial and municipal human settlement policy workshops conducted Workshops reports compiled | 2 workshops held with Limpopo and Nyandeni Local Municipality. | None |  |  | Agenda Meeting Reports Attendance Registers ANNEXURE B |
| Number of new national human settlement policy, guidelines and norms and standards approved | New policy for low income back yard rental programme and new criteria for restructuring zones | Draft programme to MINMEC submitted for approval | Policy on Backyard Rental Programme drafted and submitted to EMT | Partly achieved The MINMEC forum will only consider the policy after May 2014 | The policy development process was coordinated with the research and consultation process of SALGA This was only concluded in the beginning of March 2014. The policy drafting process only commenced in the second week of March 2014 | Policy finalized and awaiting EMT decision where after it will be submitted to MINMEC | Submission to EMT and Draft Policy ANNEXURE C |
|  |  | Draft criteria to MINMEC submitted for approval | Criteria developed and submitted to EMT for approval | Partly achieved. The MINMEC forum will only consider the policy after May 2014 | The drafting of the criteria was delayed due to uncertainty on the project scope and required outcome | Criteria drafted and submitted to EMT for approval where after it will be submitted to MINMEC | Submission to EMT and Draft criteria ANNEXURE D |
| National human settlements Policy and guidelines revised | Revised CRU and Social housing policies | Report on recommendations submitted to MINMEC | The subsidy levels of the CRU programme was adjusted. A Terms Of Reference for the appointment of external expertise has been finalized. | Report was not submitted to MINMEC | The project was delayed due to uncertainty on what the actual project requirements were. Once the project scope was established the first phase was to adjust the subsidy quantum levels. This was done. The terms of reference for the appointment of external expertise was developed presented to the Bid Specification Committee at 3 occasions before it was approved, which also retarded the project. DG's approval is now being sought. | The project for the revision of the policy will be concluded in the next financial year. | The TOR and the submission to the Bid Specification Committee. ANNEXURE E |
|  |  | Social Housing policy review project transferred to CD Strategy: Develop programme for special housing needs. Fourth Quarter Target: Investigate the mandate and obtain approval of TOR for investigation project. | Terms of reference for the appointment of expertise has been developed and finalized. Negotiations with the Department of Social Development resulted in the approval of DSD to fund the outsourcing project and to manage the project in collaboration with the Department. | Health input not covered in the TOR. NDHS does not have the budget for the project. | DG approved the revised APP at the end of 3rd Quarter. The MinMec recommended that the department consult with the Department of Health, DPT of Women Children and People with Disability and Social Development. The DSD could not attend the meetings organized with the DWCPD, however gave input which required rectification by other stakeholders. | A Meeting for additional input has been arranged for 14 May 2014 to solicit all inputs. DSD will fund the project using its own Resources. | Terms of reference and DSD confirmation to undertake project. ANNEXURE F |
| Number of municipalities assessed for accreditation | 6 Municipalities assessed for accreditation | 1 Municipality assessed for accreditation | Assessments for level 3 accreditation (Assignment) was completed for the 6 Metro Municipalities | 5 municipalities were assessed | The target was overachieved as a result of addressing the targets for the previous quarters | Completed the assessments of the total 6 Metros. | Accreditation report ANNEXURE G |
| Number of workshops to Capacitate Municipalities on the Implementation Protocols conducted | 6 workshops to Capacitate Municipalities on the Implementation Protocols conducted | 2 workshops to Capacitate Municipalities on the Implementation Protocols conducted | 2 workshops were held | None | None | None | 2 Attendance Registers 2 Reports ANNEXURE H |
| Number of workshops to capacitate Provinces and Municipalities on Assignment conducted | 6 workshops to capacitate Provinces and Municipalities on Assignment conducted | 2 workshops to capacitate Provinces and Municipalities on Assignment conducted | 2 workshops were held | None | None | None | 2 Attendance Registers and 1 Report ANNEXURE I |

SUB-PROGRAMME:  GOVERNANCE FRAMEWORKS

| Strategic Objective: develop and manage operational compliance policy framework |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Sector operational compliance policy framework Approved | Governance frameworks and implementation guidelines for 2013/14 approved | 1 Workshop on the framework with the sector submitted | The workshop on the framework was held on 14 March 2014. | None | None | None | Workshop Report and Attendance Register ANNEXURE J |
| Number of reports on Functional Governance Framework Systems submitted | Functional Governance Framework System developed | One report on Functional Governance submitted Framework System developed | The matrix has been developed and presented to Buffalo City Municipality and the City of Tshwane as pilot projects to assess the functionality of the system. | None | None | None | Reports ANNEXURE K |
| Number of reports on the sector compliance to HS Governance Framework submitted | 2reports on the sector compliance to HS governance frameworks submitted | 1 report on the sector compliance to HS governance frameworks submitted | The feedback from Buffalo City Municipality and the City of Tshwane will be analysed and utilised as a indication of sector compliance | None | None | None | Analysis Report ANNEXURE L |
| Number of approved annual builds projects implemented | Four Builds (Youth, women, Mandela Day, Military Vets, and 16 Days Builds) implemented | International Women’s Day Project launch Implemented | International Women's Day project implemented in Khayelitsha, Cape Town 08 March 2014. The houses were handed over by Deputy Minister | None | None | None | International Women's Day Report and Programme ANNEXURE M |
| Number of reports on training and mentorship programmes implemented | 4 reports on training and mentorship programmes implemented | 1 report on training and mentorship programmes implemented | 1 Report on Training and Mentorship programme for Youth Build Training Project launch held in Jan Kemp Dorp on the 28 January 2014, and bursaries secured by KSD FET College for training of 61 youth that participated in the Women's Build project August 2013 | None | None | None | Report on Training and Mentorship and programme for the Youth Build Launch and bursaries secured by KSD FET college for 61 youth that participated in Women's Build project August 2013 ANNEXURE N |
| Number of reports on the implementation of the sector transformation programmes and special projects submitted | 4 reports on the implementation of the sector transformation programmes and special projects submitted | 1 Sector Transformation and Special Projects Quarterly Report submitted | Sector transformation projects implemented in Kwa-Zulu Natal (Cornubia) |  |  |  | One Report on Sector Transformation projects implemented ANNEXURE 0 |
| Number of sector transformation strategies developed and reviewed | 2 sector transformation strategies developed (Military Vets and TRC) | 2 sector transformation strategies submitted for approval by MinMEC | Input provided on the Draft Research Report for the Empowerment Strategy for the Focus Group. | Delay in appointment of a service provider | Terms of Reference with Bid Adjudication | TOR referred back for further consultation | Report and draft input ANNEXURE P |
| Number of research reports on the identified themes in the research agenda(sustainable human settlements, demand, supply, land and tenure) submitted | 2 research reports on the identified themes in the research agenda submitted | 2 research report on the identified themes in the research agenda submitted | Research paper on Asbestos Use In South Africa: Related Health Risks And Policies For Risk Management Research Towards the development of the Empowerment strategy: Legislative , Policy And Documentary Review | None | None | None | Two reports on Asbestos Use in SA and Development of the Empowerment Strategy ANNEXURE Q |
| Number of policy analysis for input and reviews | One policy analysis and reviews | One policy analysis for input and reviews | Research paper to determine the use of institutional subsidies for the provision of Group Housing accommodation for people with special needs | None | None | None | Research paper Group Housing Accommodation for people with Special Needs ANNEXURE R |
| Number of reports on Human Settlements environment scanning and analysis (Economic and Social environment) submitted | 4 reports on Human Settlements environment scanning and analysis submitted | 1 report on Human Settlements environment scanning and analysis submitted | Research report on Human Settlements environment scanning and analysis | None | None | None | Research report on environmental scanning: developments in the global and local economy and their impact on housing development ANNEXURE S |

SUB PROGRAMME: HUMAN SETTLEMENTS STRATEGY

| Strategic Objective:To manage the development of human settlement strategy |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4Target | Actual performance | Variance |  |  |  |
| Development and approval of a human settlements macro strategy | A draft green Paper on human settlements submitted for approval to MinMec | A draft green paper on human settlements submitted for approval by MinMec | Concept paper and project plan developed for the drafting of Human Settlements Green Paper | Draft green on Human Settlements not submitted for approval to Minmec | Waiting finalization of the signing of MOU between DHS and DST | Milestone for 2014/15 are captured in the project plan | Project plan and concept paper ( Annexure 1 – File 1) |
| Conduct evaluation of Human Settlements Policy and Programmes | One evaluation on Human Settlements programmes conducted | Report on the evaluation of how housing programmes have facilitated the creation of assets for the poor and Municipalities completed | Inception report and conceptual framework on how housing have facilitated creation of assets for the poor has been submitted | None | None | None | Inception report and conceptual framework ( Annexure 2 File 1) |
|  |  | Policy implication report on how housing programmes have crated assets for the poor and for municipalities | Inception report and conceptual framework on how housing have facilitated creation of assets for the poor has been submitted | None | None | None | Inception report and conceptual framework ( Annexure 3 File 1) |
|  |  | Draft report on the evaluation of the USDG | Draft Evaluation report on the USDG developed and submitted | None | None | None | Draft report on the evaluation of the USDG (Annexure 4 File 1) |
|  |  | Four case study reports from the metros on the evaluation of the USDG | Four case studies on the evaluation of USDG submitted | None | None | None | Four case studies USDG evaluation (Annexure 5 File 1) |
|  |  | Inception report for the evaluation of the IRDP completed | Inception report for the evaluation of the IRDP completed and submitted | None | None | None | Inception report for the evaluation of the IRDP ( Annexure 6 File 1) |
| Knowledge on Human Settlements programmes collated and information disseminated | 2 National Strategy and Research Task Team forums held & one publication compiled. | One publication on human settlements completed | Publication on Human Settlements 20 year review published and National Research Task Team forum not held | None | None | Research function no longer reside with Chief Directorate after turnaround strategy | Human Settlements 20 year review ( Annexure 7 File 1) |
| Approved Human Settlement Strategy and Departmental Strategic Plans. | Approved Human Settlement Strategy and Departmental Strategic Plans 2014/17. | Approved Medium Term Strategic Framework Submitted. | Medium Term Strategic Framework drafted pending approval by incoming Minister after 7 May General Elections | Approval by incoming Minister pending as result of upcoming 7 May 2014 General Elections | Awaiting for the new Minister to approve after the elections as the MTSF cannot be approved by the outgoing Minister | Awaiting for the new Minister to approve after the elections as the MTSF cannot be approved by the outgoing Minister | Draft Medium Term Strategic framework ( Annexure 8 File 1) |
|  |  | Approved Departmental strategic plans | Branches strategic plans have been analyzed based on draft MTSF and final strategic plan will be table to Parliament after approval by incoming Minister in August 2014 as per DPME directive | None | Approval by incoming Minister pending as result of upcoming 7 May 2014 General Elections | Awaiting for the new Minister to approve after the elections as the MTSF cannot be approved by the outgoing Minister | None |

SUB PROGRAMME: HUMAN SETTLEMENTS PLANNING

| Strategic Objective: To manage human settlements programmatic planning frameworks, and support the implementation of human settlement and housing development planning frameworks. |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| National HSDG and USDG business plan compiled and submitted | National HSDG business plan business plan submitted | National HSDG Business Plan and Compliance certificate submitted | National HSDG Business Plan and Compliance certificate submitted | None | None | None | 1A. National HSDG Business Plan and Compliance certificate. 1B. Submission on the National HSDG Business Plan Annexure 9 A+B - File 2 |
| Implementation of human settlement development & programmatic planning frameworks at provincial & municipal level supported | 9 Provinces on the development of Provincial HSDG Business plan templates supported | 9 Final Provincial HSDG Business Plans received and analysed. | 9 Final Provincial HSDG Business Plans received and analysed. | None | None | None | 9 Final Provincial HSDG Business Plans. Annexure 10 File 2 |
|  |  | 1 submission on the status of the final draft HSDG Business Plans submitted | 1 submission on the status of the final draft HSDG Business Plans submitted | None | None | None | submission /Report on the status of the final draft HSDG Business Plans. Annexure 11 File 2 |
|  | Strategic Integrated Projects (SIP’s) information provided | 1 Submission on information for the Strategic Integrated Projects provided. | 1 Submission on information for the Strategic Integrated Projects provided. | None | None | None | Submission on information for the Strategic Integrated Projects provided. Annexure 12 File 2 |

SUB PROGRAMME: STAKEHOLDER AND INTERGOVERNMENTAL RELATIONS

| Strategic Objective: To Manage Stakeholder coordination, intergovernmental and sector relations and cooperation for the human settlements development |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of report on Sector Stakeholder Collaboration | 4 reports on developed and implemented Sector Stakeholder Programmes | 1 report on developed and implemented Sector Stakeholder Programmes | 1 report on developed and implemented Sector Stakeholder Programmes | None | None | None | Annex 13 File 3 1 report on Implementation of sector stakeholder collaboration framework. minutes of Govan Mbeki awards workshop. Proof of payment of prize money for Govan Mbeki Awards letter and submission on assistance to destitute families. 1 report on NEDLAC resolutions 1 report on meeting with Environmental Affairs and DBSA regarding the Green Fund 1 Resolutions of a meeting between DHS, H D A and Traditional Affairs on partnership framework. Resolutions of a meeting between DTA and H D A Signed MOU between DST and DOHS . Action plan meeting between NHBRC, DST, CSIR and DHS on on Sanitation. Action list of meeting between HS and SANCOC 3 reports on Ministerial outreach projects (Avoca hills, Delft Symphony and Cornubia. 1 report on verification of Malibongwe project |
| Number of reports on the implementation and rollout of People’s Housing Processes | 4 reports on the implementation of People’s Housing Processes submitted | 1report on the implementation of People’s Housing Processes submitted | 1report on the implementation of People’s Housing Processes submitted | None | None | None | Annex 14 File 3 1report on the implementation of People’s Housing Processes submitted Annex 1: Implementation Support Report on the status of PHP implementation in Mpumalanga Site visits conducted in Ehlanzeni District of Mpumalanga Site visit to Drommedaris Housing Project Meeting with KZN DoHS on Vulindlela Housing project Report on Status of Vulindlela project Progress report on PHP projects in the North West Status report on the roll-out of the Dromedaris PHP project Status report on the PHP pipeline projects in the Eastern Cape Status report on the implementation of the FEDUP pledge in Gauteng Annex 2 - Capacity Development evidence: Lephalale Councilor induction conducted in Limpopo PHP workshop: Eastern Cape Department Annexure C: Minister’s Programme (ad hoc) Report on the site visits to Nuwe Begin BNG project, and Dromedaris PHP project A report on the site visit to Klapmuts IRDP project, De Doorns IRDP project and Thembalethu Informal Settlements Upgrading project in George A report on the handover of the Nuwe Begin BNG project by the Minister A report on the Africa family house built in Mitchells Plain |
| Number of reports on coordination and participation of stakeholders at intergovernmental forums | 4 reports on coordination and participation of stakeholders at intergovernmental forums as described in the developed procedures and systems to support stakeholder collaborations | 1 report on coordination and participation of stakeholders at intergovernmental forums as described in the developed procedures and systems to support stakeholder collaborations | 1 report on coordination and participation of stakeholders at intergovernmental forums as described in the developed procedures and systems to support stakeholder collaborations | None | Not applicable | Not applicable | Annex 15 File 3 1 report on coordination and participation of stakeholders at intergovernmental forums as described in the developed procedures and systems to support stakeholder collaborations |
| Number of reports on the coordination of bilateral and multilateral partnerships in the international sphere | 4 reports on the coordination of bilateral and multilateral partnerships in the international sphere | 1 report on the coordination of bilateral and multilateral partnerships in the international sphere | 1 report on the coordination of bilateral and multilateral partnerships in the international sphere | None | Not applicable | Not Applicable | Annex 16 File 3 1 report on the coordination of bilateral and multilateral partnerships in the international sphere |

PROGRAMME 3:  PROGRAMME DELIVER Y SUPPORT

SUB- PROGRAMME: PROGRAMME AND PROJECT PLANNING

| Strategic Objective: Manage the conceptualization and planning of human settlements strategic human settlements programmes and projects |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Consolidated quarterly progress reports on 12 identified projects | 4 consolidated quarterly reports on 12 identified projects indicating progress achieved in planning, the provision of infrastructure, houses delivered, funds spent, socio-economic amenities delivered and compliance to the built environment standards. | 1 consolidated quarterly report on 12 identified projects indicating progress achieved in planning, the provision of infrastructure, houses delivered, funds spent, socio-economic amenities delivered and compliance to the built environment standards. | Achieved 1 consolidated quarterly report on 12 identified projects indicating progress achieved in planning, the provision of infrastructure, houses delivered, funds spent, socio-economic amenities delivered and compliance to the built environment standards | N/A | N/A | N/A | Quarterly Progress Report Annexure A |

SUB- PROGRAMME: PROGRAMME IMPLEMENTATION FACILITATION

| Strategic Objective: Oversee and facilitate the implementation of human settlement projects |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Quarterly progress reports on the 49 municipalities supported with Technical Support, Informal Settlements Classification and Formulation of Informal Settlements Upgrading plans to provide the basic services and secure tenure in line with Outcome 8 outputs. | Four quarterly progress reports on the 49 municipalities supported and assisted with technical support, informal settlements classification and formulation of informal settlements upgrading plans in line with Outcome 8 outputs. | Quarterly progress reports on the 49 municipalities supported and assisted with technical support, informal settlements classification and formulation of informal settlements upgrading plans in line with Outcome 8 outputs. | Achieved Progress reports on the 49 municipalities supported and assisted with technical support, informal settlements classification and formulation of informal settlements upgrading plans in line with Outcome 8 outputs prepared. | N/A | N/A | N/A | NUSP Progress Report Annexure B |
|  |  | Progress report on the implementation of the approved capacity building programme to guide the informal settlement upgrading programme in 49 municipalities | Not achieved. | Progress report on the implementation of the approved capacity building programme to guide the informal settlement upgrading programme in 49 municipalities not prepared. | Delayed approvals of the Terms of Reference for the Development of the Capacity Building Programme content and approval of increased tender amount. | Approval requested from the DG | Memorandum in respect of Terms of Reference Memorandum to the DG for approval of increased tender amount. Annexure C |
| Four quarterly reports developed on the implementation support provided to human settlement projects. | 4 quarterly reports on the implementation support provided to human settlement projects | Report containing 9 Provincial lists of slow moving projects with an analyses and recommendations to support. | Achieved Report produced in respect of 9 Provincial lists of slow moving projects with an analyses and recommendations to support. | N/A | N/A | N/A | Report produced in respect of 9 Provincial lists of slow moving projects with an analyses and recommendations to support. Annexure D |
|  |  | Report on support provided upon request by Provinces, Municipalities & individuals. | Achieved. Report produced on support provided upon request by Provinces, Municipalities & individuals. | N/A | N/A | N/A | Report produced on support provided upon request by Provinces, Municipalities & individuals. Annexure E |
| Number of blocked projects requiring delivery support | 4 Quarterly Reports on blocked projects requiring delivery support. | Report on blocked projects requiring delivery support | Achieved. Report on blocked projects requiring delivery support prepared | N/A | N/A | N/A | Report on blocked projects requiring delivery support Annexure F |

SUB- PROGRAMME: NATIONAL SANITATION PROGRAMME

| Strategic Objective: Manage and monitor the implementation of the Sanitation Programme |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| RHIP Programme implemented in 26 municipalities | 4 Quarterly progress reports on the implementation of the RHIP in 26 municipalities on the number of units delivered and expenditure | 1 Quarterly progress report on the implementation of the RHIP in 26 municipalities on the number of units delivered and expenditure | Not achieved, 1 Quarterly progress report on the implementation of the RHIP in 26 municipalities on the number of units delivered and expenditure RHIP has been implemented in 2 local municipalities in Eastern Cape (Engqobo) and Mpumalanga (Nkomazi) | 1 Quarterly progress report on the implementation of the RHIP in 26 municipalities on the number of units delivered and expenditure | Wrong gazetting of RHIG funds to non-WSA’s by the National Treasury | Re-gazetting of RHIG funds to WSA’s and funds were transferred to WSA’s by the Department | RHIP Quarterly report Annexure G |
| No of municipalities trained on health and hygiene programs (WASH, health and hygiene education programme | 27 municipalities trained on H&H programmes. | 9 municipalities trained on H&H programmes | Achieved 9 municipalities trained on H&H programmes in the following municipalities: Overberg, Winelands, City of Cape Town, Buffalo City, Alfred Nzo, Ekurhuleni, Joburg, City of Tshwane and Modimolle | None | None | None | Health and Hygiene reports Annexure H |
| Number of MIG projects monitored | 144 MIG projects monitored across 9 provinces (i.e. 16 per province) | 36 MIG projects monitored across 9 provinces (i.e. 4 per province) | 44 MIG projects monitored across 9 Provinces Gauteng (1): Metsi-a-Lekoa Mpumalanga (18):Nsikazi South Ward 1, Dludluma, Boschfontein, Masibekela, Ephameni, Jerusalem, Mahushu, Maguduzwane, Nkohlakalo, Phola Trust, Chochocho, Shabalala, Tekatakho, Block B- Kamaqhekeza, Block A, Tsambokhulu, Block C and Khombaso; Limpopo (12): Giyani, Nkowankowa, Skrikfontein, Ga-Chaba, Ga-Kgapane, Lenyenye, Kgautswane, Bokwidi, Senita, Lesodi, Leboeng B and Leboeng C. North West (5): Ramaphosa Ward 19, Machachora, Norokie Ward 7, Lekwa and Greater Taung | Additional 8 MIG projects monitored in Provinces | Some Provinces overachieved the target whilst other Provinces deviated from the planned target | Provinces were advised to align monitoring of projects as per the planned target | MIG site visit reports Annexure I |

SUB- PROGRAMME: TECHNICAL CAPACITY DEVELOPMENT

| Strategic Objective: Manage the development of the technical capacity in the human settlements sector |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of officials, beneficiaries and councilors trained | 160 officials, 2400 beneficiaries and 120 councilors trained | 1 report on the number of officials, beneficiaries and councilors trained | 1 report submitted on the number of officials, beneficiaries and councilors trained | None | None | None | Report on the number of officials, beneficiaries and councilors trained ANNEXURE D |
| Sector Knowledge Management Strategy developed. | Sector Knowledge Management Strategy developed | Approval of Sector Knowledge Management Strategy. | The Sector Knowledge Management Strategy has been forwarded to the Director General for approval | Awaiting approval | Awaiting approval | Follow-up, to speed-up the approval | Report on the Sector Knowledge Management Strategy Final Sector Knowledge Management Strategy ANNEXURE E |
| Number of reports on provincial departments work shopped, monitored and evaluated on the implementation of the National Technical Capacity Development Strategy | 4 Quarterly reports on 9 provincial departments work shopped, monitored and evaluated on the implementation of the National Technical Capacity Development Strategy | 1 Quarterly report on provincial departments work shopped, monitored and evaluated on the implementation of the National Technical Capacity Development Strategy | A report on provincial departments work-shopped monitored and evaluated on the implementation of the National Technical Capacity Development Strategy | None | None | None | A report on provincial departments work-shopped, monitored and evaluated on the implementation of the National Technical Capacity Development Strategy ANNEXURE F Draft model organisational structure for Accredited Municipalities ANNEXURE G |
| Number of reports on Provincial departments work shopped in the development and implementation of provincial Capacity Development Programmes and Business | Number of reports on Provincial departments work shopped in the development and implementation of provincial Capacity Development Programmes and Business | 1 Quarterly report on Provincial departments work shopped in the development and implementation of provincial Capacity Development Programmes and Business Plans | A report on Provincial Departments work-shopped in the development and implementation of provincial Capacity Development Programmes and Business Plans | None | None | None | A report on Provincial Departments work-shopped in the development and implementation of provincial Capacity Development Programmes and Business Plans Annexure H Draft Proposal on projects to be funded by the EWSETA ANNEXURE H1 |
| Number of reports on Sector professional development support programmes Implemented | 4 reports on the progress of the implementation of the Sector professional development support programmes | 1 report on the progress of the implementation of the Sector professional development support programmes | 1 report on the progress of the implementation of the Sector professional development support programmes. | None | None | None | Report on the progress of the implementation of the Sector professional development support programmes ANNEXURE I |

PROGRAMME 4: HOUSING DEVELOPMENT FINANCE

SUB- PROGRAMME:  CHIEF INVESTMENT OFFICER

| Strategic Objective: To manage and provide overall Grants Management services, administer the Home Loan and Mortgage Disclosure Act and promote investments for sustainable Human Settlements. |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Number of financial reports on the monitoring of performance of the HSDG and USDG submitted | HSDG reports submitted 12 monthly 4 quarterly 1 annual 2 reports on financial evaluation of the draft business plans 1 analysis report on the Annual provincial reports | HSDG reports submitted 3 monthly 1 quarterly 1 report on the financial evaluation of final business plans | December 2013, January and February 2014 reports were submitted to NT by the due date. The analysed 3rd quarter expenditure report was submitted to NT by the due date. Draft report was submitted to HSP unit. | None None | None None Waiting for feedback from HSP unit on resolution taken on the meeting in respect of Disaster Relief, Mining towns and Baseline information which was not available on the Business Plan. | N/A N/A | Reports Annexure 20 |
|  | USDG reports submitted 12 monthly 4 quarterly 1 annual | USDG reports submitted 3 monthly 1 quarterly | 3 monthly USDG reports submitted 1 Quarterly report submitted | none | None | N/A | Reports Annexure 21 |
| Provide secretariat function for Office of Disclosure in terms of the act. | 4 reports on secretariat functions for Office of Disclosure in terms of the Act produced and submitted. | 1 report on secretariat functions for Office of Disclosure in terms of the Act produced and submitted. | 1 report on secretariat functions for Office of Disclosure in terms of the Act produced and submitted. | None | None | N/A | Reports Annexure 22 |
|  | 3 reports from financial institutions on leding patterns developed and submitted | 1 report on lending patterns and practices by financial institutions on home loans produced and submitted | 1 report on lending patterns and practices by financial institutions on home loans produced and submitted | None | None | N/A | Report Annexure 23 |
| Number of reports on affordable housing market interventions | 2 report on Official Development Assistance (ODA) | 1 report on Official Development Assistance (ODA) | 1 Quarterly report on Official Development Assistance (ODA) submitted | None | None | N/A | Report Annexure 24 |
|  | 1 report on Mortgage Default Insurance (MDI) | 1 report Mortgage Default Insurance (MDI) | 1 Annual report on Mortgage Default Insurance (MDI) developments submitted | None | None | N/A | Report Annexure 254 |
|  | 4 reports on Improved property market | 1 report on Improved property market | A report on Improved Property Market that include: Outcome 8-output 4 (Mortgage & non-mortgage, FLISP, MDI) Affordable housing development opportunities with Nissan SA and on Merriespruit 3 CRU Project were submitted. | None | None | N/A | Report Annexure 24 |

SUB PROGRAMME: REGULATORY COMPLIANCE SERVICES

| Strategic Objective: To manage regulatory compliance services |
| --- |
| Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Compliance on performance of Housing Entities managed | Approved Annual Performance Plans 2014/15 for Housing Entities | Approved Annual Performance Plans 2014/15 for Housing Entities | 2014/15 Annual Performance Plans of Entities Submitted for Approval | Not Approved | Approval Pending | Follow up to speed-up approval | Final draft of Entities' APPs for 2014/15 ANNEXURE J |
| Compliance on performance of Housing Entities managed | Performance monitoring reports on Housing Entities ( Financial and non financial) submitted to the Department | 2013/2014 third quarter Performance monitoring report on Housing Entities ( Financial and non financial) | 2013/2014 third quarter Performance monitoring report on Housing Entities ( Financial and non financial) completed | None | None | None | Third quarter Performance report (financial and non-financial ) ANNEXURE K |
| Number of compliance monitoring report on the implementation of the rental programmes(CRU and Social Housing) developed. | 4 compliance monitoring reports on the implementation of the rental programmes (CRU and Social Housing) | 1 compliance monitoring report on the implementation of the rental programmes(CRU and Social Housing) | 1 compliance monitoring report on the implementation of the rental programmes (CRU and Social Housing) developed | None | None | None | A compliance monitoring report on the implementation of the rental programmes (CRU and Social Housing) attached as ANNEXURE L |
| Number of reports on the performance of Rental Housing Tribunal developed. | Four reports on the performance of Rental Housing Tribunal | 1 report on the performance of Rental Housing Tribunal | 1 report on the performance of Rental Housing Tribunal developed | None | None | None | A report on the performance of Rental Housing Tribunal attached as ANNEXURE M |
| Number of reports on the implementation of Human Settlements Legislations and Regulations developed. | Two reports on the implementation of Human Settlements Legislations and Regulations | 1 report on the implementation of Human Settlements Legislations and Regulations | 1 report on the implementation of Human Settlements Legislations and Regulations | None | None | None | Approved report on the implementation of Human Settlements Legislations and Regulations ANNEXURE N |

SUB- PROGRAMME: PROGRAMME MONITORING AND EVALUATION

| Strategic Objective: To manage the monitoring and evaluation of human settlements programmes |
| --- |
| Programme Performance Indicator | Actual Performance Against Targets | Reasons for Variance & non achievement (Challenges/ Problems) | Management Response/ Action Taken | Evidence |
|  | Annual Target 2013/14 | Quarter 4 Target | Actual performance | Variance |  |  |  |
| Report on implementation of the revised M&E Framework for human settlements programmes | Status report on the implementation of the approved revised M & E Framework | Distribute approved revised M&E framework for implementation | Partially achieved Final draft of MEIA submitted for approval to publish | Final draft of MEIA submitted for approval to publish | Final approval to publish awaited | Final approval to be fast tracked | Copy of submission requesting final approval for publishing Annexure J |
| Number of monitoring reports on performance of Human Settlements Programmes | 4 Quarterly Reports on performance of Human Settlements Programmes/ projects | 1 Quarterly Report on performance of Human Settlements Programmes | Achieved 1 Quarterly Report on the performance of Human Settlements projects | None | N/A | N/A | 1 Quarterly report on the performance of Human Settlements Projects Annexure K |
| Number of monitoring reports on the Human Index | Report on Human Settlements Index | Submit final draft for approval | Achieved Final draft report on Human Settlements Index submitted for approval | None | N/A | N/A | Final draft report on Human Settlements Index Annexure L |
| Number of monitoring reports on performance of Outcome 8 outputs | 4 Quarterly reports on performance of Outcome 8 outputs | 1 Quarterly report on performance of Outcome 8 outputs | Achieved 1 Quarterly report on performance of Outcome 8 submitted | None | N/A | N/A | 1 Quarterly Report on the performance of Outcome 8 Annexure M |
| Number of impact assessment reports on Human Settlements Programmes | 1 impact assessment reports on prioratised Human Settlements Programmes | First draft of impact assessment report | Not achieved Service Level Agreement was only signed on 27 March 2014 | Milestones deferred as a result of delay in signing of Service Level Agreement | Service Level Agreement between Department and Service Provider only signed on 27 March 2014 | Milestones deferred | Signed Service Level Agreement Annexure N |
|  | 1 Rapid appraisal report on prioratised Human Settlements Programmes | First draft Rapid Appraisal Report | Not achieved Service Level Agreement signed by the Department on 27 March 2014 Inception report approved by Steering Committee First draft of literature review report submitted by service provider | Inception report approved by Steering Committee First draft of literature review report submitted by service provider | Service Level Agreement signed by the Department on 27 March 2014 | Service Level Agreement signed by the Department on 27 March 2014 | Signed Service Level Agreement Approved inception report and draft Literature Review report Annexure O |
| Number of evaluation reports on the performance of provinces(HSDG) and Metropolitan Municipalities(USDG) on the Conditional Grants in terms of DORA | 4 Quarterly reports on performance of provinces(HSDG);and | 1 Quarterly report on performance of provinces on the HSDG);and | Achieved 1 Quarterly report on performance of provinces on the HSDG) | None | N/A | N/A | 1 Quarterly report on performance of provinces on the HSDG) Annexure P |
|  | 4 Quarterly reports on performance of Metropolitan Municipalities(USDG) | 1 Quarterly report on performance of Metropolitan Municipalities on the USDG | Achieved 1 Quarterly report on performance of Metropolitan Municipalities on the USDG | None | N/A | N/A | 1 Quarterly report on performance of Metropolitan Municipalities on the USDG Annexure Q |
| Number of reports on the implementation of data management, verification and analysis processes | 4 reports on the implementation of data management, verification and analysis processes | 1 report p on the implementation of data management, verification and analysis processes | Achieved 1 report on the implementation of data management, verification and analysis processes | None | N/A | N/A | 1 report on the implementation of data management, verification and analysis processes Annexure R |
| Number of performance assessment reports in terms of the management performance assessment tool(MPAT) | 1 Annual performance assessment report in terms of the management performance assessment tool(MPAT) | Final report submitted to | Achieved Final report submitted | None | N/A | N/A | Final performance assessment report in terms of the management performance assessment tool(MPAT) Annexure S |

___________________________________________________________________________________________________________