NATIONAL DEPARTMENT OF PUBLIC WORKS

1ST QUARTER PERFORMANCE INFORMATION FOR THE FINANCIAL YEAR 2014/15

16 September 2014

| Performance Monitoring and Evaluation Unit | 2014 |
| --- | --- |

Contents

I.	Introduction	3

1.	SUB-PROGRAMME: MANAGEMENT	5

2.	SUB-PROGRAMME: FINANCE AND SUPPLY CHAIN MANAGEMENT	8

3.	SUB-PROGRAMME: CORPORATE SERVICES	12

4.	SUB-PROGRAMME: ASSET INVESTMENT MANAGEMENT	16

5.	SUB-PROGRAMME: SPECIAL INTERVENTION PROJECTS	20

6.	SUB-PROGRAMME:  PROJECTS AND PROFESSIONAL SERVICES	21

7.	SUB-PROGRAMME: OPERATIONS MANAGEMENT – REGIONAL COORDINNATION	23

8.	SUB-PROGRAMME: INNER-CITY REGENERATION	27

9.	SUB-PROGRAMME: KEY ACCOUNTS MANAGEMENT	29

10.	SUB-PROGRAMME: EXPANDED PUBLIC WORKS PROGRAMME	32

11.	SUB-PROGRAMME: CONSTRUCTION AND PROPERTY INDUSTRY POLICY	35

REGULATION	35

12.	SUB-PROGRAMME: AUXILIARY AND ASSOCIATED SERVICES	38

# Introduction

Performance Information is essential to good management, public accountability and transparency, and to internal organisational learning and development against this, it is important for the Department to consistently provide clear reports of performance information that reflect the Department’s policy objectives. In addition, performance information may show how well public funds have been used (value for money) and whether planned targets/achievements are on track. Users of information both external and internal should be able to draw / or tell a story from the presentation of the information. In other words, the information should allow the user to make an informal assessment. Important elements of the information include relevance, reliability, understandability and comparability.

The Department seeks to contribute to the broader government outcomes. Attention is paid to three sector outcomes: decent employment through inclusive economic growth (Outcome 4); sustainable human settlements and an improved quality of household life (Outcome 8) and an efficient, effective and development oriented public service and an empowered, fair and inclusive citizenry (Outcome 12).  The Department of Public Works also provides full support to the realisation of a skilled and capable workforce (Outcome 5) and the creation of an efficient, competitive and responsive economic infrastructure network (Outcome 6). This report presents the performance information of the Department for the first quarter (QPR1) of the financial year 2014/15. It reflects of actual performance against planned targets.

.

Sub-Programmes

- Internal Audit and Investigation Services

- Strategic Management Unit

- Monitoring and Evaluation

- Intergovernmental Relations

- Finance and Supply Chain Management

- Corporate Services

| SUB-PROGRAMME: MANAGEMENT |
| --- |
| APP Reference Number | Performance Indicator | Planned Annual Target | Planned Quarter Target 2014/15 | Quarter performance 2014/15 | Reasons for deviation on Q1 performance |
| 1 | Risk based Internal Audit Plans Approved | 1 Internal Audit Plan Approved in April 2014 by Audit & Risk Management Committee | 1 Internal Audit Plan Approved in April 2014 by Audit & Risk Management Committee | Internal Audit Plan Not Approved in April 2014 by Audit & Risk Management Committee | Target Not Achieved Due to unforeseen operational reasons, the Audit & Risk Management Committee was rescheduled to a later date where it was subsequently approved |
| 2 | Percentage of internal audits completed | 100% Audits completed as per Approved Internal Audit Plan | 10% Audits completed as per Approved Internal Audit Plan | 10.7% Audits Completed (3 Audits out 28 Planned Audits for the year) | Target Achieved |
| 3 | Percentage of investigations initiated within 30 days based on reported allegations in line with National Treasury Regulations | 100% Investigations initiated on reported allegations within 30 days | 100% Investigations initiated on reported allegations within 30 day | 100% Investigations initiated on reported allegations within 30 days | Target Achieved |
| 4 | Annual Performance Plan compliant with Treasury Regulations tabled as per Parliamentary Programme | 2014/15 Annual performance plan tabled in parliament in March 2015 | 2014/15 Annual performance plan presented in Parliament | 2014/15 APP & 2014 – 19 strategic plan to be presented to the Portfolio Committee in Parliament on 08 July 2014 (2nd Quarter) | Not Applicable The presentation was done on 8th July 2014 after the revision of the 5th Parliamentary programme owing to the appointment of the new Portfolio Committee. |
| 5 | Risk Registers updated for Head Office and for each Regional Office | 1 Risk Register updated for each Chief Directorate at Head Office for 2015/16 1 Risk Register updated for each Regional Office for 2015/16 1 DPW high level risk register updated for 2015/16 | Departmental risk registers updated through risk monitoring for each Chief Directorate at Head Office for 2014/15 | Risk registers were updated for each of the Chief Directorates at Head Office with progress made on implementation of action plans | Target Achieved |
| 6 | Percentage of approved collection of strategic policies and procedures uploaded on the Knowledge Management System within 14 days of receipt | 100% of approved collection of strategic policies and procedures uploaded on the Knowledge Management System within 14 days of receipt | 100% of approved collection of strategic policies and procedures uploaded on the Knowledge Management System within 14 days of receipt | 100% (35 of 35) of approved collection of strategic policies and procedures uploaded on the Knowledge Management system within 14 days of receipt | Target Achieved |
| 7 | Number of Quarterly Reports on predetermined objectives completed in accordance with PFMA | 4 Quarterly Reports on predetermined objectives completed in accordance with PFMA | Completed 4th Quarter Report for the period ending March 2014 | 4th Quarter Report Completed | Target Achieved |
| 8 | Approved customised indicators for the Public Works Sector | Customised performance indicators developed with Provincial Public Works Sector by 30 June 2014 | Workshop conducted with Provincial Public Departments to draft customised performance indicators | No Workshop conducted with Provincial Public Departments to draft customised performance indicators | Not Applicable The customised performance indicators was relied largely on the Policy Statements of the Political Principals as delivered in their respective Budget Vote speeches of which most of them took place in June 2014. |
| 9 | Number of stakeholder engagements with the organs of state across the spheres of government in relation to DPW’s mandate | 72 Stakeholder engagements with organs of state across the Spheres of Government | 3 Engagements with Parliamentary committees | No engagements with Parliamentary committees | Not Applicable Parliament was on recess |
|  |  |  | 1 Engagement with each of DPW Entity | Engagement with DPW Entities to place on the 20th June 2014 as part of the Minister’s Policy Statement | Target Achieved |
|  |  |  | 3 Engagements with NEDLAC structures | 4 Engagements with NEDLAC structures | Target Achieved |
|  |  |  | 3 Engagements with Intergovernmental Bodies (Provincial/Local) | 6 Engagements with Intergovernmental Bodies (Provincial/Local) | Target Over-Achieved Over-achievement was due to increased number of engagements |
|  |  |  | 8 Engagements with internal top governance structures (EXCO, MinTop and MINMEC) | 12 Engagements with internal top governance structures (EXCO, MinTop and MINMEC) convened | Target Over-Achieved Over-achievement was due to adhoc meetings including two internal top governance forums |

| SUB-PROGRAMME: FINANCE AND SUPPLY CHAIN MANAGEMENT |
| --- |
| APP Reference No | Performance Indicator | Planned Annual Target | Planned Quarter 1 Target 2014/15 | Quarter 1 performance 2014/15 | Reasons for deviation on Q1 performance |
| 1 | Percentage change in irregular expenditure balance for DPW and PMTE | 20% Reduction in irregular expenditure baseline for DPW and PMTE | 5% reduction in the irregular expenditure baseline for DPW and PMTE | Actual 15% reduction based on the 2012/13 baseline of R3.6 billion. Total of R515.9 million reduction of the R 3.6 billion | Target Achieved Additional capacity through the Clean Audit Project; Targeted less complicated transactions for condonement |
| 2 | Percentage change in the value of newly identified transactions relating to irregular & fruitless and wasteful expenditure for DPW and PMTE | 30% Reduction in the value of newly identified transactions relating to irregular & fruitless and wasteful expenditure for DPW and PMTE | 30% (R1,08b) Reduction in the value of newly identified transactions relating to irregular & fruitless and wasteful expenditure for DPW and PMTE | Newly identified irregular expenditure of R824 million (which is 99% of target), a significant improvement | Target Achieved Improved internal control environment. Implementation of circular 17 of 2014 before approval Consequences for delinquent officials Screening of bids received by SCM before submission to Bid Committees |
| 3 | Percentage of compliant invoices settled within 30 days | 100% compliant invoices settled within 30 days | 100% compliant invoices settled within 30 days as at 30 June 2014 | 85% compliant invoices settled within 30 days as at June 2014 | Target Partially Achieved The complex nature of the business and vastly decentralised operations. |
| 4 | Percentage fraud and corruption cases within SCM detected | 100% detection of fraud and corruption cases within SCM | 100% detection of fraud and corruption cases within SCM as at 30 June 2014 | 100% (8 cases) fraudulent transactions have been detected all of these relate to IT procurement | Target Achieved |
| 5 | Percentage relevant and compliant bids awarded for construction projects within the validity period | Process and award bids for construction projects within 90 days | 70% compliant and relevant bids awarded within 90 days for construction projects | 47 construction bids were awarded with, 33 (70.2%) of them within 90 days and 14 of them awarded outside the 90 days target. | Target Achieved |
| 6 | Percentage of compliant and relevant bids for private leases awarded within the validity period | 100% compliant and relevant bids awarded within 120 days for private leases | 100% compliant and relevant bids awarded within 120 days for private leases as at 30 June 2014 | 100% compliant and relevant bids awarded within 120 days for private leases as at 30 June 2014 | Target Achieved Application of NT Special Dispensation for the extension/renewal leases through a negotiated process |
| 7 | Percentage contracts on the approved DPW procurement plan awarded in line with batch tendering processes aligned to the IDMS model | 100% construction contracts awarded in line with batch tendering processes | 30% of construction projects | 0% of 30% of construction projects achieved | Target Not Achieved Due to misalignment in the Batch tendering processes, projects could not be achieved |
| 8 | Percentage of planned maintenance contracts awarded to contractors registered on the CDP. | 30% of projects under planned maintenance programme awarded to contractors registered on the CDP | 5% of projects to CDP contractors under the planned maintenance programme for the period ending 30 June 2014 | 0% Of projects to CDP contractors under the planned maintenance programme for the period ending 30 June 2014 | Target Not Achieved Challenges and bottlenecks experienced within the business process in the awarding of tenders |
| 9 | Percentage of change of debtors balance PMTE | 80% reduction of debtors balance to less than 120 days on PMTE | 50% reduction of debtors balance to less than 120 days | 51.53% reduction of debtors balance to less than 120 days | Target Achieved Calculated the reduction of Total debtors balance and not of less than 120 days only. (Manual calculation was a challenge) |
| 10 | Number of expenditure analysis reports completed for DPW and PMTE | 4 Expenditure reports on consolidated functional expenditure estimates completed for both | Expenditure report for quarter 4 of 2013/14 completed by April 2014 | Expenditure report for Quarter 4 of 2013/14 completed by April 2014 | Target Achieved |
| SUB-PROGRAMME: CORPORATE SERVICES |
| APP Reference No | Performance Indicator | Planned Annual Target | Planned Quarter Target 2014/15 | Quarter performance 2014/15 | Reasons for deviation on Q1 Preliminary performance |
| 1 | Approved HR Plan submitted to DPSA by 31 March 2015 | Revised DPW HR Plan (including development and implementation of a Recruitment Plan and a Skills Development Plan to capacitate core business – Professional Services, Property and Facilities Management, Asset Management and SCM submitted to DPSA by 31 March 2015 | Quarterly report completed on the implementation of Recruitment Plan and Skills development Plan in capacitating core business | Quarterly report completed on the implementation of Recruitment Plan in capacitating core business | Target Achieved Draft recruitment plan completed and sent to core business for inputs which are due in September |
|  |  |  |  | Quarterly report completed on the implementation of Skills development Plan in capacitating core business | Target Achieved Workplace Skills Plan developed (forming part of the Skills Development Plan) and submitted to relevant stakeholders for input |
| 2 | Number of Beneficiaries participating in the DPW skills development programme | 914 Beneficiaries participating in the DPW skills development programme. 179 Young Professionals 545 Interns 137 Learners 53 Management trainees | 228 Beneficiaries participating in the DPW skills development programme 45 Young Professionals 136 Interns 34 Learners 13 Management Trainees | 755 beneficiaries participating into the trainee development programme 80 Young Professionals 535 Interns 100 learners 40 Management trainees | Target Over-Achieved Over-Achievement was due to CETA cut off dates being brought forward for the appointment of beneficiaries to 1st April 2014. As a result the bulk of the recruitment was done in this Quarter |
| 3 | Number of artisans participating in the artisan development programme | 200 Artisan trainees participating in the Artisan Trainee Development Programme | 50 Artisan Trainees participating in the Artisan Trainee Development Programme | 229 Artisan trainees participating in the Artisan Trainee Development Programme | Target Over-Achieved Over-Achievement was due to CETA cut off dates being brought forward for the appointment of beneficiaries to 1st April 2014. As a result the bulk of the recruitment was done in this Quarter |
| 4 | Percentage of legal opinions provided to Ministry and DPW within 10 working days of referral of each request | 100% of legal opinions provided within 10 working days of referral of each request | 100% of legal opinions 10 working days of referral of each request | 100% of legal opinions 10 working days of referral of each request | Target Achieved |
| 5 | Percentage of contracts drafted, amended and commented on within 10 working days of referral of each matter | 100% of contracts drafted, amended and commented on within 10 working days of referral of each matter | 100% of contracts drafted, amended and commented on within 10 working days of referral of each matter | 100% of contracts drafted, amended and commented on within 10 working days of referral of each matter Signed – 167 Drafted – 4 Amended – 5 Commented – 1 Cont Cancelled – 2 Gaurantee Received – 6 Guarantee Released – 9 Guarantee called up – 0 Guarantee cancelled – 0 | Target Achieved |
| 6 | Developed ICT infrastructure at the DPW Disaster Recovery Site | Disaster recovery site developed for DPW | Procurement of ICT infrastructure (network & server for the disaster recovery site | Installation of servers and system performance enhancement tools at main data centre (SITA) has been achieved | Target Achieved |
| 7 | ICT infrastructure upgrade to secure system access for PMTE and DPW business units | Upgrade of application servers to enhance performance of business office automation applications. Business Enablement of IE works applications | Installation of servers and system performance enhancement tools at main data centre (SITA) | Installation of servers and system performance enhancement tools at main data centre (SITA) has been achieved | Target Achieved |
| 8 | Number of corporate communication campaigns conducted in support of government long term plans | 24 Events conducted in support of the 20 years of freedom campaign | 6 Events conducted in support of the 20 years of freedom campaign | 7 Events conducted in support of the 20 years of freedom campaign | Target Achieved |
| 9 | Approved DPW strategic framework on Youth Development in the Built Environment | Completed DPW Strategic Framework on Youth Development in the Built Environment incorporating 4 implementation plans | Youth Employment plan in Built Environment | Drafted the Youth Development Strategic Framework to guide the 4 implementation plans in the built environment | Target Partially Achieved Literature review commenced in identifying best practices for incorporation into the final Youth Employment plan |

.

Sub-Programme

- Strategic Asset Investment Analysis

- Project and Professional Services

- Inner-City Regeneration

- Operations Management

- Key Accounts management

- Prestige Management

| SUB-PROGRAMME: ASSET INVESTMENT MANAGEMENT |
| --- |
| APP Reference No | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Quarter Performance 2014/15 | Reasons for Deviation on Q1 performance |
| 1 | Number of properties in the immovable Asset Register populated with information fields that are GRAP compliant | 56 871 Properties in the Immovable Asset Register populated with information fields that are compliant to GRAP | 14 214 properties in the Immovable Asset Register populated with information fields that are compliant to GRAP | 22 514 properties in immovable asset register populated with information fields that are compliant to GRAP | Target-Over Achieved Concerted effort to finalize physical verification of the department’s immovable assets and incorporation of Quality Assurance outcomes |
| 2 | Number of land parcels vested | 11 000 Land parcels confirmed ownership (vested) Port Elizabeth & Umtata – 1000 Bloemfontein – 200 Johannesburg & Pretoria – 200 Durban – 3000 Polokwane – 2000 Nelspruit – 1000 Kimberley – 500 Mmabatho – 1000 Cape Town - 1300 | 2 750 land parcels confirmed ownership (vested) Port Elizabeth & Umtata – 250 Bloemfontein – 50 Johannesburg & Pretoria – 250 Durban – 750 Polokwane – 500 Nelspruit – 250 Kimberley – 125 Mmabatho – 250 Cape Town - 325 | 100 land parcels vested (confirmed ownership) Port Elizabeth & Umtata – 4 Bloemfontein – 25 Johannesburg & Pretoria – 11 Durban – 1 Polokwane – 7 Nelspruit – 22 Kimberley – 6 Mmabatho – 5 Cape Town – 19 | Target Not Achieved Much effort was spent on reconciliation of electronically and manually vested land parcels, together with relevant enabling vesting documentation, in mobilising the vesting process that has been put in place to achieve the 31 March 2016 target |
| 3 | Number of immovable Assets valued to determine deemed carrying amounts | 113 742 Immovable Assets valued to determine deemed carrying amounts Bloemfontein – 9006 Cape Town – 17 902 Durban – 18 384 Johannesburg – 8 546 Kimberley – 7 515 Mmabatho – 10 368 Nelspruit – 7 913 Polokwane – 12 221 Port Elizabeth – 7 089 Pretoria – 11 858 Umtata - 2940 | 28 432 Immovable Assets valued to determine deemed carrying amounts: Bloemfontein – 2 251 Cape Town – 4 475 Durban – 4 596 Johannesburg – 2 136 Kimberley – 1 878 Mmabatho – 2 592 Nelspruit – 1 978 Polokwane – 3 055 Port Elizabeth – 1 772 Pretoria – 2 964 Umtata - 735 | 29 496 Immovable Assets valued to determine deemed carrying amounts: | Target Achieved Quarterly targets were determined prior to the development of the valuation model and application of ASB Directive 2 on the PMTE. |
| 4 | Approved Immovable Asset Management Framework | Asset Management Framework approved by the Accounting Officer by 30 September 2014 | Asset Management Framework developed | ToR development of an asset management framework/ strategy completed. Commenced with processes to insource service provider to assist with relevant expertise. | Target Not Achieved Effort focused on research and consultation to scope the project |
| 5 | Approved property performance standards (PPS) for all categories of Immovable Assets | Property Performance Standards approve by the Accounting Officer by 30 September 2014 | Property Performance Standards Developed | ToR for Property Performance Standard developed | Target Not Achieved Effort focused on research and consultation to scope the project |
| 6 | Approved Custodian Asset Management Plan (C-AMP) | 2016/17 C-AMP approved by the Accounting Officer | 2015/16 C-AMP approved by the Accounting Officer Commence with review of Custodian Asset Management Plan for 2016/17 Completion of Custodian Asset Management Plan inputs for 16 small user departments 1 – 100 facilities per portfolio) | 2015/16 C-AMP approved by the Accounting Officer | Target Achieved |
| 7 | Approved Construction Implementation Programmes for 2015/16 | 1 DPW CWIP for 2015/16 approved by the Budget Committee by 30 June 2014 1PMIP for 2015/16 approved by the Infrastructure Budget Committee by 30 June 2014 | 1 DPW CWIP for 2015/16 approved by the Budget Committee 1PMIP for 2015/16 approved by the Infrastructure Budget Committee | 1 DPW CWIP completed for approval by the Budget Committee 1PMIP completed for approval by the Budget Committee | Target Achieved |
| 8 | Approved Construction Implementation Programmes 2016/17 | 1 DPW CWIP for 2016/17 approved by the Infrastructure Budget Committee by 30 June 2014 1PMIP for 2016/17 approved by the Infrastructure Budget Committee by 30 June 2014 | 1 DPW CWIP for 2016/17 approved by the Infrastructure Budget Committee 1 PMIP for 2016/17 approved by the Infrastructure Budget Committee | 1 DPW CWIP for 2016/17 completed for approval by the Infrastructure Budget Committee at its next meeting in July 2014. 1 PMIP for 2016/17 completed for approval by the Infrastructure Budget Committee at its next meeting in July 2014 | Target Partially Achieved The planning of the CWIP and PMIP for 2015/16 was protracted owing to a reduction in budget to be allocated to an increased number of projects in future years necessitating extensive project evaluation and prioritisation prior to seeking approval from the IBC |
| 10 | Number of properties released for Land Reform | 40 Properties approved by Minister for release for Land Reform purposes as identified by DRDLR: Cape Town - 29 Nelspruit – 1 Polokwane - 10 | 7 Properties approved by Minister for release for land reform purposes: Cape Town - 29 Nelspruit – 1 | 0 properties approved for release for Land Reform purposes | Target Not Achieved Release of land delayed owing to inadequate information required as well as extensive investigations with stakeholders to inform decisions. No new formal request were received from User Departments |
| 11 | Number of properties released for Human Settlements | 22 Properties approved by Minister for Human Settlement as identified by the Department of Human Settlement and Agency Pretoria – 2 Johannesburg – 5 Durban – 5 Nelspruit – 5 Cape Town - 5 | 4 Properties approved by the Minister for release for Human Settlement : Cape Town – 2 Pretoria - 2 | 0 properties approved for release for Human Settlement | Target Not Achieved Release of land delayed owing to inadequate information required as well as extensive investigations with stakeholders to inform decisions. No new formal request were received from User Departments |
| SUB-PROGRAMME: SPECIAL INTERVENTION PROJECTS |
| APP Reference No | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Quarter Performance 2014/15 | Reasons for Deviation on Q1 performance |
| 1 | Number of Schools Constructed | 36 Schools constructed as prioritised by the Department of Basic Education | 18 Schools Designed | 0 Schools Designed | Target Not Achieved Delays experienced as part of consultation in registering projects on the Works Capital System (WCS) |
| 3 | Number of Low Cost Bridges Constructed | 10 Low Cost Bridges Constructed as prioritised by DPW | 1 Low Cost Bridge Constructed | No Low Cost Bridge Constructed | Target Not Achieved The project has been on hold since the beginning of the financial year due to legal issues emanating from the appointment of a company to provide low cost bridges components. |

| SUB-PROGRAMME: PROJECTS AND PROFESSIONAL SERVICES |
| --- |
| APP Reference No | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Quarter Performance 2014/15 | Reasons for Deviation on Q1 performance |
| 1. | Number of planned construction projects completed as per approved construction implementation programmes | 542 construction projects (6A) Bloemfontein – 130 Cape Town - 80 Durban – 41 Johannesburg – 28 Head Office – 19 Kimberley – 43 Mmabatho – 21 Nelspruit – 39 Polokwane – 10 Port Elizabeth – 64 Pretoria – 24 Umtata - 43 | 136 Construction projects completed (Status 6A) | 27 construction projects completion (achieved status 6A on WCS) | Target Not Achieved Due to change of scopes and extension of contract period in other projects, only a few projects were completed |
| 5. | Number of user departments with approved Infrastructure Programme Implementation Plans (IPIPs) | 11 User departments with approved IPIPs (DoA, DAC, DCS, DoD, DoH, DHET, DHA, DoJ&CD, DoL, DRDLR, SAPS) | 2 User departments with approved IPIPs (DoA, DAC) | Zero (0) User departments with approved IPIPs (DoA, DAC) | Target Not Achieved Awating UAMPs by client departments to develop IPMP |
| 6. | Percentage of current projects with approved project scopes. | 50% current projects with approved projects scope. | 10% current projects with approved project scopes | 27% current projects with approved project scopes (147 projects with scopes) | Target Over-Achieved Concerted efforts by Projects & Professional Services in ensuring that all projects have projects scopes |
| 7. | Ratio of Project Managers to projects | 1: 10 Ratio of Project Mangers to projects | 1: 20 Ratio of Project Managers to Projects | 1:45 Ratio of Project Managers to Projects | Target Not Achieved The ratio issue has been identified and is being addressed through the review of the organisational structure |
| 8. | Percentage budget variance on each completed project | Less than 15% budget variance on each completed project | Less than 15% budget variance on each completed project | 29 projects completed with less than 15% budget variance | Target Achieved Concerted efforts to avoid variation orders of more than 15% budget variance |

| SUB-PROGRAMME: OPERATIONS MANAGEMENT – REGIONAL COORDINATION |
| --- |
| APP Reference No | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Quarter Performance 2014/15 | Reasons for Deviation on Q1 performance |
| 1 | Number of expired leases for leased accommodation | 0 expired leases for leased accommodation. | 0 expired leases for leased in accommodation | 449 expired leases(Backlog and current) for leased in accommodation | Target Not Achieved PMIS Integrity Clients not confirming funds, therefore resulting in unavailability of PI's |
| 2 | 100% of leases for 2014/15 signed within 30 days after finalisation of the open bid process. | 100% of leases for 2014/2015 signed within 30 days after finalisation of the open bid process. | 100% of lease signed within 30 days after finalisation of the open bid process for the period ending 30 June 2014 | 97% of leases signed within 30 days of finalization of the open bid process for the period ending 30 June 2014 | Target Achieved Lessors disputing clause of the contract |
| 3 | Percentage of day-to-day maintenance breakdowns addressed (calls closed) within agreed timeframes after logging of complaint | 100% Breakdowns completed within agreed timeframes after logging of complaint | 100% Breakdowns completed within agreed timeframes after logging of complaint | 8% Breakdowns completed within agreed timeframes after logging of complaint: | Target Not Achieved Calls not successfully closed because of dissatisfaction by user Departments on the services provided |
| 4 | Number of buildings retrofitted in terms of green building principles. | 300 Building retroffited with Energy efficiency installations. Johannesburg 10 Polokwane: 30 Mmabatho: 40 Cape Town: 100 Durban: 100 Bloemfontein: 20 | 75 Buildings retrofitted with Energy efficiency installations. Johannesburg: 10 Mmabatho: 40 Cape Town : 25 | No Buildings were retrofitted with Energy efficiency installations. Johannesburg: 0 Mmabatho: 0 Cape Town : 0 | Target Not Achieved Awaiting calibration of smart meters by the relevant department |
| 5 | Number of buildings audited for retrofitting in terms of green building principles | 19 Buildings retrofitted with water savings installations in: Cape Town: 2 Durban: 2 Johannesburg: 1 Kimberley: 2 Mmabatho: 2 Umtata: 2 Nelspruit: 2 Polokwane: 2 Pretoria: 4 | 1 Building retrofitted with water saving installations in: Pretoria: 1 | No Building was retrofitted with water saving installation in Pretoria | Target Not Achieved Challenges with ratio of work to be completed compared to the current capacity |
| 6 | Number of buildings audited for retrofitting in terms of green building principles. | 22 Buildings retrofitted with waste management installations in: Cape Town: 2 Durban: 2 Johannesburg: 4 Kimberley: 2 Mmabatho: 2 Umtata: 2 Nelspruit: 2 Polokwane: 2 Pretoria: 4 | 1 Building retrofitted with waste management installation in Pretoria 1. | No Building was retrofitted with waste management installation in Pretoria | Target Not Achieved Challenges with ratio of work to be completed compared to the current capacity |
| 7 | Number of outcomes based Facilities Management contracts signed for State owned building | 12 Pilot Outcomes - based Facilities Management contracts by the Project Manager Cape Town: 2 Durban: 1 Johannesburg: 1 Kimberley: 1 Mmabatho: 1 Umtata: 1 Nelspruit: 1 Polokwane: 1 Pretoria: 2 Bloemfontein: 1 | 5 Pilot Outcomes-based Facilities Management contracts signed by the Project Manager. Cape Town: 2 Durban: 1 Pretoria: 2 | 0 Pilot Outcomes-based Facilities Management contracts signed by the Project Manager. Cape Town: 0 Durban: 0 Pretoria: 0 | Target Not Achieved Budget Constraints |

| SUB-PROGRAMME: PRESTIGE MANAGEMENT |
| --- |
| APP Reference No | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Quarter Performance 2014/15 | Reasons for Deviation on Q1 performance |
| 1 | Response times for the provisioning of office and residential movable assets to Prestige clients (in line with the Ministerial Handbook) from date of receipt of request | Office and residential movable assets to Prestige clients (in line with the Ministerial Handbook) within 60 days from date of receipt of request | Office and residential movable assets to Prestige clients (in line with the Ministerial Handbook) within 60 days from date of receipt of request | Pretoria: 21 queries received and 2 requests were resolved within 60 days Cape Town Requests received prior to 1st April and others in May/June and only resolved in July August | Target Not Achieved Pretoria 19 of the 21 requests were not resolved due to unavailability of clients, indecision of clients Cape Town Request were received but finalized in July |
| 2 | Response times for resolution of Prestige maintenance issues after logging a complaint (within the mandate of DPW) | Maintenance issues (electric and plumbing) resolved within 5 days after logging a complaint | Maintenance issues (electric and plumbing) resolved within 5 days after logging a complaint | Cape Town 361 queries received and 344 Electricity & Plumbing queries resolved within 5 days (95%) Pretoria 74 queries received and 72 electrical & plumbing queries were resolved (97%) | Target Achieved Cape Town 17 of the 361 Could not be resolved due to complexities of the query Pretoria 2 of the 74 queries could not be resolved within the 5 days due to the complexity of the query |
|  |  | Maintenance issues (excluding electric and plumbing) resolved within 30 days after logging a complaint | Maintenance issues (excluding electric and plumbing) resolved within 30 days after logging a complaint | Cape Town 782 queries received and 701 Mechanical and other maintenance queries were resolved within 30 days (87%) Pretoria 123 of the 132 queries resolved in respect of mechanical and others were resolved within 5 days (93%) | Target Achieved Cape Town 81 of the 782 Could not be resolved due to inaccessibility to the Units, complexities of the queries and unavailability of clients Pretoria Of the 132 queries in respect of mechanical and others received 9 could not be resolved within 5 days due to complexities of the queries |

| SUB-PROGRAMME: INNER-CITY REGENERATION |
| --- |
| APP Reference NO | Performance Indicator | Planned Annual Target | Q1 - Planned Quarterly target | Quarter performance 2014/15 | Reasons for deviation on Q1 performance |
| 1 | Approved Government boulevard within the Tshwane Inner City Development Framework | 1. Redefine Government estate footprint within the identified boulevard 2. Salvokop Spatial Development Framework approved 3. Salvokop Township Proclaimed | Salvokop spatial framework completed | Salvokop spatial framework completed | Target Achieved |
| 2 | Number of accommodation solutions produced for project implementation for Tshwane | 5x accomodation solutions produced for (DSD, DHS, DHET, DoJ&CD, DHA) for project implementation | 1x Accommodation solution produced for DHET for project implementation in Tshwane | 1x Accommodation solution produced for DHET for project implementation in Tshwane | Target Achieved |
| 3 | Government precincts integrated with the spatial development frameworks of identified municipalities | Polokwane Government precinct integrated with municipal spatial development framework | Scope of Project deliverables and terms of reference | Scope of Project deliverables and terms of reference | Target Achieved |
| 4 | Number of accommodation solutions produced for project implementation in other metro and district municipalities (outside Tshwane) | Accommodation solutions produced for (DPW, SAPS and DoJ&CD) for project implementation in Polokwane | Scope of Project deliverables and terms of reference | Scope of Project deliverables and terms of reference | Target Achieved |
| 5 | DPW's infrastructure programme integrated with sector departments and rural municipal spatial development frameworks | DPW infrastructure plans integrated with 5 rural municipalities' Spatial Development Frameworks | Scope of Project deliverables and terms of reference | Scope of Project deliverables and terms of reference | Target Achieved |

| SUB-PROGRAMME: KEY ACCOUNTS MANAGEMENT |
| --- |
| APP Reference No | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Quarter Performance 2014/15 | Reasons for Deviation on Q1 performance |
| 1 | Completed Service Delivery Standards for immovable Asset lifecycle management towards compilation of a Client Value Proposition. | Update Service Delivery Standards. | Update Service Delivery Standard processes related to planning. | Updated Service Delivery Standard processes related to planning. | Target Achieved |
| 2 | Completed Client Survey Index for the Service delivery Improvement Plan towards compilation of Client Value Proposition. | Development of survey index researched and collated. | Information received from three Private Sector Property Companies on formulation of Client Surveys. | Information received from three Private Sector Property Companies on formulation of Client Surveys. | Target Achieved |
| 3 | Number of Service Level Agreements approved by identified User Departments | 30 Service Level Agreements approved by identified User Departments | 7 Service level agreements submitted to identified User Departments, i.e. DAC, COGTA, DBE, DHET, DHA, GCIS & NT | 7 Service level agreements submitted to identified User Departments, i.e. DAC, COGTA, DBE, DHET, DHA, GCIS & NT | Target Achieved |
| 4 | Number of User Departments UAMP templates completed to assist User Departments compiles long term Service Delivery Infrastructure Plans | 42 User Department's UAMP templates (1-12) for 2016-17 completed by 31 December 2014 | System information (i.e. project and leasing schedules) sent to 42 user departments for verification. | System information (i.e. project and leasing schedules) sent to 42 user departments for verification | Target Achieved |
| 5 | Approved 2015/2016 Capital Works Implementation Programmes (CWIP) for identified user departments | 9 CWIP's approved by user departments for financial year 2015/2016 by 30 June 2014 | 9 CWIP's approved by user departments for financial year 2015/2016 by 30 June 2014 | 2 CWIP's approved by user department (DOD & DRDLR) for financial year 2015/2016 by 30 June 2014. 7 drafts allocation completed for (SAPS,DOJ,DCS,DHA,DAC,DOL & DAFF) for financial year 2015/2016 | Target Partially Achieved 7 CWIP's not yet approved based on the draft allocations. The process has commenced to assist the User Departments to finalise the process |
| 6 | Approved 2016/2017 Capital Works Implementation Programmes (CWIP) for identified user departments | 9 CWIP's approved by user departments for financial year 2016/2017 by 30 June 2014 | 9 CWIP's approved by user departments for financial year 2016/2017 by 30 June 2014 | 2 CWIP's approved by user department (DOD & DRDLR) for financial year 2016/2017 by 30 June 2014. No drafts allocations completed for (SAPS,DOJ,DCS,DHA,DAC,DOL & DAFF) for financial year 2016/2017 | Target Not Achieved 7 CWIP's not approved by User Departments. The process The process has commenced to assist the User Departments to finalise the process |

.

Sub-Programme

Expanded Public Works Programme

Performance Based Incentive Allocations

| SUB-PROGRAMME: EXPANDED PUBLIC WORKS PROGRAMME |
| --- |
| No | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Quarter Performance 2014/15 | Reasons for Deviation on Q1 performance |
| 1 | Number of work opportunities created through the labour intensive approach aligned to the EPWP business plan | 1 045 000 Work opportunities created through. EPWP Phase 3 | 262 000 Work opportunities created through EPWP | 423 387 Work opportunities created through EPWP | Target Over-Achieved Improved data management process, with a decreased number of projects excluded from the report due to poor data quality |
| 2 | Percentage of disbursed performance based incentive allocations to eligible Public Bodies across all sectors. | 90% of performance based incentive allocations disbursed to eligible Public Bodies across all sectors. | 90% of performance based incentive allocations disbursed to eligible Public Bodies across all sectors. | 39% (integrated grant to provinces) 40% Social Sector 0% integrated grant to municipalities | Target Not Achieved Disbursement for provincial departments is done according to DORA payment schedule (15 May, 15 August and 15 November). Municipal disbursements to start in Q2. |
| 3 | Number of beneficiaries trained through the National Skills Fund. | 800 Beneficiaries trained through the National Skills Fund. | 200 Beneficiaries trained through the National Skills Fund. | 898 Beneficiaries trained through the National Skills Fund | Target Over-Achieved The overachievement in number of EPWP beneficiaries trained is due to improved procurement i.e. Decentralisation and NDPW Head Office procurement |
| 4 | Number of youth participating in the National Youth Services programme within DPW. | 3 500 Youth participating in the National Youth Service programme. | 500 Youth participating in the National Youth Service programme. | 360 Youth participating in the National Youth Service programme. | Target Partially Achieved Identified projects for 2014/15 for have not yet been implemented in PE, JHB,MM, and MP Regional offices |
| 6 | Number of work opportunities created in rural municipalities aligned to the EPWP business plan. | 600 000 Work opportunities created in rural municipalities. | 200 000 Work opportunities created in rural municipalities | 318 089 Work opportunities created in rural municipalities | Target Over-Achieved Improved data management process, with a decreased number of projects excluded from the report due to poor data quality |
| 7 | Number of EPWP work opportunities created by DPW | 20 000 Work opportunities created by DPW | 5 000 Work opportunities created by DPW | 1 006 Work opportunities created by DPW | Target Not Achieved Projects identified were not implemented as planned by Projects and Regional Coordination Branches |

.

Sub-Programme

Construction Industry Development Programme

Property Industry Development Programme

| SUB-PROGRAMME: CONSTRUCTION AND PROPERTY INDUSTRY POLICY REGULATION |
| --- |
|  | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Quarter Performance 2014/15 | Reasons for Deviation on Q1 performance |
| 1 | Participation in Parliamentary process towards enactment of Agrément South Africa (ASA) Bill | ASA Bill tabled in Parliament by 31 December 2014 and participated in the Parliamentary process towards enactment of ASA Bill | Draft ASA Bill finalized for submission to Cabinet | Draft ASA Bill finalised for submission to Cabinet | Target Achieved |
| 3 | Draft amendments to legislative framework for the Built Environment Professions (BEPs) developed | Draft amendments to BEP legislation submitted to Cabinet for approval to gazette for public comment by 31 March 2015 | Stakeholders consulted on draft BEP Policy | Stakeholders consulted on draft BEP Policy | Target Achieved |
| 4 | Revised draft Independent Development Trust (IDT) Bill developed | Revised draft IDT Bill developed by 31 March 2015 | IDT Business Case submitted to Joint Evaluation Committee (National Treasury and DPSA) for approval | Draft IDT Business Case developed Draft HR and Finance Models developed and are being refined for inclusion in the draft IDT Business Case | Target Not Achieved The refinement of both the HR and Finance Models led to delays in the finalisation of IDT Business Case, prior submission to the Joint Evaluation Committee for approval |
| 5 | Draft revised DPW White Papers developed | Draft 1 of revised White Papers on: (1) the Public Works function; and (2) the Construction Industry developed by 31 March 2015 | Situational analysis and consultation with Government and Industry stakeholders on White Papers: (1) Public Works towards the 21st Century (1997); and (2) Creating an Enabling Environment for Reconstruction, Growth and Development in the Construction Industry (1999) commenced | Situational analysis and consultation on DPW White Papers commenced. Received comments are currently being analysed. | Target Partially Achieved |
|  | Construction and Property Sector Codes aligned to the revised BBBEE Codes of Good Practice (2013) | Final revised Construction and Property Sector Codes submitted to the dti for gazetting in terms of Section 9(1) of the BBBEE Act, 2003 by 31 December 2014 | Draft revised Construction and Property Sector Codes gazetted for public comment | Shortlisting of a service provider completed for consideration by CSCC | Target Not Achieved Review of Construction Sector Codes is driven by the Construction Sector Charter Council. The process will commenced after shortlisting |
|  | Implementation of Revised Property Sector Codes |  |  | Participation in the Alignment of Property Sector Codes with amended BBBEE | Target Not Achieved Meeting scheduled between PSCC, DTI and DPW postponed several times. |

.

Sub-Programme

State Functions

| SUB-PROGRAMME: AUXILIARY AND ASSOCIATED SERVICES |
| --- |
|  | Performance Indicator | Planned Annual Target 2014/15 | Planned Quarter Target 2014/15 | Preliminary Quarter Performance 2014/15 | Reasons for Deviation on Q1 Preliminary performance |
| 1 | Number of Prestige Events supported with infrastructure related service | Infrastructure support provided for 13 planned Prestige Events. | Infrastructure support provided for 4 planned Prestige Events. | Infrastructure support provided for 9 planned Prestige Events | Target Over-achieved Infrastructure support is provided according to procurement plan. Some of the events have no specific dates. The over-achievement reflects the events that took place within the quarter but had no specific dates. |

# Text boxes

Strategic Objective

This programme serves to provide strategic leadership and support services, including for the accommodation needs and overall management of the Department of Public Works.  It is responsive to meet strategic objective 6 of the Department of Public Works and has links with all four other departmental programmes

PROGRAMME 1

MANAGEMENT

The management programme is large a support programme to the core business of the Department. Its purpose is to provide strategic leadership and support services, including the accommodation and overall management of the Department.

PROGRAMME 2

IMMOVABLE ASSET MANAGEMENT

Strategic Objective

This programme is the largest programme of the Department of Public Works and appropriates a large percentage of the departmental allocation budget. It provides and management government’s immovable property portfolio in support government social, economic, functional and political objectives.

This programme represents the core business of the Department. The purpose of the programme is to provide and manage Government’s immovable property portfolio in support of Government’s social, economic, functional and political objectives

PROGRAMME 3

EXPANDED PUBLIC WORKS PROGRAMME

Strategic Objective

This programme ensures the creation of work opportunities and the provision of training for unskilled, marginalised and unemployed people in South Africa by coordinating the implementation of EPWP

This programme represents the coordinating business of the Department with regard to public employment programmes. Its purpose is to provide work opportunities and income support to poor and unemployed people through the Labour-intensive delivery of public and community assets and services, thereby contributing to development

PROGRAMME 4

CONSTRUCTION AND PROPERTY INDUSTRY POLICY REGULATION

Strategic Objective

This programme promotes the growth and transformation of the construction and property industries, promote uniformity and best practice in construction and immovable asset management in the public sector.

This programme represents the core business of the Department, particularly around transforming the built environment.  The purpose of the programme is to promote the growth and transformation of the construction and property industries. Promote uniformity and best practice in construction and immovable asset management in the public sector.

PROGRAMME 5

AUXILIARY AND ASSOCIATED SERVICES

Strategic Objective

This programme provides for various services, including compensation for losses on the Government assisted housing scheme and assistance to organisations for the preservation of national memorials. Meet the protocol responsibilities for state functions.

This programme represents the core business of the Department, particularly around transforming the built environment.  Its purpose is to provide for various services, including compensation for losses on the Government assisted housing scheme and assistance to organisations for the preservation of national memorials. Meet the protocol responsibilities for State functions.