## Slide 1: 2015 SGB Elections Presentation to the Portfolio Committee on Basic Education 03 March 2015

## Slide 2: Outline
Aim
Background
Strategic significance
Preparations
Progress
Advocacy campaign
Management plan

## Slide 3: Purpose
To inform the Portfolio Committee on Basic Education about the 2015 SGB election preparations

## Slide 4: Background
Section 31 of the South African Schools Act, Act no. 84 of 1996 (SASA) as amended, stipulates that term of office of a member of a governing body other than a learner may not exceed three years.
The previous SGB elections were conducted in March 2012.
The term of office of the current governing bodies expire in March 2015.
The Minister of Basic Education has approved the holding of the 2015 Schools Governing Bodies Elections from 06-28 March 2015

## Slide 5: Background
Over 250 000 governors are elected every three years to serve in our public schools, united by a common purpose, to make education a real societal issue.
School Governing Body Elections will take place from 6 to 28 March 2015 around the country

## Slide 6: Strategic significance of the elections
The election of SGBs is one of the flagships of the education sector that has to be prioritised by all provinces in terms of planning, budget allocation and the allocation of both physical human resources.
Governing bodies have a strategic significance as identified by the National Development Plan (NDP) which calls for the alignment of the interests of all stakeholders to support the common goal of achieving good educational outcomes that are responsive to community needs and economic development.
The SGB elections contribute to the development of a strong sense of community ownership.
The performance of schools tends to improve when parents are actively involved and take an interest in the affairs of the school .

## Slide 7: PREPARATIONS AT NATIONAL LEVEL
Before every election, the Department of Basic Education launches a project to support provinces in the running of the elections by:
Developing National Guidelines for School Governing Body Elections;
Developing a training manual for electoral officers;
Coordinating and conducting an advocacy campaign to encourage all eligible voters to participate in the forthcoming elections;
Monitoring the election process to ensure that the elections are free and fair; and
Reporting on the outcomes of the election process

## Slide 8: PREPARATIONS AT PROVINCIAL LEVEL
Each province is expected to:
Promulgate provincial Regulations for each election period;
Appoint electoral officers;
Provide training to electoral officers;
Pair schools to swop electoral officers who are principals at school level;
Ensure that schools compile voters rolls;
Conduct advocacy campaign; and
Develop election schedule.

## Slide 9: PROGRESS
ACTIVITY | PROGRESS
Establishment of an SGB Elections Task Team (DBE, Provinces and NCF); | Done
Development of elections guidelines; | Done
Development of training manual for electoral officers | Done
Setting of election dates | Done
Appointment of Provincial Electoral Officers | Done
Appointment of District Electoral Officer | Done
Development of provincial management plans | Done

## Slide 10: Election planning process and progress
ACTIVITY | PROGRESS
Sending out of circulars to schools | Done
Advocacy campaigns | done
Training of electoral officers | done
Twinning of schools | done
Elections | Done
Monitoring | done
Compilation of final SGB report | done
ACTIVITY | PROGRESS
Sending out of circulars to schools | Done
Advocacy campaigns | Began 9 Oct
Training of electoral officers | November
Twinning of schools | January
Elections | March
Monitoring | See plan
Compilation of final SGB report | May 2015

## Slide 11
PROVINCE | STATE OF READINESS
Eastern Cape | Ready, has appointed officials, a management plan and a budget
Free State | Ready, has appointed officials, a management plan, regulations and a budget
Gauteng | Ready, has appointed officials, a management plan, regulations and a budget
Kwa-Zulu Natal | Ready, has appointed officials, a management plan, regulations and a budget
Limpopo | Ready, has appointed officials, a management plan, regulations but no budget
Mpumalanga | Ready, has appointed officials, a management plan, regulations and a budget
Northern Cape | Ready, has appointed officials, a management plan, regulations and a budget
North West | Ready, has appointed officials, a management plan, regulations and a budget
Western Cape | Ready, has appointed officials, a management plan, regulations and a budget

## Slide 12: Advocacy
It is crucial for the sector to run an advocacy campaign to:
raise awareness about the SGB elections;
communicate the benefits of participation in the elections;
explain the role of members of the community in the elections;
attract quality volunteers and
promote good governance in schools

## Slide 13: Target audience
Our target audience are as follows;
Parents;
Educators;
School administrators;
Non-government organisations;
Learners; and
SA citizens.

## Slide 14: Some Key Messages
Encourage all parents to support the elections by standing as candidates or by participating as voters in the SGB elections as voters.
Without parental and community support, education can never be a societal issue as envisaged by government.
Good governance in schools starts with you!
Get involved! Your school needs you!

## Slide 15: Progress
Public announcement of the election at the Social Protection, Communication and Human Development (SPCHD) cluster media briefing on 9 October 2014;
    Release of press statement to major media houses on 9 October 2013: Meeting of all Communicators in the education sector to plan for the advocacy campaign;
    Meeting of all Communicators of the SPCHD cluster to plan for the involvement in the SGB elections advocacy campaign
    Presentation of the election report to the SPCHD technical working committee on 4 November 2014;
    Meeting between governance officials and Provincial QLTC Coordinators to discuss the expected role of the QLTC in the advocacy and monitoring of the elections;
    Ministerial roadshows and Provincial launches; and
    Cabinet Presentation

## Slide 16: Tools and methods
Website & Intranet
Social Media
Opinion piece
Speeches
Press releases
Media interviews
Television
Radio
Print

## Slide 17: Management plan
ACTIVITY | RESPONSIBILITY | 
Presentation at SPCHD cluster meeting | Director-General | 19 November 2014
Minister’s meeting with NCF | Minister | 26 November 2014
Announcement at the ANA results release | Minister | 4 December
Minister’s planning meeting with District Directors | Mr Kojana | 4 & 5 December 2014
Announcement at the release of NSC results | Minister | January 2015
Appointment of School Electoral officers | District Directors | January 2015
Submission of election dates to districts | Schools | January 2015
Training of electoral officers | Provinces and districts | February 2015
Monitoring of provincial and district readiness | DBE and QLTC | February 2015
Provincial launch | Provinces | January 2015
Advocacy campaigns | DBE and provinces | January – March 2015
Finalisation of learner admissions | Schools | 30 January

## Slide 18: Management plan
ACTIVITY | RESPONSIBILITY | DATE
Provincial launch | Provinces | January 2015
Advocacy campaigns | DBE and provinces | January – March 2015
Finalisation of learner admissions | Schools | 30 January
Provincial launch | Provinces | January 2015
Advocacy campaigns | DBE and provinces | January – March 2015
Finalisation of learner admissions | Schools | 30 January
Provincial launch | Provinces | January 2015
Advocacy campaigns | DBE and provinces | January – March 2015
Finalisation of learner admissions | Schools | 30 January
Twinning of schools | District offices | 30 January
Submission of voters roll to districts | Schools | 7 February 2015
Submission of monitoring programme to DBE | Provinces | 14 February 2015

## Slide 19: Management plan
ACTIVITY | RESPONSIBILITY | DATE
Hand-over process between SGBs | Districts | Not later than a week after the elections
Orientation of newly elected SGBs | Provinces and districts | April 2015
Appeal process | Provinces | April 2015
Submission of election reports to DBE | provinces | May 2015
Finalisation of election report | DBE | June 2015

## Slide 20: Thank You