## Slide 1
04 MARCH 2015
PROGRESS REPORT ON FUNCTION SHIFT OF AET AND TVET CENTRES
to the
PORTFOLIO COMMITTEE ON HIGHER EDUCATION AND TRAINING
BOKONE BOPHIRIMA EDUCATION AND SPORT DEVELOPMENT DEPARTMENT

## Slide 2: OUTLINE OF THE PRESENTATION
Human Resources
Finance
Governance and Management
Legal
IT and Infrastructure
Assets and Liabilities

## Slide 3: PRESENTATION HRM OUTLINE
AET staff to be transferred
Physical Verification Process of AET staff.
Challenges of Physical Verification Process-AET staff.
TVET Colleges to be transferred
Progress on HR function shift activities

## Slide 4: AET STAFF TO BE TRANSFERRED
Nature of appointment of AET tutors: Abnormal and extra ordinary appointments can’t transfer programmatically.
CATEGORY OF STAFF | NUMBER OF STAFF
AET tutors staff | 1490
Public Service staff | 3
Office based educators | 26
TOTAL | 1519

## Slide 5: Verification process as per Circular No 8:
Verification forms were filled by the educators.
Contract forms for the year 2015 January up to 2015 December are completed by Educators.
Attachments required are also in place.
Forms that are in complete are labelled red for DHET officials to take note.
Files for each educator has been opened and all the necessary documents put inside.
These files are to be taken to DHET for new capturing as the type of appointment used cannot be transferred programmatically.

## Slide 6: Challenges Verification process as per Circular No 8:
Un/under qualified educators.
SACE certificates not valid.
No Std 10 certificate.
Foreigners not having all the required documents by Home Affairs.
There are 146 AET tutors that are not appointable as a result of not having the necessary required appointment documents

## Slide 7: TVET COLLEGES STAFF TO BE TRANSFERED
 | PERSAL PAID |  | COLLEGE PAID |  | TOTAL
TVET COLLEGE | LECTURERS | SUPPORT STAFF | LECTURERS | SUPPORT STAFF | 
TALETSO TVET | 30 | 40 | 117 | 88 | 275
ORBIT TVET | 35 | 18 | 173 | 153 | 379
VUSELELA TVET | 68 | 29 | 93 | 88 | 278
TOTAL |  |  |  |  | 932

## Slide 8: PROGRESS OF FUNCTION SHIFT ACTIVITIES
ACTIVITY: All Staff Update forms received and signed off
TVET | PROGRESS
ORBIT | Done, fully completed
VUSELELA | 95% achieved, done at 5 sites. Left with Corporate Centre
TALETSO | Done, fully completed

## Slide 9: PROGRESS OF FUNCTION SHIFT ACTIVITIES
ACTIVITY: Salary Disparities, discrepancies identified .
PROGRESS:
Pay progression: PED has done preliminary calculations and forwarded same to TVET colleges. A meeting to be held with HOD to conclude the matter.
Top-Ups: PED will not implement the top-ups due to the fact that the organisational structure of TVET colleges after FET Recapitalisation do not exist on Persal.
Incorrect Pay points: PED is currently relocation staff to their correct pay point as advised by TVET Colleges, to be finalised by 6 March 2015

## Slide 10: PROGRESS OF FUNCTION SHIFT ACTIVITIES
ACTIVITY: File and Leave Audit of PERSAL employees [using the file audit control sheet].
PROGRESS:
PED is currently auditing files of TVET Colleges Persal employees and expect to complete the process by the 14 March 2015.
SCC: SCC for permanent TVET staff cannot be registered due to fact that their number is less than 500. The transfer will be done manually on the 31 March 2015

## Slide 11: Programme 6: Adult Education and Training 2014/15 budget Allocation
R thousand | Adjusted Appropriation
Public Centres | 158 144
Subsidies to Private Schools | 
Professional Services | 13 588
Human Resource Development | 2 637
Subtotal | 174 369

## Slide 12: 2015/16 Medium Term Allocation
Source of Funding | 2015/16 Medium Term Allocation |  | 
 | 2015/16 | 2016117 | 2017/18
Education and Sports Development |  |  | 
Equitable Share | 12 187 918 | 13 021 344 | 13 672 411
Changes to the baseline |  |  | 
of Which: Function shift to National | -214 209 | -225 857 | -237 204
Administration | -21 258 | -22 638 | -23 809
Adult Education and Training | -184 322 | -194091 | -203 796
Auxilliary and Associated Servrces | -8 629 | -9 128 | -9 599
Further Education and Training College Sector Grant | -88 237 | -93 102 | -93 102

## Slide 13: GOVERNANCE AND MANAGEMENT
College Council are in place and well functioning.
Monitoring and report is done by both TVET directorate and the Strategic Panning directorate in the department.
Although AET Centre Governing bodies are in place and well constituted, but some are still struggling governance issues.
TVET and AET deliverables will be audited as part of the department’s Annual report for 2014/15.

## Slide 14: LEGAL ISSUES
Protocol Agreement between the national department and the provincial department was signed.
Protocol for office accommodation in respect of provincial staff is still outstanding, however affected officials will remain in their current offices pending resolution of this matter.

## Slide 15: IT AND INFRASTRUCTURE
Survey of IT Software used by TVET colleges was done and submitted to the TAU.
IT equipment and other related services for AET centers are currently provided by the department (i.e. Windows, PERSAl, BAS, etc).
With regards office space, AET and TVET directorates are still using departmental offices, pending identification of alternative office accommodation by DHET.

## Slide 16: ASSETS AND LIABILITIES
All Colleges have already submitted their Asset lists to DHET.
The AET directorate has also submitted the directorate asset lists as required.
Asset lists for the FET as well as AET centers have been finalised and only waiting for the HOD’s sign off. However soft copies were submitted.
Contracts for photocopy machines leased by AET and TVET directorates will be ceded to DHET.

## Slide 17
RE A LEBOGA