DEPARTMENTAL PROGRAMME PERFORMANCE INFORMATION FOR THE 2013/14 FINANCIAL YEAR

PROGRAMME 1: ADMINISTRATION

| STRATEGIC OBJECTIVE | PERFORMANCE INDICATOR | BASELINE | ANNUAL TARGET 2013/14 | PROGRESS/ ACHIEVEMENT AGAINST TARGET | COMMENTS (CHALLENGES /EXPLANATIONS ON VARIANCES ) | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- | --- |
| Adequate and appropriately skilled staff | Percentage vacancy rate | 11,9% (183/1532) | 12% | 13.7% (252/1834) vacancy rate | Delays and challenges in filling vacancies in specialised skills/ scientific fields | Facilitate filling on vacancies in 2014/15 and consider other targeted recruitment options such as headhunting where necessary |
|  | Percentage implementation of PMDS policy framework | 85% (1105/1299 first biannual assessment reports received) | 95% | 98 %implementation of PMDS policy framework ( 1264/1287 performance agreement/work plans and 1176/1210 biannual performance assessment report submitted ) | Planned target exceeded with a variance of 3%. A higher percentage of compliance (100%) would be ideal. This had no implications on resources |  |
|  | Number of HRD strategy initiatives implemented | 100 interns recruited 30 external bursaries issued 100% of WSP implemented (448 training interventions) | 3 Interventions (40 Interns recruited, 30 bursaries issued; 70% of WSP Implemented) | 3 Human Resource Development interventions facilitated (100 interns recruited; 38 external bursaries issued and 97%- 880/907- of WSP implemented ) | Planned target exceeded by a small margin. Exceeding of the target had no impact on resources earmarked for other priorities |  |
| Secure, harmonious, transformed and conducive working environment | Percentage compliance to the Employment Equity targets | Women 56% (757/1349) | 50% | 56%(891/1588) women | Planned target exceeded with a variance of 6%. An achievement higher than the planned target is ideal as it is in line with DEA transformation objectives. Exceeding the target had no implications on resources |  |
|  |  | Blacks 88% (1197/1349) | 90% | 90% (1437/1588) blacks |  |  |
|  |  | People with disabilities1,7% (22/1291) | 2% | 2.2 % (35/1588) people with disabilities | Planned target exceeded with a variance of 0.2%. An achievement higher than the planned target is ideal as it is in line with DEA transformation objectives. Exceeding the target had no implications on resources |  |
|  | Phased implementation of DEA New Head-Office Building PPP project. | Phase 1 Construction initiated | Phase II on construction of DEA Building project implemented | Phase II construction DEA New Head-Office Building project is currently in progress. There was a 22 days delay on construction work | Industrial strike and an extended rainy season in summer resulted in the delays on construction work | Increased working hours (overtime) to speed up construction and make up for part of the lost work days |
|  | Percentage implementation of security risk Assessment recommendations | Security threat and risk Assessment conducted | 100% implementation of security risk Assessment recommendations | 100% of the security risk assessment recommendations implemented (recommendations on 6 risk assessment findings implemented and responses provided where required) |  |  |
| Efficient and Effective Information Technology service | Percentage implementation of Funded Master Systems Plan (MSP) initiatives | Master System Plan approved | 100% implementation of 7 funded initiatives | 57% implementation of Master System Plan (MSP) projects (4 /7 MSP projects implemented as scheduled. There were delays on the other 3 projects) | 3 projects were delayed as a result of external dependencies on SITA and delays in construction of the DEA building | Delayed MSP projects to be prioritised in the first quarter of 2014/15 |
|  | Percentage availability of IT services | 96% availability of IT Services | 97% availability of IT Services | 98%availability of IT services achieved | Planned target exceeded with a variance of 1%. The exceeding of the planned target has no impact on resources earmarked for other priorities. |  |
| Equitable and sound corporate governance | Percentage compliance with statutory tabling and key government prescripts(PFMA, Treasury regulations and Guidelines) | 100% (DEA 2011/12Annual Report and 2012/13 Strategic Plan and Annual Performance Plan tabled on time) | 100% | 100% compliance (complied with key requirements and set timeframes – DEA ENE quarterly reports and interim financial statements submitted to National Treasury on time, Annual report for 2012/13 tabled, 1st and 2nd draft Strategic Plan and Annual Performance Plan submitted to National Treasury and Presidency, DEA 2018/19 Strategic and 2014/15 Annual Performance Plan approved and tabled in parliament, complied with all financial management and reporting requirements) |  |  |
|  | Unqualified audit report | 2011/12 Unqualiﬁed audit report | Unqualified Audit Report | 2012/13 unqualiﬁed audit report |  |  |
|  | Percentage expenditure | 2011/12 98% (R4,202billion budget R4,109billion spent) | 98% | 99.0% expenditure (5 200 307 / 5 206 842 billion of allocation spent by 31 May 2014) | Planned target exceeded with a variance of 1%. A higher expenditure (100%) would be an ideal achievement as it is in line the PFMA and it’s a good principle of financial management |  |
|  | Percentage of expenditure on affirmative procurement | 2011/12 65% (R605million out of R925 million) | 61% | 78% of expenditure on affirmative procurement(R 830 Million of R 1 073 Billion ) | Planned target exceeded with a variance of 18%. A higher expenditure than the planned target is ideal and in line with the DEA objective on BBBEE |  |
| Improved access to information | Number of media statements and speeches issued and number of opinion pieces published | 170 media statements and speeches issued | 120 media statements/ speeches issued | 169 media statement/speeches issued | Planned target exceeded with a variance of 41%. Exceeding the target had no impact on resources earmarked for other priorities |  |
|  |  | 3 opinion piece | 6 opinion pieces | 7 opinion pieces published | Planned target exceeded with a variance of 17%. Exceeding the target had no impact on resources earmarked for other priorities |  |
|  | Number of communication events including Ministerial Public Participation Programme (PPP) events | 10 events | 11 events | 17 events were held | Planned target exceeded with a variance of 54%. Exceeding the target had no impact on resources earmarked for other priorities. Savings were realised through planning events internally and adopting a centralised model |  |
|  | Number of publications produced | 4 stakeholder publications | 4 stakeholder publications | 4 stakeholder publications were produced and published |  |  |
|  | Number of website hits per annum | N/A | 320 000 website hits per annum | 495 050 website hits | Planned target exceeded with a variance of 55%. Exceeding the target had no impact on resources earmarked for other priorities |  |
| Improved sector education and awareness | Number of teachers trained in the Curriculum Assessment and Policy Statements (CAPS) | 80 teachers trained | 100 teachers trained per annum | 145 teachers trained | Planned target exceeded with a variance of 45%. Exceeding of the planned target had no impact on resources earmarked for other priorities |  |
|  | Number of environmental awareness campaigns conducted | 6 campaigns | 8 campaigns | 5 environmental awareness campaigns conducted Environment month campaign Rhino Anti-coaching campaign Green cars campaign National Marine week Greenest Municipality Campaign | Planned target missed by a variance of 37% (3 campaigns). Awareness campaign on coastal management not conducted due to the pending integrated coastal management bill. The other two campaigns were not conducted to manage impact of the ones conducted and avoid overload of campaigns in light of events. | Environmental awareness campaigns will continue in 2014/15 as planned |
|  | Number of officials undergoing/ completed environmental management training (EMI/IEM) | 142 officials participated in NEMA accredited EIA training | 144 officials undergoing NEMA accredited IEM training, | 172 officials undergone/ completed environmental management accredited NEMA EIA training in the 2013/14 financial year | Planned target exceeded with a variance of 19%.Exceeding the planned target had no impact on resources earmarked for other priorities. |  |
|  |  | 242 | 240 (EMI Training) | 262 underwent EMI training | Planned target exceeded with a variance of 9%. Exceeding the target had no impact on resources earmarked for other priorities |  |
|  | Number of accredited training person days created | 37 831 | 184 263 | 145 527of accredited training person days | Delays in commencement of some of the planned projects due to extended consultations with stakeholders (i.e. municipalities) and finalisation of owning entity agreement and other matters | The outstanding matters which led to the delays of the projects have since been addressed the projects will be implemented in 2014/15 |
| Effective knowledge and information management for the sector | Number of environmental knowledge and information management systems/tools developed and implemented / operational | OC System specification and design made and project plan determined Technical development ofsystem initiated. Reviewed MRVcapacities andinstruments in SouthAfrica EIAapplicationmonitoring systemoperational andreporting from2competentauthorities GIS intranet available and 3Environmentalsectorprojects andinitiatives supportedby GIS SAAQISPhase IIsystemarchitecturedeveloped | 4 systems developed / refined &operational Ocean & Coast information system Climate Change ResponseM&E System SAAQIS GIS | Ocean and Coasts System: A due diligence study had to be conducted first. An audit firm was commissioned to undertake the due diligence study conduct the study and a final report issued. The report recommended that the system be procured through SITA. A draft CC Response M&E System has been developed SAAQIS Phase II has been finalized. (Emissions inventory, AEL system) GIS intranet maintained and supported, seven updates done | Ocean and Coasts System : The required due diligence process resulted in the delay on the project | The draft terms of reference for the system have been developed and the project will continue in 2014/15 |
|  | Number of environmental knowledge and information management, monitoring and evaluation reports/ publications and response options produced | Annual State of the Oceans Report compiled Nine SAEO specialist chapters of the report integrated Identified and initiated accreditation process for Protected Areas Geographical dataset 15 peer-reviewed scientific publications (including theses) | 5 Environmental reports / publications: Annual State of the Oceans Report compiled South Africa environment Outlook (2nd SAEO) published 15 peer-reviewed scientific publications (including theses) per annum Protected Area indicator dataset improvement plan Quarterly Early Warning Management reports / Response options | Annual State of the Oceans Report produced South Africa environment Outlook (2nd SAEO) not published. In the process of incorporating the last set of comments receives on Energy, Human settlement and Land chapters. 17 Peer-reviewed Scientific Papers; 1 MSc Thesis and1 B-Tech Mini-Thesis submitted Quality Statement and the final Improvement Plan for the Protected Area indicator dataset in place. 2 Early Warning Management reports / Response options produced | Publishing of the SAEO report delayed due to delayed sign off by stakeholders on outstanding chapters . | Meetings convened with relevant stakeholders and currently finalising the outstanding chapters (Energy, Human settlement and Land chapters) |
| Effective Cooperative Governance and Local Government Support | Local government support strategy developed and implemented | IDP Review framework; Annual Analysis Reports and Local Government Cooperative Agreements | Local government support strategy and annual action plan finalised (100% of annual action plan implemented) | The Local Government Support Strategywas finalised and approved by MINMEC. 80% of the strategy implemented (33 of the planned 42 interventions | The Local Government Strategy was approved late in the 4th quarter and this did not provide sufficient time for implementation of all planned interventions/priorities | Implementation of interventions outlined in the plan will continue in 2014/15 |
|  | Sector conflict management tools and guidelines developed and implemented | NEMA Chapter 4 provisions for Conflict resolution and mediation within the sector | Environmental Conflict Management tools developed and implemented | Consultation process with the environment sector on the establishment of the panel of arbitrators and mediators facilitated. Recommendation for approval of panel of arbitrators and mediators submitted to Minister for consideration. | The recommended list of mediators and arbitrators to serve on the panel not yet approved | Sector conflict case will be processed and resolved through the conflict management upon finalisation and approval of the panel of list of mediators and arbitrators |
| Enhanced International governance, instruments and agreements supportive of SA environmental and sustainable development priorities | Number of South African positions on Chemical and Waste, Biodiversity, Sustainable Development (SD), African and bilateral South- South, South-North and International Environmental Governance (IEG) processes prepared, negotiated and reported | CBD, CPB,NagoyaProtocol, KLNsupplementary WHCCITES Ramsar CMS UNCCD | 30 Positions: 13 Bilateral /Pleurilateral (Africa,IBSA, S-S, S-N) 3 Multilateral (IEG) 8 Biodiversity relatedPositions (UNCCDCOP11 CRIC 11 andCST, World HeritageConvention CBDrelated inter-sessionalmeetings (SBSTTA-17;Article 8j WG8, andICNP3) AEWA: 9thStandingCommitteeMeeting; CMS: 41stStandingCommitteeMeeting; 46th April2013 meeting oftheRamsar Convention) 4 Positions on Chemical & Waste 2 Climate Changepositions for formalinternationalengagements(UNFCCC) | 52 positions prepared , approved and negotiated: 18 Bilateral meetings 9 Pleuri-lateral meetings 8 Multilateral Environmental Agreement meetings 10 x IEG & finance meetings 7 African Union and SADC meetings | Annual target exceeded with a variance of 73%. The exceeding of the planned target has no impact on resources earmarked for other priorities |  |
|  | The financial value of resources raised from multilateral and bilateral donors to support the departments SA and Africa’s programme | Total funds mobilised: US$ 24 060 000 | US$25 million from all sources | US$40.50 million funds mobilised | Planned target exceeded with a variance of 62%. Exceeding the planned target has no impact on resources earmarked for other priorities. Ability to mobilise more funds is ideal |  |
|  | Integrated development and management tools for TFCAs developed and implemented | International agreement establishing 6 TFCAs | MDTP 5 Year action planapproved | 5 year action plan approved by Bilateral Coordinating Committee |  |  |
|  | Mandatory international and national reports prepared and submitted within time frame (in terms of relevant legislation and/or international obligations/ conventions) | Scoping of information for the 2014BiennialUpdate Report(BUR) completed | Draft First Biennial Update Report developed | Draft BiennialUpdate Report finalised |  |  |
|  |  | Contractual agreements for the Third National Communication (TNC) in place | Scoping of information for the Third National Communication (TNC) reportcompiled | The planned target has been delayed due to pending approval process for funding from the Global Environmental Facility (GEF).Service providers will be appointed to draft the different chapters of the TNC after the funding arrangement with GEF have been finalised . Terms of reference for authors that will participate in the TNC compilation developed | Delays in the finalisation of the funding application by the Global Environmental Facility (GEF) | The department will enter into contracts directly with authors that are appointed through the bidding process. In this regard, Terms of reference for authors that will participate in the TNC compilation have been developed |
|  |  | Draft GHG inventory in place | 2000-2010 GHG inventory finalised | 2000-2010 GHG Inventory not finalised | Preparation of the GHG inventory has been completed but has not been finalized due to non-inclusion on the cabinet meeting agenda which took place in March 2014 | The work will be finalised in 2014/15 |
|  |  | 2011/12 NEMA Report tabled to Parliament | 2012/13 NEMA S26 report tabled to Parliament within timeframe | 2012/13 NEMA S26 report tabled to Parliament within timeframe. |  |  |

f

PROGRAMME 2: LEGAL AUTHORISATIONS COMPLIANCE AND ENFORCEMENT

| STRATEGIC OBJECTIVE | PERFORMANCE INDICATOR | BASELINE | ANNUAL TARGET 2013/14 | PROGRESS/ ACHIEVEMENT AGAINST TARGET | COMMENTS (CHALLENGES/EXPLANATIONS ON VARIANCES ) | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- | --- |
| Improved compliance with environmental legislation | Number of authorisations inspected | 51 | 125 | 135 authorisations were inspected | Planned target exceeded with a variance of 8%. Exceeding of the planned target had no impact on resources earmarked for other priorities as the work is done with existing human resources and in partnership with other stakeholders. |  |
|  | Percentage of administrative enforcement actions resulting incompliance | 67% (14/21) | 75% | Average of 72%compliance against administrativeenforcement actions issued on 24 projects monitored | Planned target missed by a variance of 3%. This has been as a result of delays by industry to fully implement enforcement directives | This indicator and annual target measure compliance by industry to assess the effectiveness of administrative enforcement actions provided for by legislation |
|  | Compliance and Enforcement Strategy forthe Environmental Management Inspectorate developed andimplemented | Service provider appointed and project initiated | Draft strategy developed | Draft strategy framework developed | The Project Steering Committee made a decision to extend Phase III of the project to allow for additional stakeholder consultation | The development and finalisation of the strategy will be prioritised in 2014/15 |
|  | Number of criminal investigations finalised and dockets handedover for prosecution | 17 | 24 per annum | 26 criminal investigationsfinalised and dockets handedover to the National Prosecuting Authority | Annual target exceeded with a variance of 8%. Exceeding of the planned target had no impact on resources earmarked for other priorities |  |
|  | Number of interventions implemented for safety andsecurity of wild life includingrhinoceros populations inSouth Africa | 3 compliance operations/ inspections organised and executed (Operation Worthy; Operation Hunt; Operation Compliance) | 5 interventions implemented for the Safety and Security of rhinoceros populations in SA: Agreementon areas ofcooperationwith Safety andSecurity Agencies Engaging regionaleconomiccommunities(RECs) and othergroupings Rhino fundingmechanism Facilitatereconstructionof border fencebetween SouthAfrica andMozambique Verification ofRhino Stockpile | 5 planned interventions have been implemented Agreementon areas ofcooperationwith Safety andSecurity Agencies Implementation plan for SSA developed and in negotiation with the SSA. Project framework developed and draft Joint Operation under development MOU with Mozambique finalised and scheduled for signing early in 2014/15 MOU and implementation with Lao negotiated and finalised MOU with Hong Kong tabled, initial negotiations undertaken in November 2013 Implementation plan with China SFA negotiated and awaiting finalisation Consultation with Private Rhino Owners and Law enforcement on engagement mechanism conducted in February 2014 Discussion with the Department of Home Affairs initiated and a draft MOU in place Engaging regional economic communities (RECs) and other groupings Meeting with SADC countries took place, and report compiled and distributed to participants for comment. Rhino funding mechanism Alternative Rhino funding options where considered and submitted to National Treasury for input and advice on a preferred option. Constructionof border fencebetween SouthAfrica andMozambique Implementation plan approved and construction of the fence has commenced Verification of Rhino Stockpile The rhino stockpile information has been analysed and recorded. Consultation undertaken with the Department of Justice and Constitutional Development, National Prosecuting Authority, and South African Police Service (HAWKS) relating to amnesty |  |  |
|  |  | 460 wildlife monitors trained and deployed | 1000 wildlifemonitorstrainedand deployed | 1 003 wildlife monitors trained and deployed with host employer across the country | Planned target exceeded with a variance of 0.30%. This is not significant and resources were diverted from other priorities |  |
| Potential negative impacts of all significant developments prevented or managed | Number of tools for mitigation of negative impacts of development developed and implemented | Draft Minimum requirements for biodiversity in landuse Planning and IEMrevised | Minimum requirements for biodiversity in land use Planning and IEM updated | Minimum requirements for biodiversity in Land Use Planning and IEM updated |  |  |

PROGRAMME 3: OCEANS AND COASTS

| STRATEGIC OBJECTIVE | PERFORMANCE INDICATOR | BASELINE | ANNUAL TARGET 2013/14 | PROGRESS/ ACHIEVEMENT AGAINST TARGET | COMMENTS (CHALLENGES/EXPLANATIONS ON VARIANCES ) | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- | --- |
| Ocean and coastal environment protected and conserved | Ocean management regime developed | Green Paper finalised | Ocean Management White Paper approved | Ocean Management White Paper approved by Cabinet |  |  |
|  | Strategies and plans for management of ocean and coastal environment developed and implemented | Southern Oceans and sub-Antarctic Islands management strategy approved | Southern Oceans and sub-Antarctic Islands management strategyimplementation plan developed | Implementation Plan for the Southern Oceans andSub-Antarctic Islands Management Strategy developed |  |  |
|  |  | Draft National Coastal Management Programme (NCMP) compiled | National Coastal Management Programme developed | National Coastal Management Programme developed and approved |  |  |
|  |  | 9 of 25 local oil pollution emergency response plans updated | 11 of 25 oil pollution emergency response plans updated | Wild Coast oil spill contingency plan and draft National oil spill contingency plan finalised. A cumulative total of 11 out of 25 oil spill contingency plans updated |  |  |
|  |  | 20 estuary management plans developed | Additional 5 Plans developed (25 estuary management plans cumulative ) | Additional five estuarine management plans developed ( Mngazi ; Mngazana ; Grootbrak ; Ntafufu; Thukela ; Nahoon) |  |  |
|  |  | Two (2) protected marine species with Management Plans / policies | 1 protected marine Species Management Plan finalised and one draft plan in place | African Penguin Biodiversity Management Plan approved for implementation andShark Biodiversity Management Plan approved by for public comments. |  |  |
|  | Number of NPOA initiatives implemented | NPOA forprotection ofthe marineenvironment fromLand-basedsources ofpollution Updated Recreational Water Quality Guidelines | Coastal waste water management policy developed | A National Guideline on Coastal Effluent Discharge approved by MINTECH |  |  |
| Ocean and coastal environment protected and conserved | Percentage increase of coastline under MPA’s with partial orfull protection | Partial protection =13.5 % (486/3600km) full protection = 9%(324/3600km) | Partial protection = 13.5% (486/3600km) full protection = 9.5% (324/3600km) | Addo Marine Protected Area expansion process facilitated and draft submission to gazette for public comment. The process had to be halted due to changes in legislation applicable to MPA management ((from Marine Living Resources Act to Protected Areas Act) | The process had to be halted due to changes in legislation applicable to MPA management (from Marine Living Resources Act to Protected Areas Act) | The process will be continued in 2014/15 in line with applicable legislation |
|  | Percentage increase of total area of EEZ under protection | Less than 1% of offshore environment protected | 2% of offshore environment protected | 2% (30,000/1500000 Km2) of EEZ protected (through the declaration of the Price Edward Islands) |  |  |
|  | Number of relief voyages toremotestations (Antarcticaand Islands)undertaken | 3 relief voyages undertaken | 3 relief voyages undertaken | 3 relief voyagesundertaken (SANAE , Marion Islands and Gough Islands ) |  |  |
| Strengthened national science programmes for integrated oceans and coastal management | Ocean and coastalresearch projects,surveys completedand monitoring projects undertaken | Draft Coastal research plan compiled | 1 Coastal research project completed and 1 monitoring project undertaken | Coastal Research Project Coastal research plan developed and consulted on at two National Forums and comments received. Monitoring Project Undertaken : Estuarine Monitoring Draft register of estuarine monitoring sites compiled DEA data report on estuary monitoring compiled, and communication undertaken with partners to make maximum use of information Results of Estuary Monitoring summarised for State of Oceans report |  |  |
|  |  | 2 surveys of representative orpriority habitats | 3 surveys of representative priority habitats (cumulative) | 4 surveys undertaken as follows : Survey undertaken of underwater habitat in the Table Mountain MPA. Survey completed for inshore priority habitat (Table Mountain MPA-West Coast) Additional surveys undertaken of the TMMPA Monitoring of the De Hoop MPA | Planned target exceeded with a variance of 25% (one additional survey). This is not significant and resources were not diverted from other priorities |  |
|  |  | Annual seabird population estimate for 12 species around SA 1 additional Southern Ocean species | Annual seabird population estimatefor 12 species around SA and1 additional Southern Ocean species | Annual population estimates for 12 seabirdspecies and1additional SouthernOcean species produced |  |  |
|  | Number of observation alplatforms contributing to an Ocean and Coastal Observation and Monitoring Network | 3 Observational platforms deployed and maintained | 4 Observational platforms deployed and maintained | 4 Observational platforms deployed as follows: Superbuoy at Slangkop Coastal radar at Slangkop Moorings and monitoring platforms deployed in Atlantic Ocean Buoy and Mooring array in Algoa Bay |  |  |
|  | Number of ecosystem process studies undertaken per annum | Integrated Ecosystem Project undertaken on the West Coast | 1 Ecosystem process study undertaken per annum | 2 Ecosystem process studies undertaken.(Integrated Ecosystem Project (IEP) on the West Coast; Ecosystem study on Agulhas Bank). | Planned target exceeded with a variance of one additional survey. Resources were not diverted from other priorities |  |

PROGRAMME 4: CLIMATE CHANGE AND AIR QUALITY

| STRATEGIC OBJECTIVE | PERFORMANCE INDICATOR | BASELINE | ANNUAL TARGET 2013/14 | PROGRESS/ ACHIEVEMENT AGAINST TARGET | COMMENTS (CHALLENGES/EXPLANATIONS ON VARIANCES ) | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- | --- |
| Climate change impacts effectively managed | Long Term Adaptation Scenarios for South Africa | Implementation plan developed and baseline research completed into three sectors: Water Agriculture Biodiversity andecosystems | LTAS reports finalized on Climate Scenarios, Impact Scenarios and Adaptation Options for 5 sectors (Biodiversity, Human Health; Water; Agriculture & Marine Fisheries) and 4 draft reports (Disaster Risk reduction; Human setlements (urban, coastal and rural). | LTAS Phase 1 reports on Climate Scenarios, Impact Scenarios and Adaptation Options for 5 sectors: Reports finalized ( Biodiversity, Human Health, Water, Agriculture, and Marine Fisheries) Phase 2 draft reports compiled for Disaster Risk Reduction and Human Settlements (Urban, Coastal, Rural), Sub regional Assessment , Integrated economic assessment and Scenario Planning |  |  |
|  | Number of sector adaptation plans aligned with the National Climate Change Response Policy | Scoping report to support policy alignment for climate change adaptation | Recommendations finalised for 4 sectors on mainstreaming climate change adaptation response measures into sector plans and policies : Water Agriculture and Commercial Forestry Biodiversity & Ecosystems Health | Final climate change policy alignment and review reports completed for the 4 planned sectors |  |  |
| A fair contribution to the global effort to stabilize GHG concentrations in theatmosphere facilitated | Number of sector mitigation potential and impact studies conducted | 2 Interventions: Mapping existingrelevant esearch,planning andmodelling process Carbon budget/tax interface | 4 studies conducted: Initial mitigationpotential analysisfor 5 sectorsfinalised Initial sectoralsocio-economicand environmentalimpact studiesfinalised for5 sectors National Sinks Assessment 2050 Pathways Calculator finalised | The 4planned studies were conducted: Initial mitigationpotential analysisfor 5 sectorsfinalised National SinksAssessment 2050 PathwaysCalculator finalised Initial sectoralsocio-economicand environmental impact studies for5 sectors |  |  |
|  | Number of Climate Change Response Policyinterventions implemented | Mitigationpotential andimpact studiesfor the energy,industry, transport,agriculture andforestry andwaste sectors Report thatoutlines criteriafor South Africa’sclimate changeresponse flagshipprogrammesanddescribes theexisting mitigationand adaptationprojects withinthe key dentifiedflagshipcategories | climate change response policy interventions: Draft report on Initial desired emission reduction outcomes for five sectors | A service provider has been appointed for development of Desired Emission Reduction (DERO). A concept/approach document has been developed | Delay in finalising the (MPA) led to the delay in finalising the DERO's process which should be informed by the MPA | The Initial Mitigation Potential analysis process finalised and the DEROs will developed in 2014/15 |
|  |  |  | Report on initial mix of policies, measures and instruments for 5sectors (including carbon budgets) | A service provider has been appointed to undertake the process of development of the Mix of Measures. The process has been initiated. An approach document finalised | Delays in approval of donor funding by GIZ | A service provider has been appointed and the project is underway |
|  |  |  | 1 Regulation tolist GHG as prioritypollutants underthe Air Quality Actto provide thelegal framework formitigation plans | The Notice and regulations approved by the Minister. The Notice and regulations were published in the Government Gazette for public comments. |  |  |
|  |  |  | Framework for implementation of 2 flagships, facilitated: Public Works Adaptation research | Framework for implementation of 2 flagships (Waste Management and Adaptation Research -Long Term Adaptation Scenarios) facilitated. The Public Works Flagship programme is in process. |  |  |
|  | Number of sector mitigation plans aligned with the National Climate Change Response Policy | Mainstreaming recommendations ontwo plans | Recommendations Mainstreaming of mitigation action in 5 sectoral policies and plans | RecommendationsMainstreaming ofmitigation action in 5 sectoral policies andplans finalised |  |  |
|  |  |  | Guideline for mitigation plans | A draft framework of the draft guideline for mitigation planning has been developed and circulated for comments | Finalisation of the guideline for mitigation plans is depended on the finalisation of the DEROs and the GHG regulations and the two processes has been delayed. | The guideline will be finalised in 2014/15 |
| Cleaner and healthy air | The National Air Quality Indicator (NAQI) | 1.145 | 1.140 | 0.939 | Planned target exceeded with low margin. A lower figure is an indication of improvement on the quality of air and is ideal achievement. Exceeding the target had no impact on resources earmarked for other priorities |  |
|  | Number of air quality monitoring stations reportingto SAAQIS | 63 | 90 (77 governmentowned) | 107 stations (84 government-owned) are currently reporting data on SAAQIS | Planned target exceeded with a variance of 18%. Exceeding of the planned target had no impact on resources earmarked for other priorities |  |
|  | AQA Regulatory Framework development implemented | 2 interventions: Air Quality Management Framework Reviewed Promulgationof Regulations/Notices Ambient,S21,Aviation, Dust, S23 | 2012 NationalFramework for AirQuality Managementpublished in thegazette | The 2012 National Framework for AirQuality Managementhas been published/promulgated |  |  |
|  |  |  | Draft EmissionsOffset Policy forAQM submitted forapproval | Draft Offset policy finalised and Cabinet memorandum submitted for approval |  |  |
|  |  |  | S23 – MobileAsphalt Declared asControlled Emitters | Final Declaration of Mobile Asphalt plant as controlled emitters has been published |  |  |
|  | Air Quality Management Tools developed and implemented | 2 Priority AreaAQMPs underimplementation (Vaaland Highveld) 1 Priority Area AQMPunder development(Waterberg-Bojanala) Vaal Triangle AQMPunder review | 2 Priority AreaAQMPsunder implementation (Highveld and VaalTriangle Airshed) | The annual plans for the two Air Quality Management Plans have been implemented (Vaal Triangle and Highveld Priority Areas) and annual implementation progress reports compiled |  |  |
|  |  |  | Waterberg Bojanala Priority Area AQMP Baseline Assessment finalised | Service provider appointed and the process of developing the plan is underway. A first draft baseline assessment has been compiled | Technical information required for establishing an emissions inventory and modelling future emissions required for the threat assessment. The required information and expertise is not available in-house. The project was outsourced and this led to delays | A service provide provider has since been appointed and work will continue in 2014/15 |
|  |  | 2 draft strategies developed (vehicle emissions and dense low-income) | Draft Vehicle EmissionsControl Strategycompiled andImplementation TaskTeam established | The Draft Vehicle Emissions Control Strategy has been compiled however the Implementation Task Team has not yet been established The department has signed letters which were forwarded to Directors-General of relevant departments requesting them to nominate members of the Strategy Implementation task team. | Poor response from the relevant departments to be involved in the task team | The work will be prioritised in the 1st quarter of 2014/15 |

PROGRAMME 5: BIODIVERSITY AND CONSERVATION

| STRATEGIC OBJECTIVE | PERFORMANCE INDICATOR | BASELINE | ANNUAL TARGET 2013/14 | PROGRESS/ ACHIEVEMENT AGAINST TARGET | COMMENTS (CHALLENGES/EXPLANATIONS ON VARIANCES ) | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- | --- |
| Biodiversity conserved, protected and threats mitigated | Percentage of land under conservation | 7.7% (9502088/ 121991200ha) | 8.2% (10112044/ 121991200ha) | Total size of conservation estate has been increased to 10.67% hectares (13 016 758/121 991 200 ha) of land of South Africa. | Planned target exceeded by 2.47. Resources were not diverted from other priorities |  |
|  | Percentage of all state managed protected areas with a METT score above 67% | Management effectiveness mean for SA’s state managed protected area is 49%; 21% of protected areas scored above 67% | 60% of state managed protected areas with a METT score of 68% | 84% area of protected areas adequately managed, with a METT score of 68% and above (68%-100%) |  |  |
|  | Number of legislative tools to ensure the protection of species and ecosystems developed and implemented | Draft regulations for the registration of Professional Hunters and Hunting Outfitters | Regulations for the registration of Professional Hunters Hunting Outfitters and trainers developed | Regulations for the registration of professional hunters, hunting outfitters and trainers developed |  |  |
|  |  | Draft Norms and standards for the translocation of large herbivores developed | Guidelines for the translocation of indigenous species in South Africa finalised | Translocation guidelines changed to Norms and Standards following a recommendation by MINTECH and Norms and Standards approved by MINMEC for implementation |  |  |
|  |  | Draft TOPS regulations published for public participation | TOPS regulations for terrestrial species finalised | TOPS Regulations developed incorporating public comments |  |  |
|  |  | Draft Norms and Standards for Biodiversity Management Plans for Ecosystems (BMP-Es) finalised | Norms and Standards for Biodiversity Management Plans for Ecosystems (BMP-Es) published for implementation | Norms and standards for BMP-Es published for implementation |  |  |
|  |  | Draft Norms and Standards for the management of protected areas | Norms and Standards for the management of protected areas completed | Norms and Standards developed and submitted to MINMEC for consideration and approval |  |  |
|  |  | MoA for proclamation of Vredefort Dome WHS and establishment of management authority | Regulations for the Vredefort Dome world heritage site developed | Regulations for the Vredefort Dome world heritage site have been developed. | Gazetting of the regulation has been delayed pending finalisation of matters raised by land owners | Consultation with the representatives of the land owners to resolve the disputed areas and finalise the process |
|  | Number of Ramsar sites with management plans developed and implemented in accordance with Ramsar Convention requirements | 15 Ramsar management plans developed and implemented | 5 Management plans for Ramsar sites evaluated Isimangaliso wetland Park, (St Lucia, Lake Sibaya, Turtle beaches/coral reefs of Tongaland, Kosi Bay) and Ndumo Game Reserve | 5 Management plans for Ramsar sites evaluated ( iSimangaliso IntegratedManagement Plan-Incorporating - St Lucia; Lake Sibaya ; Kosi Bay; Turtle beaches/ coral reefs of Tongaland evaluated and Ndumo Management plan) |  |  |
|  | National strategy forinvasive Allien Speciesdeveloped andimplemented | Riskassessmentframeworkand guidelinefor evaluationdeveloped Draft guidelinefor monitoringand controlplansdeveloped | National strategy approved and priority interventionsimplemented | National Strategy developed and submitted approval | Delays in finalizing terms of reference due to prolonged consultation with stakeholders. Approval of strategy delayed and implementation of key interventions could not be facilitated | All the issues were resolved and Strategy was developed by the end of March, however, could not be implemented |
| Fair access and equitable sharing of benefit from biological resources promoted | Biodiversity Sector transformationframework developedand implemented | Wildlife Sector transformation negotiations initiatedthrough the wildlifeforum platform | Biodiversity sub-sector analysis undertaken and biodiversity sector transformation frameworkinitiated | Biodiversity sub-sector analysis for biodiversity sector transformation framework report developed |  |  |
|  | Number ofsustainable natural resource based projects implemented | Operationalisation of Aweleni Ecotourism Lodge facilitated. Ecotourism development programme for TFCAsin place | One project from TFCA Catalogue | One project implemented (Polentswa Lodge in Kgalagadi Transfrontier Park) |  |  |

PROGRAMME 6: ENVIRONMENTAL PROGRAMMES

| STRATEGIC OBJECTIVE | PERFORMANCE INDICATOR | BASELINE | ANNUAL TARGET 2013/14 | PROGRESS/ ACHIEVEMENT AGAINST TARGET | COMMENTS (CHALLENGES/EXPLANATIONS ON VARIANCES ) | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- | --- |
| Improved socio-economic benefits within theenvironmental sector | Number of Full Time Equivalents (FTEs) created | 23 136 | 34 019 | 25 552 Full Time Equivalents (FTEs) created | Delays in commencing of projects have resulted in the target not being achieved. Some projects were delaying due to extended consultation and finalisation of key requirements ( i.e. signing of owner entity agreements) | Engaging internally to ensure that there is alignment between planning, implementation and reporting within the financial year and also the possibility of reviewing contracting models for some of the programmes. |
|  | Number of Work Opportunities created | 73 678 (Women - 49%; Youth- 63% & People withDisabilities - 3%) | 65 494 (Women - 55%; Youth - 55%& People with Disabilities- 2%) | 80 658 (53% women) | Delays in commencement of a number of planned projects | Prioritise individuals from designated groups in the new projects |
|  |  |  |  | 80 658 (1.73% people with disabilities) |  |  |
|  |  |  |  | 80 658 (62% youth) | Planned target exceeded with a variance of 7%. A higher percentage of youth is in line with objective of the EPWP |  |
|  |  | N/A | 300 Jobs opportunities created | 359 Jobs Created | Planned target exceeded with a variance of 19%. Exceeding of the planned target had no impact on resources earmarked for other priorities |  |
|  | Number of youths Benefitting from the Youth Environmental Service | 100 | 900 | 1 353 | Planned target exceeded with a variance of 33%. Resources were not diverted from other priorities |  |
|  | Number of overnight visitor and staff accommodation units established and /or renovated | 288 | 139 | 137 number of overnight visitor and staff accommodation units (92 established and 45 renovated) | Planned target missed by a variance of 1%. The units from the Sterkfontein project in Free State could not be finished due to delays from the provincial public works in certifying the work | The issue was resolved the 4th quarter with the Free State Provincial Department (DETEA)construction has resumed and the outstanding units will be completed in the 1st quarter of 2014/15. |
| Ecosystem services restored and maintained | Number of wetlands under rehabilitation | 93 | 110 | 122 | Planned target exceeded by a variance of 11%. Resources were not diverted from other priorities |  |
|  | Number of hectares of invasive alien plants treated/ cleared | 532 701 | 863 067 | 945 276 number of hectares of invasive alien plants treated/cleared | Planned target exceeded by a variance of 10%. Resources were not diverted from other priorities |  |
|  | Area (ha) of land restored and rehabilitated | 36 925 | 28 428 | 46 181 area (ha) of land restored and rehabilitated | Planned target exceeded by a variance of 62%. Resources were not diverted from other priorities |  |
|  | Number of kilometres of accessible coastline cleaned | 2 682 | 2 113 | 2 174 number of kilometres of accessible coastline cleaned | Planned target exceeded by a variance of 3%. Resources were not diverted from other priorities |  |
|  | Number of fires suppressed | 1 940 | 2 000 | 1885 | Planned target missed by a variance of 6%. Fewer fires than the planned target were reported and this is an ideal occurrence. The annual target estimated based on historical data | The indicator has been revised in the 2014/15 annual performance plan to measure a percentage of fires successfully suppressed out of the total reported fires |
| Enhanced contribution of theenvironmental sector towards Sustainable development and transition to a greeneconomy | Number of sustainable development, policies, plans& strategiesresearched, formulated, aligned, coordinated, promoted and reviewed | 5 researched - GreenEconomy Modeling;4 sectorstrategies &plans | 4 researched (NSSD2, green economy; sustainable consumption and production framework; green economyre search evidence strategy) | 4 policies researched (Sustainable Development research strategy & green economy research strategy; green economy framework; sustainable consumption production framework) |  |  |
|  |  | 1 formulated -EnvironmentalSectorResearch,Development &EvidenceFramework(RD&E) | 2 formulated (green economypolicy; sustainabledevelopmentresearch-evidencestrategy) | 3 policies formulated: Draft Green Economy policy framework SD RD&E Strategy Green Economy RD&E | Planned target exceeded with a variance of 1 additional policy This is not significant and resources were not diverted from other priorities |  |
|  |  | 1 aligned –NationalSustainableDevelopment StrategicPlan (NSSD1) withClimate Flagships | 2 aligned (NSSD/NCCRP/SCP; & NSSD/NGP/NDP) | NSSD1 and NCCRP/NCP reports aligned. NSSD1, NGP & NDP policy alignment report is finalised |  |  |
|  |  | Coordinated – GreenFundoperationalpolicies | 5 coordinatedand supported(climate 3rd nationalcommunication,biodiversity, waste,oceans & coast, airquality) | Coordination and support provided for the development of the 5 thematic strategies as follows : Attendance of Biodiversity science policy seminar compliance and enforcement on their RDE theme strategy Engaged with DST on the development of the Waste HCD roadmap –elements which will be incorporated in to the green economy research strategy Presented the NSSD and Science-policy framework at the biodiversity CDB workshop Provided input to the DST on the Draft discussion document on DST-DEA annual implementation plan. Engaged with biodiversity and waste themes Attended biodiversity working group 1 Engagements made with Water Research Commission this included presenting the SD RDE strategy Presentation made at the AISA on environment sector RD&E strategies Provided initial engagement and comments to the SABS on the approach to the sustainable procurement ISO standard initiative to setup national structures. |  |  |
|  |  | 2 promoted –sciencepolicy; NSSD events | 2 Promoted throughforums (RD&E;NSSD) | RD& E and NSSD policies were promoted through the CSIR and DST meetings. Supported NSSD related meetings: Participated at Working Groups (as part of NSSD associated structures) Attended the local government support strategy workshop (as part of NSSD associated structures) Presented the NSSD during the Local Government Workshop on Mainstreaming Biodiversity, Informing South Africa’s National Development Plan and New Generation National Biodiversity Strategy and Action Plan Coordinated and presented at the DEA/CSIR MOU green economy technical session |  |  |
|  |  |  | NSSD 1 Review reportdraft | Draft NSSD 1 M&E Report in place |  |  |
|  | Percentage of allocated resources committed to implementation of catalysed Green Economy (GE) initiatives | Green Fundbudgetallocation for2012/13& 2013/14. 11 Green legacyimplementationprojects 9 Green Fundimplementationprojects | 100% of allocated funds committed to projects | 99% of allocated funds (about R790 million of the R800 million) committed to 34 Projects inclusive of 16 research and development initiatives | Planned target missed by a marginal variance | The outstanding amounts will be committed to approved projects |
|  | Number of instruments of the IEM [Regulatory and Authorisation] system (tools, standards, guidelines, regulations, best practice etc.) evaluated, adjusted, [and/or] developed and/ or streamlined [interventions implemented] | Amendments to theEIA regulations draftedfor discussion Draft standard forthe 4x4 industrydeveloped EIAMS Second draftTheme reports. Draft EMF strategyavailable, 2 national EMFsfinalised 6 provincial EMFsapproved by theMinister and MECs andconcurrence lettersto initiate three EMFssigned by the Minister Draft Portsguidelineavailable, Aquaculture guidelinegazetted for comment Social Infrastructureguideline initiated Draft matrix forinterventionsfor streamliningenvironmentalauthorisation forSIP IPAP | 2 strategies drafted (EIAMS and EMF strategy) | Draft Environmental Impact Assessment Management Strategy developed. Draft EMF strategy approved | The Project Steering Committee requested that thestrategy be further refined based on comments received. Delay in process as a result of task team established to consider comments and amend strategy | Task team established to consider comments and compile second draft strategy. Business plan and budget for 2014/2015 accordingly drafted |
|  |  |  | 2 legal instrumentsreviewed (EIAregulations and EMFregulations) | EIA regulations amendments considered/identified and consultation undertaken with Provincial authorities and Dept. of Minerals Resources The outcome of a legal opinion requested indicated that the s to are required, indicated that there were no amendments required on the EMF regulations at this stage |  |  |
|  |  |  | 2 standards drafted (standards for storageof dangerous goodsand standards for the4x4 industry) | Standards on storage of dangerous goods drafted and consulted with industry. Standards for 4X4 industry under consideration by industry for finalisation |  |  |
|  |  |  | 2 EMFs developed(Vredefort EMFfinalisedand MapungubweEMF final status quodeveloped) | Vredefort EMF approved for gazetting Draft status quo report for Mapungubwe EMF produced and circulated for comments Desired state report for Mapungubwe EMF produced and circulated for comments | Delayed due to the request to extend the scope and time frame for the project | Mapungubwe EMF to be finalised in 2014/15 |
|  |  |  | 3 Sector guidelinesgazetted (Ports,Aquaculture andsocialinfastructure guidelines) | Aquaculture guideline finalized and gazetted for implementation Ports guidelines finalised and will not be gazetted. Request made by Ports authority who will use the guideline for the guideline not to be gazetted. Social infrastructure guidelinesfinalised and will be gazettedfor public comments | Social Infrastructure Guidelines not approved yet due to postponed MINMEC. | A request to gazette the social infrastructure guidelines submitted |
|  |  |  | Environmentalmanagementinterventions for SIPI - 18IPAP priorities identifiedand three draftinterventions in place | Three environmental management interventions for SIP 1-18 identified (SEA’s interventions – Solar, Wind and Transmissions) and in progress Renewable Energy Guidelines were identified as IPAP priority in this financial year. Matrix for the environmental authorisation interventions for the 18 SIP’s finalized and loaded on EDMS for easy access to DEA managers. Draft interim SEA results on SIP 8 initiated and presented to PSC and ER. The resource maps are available and the study areas identified TOR for SIP 10 approved and funds secured TOR approved and funds secured. Draft TORs for SIP 16 circulated for internal comment Draft scenario for SIP 8 SEA finalised SIP 1 authorisation plan implemented by IEA Final draft TORs for railway corridors drafted for comment |  |  |

PROGRAMME 7: CHEMICALS AND WASTE MANAGEMENT

| STRATEGIC OBJECTIVE | PERFORMANCE INDICATOR | BASELINE | ANNUAL TARGET 2013/14 | PROGRESS/ ACHIEVEMENT AGAINST TARGET | COMMENTS (CHALLENGES/EXPLANATIONS ON VARIANCES ) | CORRECTIVE MEASURES |
| --- | --- | --- | --- | --- | --- | --- |
| Less waste better managed | Wastemanagement instruments developed and implemented | Waste act inPlace SAWISregulations | Waste Classificationand Management RegulationsPromulgated | Waste classification and management regulations promulgated |  |  |
|  |  |  | HCRW ManagementRegulations and NoncombustionEfficacyStandard gazetted | Draft HCRW ManagementRegulations and NoncombustionEfficacyStandard developed. Submission to request gazetting and letters to the Dept. of Trade, Industry , National Council of Provinces and National Assembly submitted to Legal Services for vetting | Extended consultation process resulted in delay in finalising and gazetting the regulations and standards as planned | The regulations and standards will be finalised and gazetted in 2014/15 |
|  |  |  | Norms and Standards for the operation of blending platforms developed | Stakeholder inception workshop and International literature review conducted. Site visit questionnaire and Database of list of licensed facilities developed | The project was delayed by a further consultation process to ensure alignment with sector requirements | Meeting held with service provider to discuss the scope of the project.Service provider to submit a revised project plan .The project to be prioritised in 2014/15 |
|  |  |  | Norms and standardsfor composting organicwaste gazetted | Norms and standardsfor composting organicwaste developed and submitted to Minister for gazetting | Delays in consultation process due to time required and availability of stakeholders | Norms and standards to be finalised and gazetted in the 1st quarter of 2014/15 |
|  |  |  | Norms and standardsfor remediation ofcontaminated land andsoil quality gazetted | Norms and standardsfor remediation ofcontaminated land andsoil quality approved by Minister | The Norms and Standards were approved late in the 4th quarter and will be gazetted in the 1st quarter of 2014/15 | Norms and standards to be gazetted in the 1st quarter of 2014/15 |
|  |  |  | Regulations for industryWaste Managementplans developed | Consultation facilitated with e-waste and packaging sector to prioritise plans, engage on the legislative options and explain the rationale of the new recycling economy and the role of Industry Waste Management Plans. Draft concept document developed and submitted for approval | Delays in consultation process due to time required and availability of stakeholders | The work will be continued in 2014/15 Within the context of Waste Act amendments |
|  |  |  | Amendment to theWaste ManagementActivity List finalised | The Waste Management Activity List was published for implementation on 29 November 2013 |  |  |
|  |  |  | SAWIS implemented nationally | SAWIS has been implementednationally Registered 49 waste facilities on SAWIS in Q4 (LP, FS, EC, MP, NC, NW & KZN). 72 waste facilities imported from IPWIS (WC) 7 Capacity building for waste data collection and reporting conducted in the following provinces: MP(1) and KZ(4) and FS(2). Waste data submitted to SAWIS processed within 5 days SAWIS implementation monitored report available |  |  |
|  | Percentage decrease in waste going to landfill sites | Waste tyre industry waste management plans under review | Targets for waste tyresestablished | Waste tyres targets set as follows: 2014 - 59000 2015 - 90000 2016 - 120000 2017-175000 |  |  |
|  | Number of unlicensed waste disposal sites authorised per annum | 341 surveyed unlicensed waste disposal sites | 15 | 84 Basic Assessment Reports (BAR) finalised and submitted to relevant provinces (WC, LP, and NC &EC) for the issuing of decisions | Delays in the appointment of service providers and the confirmation of the availability of funding with regard to licensing the unlicensed site DWA had to conduct site visits in all sites prior the issuance of RODs. This will delay the issuance of licenses by provinces | DWA has been engaged and draft addendum to the existing MOU has been sent to DWA for comments before signing by both DGs of DWA and DEA |
|  | Number of buy-backcentres established | 6 | 15 | 10 buy-back centres established | Unforeseen delays in finalising consultations with municipalities resulted in some projects being approved later than planned (September 2013).There were delays in finalising the process with City of Tshwane where 3 centres were to be established. 2 buy-buck centres will be established in Vryburg and in Bushbuckridge | The outstanding matters have been finalised and the remaining buy back centres will be established in 2014/15 |
| Impacts of chemicals better managed | Number of chemical management instruments developed | Multilateral environmental agreements | Methyl bromide phaseout plan finalised | The Methyl bromide plan has been finalized and continually been implemented through the processing of permit applications |  |  |
|  |  |  | PCB inventory formunicipality developed | Final Report for PCB Inventory available |  |  |
|  |  |  | Regulations for OzoneDepleting Substancespromulgated | Regulations were submitted to the Minister for approval to publish for implementation | Delays experienced in finalising regulations for public comment | Regulations to be published in the 1st quarter of 2014/15 |