| Strategic Objective 1 : |
| --- |
| To ensure the creation and implementation of an enabling legislative framework that promotes the attainment of gender equality |
| Planned Outcome : Continuous improvements in the legislation policies and practices to advance gender equality (50/50) |
| Sub-strategies | Performance Indicator | Annual target | Performance Plan and Progress for 1 July 2014 to 31 September 2014 | Performance Plan and Progress for 1 October 2014 to 31 December 2014 |
|  |  |  | Quarter Two | Progress | Corrective Actions | Quarter Three | Progress | Variance | Corrective Actions |
| 1. To monitor equality and evaluate the promotion of gender equality and relevant policies an practices of the public and private sector and report parliament | One amendment setting as re-defined gender equality target and timeframes in 2014/2015 financial year | 9 consultations conducted | Conduct follow-up consultations with stakeholders on EE in three provinces | Mpumalanga has conducted a follow-up hearing. Other provinces have not implemented yet because dates with stakeholders could not be secured in this quarter | Provinces have secured dates for October and November | Conduct follow-up consultations with stakeholders on EE in three provinces | Follow-up hearings were conducted in LIM, GP, WC, NC, EC, NW and FS | No variance | No corrective action |
|  | Number of Gender Transformation Hearings at/on Tertiary Institutions | 1 Investigation report on Gender Transformation in tertiary | 1 Gender Transformation investigative hearing | Information from UNISA has been received and analysed. Still awaiting information from UNIVEN. Hearing could not take place | Hearing has been scheduled for November 2014 | 1 Gender Transformation investigative hearing | Gender transformation hearing was conducted with UNIVEN and UNISA. A report gas been drafted but not finalised | No variance | No corrective action |
|  | Number of Gender Transformation Hearings with targeted government departments on women empowerment and gender equality | 1 Investigation report on gender transformation on women empowerment and gender equality | 1 Gender Transformation investigative hearing | DHE was identified. Information was requested. Information has been analysed. Hearing has not taken place. | Hearing will take place in November 2014 | Drafting of investigative report | Gender transformation with DHET was held. A report has been drafted but not finalised | No variance | No corrective action |
|  | Number of National Gender Barometer Reports on the Status of Gender Policies and Practices in the Public and Private sector | 1 Gender barometer report | Administer the gender barometer tool | All briefing sessions have been conducted with 9 x Provincial Depts. & 2 x National Depts. Fieldwork/data collection currently under way with selected national & Provincial Depts. It should be noted that the Commission withdrew SABC form the list of institutions that that will be assesses | No corrective | Compile and analyse data collected | Data collection was compiled and analysis completed. A draft report has been completed and submitted to the HOD for review and editing | No variance | No corrective action |
| 2. To initiate and/or participate in the review of the legislative framework in all spheres of government that impact on gender equality | Number of submissions made for legislative and policy enhancement of the gender equality framework | 12 submissions per year | 3 submissions | 7 submissions | No corrective | 3 submissions | 2 submissions drafted | In previous quarters the target was exceeded by 4 submissions | Submissions for the next quarter will be corrected and reported according to plan |
| 3. To conduct performance assessments of political parties and the public and private sectors on the effective implementation of gender equality legislation policies and practices | Number of assessment reports on women representation in political parties | 1 Assessment report on women's representation in political parties | Analyse and compile elections monitoring report | First Draft report completed. Report is currently being reviewed and additional data analysis is required for finalisation of the report | Report will be finalised in the next quarter | Finalise report | Report has been finalised, copy edited and is currently being prepared for layout, design & printing | No variance | No corrective action |
|  | An assessment report prepared and tabled to parliament on the effective functioning of the GBV Council | 1Assessment report on the effective functioning of GBV Council | Implement monitoring tool | Fieldwork for monitoring of the GBV Council under way; on-going interviews with key stakeholders | No corrective action | Compile and analyse data collected | Not much fieldwork was carried out due to the uncertain formal status of the GBV Council during this financial year. Also the Council has not carried out any activities during this year. | No variance | No corrective action |
| 4. To evaluate the implementation and effectiveness of national justice facilities in addressing gender discrimination. | No of evaluation reports on courts (Equality Domestic Violence, Sexual Offences and Maintenance) | 1 Monitoring report | Monitoring and evaluation of maintenance courts in provinces | Monitoring and evaluation of maintenance courts have taken place in all provinces | No Corrective Action | Monitoring and evaluation of Domestic violence and Sexual Offences courts in provinces | As guided by concept paper and questionnaires, court monitoring has taken place in all provinces | No variance | No corrective action |
| 5. To convene policy dialogues with relevant policy makers at national and provincial level on recommendations to promote gender equality contained in research reports and research activities | Number of Dialogues with policy makers convened (based on research studies conducted in previous financial year) | 18 policy dialogues conducted | 6 policy dialogues conducted | Policy Dialogues series under way – First Policy Dialogue conducted in Western Cape on 23rd Sept. 2014. 5 Policy dialogues still need to be conducted | Policy dialogues will take place in the next quarter | 6 policy dialogues conducted | 9 policy dialogues have been conducted | No variance | No corrective action |

| Strategic Objective No. 2 |
| --- |
| To protect and promote gender equality by engaging with relevant stakeholders to educate and raise awareness on issues of gender equality challenge patriarchal perceptions and stereotypes and take action against infringements of gender rights through the implementation of appropriate redress. |
| Planned Outcome: A society educated in constitutional rights to gender equality that demonstrates the transformative behaviour of the obligation to respect and uphold gender equality. To further ensure effective and efficient application of social justice for victims of gender violations. |
| Sub-strategies | Performance Indicator | Annual target | Performance Plan and Progress for 1 July 2014 to 31 September 2014 | Performance Plan and Progress for 1 October 2014 to 31 December 2014 |
|  |  |  | Quarter Two | Progress | Corrective Actions | Quarter Three | Progress | Variance | Corrective Actions |
| 1. To timeously investigate complaints of violations of gender rights and identify appropriate redress | 720 of complaints received attended to in terms of the CGE complaints manual (as prescribed by the complaints manual) | 720 complaints attended to in terms of CGE Complaints manual | 180 of complaints and attended to in terms of the CGE Complaints manual | A total of 244 files were opened | No corrective action | 180 of complaints and attended to in terms of the CGE Complaints manual | A total of 170 files were opened | Less files were opened this quarter because in the second quarter the target was exceeded by 64 | Measures will be put in place by Legal dept to ensure that target are reached. |
|  | No of legal clinics conducted in Provinces | 27 legal clinics per year | Conduct legal clinics in all provinces to educate the public on gender rights and obligations; assist the public in lodging complaints; to provide initial advice for quick resolution of complaints | 56 legal clinics were conducted | No corrective action | Conduct legal clinics in all provinces to educate the public on gender rights and obligations; assist the public in lodging complaints; to provide initial advice for quick resolution of complaints | 31 legal clinics conducted | No variance | No corrective action |
| 2. Initiate an investigation into systemic violations of gender rights and identify remedial action. | A systemic investigation | 2 systemic investigations conducted | Investigate systemic weakness | Two investigations with systemic weakness were initiated, namely the Judicial complaint and Sex work complain. This is work in progress | No corrective action | Determine and implement remedial action for systemic weakness | Judicial complaints: Has sought written legal opinion from Pierre De Vos to provide his expert guidance on the matter Concurrent to this process, the Legal Team has commenced drafting the fully detailed investigation report. | No variance | No corrective action |
|  |  |  |  |  |  |  | Sex work complaint- We await feedback from complaints to interview witnesses on the 21st to the 23rd of January 2015. Have a scheduled meeting with Advocate Pillay on the 29th of January 2015, to finalise the details of the envisaged way forward. |  |  |
| 3. To develop co-ordinated programme to promote gender equality | Number of co-ordination programmes developed with targeted stakeholders on gender discrimination | 9 reports on coordinated programme conducted in provinces | 1 Develop an educational awareness programme on gender equality with targeted stakeholders on early child marriages and forced marriages | NW: Achieved FS: Achieved KZN: Achieved MP: Achieved NC: Achieved WC: Not achieved LIMP: Achieved GP: Achieved EC: Achieved | WC will implement in the next quarter | 1 Develop an educational awareness programme on gender equality with targeted stakeholders | NW: Achieved | No variance | No corrective action |
|  |  |  |  |  |  |  | FS: Achieved |  |  |
|  |  |  |  |  |  |  | WC: Achieved |  |  |
|  |  |  |  |  |  |  | NC: Achieved |  |  |
|  |  |  |  |  |  |  | MP: Achieved |  |  |
|  |  |  |  |  |  |  | LIMP: Achieved |  |  |
|  |  |  |  |  |  |  | GP: Achieved |  |  |
|  |  |  |  |  |  |  | KZN: Achieved |  |  |
|  |  |  |  |  |  |  | EC: Achieved |  |  |
|  | Number of campaigns initiated with the aim of promoting gender equality | 1 national summit report and 3 campaign reports per province | Conduct a Women's month campaign guided by concept paper | Concept paper was developed. 9 provinces implemented the Women’s month programme | No corrective action | Conduct a 16 days programme during November and December | 9 provinces achieved | No variance | No corrective action |
|  | To use public media platforms to disseminate gender equality education and information | 54 radio slots | Community radio slots presented as NCRF MOU | 33 Radio Slots took place | No corrective action | Scheduled SABC television and radio appearances and Community radio slots presented as per NCRF MOU | Recorded panel discussion on femicide and also recorded in different languages for community radio (NCRF & NEMISA) 38 radio slots were conducted | No variance | No corrective action |
| 4. To initiate interventions for the sustainable development and promotion of gender equality by addressing violations in the social cultural political economic security and human rights dimensions | Number of intervention programmes on gender violations initiated with traditional leadership and religious sector | 9 provincial report | I education programme with HTL per province | NW: Not achieved WC: Achieved KZN: Not achieved GP: Achieved EC: Achieved LIMP: Achieved NC: Achieved FS: Not Achieved EC: Achieved | Interventions in NW and FS will take place in the next quarter | I education programme with Religious Sector per province | NW: Not achieved | NW, EC and NC Could not secure meeting with religious sector. Reasons provided by them was that their schedules were too tight | Engagements in NW, EC, FS, and NC will be conducted in the next quarter |
|  |  |  |  |  |  |  | NC: Not achieved |  |  |
|  |  |  |  |  |  |  | WC: Achieved |  |  |
|  |  |  |  |  |  |  | KZN: Achieved |  |  |
|  |  |  |  |  |  |  | MP: Achieved |  |  |
|  |  |  |  |  |  |  | EC: Not Achieved NW: Not achieved |  |  |
|  |  |  |  |  |  |  | NC: Not achieved |  |  |
|  |  |  |  |  |  |  | WC: Achieved |  |  |
|  |  |  |  |  |  |  | KZN: Achieved |  |  |
|  |  |  |  |  |  |  | MP: Achieved |  |  |
|  |  |  |  |  |  |  | EC: Not Achieved |  |  |
|  |  |  |  |  |  |  | LIMP: Achieved |  |  |
|  |  |  |  |  |  |  | GP: Achieved |  |  |
|  |  |  |  |  |  |  | LIMP: Achieved |  |  |
|  |  |  |  |  |  |  | GP: Achieved |  |  |
| 5. To collaborate with organs of state civil society and other institutions for the effective development protection promotion and attainment of gender equality | No of joint programmes targeting the interests of LGBTI with Chapter 9 institutions | 2 joint coordinated programme per province | Joint coordinated programme conducted with LGBTI stakeholders | NW: Not achieved WC: Achieved KZN: Not achieved GP: Achieved EC: Achieved LIMP: Achieved NC: Achieved FS: Achieved MP: achieved | NW and KZN interventions have been scheduled for next quarter | No Activity | NW: Not Achieved | Engagement in partnership with DOJCD was cancelled due to unforeseen circumstances | Engagement has been rescheduled for the next quarter |
|  |  |  |  |  |  |  | WC: Achieve |  |  |
|  |  |  |  |  |  |  | KZN: achieved |  |  |
|  |  |  |  |  |  |  | GP: Achieved |  |  |
|  |  |  |  |  |  |  | EC: Achieved |  |  |
|  |  |  |  |  |  |  | LIMP: achieved |  |  |
|  |  |  |  |  |  |  | NC: achieved |  |  |
|  |  |  |  |  |  |  | WP: Achieved |  |  |

| Strategic Objective No. 3 |
| --- |
| To monitor state compliance with regional and international conventions covenants and charters which have been acceded to or ratified by the Republic relating to the object of the Commission for Gender Equality. |
| Planned Outcome: Assessment of State compliance with regional and international commitments that promote gender equality and recommendations tabled with parliament. |
| Sub-strategies | Performance Indicator | Annual target | Performance Plan and Progress for 1 July 2014 to 31 September 2014 | Performance Plan and Progress for 1 October 2014 to 31 December 2014 |
|  |  |  | Quarter Two | Progress | Corrective Actions | Quarter Three | Progress | Variance | Corrective Actions |
| 1. To conduct annual reviews and audits of state compliance with obligations under the conventions covenants and charters and to report on a regular basis to Parliament and the Office of the Speaker of Parliament | Number of review reports presented (CEDAW Beijing MDG's African Charter) | 3 reports | Printing and tabling of MDGs report with parliament. Conducting consultative meeting with targeted stakeholders on findings of the report | The Beijing Report had gaps and had to be reviewed. Printing had to be delayed. Gaps in the MDGs report were identified and had to be sent for peer review. Printing has therefore not taken place | Reports will be printed in the next quarter | Develop reports assessing the Country CEDAW Report, Beijing, MDGs reports and SADC Protocol on Gender and Development | Printing the report has not been finalised. Assessment reports have not been finalised | Tables in the report are skewed and had to be re-typed Country report on CEDAW and assessment could not be done has not been finalised. | Printing will be finalised in the next quarter. Country reports will be assessed in the next quarter |
|  | Number of reports on Africa Gender Development Index (AGDI) | 1 AGDI report drafted | Develop project plan with specified timelines. Constitute project research team | First meeting of the AGDI National Advisory Panel convened on 22nd July 2014; Training of Panel Members conducted by UNECA official on 19-23 August 2014. Project plan was developed and finalised | No corrective action | Collection of data | Data collection was carried out and the report is being drafted | No variance | No corrective action |
| 2. To interact with and present reports to national regional and international bodies on state compliance with conventions covenants and charters acceded to or ratified make recommendations for improvements and monitor implementation | Number of presentations made to relevant national regional and international stakeholders | 1 presentation conducted | Presentation of CGE CEDAW Conducting consultative meeting with targeted stakeholders on findings of the report | Consultative meeting has not taken place . | Invitations will be sent out in the next quarter. Meeting with stakeholders will be held in the next quarter | NO Activity | Consultative meetings with stakeholders did not take place | Meetings with stakeholders could not be secured | Consultative meeting still needs to be arranged with stakeholder |
|  | CEDAW training manual | 1 training manual developed | Develop CEDAW Training manual | First draft training manual has been developed. The manual will still needs to be reviewed | The manual will be finalised in the next quarter | Conduct consultative session on CEDAW Training Manual | Consultative meeting on training manual has not taken place. Manual has been shared with research to provide further inputs | Manual still needs to be reviewed by research before sharing with broader stakeholders | Consultative meeting will be held in the next quarter |
|  | Simplification of international and regional conventions and charters | 3 booklets developed | Develop Simplified booklets on Beijing Declaration and MDGs | Draft CEDAW booklet has been developed. Booklets on Beijing and MDGS have not been developed | Booklets will be simplified and finalised in the next quarter | NO Activity | NO Activity | NO Activity | NO Activity |
|  | Engagements with stakeholders on CGE attendance at international and regional events | 4 | Presentation of reports international and regional events to selected targeted stakeholders | Presentations were not done | Presentations will take place in the next quarter | Presentation of reports international and regional events to selected targeted stakeholders | Presentation on CSW 58 took place. Presentation with selected | Meetings could not be secured with stakeholders | Meetings will be scheduled for next quarter |

| Strategic Objective No. 4 |
| --- |
| To build an effective efficient and sustainable institution that will fulfil its constitutional mandate on gender equality. |
| Sub-strategies | Performance Indicator | Annual target | Performance Plan and Progress for 1 July 2014 to 31 September 2014 | Performance Plan and Progress for 1 October 2014 to 31 December 2014 |
|  |  |  | Quarter Two | Progress | Corrective Actions | Quarter Three | Progress | Variance | Corrective Actions |
| 1. To maintain optimal governance and oversight structures and policies between Commissioners and the Secretariat. | Develop and review a delegation of authority between the Office of the Chair and the CEO as directed by the CGE Act. | 1 | Drafting of delegation of authority | Consultation between the office of the chairperson and CEO took place in this quarter. A draft document on delegation of authority has been developed | No corrective action | No activity | No activity | No activity | No activity |
| 2. To develop a financial management strategy that promotes effective efficient and economic utilisation of resources as well as accountability. | Clean audit report from the AGSA | Clean audit report | Develop commitments on key controls improvement | Progressively implemented in line the planned timelines | No corrective action | No activity | No activity | No activity | No activity |
|  | Approved financial management strategy based on delegation of authority and revised and approved policies and procedures. | Approved management strategy and its implementation based on delegation of authority and revised polices | Development streamlining process improvement and execution of blue-print arising from the strategy | Upgraded to Pastel Evolution and all financial data migrated. New system fully operational. Integration of Asset management, Procurement and other sub-modules were implemented effective from April 2014 | No corrective action | No activity | No activity | No activity | No activity |
|  | Process alignment and internal controls improvements | Regular effective Key controls assessment by the AGSA | Full migration of the accounting system to a fully integrated ERP environment | Assets management activities completed. FAR on electronic database and bi-annual counts executed during September 2014.The reconciliations of the asset counts exercise to be finalised on 15 October 2014 as per timelines of the project | No Corrective action | No activity | No activity | No activity | No activity |
|  | Efficient management of resources towards an effective service delivery | Spending within budget: Funded APP cost controls and sound financial position | Maintenance of regular records on Revenue Expenditure Assets Liabilities and report timely for oversight and performance | Spending monitored and variance maintained within the tolerance rage. Quarterly reported and figures assured for timeliness and accuracy | No corrective action | Maintenance of regular records on Revenue Expenditure Assets Liabilities and report timely for oversight and performance | Spending monitored and variance maintained within the tolerance rage. Quarterly reported and figures assured for timeliness and accuracy | No variance | No corrective action |
| 3. To develop and maintain an IT infrastructure that supports and promotes the organisational objectives of the CGE | % of resolutions to reported IT incidents | 80% | 80% of IT incidents reported resolved | All IT incidents received have been resolved | No corrective action | 80% of IT incidents reported resolved | All IT incidents received have been resolved | No variance | No corrective action |
|  | ICT Infrastructure upgrade | 4 phases of infrastructure upgrades | WAN, LAN and VIOP Upgrades | This is dependent on ICT Infrastructure upgrade. The project has not commenced as yet | Approval expected in the next quarter | Desktop and laptop upgrade | Approval of IT infrastructure upgrade was approved. Tenders were sent out and the closing date for tenders is 22 January 2015. SCM processes will then commence | Approval was late and have therefore impacted on acquisition processes | Desktop/ laptop acquisition will take place in the next quarter |
|  |  | Microsoft software upgrade and Licensing | Microsoft software upgrade and Licensing | This is dependent on ICT Infrastructure upgrade. The project has not commenced as yet | Approval expected in the next quarter | NO Activity | ICT infrastructure upgrade has been finalised. Software upgrade and licensing will take place next quarter |  |  |
|  |  | enhanced website | identify and update content | Website has been tested. Migration to new host has commenced. Content identified and uploaded | Approval expected in the next quarter | management and maintenance of the website | Documents have been uploaded and errors have been corrected, management and maintenance has been done through the service provider | No variance | No corrective |
|  | Information Technology Policies reviewed and aligned to the new environment | Four (4) existing policies revised |  | Polices have been developed. | Expected approval in the next quarter | Review and update existing 4 IT policies | 12 policies were approved | No variance | No corrective action |
|  | Maintenance of Integrated Business Application Software | 100% availability and reliability of systems | Support and daily backup of ESS and VIP Pastel | ESS is operational and backups are conducted | No corrective action | Support and daily backup of ESS and VIP Pastel | System is working and backups are conducted | No variance | No corrective action |
| 4. To develop and implement comprehensive HR policies procedures and practices | Develop and maintain Training Plan and Annual Training Report | 1 training Plan implemented | Implementation of training plan | Training needs have been identified. RFQs have been sent to prospective service providers. Responses have been received. Bid Committee still has to evaluate | Programme will be implemented next quarter. | Implementation of training | Training on M & E has commenced as per revised plan | No variance | No corrective action |
|  | Implement Employee Self Service (ESS) for leave applications and approvals | Fully automated leave management system | Implementation of the ESS system | ESS has been implemented | No corrective action | training of staff on ESS | All staff members have been trained on ESS | No variance | No corrective action |
|  | Review current PMDS system and ensure that APP is translated into individual performance measures | Fully automated PMDS system | Review PMDS system | Review of Performance agreements and PMDS has been completed. | No corrective action | Implement the revised system | Performance agreements have been revised and loaded on the electronic system. Training has been scheduled for the next quarter | No variance | No corrective action |
|  | Maintain and report on the implementation of an organisation wide Employee Assistance Programme (EAP) | Assessment Report of Implementation of EAP | monitor the effectiveness of the programme | Monitoring reports have been received from the service provider. System is still operational | No corrective action | monitor the effectiveness of the programme | Monitoring report has been sent by the service provider. EAP programme has been implemented | No variance | No corrective action |
|  | Review update and approve HR policies | Reviewed and developed policies | Develop remuneration policy | Draft policy has been developed | No corrective action | Develop bereavement policy | A draft policy has been developed | No variance | No corrective |
|  | Ensure that staff vacancies are filled in line with the Recruitment and Selection Policy | 100% of staff compliment filled | Filling of vacant post | Advertisements have been placed in Sunday Times. Short-listing has commenced for Research, Communications and Manager in the Chairperson’s office. Interviews for Communications manager were conducted. Report will be finalised in the next quarter | No corrective action | Filling of vacant posts | Shortlisting was done for Education Officer Lim. No suitable candidate was found. Two researchers have been recommended for appointment | No variance | No corrective |
|  | Conduct annual staff awareness workshops on HR policies and changes in basic conditions of employment | 1 awareness program for each office and/or job family | Workshop staff on HR policies | Dates for workshops have been identified. Workshops have commenced | No corrective action | Workshop staff on HR policies | 8 provinces have been workshoppedH/O and NC are outstanding | Dates could not be secured | Dates have been secured for next quarter |
| 5. Implement an effective communications strategy and policy that promotes and enhances a positive public image of the CGE | No of media releases and opinion pieces per month linked to programme work of the CGE | 4 media monitoring reports | Media release that highlights a CGE programs & campaign | Media releases have been sent out and interviews have been generated | No corrective action | Media release that highlights a CGE programs & campaign | Media interviews have been sent out and interviews have been conducted | No variance | No corrective action |
|  | Workshop national and provincial staff on communication media and stakeholder policies and procedures | 2 policy workshops conducted | No Activity | No Activity |  | Conduct a workshop with PCs to identify challenges in implementing the strategy and policies | Individual workshops with Provinces ongoing through monthly engagements | No variance | No corrective action |
|  | Conduct annual media monitoring audit | 1 media monitoring report | Quarterly media monitoring report which covers campaigns and projects | Media monitoring report has been obtained through the service provider. The report has been analysed | No corrective action | Quarterly media monitoring report which covers campaigns and projects | Media monitoring ongoing | No variance | No corrective action |
|  | Develop and manage media and communication partnerships | 2 national partnerships | Draft proposals and presentations for prospective partners | Partnerships have been consolidated, viz, SABC, StatSA, FISD, Nemisa and NCRF | No corrective action | Engagements and negotiations with prospective partners | Implementation done for 16 Days Campaign | No variance | No corrective action |
|  | Develop a baseline for social media interaction (baseline report) | 1 baseline report | Social Media Monitoring report for the quarter | Social media monitoring report is has been obtained from service provider | No corrective action | Social Media Monitoring report for the quarter | Social monitoring report was obtained by from the service provider | No variance | No corrective action |
|  | Report on National and Provincial stakeholder engagements on an annual basis | I stakeholder engagement report | Implementation of the stakeholder strategy and quarterly report | Stakeholder strategy document has been developed and still needs to be discussed at Manco. Implementation of the strategy has not taken place | Strategy will be discussed and adopted in the next quarter | Implementation | Implementation ongoing | No variance | No corrective action |
|  | Lead a process to develop and maintain a national and provincial stakeholder database. | 1 complete stakeholder database | Generate and update stakeholder lists and details | Stakeholder database has been developed and is updated regularly | No corrective action | Generate and update stakeholder lists and details | Stakeholder database that is in place has been updated | No variance | No corrective |