## Slide 1: STATUS/PROGRESS REPORT ON PACOFS
Presented by: Acting Director-General
Date: 04 AUGUST 2015

## Slide 2: PURPOSE OF THE PRESENTATION
Provide an update on the progress made in addressing the issues raised by the Portfolio Committee during their oversight visit to the PACOFS on the 25 November 2014

## Slide 3: INTRODUCTION & BACKGROUND
The Portfolio Committee visited the PACOFS on 25 November 2014
The primary reason for the oversight visit was to meet with staff and learn more about the operations of the entity.
Decision taken following the site visit:
The DAC, together with the entity should develop an intervention plan to resolve the issues raised by the PC and monitor progress.
3

## Slide 4: BROAD ISSUES IDENTIFIED FOR INTERVENTION
Improving both internal (staff and labour union) and external (provincial and municipal) Working Relations
Address HR, Financial and Governance short-comings
Encourage an Inclusive and Conducive working environment at PACOFS
Develop and monitor the Audit Improvement Plan
4

## Slide 5: MILESTONES TO BE ACHIEVED
Improved staff moral
Improved Provincial government and Municipal relations
Transparency and good work ethic among all staff
Improved governance and financial accountability

## Slide 6: PROGRESS TO DATE
ISSUE | PROGRESS
Improve both internal (staff and labor union) and external (provincial and municipal) working relations No clear organizational structure Salary Discrepancies | Schedule of dates for meetings with staff were developed. Some of the meeting did not materialised due to continued disruptions Meetings with the Union were held in January and February to continue discussions on the recommendations of the DAC and Portfolio Committee Organisational structure has been developed and approved. A Promines System is in place for salary grading

## Slide 7: PROGRESS TO DATE
ISSUE | PROGRESS
No Performance Agreements for employees No job descriptions | So far the Scorecards have been developed for management. To ensure alignment, job descriptions are being finalised. These will be finalised by end of Quarter 2
Low staff morale | ADG visited the entity in efforts to boost staff morale and to calm the situation
Lack of Skills development for the staff | Training and Development Plan was submitted to CATHSETTA in Q1 OHS Training was done with Damelin in Q4 Computer training was also conducted with Damelin in Q4

## Slide 8: PROGRESS TO DATE
ISSUE | PROGRESS
Lack of managerial experience | Managers attended a short course at UFS on PFMA and on Management Development Programme
Address HR, Equity (Gender priorities) and Labour issues | Equity Plan is in place Gender issue is a priority for vacant posts of CFO, Marketing and IT. Posts have been re-advertised
Language Signage and Use of Official Language Act | Attended two workshops facilitated by DAC, however the Language Policy has not yet been finalised.

## Slide 9: PROGRESS TO DATE….
ISSUE | PROGRESS
No Strategic Planning with staff | Strategic planning currently involves Council and management. Managers are expected to do operational planning with the staff. The process of scorecard and job description will also assist in the planning processes.
Revise the Vision and Mission of PACOFS | The appointed Council will discuss and finalise the issue during their planned meeting of the 06/08/2015
Misuse of funds on certain projects (tenders for infrastructure and consultants) | Funds utilised are accounted for in quarterly and other reports DAC has conducted an audit of the Infrastructure Programme and the audit report is being finalised

## Slide 10: FURTHER DEVELOPMENTS
The Council of PACOFS had 2 resignations, the Chairperson and another member
The process of replacing the 2 council members, including the Chairperson is at an advanced stage
NEHAWU members disrupted shows or performances claiming that PACOFS management is corrupt and embroiled in fraud. This has attracted negative media publicity and raised safety concerns for PACOFS customers

## Slide 11: THANK YOU
11