## Slide 1: STATUS/PROGRESS REPORT ON NELSON MANDELA MUSEUM 2015
Presented by: Act DIRECTOR-GENERAL
Date: 04 AUGUST 2015

## Slide 2: PURPOSE OF THE PRESENTATION
Provide an update on the progress made in addressing the issues raised by the PC during their oversight visit to the Nelson Mandela Museum on 24 November 2014

## Slide 3: INTRODUCTION & BACKGROUND
Portfolio Committee visited the Museum on 24 November 2014
The primary reasons for the oversight visit was a fact finding mission – informed by the regression of the institution’s audit outcome
The visit was also aimed at seeking ways to assist the institution improve the qualified audit outcome
It was concluded that :
The Museum management had no sense of commitment, as such the Museum was in a crisis situation and needed a turnaround plan
The institution, in collaboration with the DAC should develop an intervention plan to resolve the issues raised by the AG and PC
2

## Slide 4: 4 BROAD ISSUES WERE IDENTIFIED
Improve the Reputation, Image and the Integrity of the Museum
Address the HR, Financial and Governance short-comings
Assist and encourage an Inclusive and Conducive working environment amongst all Museum staff
Monitor the Audit Improvement Plan and provide assistance where needed.
3

## Slide 5: MUSEUMS MILESTONES TO BE ACHIEVED
Improvement of staff moral
To deliver better product to the public through commitment and dedication
To inculcate the spirit of Ubuntu among all staff
Improve governance and financial accountability

## Slide 6: PROGRESS TO DATE
Reputation, Image and Dignity of the Museum
ISSUE A: Revision of Vision, Mission and Values
New vision: Inspire positive change in society through the legacy and values of Nelson Mandela
New Mission : A centre of excellence that preserves the legacy, disseminate knowledge, interprets and upholds values of Nelson Mandela to promote social cohesion and nation building
New Values: Ubuntu, Stewardship, Integrity, Service excellence, learning and development, Innovation

## Slide 7: PROGRESS TO DATE ….
ISSUE B: Lack of content in exhibitions at Qunu
The museum will ensure that more content/exhibitions are installed in the renovated Bhunga building – The project to renovate the Bhunga Building has not been completed as yet
More funds will be needed for exhibition development. The current museum base funding cannot accommodate this- Council with management will cost this with the assistance by DAC
Workshops for Tour Guides were held with the Tourism Department and internal Museum Units to assist improve the telling of the Nelson Mandela Museum narrative

## Slide 8: PROGRESS TO DATE….
2. HR, Finance and Governance
ISSUE: The organogram is being reviewed
Some critical positions such as curator, collections, conservator cannot be filled due the limitations of the funding baseline
Council and Management have started engaging in a restructuring exercise. This exercise will be linked to the new strategic plan
CEO’s ,Senior Managers and Staff have all their performance agreements signed
Unit managers have since sat with individual staff members and clarified their job description

## Slide 9: PROGRESS TO DATE…
2. HR, Finance and Governance
ISSUE: Low staff moral
The root cause of low moral was indicated as “low salaries”.
On the 28 February 2015, management organized a consultation forum between staff and Council as part of boosting staff moral
All staff members receive inflationary salary adjustments
In terms of performance bonus, the Museum has planned a policy review workshop which is now due to be held in August 2015

## Slide 10: PROGRESS TO DATE….
ISSUE: Supply chain management policies need to be in place, discussed and approved
Supply management policies are in place
Bid Specification, Evaluation and Adjudication committees were appointed
SCM committees were established and trained by PALAMA
ISSUE: Provide support and ensure monitoring and evaluation & Governance
Misalignment of the strategic plan, annual performance plan and quarterly reports – the DAC provides technical support when necessary
Strategic plan session was facilitated by DAC and it was attended by all staff members
Site visits are conducted quarterly or as needed
Compliance to prescripts is monitored (submission or required documents and feedback to both Council and Management is provided)
Council meetings are held

## Slide 11: PROGRESS TO DATE
3.Inclusive and conducive working environment
ISSUE: Need to build an inclusive and conducive environment for all staff of the Museum
Staff Meetings schedule was developed and circulated.
All staff members were issued with all existing policies to read and comment.
In February 2015, Management with Council organized a consultative forum with staff as part of boosting staff moral

## Slide 12: PROGRESS TO DATE
4. Audit Improvement Plan
ISSUE: Turnaround the Qualified Audit report
The Audit Committee has met quarterly to review the internal audit report
Audit improvement plan is being adhered to. Progress is reviewed quarterly and a report is generated
The DAC conducted a site visit on 18 March 2015 to assess audit readiness for 2014/15 financial year. It was noted that some of the findings will be recurring to the 2014/15 audit as they were not yet resolved.

## Slide 13: FURTHER DEVELOPMENTS
DAC and the Museum have scheduled a workshop for the 6-7August 2015 to address and take forward some of the issues raised by the PC
Issues to be addressed during the workshop are as follow:
Analysis of the current museums’ strategy for affordability
Functions required to achieve the museum’s objectives
What is an ‘ideal’ organisational structure vs current
Taking ‘stock’ of the human resources available (an introspection)
Development of job descriptions for positions (current & those identified as needed)

## Slide 14: THANK YOU
13