RE:	BRIEFING DOCUMENT OUTLINING UPDATE ON ACTIONS UNDERTAKEN AND OUTSTANDING IN TERMS OF THE SETTLEMENT AGREEMENT BETWEEN THE DAC AND SARA:

There have been considerable interactions between the Department and the South African Roadies Association (SARA) in following up on the Settlement Agreement between the two parties.

ACTIONS THAT HAVE BEEN UNDERTAKEN:

- Actions towards Clause 4.1.1 of Settlement Agreement

  - Support towards International Interactions proposal:

SARA submitted a proposal towards three (3) year administration, operations and International Relations programme over 3 years.

The Department considered the proposal and settled to support the International Interactions, to the value of R2 838 402.00 which was the total amount requested by SARA over a period of three (3) years. The Department indicated to SARA that as per frameworks governing the public sector, it cannot support the Administrative and Operations request. An MOA was entered into by the two parties which stipulated clear allocations per year starting from 2014 to end in 2016.

- The 1st Year (2014/2015) has been successfully completed.

- The 2nd Year (2015/2016) transfer has been approved.

- Actions towards /4.1.2/4.1.3/4.1.7/4.1.9 of Settlement Agreement

  - Assessments on SARA House

The DAC assigned the Independent Development Trust (IDT) to conduct an assessment of the SARA building. The findings of the IDT indicated that the SARA building was in a dilapidated condition and has reached its useful life and that it was not prudent to invest government resources in renovating the structure.

  - Support towards Building Renovations proposal:

In respect to the proposal requesting support towards Building Renovations, the Department informed SARA on the findings from the IDT report and a meeting was planned between the two parties to discuss the matter further.

Subsequently a meeting was held with SARA at which the Department committed to ring-fence R10 000 000.00 (Ten Million) for accelerating building renovations towards SARA House infrastructure renovations. It was acknowledged that further engagements are needed on how to implement and in this regard the Department suggested to SARA to submit a comprehensive plan or proposal for DAC to identify areas that they might be able to assist.

In addition to the above SARA was requested to identify other Institutions and potential partners or funders that the DAC could assist in facilitating engagements towards the SARA House infrastructure renovations.

- Actions towards Clause 4.1.4. of Settlement Agreement:

The Department has a unit which is mandated in developing the Event, Technical and Production Services sector. SARA falls within this sector and therefore personnel towards the programme are addressed.

The unit is providing the required oversight and DAC administrative functions on SARA matters.

- Actions towards Clause 4.1.5. of Settlement Agreement:

The DAC has requested SARA to identify other institutions for DAC to facilitate engagements. The matter was included in the letter sent to SARA.

- Actions towards Clause 4.1.6. of Settlement Agreement:

- SARA requested support towards the hosting of the Live Events, Technical and Production Conference (LETPC) in 2015.

The Department supported SARA with an additional R800 000.00 for the LETPC in view of that it was a SARA lead initiative focusing at addressing sector wide stakeholders on training and skills development. The Minister of Arts and Culture and DAC Officials attended the event and affirmed the importance of the initiative. As per Settlement Agreement this was responding to ensuring that SARA’s vision and mission as a training organisation servicing the technical and production sector is enhanced, facilitated and supported. The main focus of the conference was on training and skills development in the Live Events Technical Production.

- The DAC includes provisions for SARA interns to work within large scale projects such as MOSHITO and all National Day events, an intervention that has yielded good results for the event, DAC and SARA. This will continue in the coming years

- DAC has continued to avail itself for engagements with SARA to ensure good working relations

- Actions towards Clause 4.1.8. of the Settlement Agreement:

N/A.

- Actions towards Clause 4.1.9. of the Settlement Agreement:

Ongoing updates to the PPSA and the Department has scheduled a meeting with them for 12 August 2015.

- Actions towards Clause 4.1.10 of the Settlement Agreement:

N/A.

OUTSTANDING ACTIONS:

- International Interactions programme:

SARA is ongoing implementation of the International Interactions programme which is entering its 2nd year this year (2015). The programme will be completed in 2016 which will be the final year.

- Building infrastructure renovations:

The Department requested SARA to provide other funding sources in order for the Department look at how it could assist in facilitating engagements for SARA to solicit further support or funding towards the SARA House infrastructure renovations.

- Support towards Live Events, Technical and Production Conference (LETPC) 2015:

The DAC is anticipating a report from SARA on the LETPC. When the report is satisfactory the Department will transfer the final tranche.