## Slide 1: DEPARTMENT OF ENVIRONMENTAL AFFAIRS
ANNUAL PERFORMANCE REPORT DASHBOARD
2014/15

## Slide 2
PROGRAMME 1: ADMINISTRATION

## Slide 3: PROGRAMME 1: ADMINISTRATION
SO: Adequate and appropriate skilled staff |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage vacancy rate | 19.3% (366/1897) | 9.5% | Progress: 10.4% (191/ 1845) vacancy rate Challenges: 1. delays/challenges in filling posts in specialised skills/ scientific fields, 2. financial constraints and the need to reprioritise/delay filling of some funded vacancies Corrective measures: Prioritise key posts and facilitate filling of vacancies in 2015/16, exploring other targeted recruitment options such as headhunting where necessary.
Percentage turnover rate | 10% | 10% | 5.2 % (83 employees left /out of 1588 employee at the beginning of the period)

## Slide 4: PROGRAMME 1 : ADMINISTRATION
SO: Adequate and appropriate skilled staff |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage implementation of Performance Management and Devevelopment System (PMDS) policy framework | 73% (83% - 1253/1514 Biannuals/ Verifications Statements received) | 95 % Compliance with contracting and assessment requirements | Progress: Compliance/ implementation of key PMDS policy framework requirements: 96% 96% (1582/1647) compliance with submission of first biannual individual assessment reports 97% (1659/1703) submission of employee performance agreements.
Number of Human Resourse Development (HRD) strategy initiatives implemented | • 68% (635/934) of Workplace Skills Plan (WSP) implemented • 40 full time bursaries and 55 part time bursaries approved | 3 Interventions: •100 Interns recruited •70 bursaries issued (30 full time and 40 part time) • 80% of WSP implemented | Progress: 3 Human Resource Development interventions implemented: 100 Interns appointed 100% of WSP implemented (1002 planned WSP interventions undertaken) 84 bursaries awarded (49 part time and 35 full time bursaries.

## Slide 5: PROGRAMME 1: ADMINISTRATION
SO: Secure, harmonious, transformed and conducive working environment |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage of Women, Blacks and People with disabilities at DEA | Women 56% (846/1514) | 50 % | Progress: 56% (926/ 1654)
Percentage of Women, Blacks and People with disabilities at DEA | Blacks 90% (1360/1514) | 90 % | Progress: 90.5% (1497 /1654)
Percentage of Women, Blacks and People with disabilities at DEA | 2% People with disabilities (32/1514) | 2 % | Progress: 2.8 % (47/1654)

## Slide 6: PROGRAMME 1 : ADMINISTRATION
SO: Secure, harmonious, transformed and conducive working environment |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Average number of days taken to resolve disciplinary cases | 99% | 90 days for misconduct cases | Progress: Average number of 90 working days taken to resolve misconduct cases. (28 of 31 cases due for finalisation were finalised)
 |  | 30 days for grievance cases | Progress: Average number of 53 working days taken to resolve grievance cases (35 of 38 cases due for finalisation were finalised)

## Slide 7: PROGRAMME 1: ADMINISTRATION
SO: Secure, harmonious, transformed and conducive working environment |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Phased implementation of DEA New Head- Office Building Public Private Partnership (PPP) project | Phase II on the construction of DEA Building project underway | Phase I of operations implemented (service commenced as per the project plan) | Progress: Phase I of operations implemented (service commenced as per the project plan) as follows: Inspections services were conducted as per schedule to ensure compliance and oversee the service level standards requirements. Occupational Health and Safety (OHS) services standards as outlined in the schedule were monitored and recommendations were implemented as planned Steering committee/Operational Project Committee monthly meetings held

## Slide 8: PROGRAMME 1 : ADMINISTRATION
SO: Secure, harmonious, transformed and conducive working environment |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage implementation of security risk assessment recommendations | 83% implementation of security risk assessment recommendations | 90% implementation of security risk assessment recommendations | Progress: 61% (11 out of 18 security assessment recommendations implemented) Challenges: Implementation of some recommendations requires cooperation from other organisations (i.e. Department of Public Works). Additional time was required to facilitate such consultation Corrective measures: The outstanding assessment to be prioritised for implementation in the 2015/16 financial year

## Slide 9: PROGRAMME 1: ADMINISTRATION
SO: Efficient and Effective Information Technology service |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of funded Master System Plan (MSP) initiatives implemented (as per the schedule) | 7 initiatives implemented | 9 funded Master System Plan initiatives implemented (per schedule) | Progress on implementation of MSP projects : 2 projects implemented as planned 3 partially implemented 2 projects delayed 1 project on hold and 1 project cancelled Challenges: Lack of funds to complete all planned projects resulted in a decision to cancel, put on hold and delay implementation of some projects Corrective measures: Funding requirements to be addressed and intervention plan developed to fast track implementation of delayed MSP projects

## Slide 10: PROGRAMME 1: ADMINISTRATION
SO: Efficient and Effective Information Technology service |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage of availability of IT services | 98.06% availability of IT Services | 97 % availability of IT Services | Progress: 99.% availability of IT Services
SO: Equitable and sound corporate governance |  |  | 
Percentage compliance with statutory tabling and prescripts | 100% 2012/13 Annual report ; 2013/14 - 2017/18 Strategic Plan and APP tabled in Parliament 2014/15-2018/19; 1st draft Strategic Plan and APP submitted to Presidency and DPME | 100 % compliance with statutory tabling and prescripts (All Management Performance Assessment Tool (MPAT) Standards with moderated score of 3 and above) | Progress: 100% compliance with key governance requirements and set timeframes – DEA ENE quarterly reports and interim financial statements submitted to National Treasury on time, Annual report for 2013/14 tabled, 1st and 2nd draft Strategic Plan and Annual Performance Plan submitted to National Treasury and Presidency/DPME, DEA 2019/20 Strategic and 2015/16 Annual Performance Plan approved and tabled to parliament on time. An average score of 3.5 on MPAT

## Slide 11: PROGRAMME 1: ADMINISTRATION
SO: Equitable and sound corporate governance |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Unqualified audit report | 2012/13 Unqualified audit report | Unqualified audit report | Progress: Department received an unqualified audit report/opinion from the Auditor General of South Africa (AGSA) for the 2013/14 financial year
Percentage adherence to cabinet and cluster schedule as per the approved protocol | 93% | 100% | Progress 95% ( 36 out of 40 scheduled meetings attended) Corrective measures: Identification of alternative Senior Managers to attend other meetings in cases of clashes.

## Slide 12: PROGRAMME 1: ADMINISTRATION
SO: Equitable and sound corporate governance |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage expenditure | 96 % 9 [ R4 942 661/ R5 175 321] Expenditure (excluding the Green Fund is 99.7 percent) | 98 | Progress: 99.91% expenditure ( 5 680 386 / 5 675 470 billion of allocation spent by 31 March 2015)
Percentage of expenditure on affirmative procurement | 61 % (R879 665 892 spent on BEE out of total expenditure of R1 447 933 826) | 65 % | Progress: 83% of expenditure on affirmative procurement (R 893 million of R1 081 billion )

## Slide 13: PROGRAMME 1: ADMINISTRATION
SO: Improved access to information |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of media statements/speeches issued and opinion pieces published | 137 statements/ speeches | 120 statements/ speeches | Progress: 126 media statements/speeches issued
 | 3 opinion pieces published | 6 opinion pieces | Progress: 9 opinion pieces published in the media
Number of communication events including Ministerial Public Participation Programme (PPP) events | 10 Public Participation Events hosted | 20 Public Participation events | Progress: 25 Public Participation events conducted
Number of publications produced and distributed | 4 editions of stakeholder publications per annum. | 4 editions of stakeholder publications per annum. | Progress: 4 stakeholder publications produced and distributed
Number of website hits per annum | 216 317 website hits | 450 000 visit hits per annum | Progress: 665,622 website hits recorded

## Slide 14: PROGRAMME 1: ADMINISTRATION
SO: Improved sector education and awareness |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of environmental awareness activities conducted (Learnerships, Curriculum and Assessment Policy Statements (CAPS) training and campaigns | 82 teachers trained | 100 teachers trained | Progress: 117 teachers trained
 | 100 unemployed youths recruited and learnership programme implemented | 100 unemployed youths recruited and learnership programme implemented | Progress: 100 young people recruited and trained as part of the learnership programme. 9 beneficiaries left the programme during the fourth quarter
 | 5 Environmental awareness campaign | 8 Environmental awareness campaign implemented | Progress: 12 environmental awareness campaign conducted

## Slide 15: PROGRAMME 1: ADMINISTRATION
SO: Improved sector education and awareness |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of Sectort Education and Training Authority (SETA) sector skills plans with environmental focus | ESSP 2009 implemented | 6 Sector skills plans with environmental focus | Progress: 6 sector skills plans were confirmed to have of environmental focus
Number of officials undergoing/ completed Environmental Management training and (EMI/ IEM) | 200 officials undergoing National Environment Management Act (NEMA) accredited IEM training | 400 Officials undergoing IEM training per IEM quarterly training program | Progress: 1108 officials trained including officials from DEA, Provinces and other stakeholders ( i.e. Eskom, Transnet)
 | 240 EMI’s trained | 240 | Progress: 392 officials trained
Number of accredited training persons days created | 84 758 | 139 915 | Progress: 164 746 accredited training person days created

## Slide 16: PROGRAMME 1: ADMINISTRATION
SO: Effective knowledge and information management for the sector |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Outcome 10 Delivery Agreement developed and implementation facilitated | Outcome 10 Delivery Agreement 2014 -2019 | Approved Outcome 10 Delivery Agreement for sector on new priorities (2014 -2019) | Progress: Outcome 10 Delivery agreement for the 2014-2019 Medium Term Strategic Framework period approved and published
Number of environmental knowledge and information management systems/tools developed, refined and or operational (Enterprise GIS, NEAS, Oceans &Coast Online system, Climate Change Monitoring &Evaluation system etc) | Geographic Information System (GIS) intranet maintained and supported. GIS internet developed 8 environmental sector projects / initiatives supported by GIS | GIS internet developed | Progress: GIS Protected Area Register(PAR)internet developed

## Slide 17: PROGRAMME 1: ADMINISTRATION
SO: Effective knowledge and information management for the sector |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of environmental knowledge and information management systems/tools developed, refined and or operational (EGIS, NEAS, O&C Online system, CC M&E system) | Approval of the establishment of the Bid Specification Committee for the South African National Environmental Information Meta-Database Project | Phase I of the South African National Environmental Information Meta-Database Project finalised | Progress: Phase 1 of Meta-database project not finalised. Project inception meeting between DEA Steering Committee and Project Consultants facilitated Challenges: The project was delayed due to financial constraints and subsequent need for reprioritisation Corrective measures: The project will be prioritised in 2015/16

## Slide 18: PROGRAMME 1: ADMINISTRATION
SO: Effective knowledge and information management for the sector |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of environmental knowledge and information management systems/tools developed, refined and or operational (EGIS, NEAS, O&C Online system, CC M&E system etc) | 1 component - EIA application monitoring system operational and providing statistics for 8 competent authorities for Outcome 10 reporting | 2 component of the NEMA Chapter 5 Environmental Regulatory Authorization system monitored (EIA amended timeframes module and the appeals module) | Progress: 2 components of National Environmental Authorisation System (NEAS) monitored as follows: EIA process monitored and Outcome 10 quarterly reports for 10 competent authorities produced NEAS system for Appeals monitoring available Facilitated the NEAS quarterly task team meetings Action plan for populating the NEAS appeals register for two competent authorities developed

## Slide 19: PROGRAMME 1: ADMINISTRATION
SO: Effective knowledge and information management for the sector |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of environmental knowledge and information management systems/tools developed, refined and or operational (EGIS, NEAS, O&C Online system, CC M&E system etc) | Draft Climate Change Response M&E System Developed | Design of Climate Change response M&E system approved | Progress: Design of Climate Change response M&E system approved by MINMEC
 | South African Air Quality Information Systen (SAAQIS) Phase II System Finalized (National Atmospheric Emissions Information System) | 50 % of facilities with AELs reporting to the National Atmospheric Emissions Inventory System (NAEIS) | Progress: The 50% target was not achieved. The NAEIS reporting regulations were only gazetted in the week of 01 April 2015. Challenges: Delays in finalising the NAEIS reporting regulations Corrective measures: The regulations have since been finalised at the time of preparing this report.

## Slide 20: PROGRAMME 1: ADMINISTRATION
SO: Effective knowledge and information management for the sector |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of environmental knowledge and information management, monitoring and evaluation reports/ publications and response options produced | State of the Oceans Report compiled | State of the Oceans Report compiled | Progress: State of the Oceans Report has been produced
 | 15 peer-reviewed publications (including theses | 18 peer-reviewed scientific publications (including theses) | Progress: 26 scientific publications peer reviewed.
 | All South African Environmental Outlook (SAEO) specialist chapters of the report inter Protected Areas Database formally assessed against the South African Quality Assessment Framework (SASQAF) | 2012 SAEO Report Published National Strategy for sustainable Development (NSSD1) M&E Report Finalized | Progress: 2012 SAEO report completed but not published. NSSD 1 M&E Report finalised

## Slide 21: PROGRAMME 1: ADMINISTRATION
SO: Effective Cooperative Governance and Local Government Support |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Local government support strategy implemented | 50% implementation of action plan | Annual action plan fully implemented (100 % implementation) | Progress: 80% implementation of planned actions. (36/45) of the planned actions are on target Challenges: Implementation of other planned activities was depended on consensus with relevant stakeholders Corrective measures: Implementation of delayed action will be prioritised in 2015/16 after reaching consensus
Percentage of Sector conflict management tools implemented | Recommended list of individuals to sit on the Panel of Mediators and Arbitrators not yet approved | 50 % of received conflict cases dealt with (in line with NEMA Chapter 4 provisions) | Progress: All conflict cases referred for consideration in terms of NEMA chapter 4 interventions were withdrawn

## Slide 22: PROGRAMME 1: ADMINISTRATION
SO: Enhanced International governance, instruments and agreements supportive of SA environmental and sustainable development priorities |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of South African positions on Chemical and Waste, Biodiversity, Sustainable Development (SD), African and bilateral South-South South-North and International Environmental Governance (IEG) processes prepared, negotiated and reported | 100 % Positions researched and developed (World Economic Forum (WEF); BASIC; AU summit; UNEP Governing council and COP18) | 13 Bilateral/Pleurilateral (Africa, IBSA (India Brazil South Africa), S-S, S-N) approved | Progress: 21 International Environmental Management engagements coordinated and positions prepared (Bilaterals/ Pleurilaterals ):- Africa ; Brics ; South – South and South- North )
 | 100 % (Positions researched and developed for the following meetings: WEF; BASIC; AU summit; UNEP Governing council and COP18) | 3 Multilateral position (SD and IEG) approved | Progress: 5 Multilateral positions approved: United Nations Environment Assembly High Level Political Forum (HLPF) United Nations General Assembly (UNGA) Technical position (on Post-Rio+20 areas such as Sustainable Consumption and production (SCP), International Resource Panel (IRP, Group of Friends of Para 47 (GoF47), Global Environment Outlook (GEO)) African Ministerial Conference on the Environment (AMCEN)

## Slide 23: PROGRAMME 1: ADMINISTRATION
SO: Enhanced International governance, instruments and agreements supportive of SA environmental and sustainable development priorities |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of South African positions on Chemical and Waste, Biodiversity, Sustainable Development (SD), African and bilateral South-South South-North and International Environmental Governance (IEG) processes prepared, negotiated and Reported | Chemicals and waste position papers | 3 chemicals and waste positions approved | Progress: 3 position papers developed for the following international chemicals/waste management engagements Vienna COP 10/MOP26, (17-21 November 2014) Mercury Intergovernmental Negotiating Committee 6 (INC 6), Strategic Approach to International Chemicals Management (SAICM) 2nd Open Ended Working Group (OEWG)

## Slide 24: PROGRAMME 1: ADMINISTRATION
SO: Enhanced International governance, instruments and agreements supportive of SA environmental and sustainable development priorities |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
No. of SA positions on Chemical and Waste, Biodiversity, Sustainable Development (SD), African and bilateral South-South South-North and international environmental governance (IEG) processes prepared, negotiated and reported | South Africa is party to: Convention on Biological Diversity (CBD); Nagoya Protocol on Access and Benefit Sharing (ABS); Ramsar Convention, Convention on Migratory Species (CMC); United Nation Convention to Combat Desertification (UNCCD), African-Eurasian Migratory Waterbird Agreement (AEWA); Intergovernmental Platform on Biodiversity and Ecosystem Services (IPBES); Raptors MoU, IUCN, World Heritage Convention (WHC) Man-and-Biosphere (MAB) Programme | 10 Biodiversity positions approved | Progress: : 10 position papers Scientific, Technical and Technological Advice Working Group on Review of Implementation (WGRI) Standing committee of the Ramsar Convention CITES: Animals Committee Meeting ( 2 May 2014) CITES: Standing Committee Meeting (7 - 11 July 2015 CITES: 21st Plants Commitee Meeting COP-MOP1 Conference of the Parties to the Convention on Biological diversity MAB International Coordinating Council (ICC) Convention on Migratory Species (CMS)

## Slide 25: PROGRAMME 1: ADMINISTRATION
SO: Enhanced International governance, instruments and agreements supportive of SA environmental and sustainable development priorities |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of South African positions on Chemical and Waste, Biodiversity, Sustainable Development (SD), African and bilateral South-South South-North and international environmental governance (IEG) processes prepared, negotiated and reported | Climate Investment funds; UNFCCC long term finance; Green Climate fund and Adaptation Fund | 2 Climate change positions for formal international engagements (UNFCCC) developed and approved | Progress: 2 Climate change positions for formal international engagements: UNFCCC - COP 20 CMP10 IPCC
The financial value of resources raised from multilateral and bilateral donors to support the department, SA and Africa’s programmes | Total: US$ 25 million (Multilateral : US$ 15 million and Bilateral: US$ 10 million | US$30 million from all sources (Multilateral: US$20 million; Bilateral: US$10 million) | Progress: Total resources mobilized for the year: US$ 80,513,812 (US$ 30.616,964 approved and US$ 49,896,848 Endorsed)

## Slide 26: PROGRAMME 1: ADMINISTRATION
SO: Enhanced International governance, instruments and agreements supportive of SA environmental and sustainable development priorities |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Mandatory international and national reports prepared and submitted within timeframe (in terms of relevant legislation and/or international obligations/conventions | 2012/13 NEMA S26 report tabled to Parliament within timeframe | 2013/14 NEMA S26 report tabled to Parliament within timeframe | Progress: 2013/14 NEMA S24 report in Parliament tabled within timeframe in May 2014
 | Draft First Biennial Update Report developed | First Biennial Update Report (BUR) completed and submitted to UNFCCC | Progress: BUR submitted to the UNFCCC and BUR Summary for Policy Makers finalised and submitted to Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) for printing

## Slide 27: PROGRAMME 1: ADMINISTRATION
SO: Enhanced International governance, instruments and agreements supportive of SA environmental and sustainable development priorities |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Mandatory international and national reports prepared and submitted within timeframe (in terms of relevant legislation and/or international obligations/conventions | Scope of information for the Third National Communication (TNC) completed | Principles and procedures for compilation of TNC finalised | Progress: Principles and procedures for compilation of TNC have not been finalised. Terms of reference for the appointment of TNC authors have been finalised and tender advertised. Evaluation of the submitted tender proposals will take place in May 2015 Challenges: Principles and procedures for compilation of TNC were not finalised due to delays in accessing committed donor funds (GEF) Corrective measures: Principles and procedures for compilation of TNC will be finalised in 2015/16 and the work will be carried along simultaneously with the process of appointing TNC authors

## Slide 28: PROGRAMME 1: ADMINISTRATION
SO: Enhanced International governance, instruments and agreements supportive of SA environmental and sustainable development priorities |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Mandatory international and national reports prepared and submitted within timeframe (in terms of relevant legislation and/or international obligations/conventions | Green House Gas (GHG) Inventory 2000-2010 finalised | Draft GHG Inventory 2000-2012 compiled | Progress: Draft of the GHG inventory 2000-2012 compiled

## Slide 29: ANNUAL PERFORMANCE SUMMARY : PROGRAMME 1
% Achieved | Partially achieved | % Off Target | Exceeded Annual Targets
90% (47/52) | 4% (2/52) | 6% (3/52) | 43% (20/47)
Chart: 
| On target | off target | partial
Sales | 0.9 | 0.06 | 0.04

## Slide 30
PROGRAMME 2: LEGAL AUTHORISATIONS, COMPLIANCE AND ENFORCEMENT (LACE)

## Slide 31: PROGRAMME 2: LACE
SO: Improved compliance with environmental legislation |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of environmental authorisations inspected | 125 | 135 | Progress: 247 environmental authorisations inspected
Percentage of administrative enforcement actions resulting in compliance | 75 % | 75 % | Progress: An average of 83% annual compliance with administrative enforcement actions issued on 129 projects.
Compliance and Enforcement Strategy for the Environmental Management Inspectorate developed and Implemented | Draft strategy developed | Final strategy approved for implementation across all EMI institutions | Progress: Compliance and Enforcement Strategy and approved. Draft implementation plan been developed.
Number of criminal investigations finalised and dockets handed over for prosecution | 24 | 26 per annum | Progress: 30 criminal Investigations finalised

## Slide 32: PROGRAMME 2: LACE
SO: Improved compliance with environmental legislation |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions implemented for Safety and Security of wildlife including rhinoceros populations in South Africa | 1 intervention implemented for the safety and security of wildlife including rhinos • MoU with State Security Agency (SSA) • Key negotiations with strategic government partners | Review of the national strategy for the safety and security of rhinoceros population in South Africa | Progress: Stakeholder consultation facilitated and comments/inputs consolidated for the review of the national strategy for the safety and security of rhinoceros population. Analysis of comments conducted as part of the review of the strategy Challenges: Slow response from stakeholders delayed the review process Corrective measures: The review will be finalised in the 2015/16 financial year

## Slide 33: PROGRAMME 2: LACE
SO: Improved compliance with environmental legislation |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions implemented for Safety and Security of wildlife including rhinoceros populations in South Africa | 1 intervention implemented for the safety and security of wildlife including rhinos • MoU with SSA • Key negotiations with strategic government partners | MoUs with strategic government departments (Justice and Constitutional Development, Home Affairs, Correctional services and police) on safety and security of wildlife including rhino management | Progress: 4 MoUs developed with the following key Government stakeholders : Department of Home Affairs State Security Agency Department of Transport Department of Social Development
 | 1 intervention implemented for the safety and security of wildlife including rhinos • MoU with SSA • Key negotiations with strategic government partners | Implementation of corrective actions relating to TOPS regulations monitored in 2 provinces. | Progress: Implementation of corrective actions relating to TOPS regulations monitored in 2 provinces: North West : Department of Rural, Environment and Agricultural Development Limpopo : Department of Economic Development, Environment and Tourism

## Slide 34: PROGRAMME 2: LACE
SO: Improved compliance with environmental legislation |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions implemented for Safety and Security of wildlife including rhinoceros populations in South Africa | 1 intervention implemented for the safety and security of wildlife including rhinos • MoU with SSA • Key negotiations with strategic government partners | Compliance assessments on the implementation of CITES (Convention on International Trade in Endangered Species of Wild Fauna and Flora) regulations conducted in two provinces. | Progress: Compliance assessments on the implementation of CITES regulations conducted in 2 provinces: North West : Department of Rural, Environment and Agricultural Development Limpopo : Department of Economic Development, Environment and Tourism
 | 907 | 1 100 Environmental monitors trained and deployed | Progress: 1 102 Environmental monitors trained and deployed

## Slide 35: PROGRAMME 2: LACE
SO: Potential negative impacts of all significant developments prevented or managed |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of tools for mitigation of negative impacts of development developed and implemented | Draft Minimum requirements for biodiversity in land use planning and IEM | Minimum requirements for biodiversity in land use planning and IEM finalised | Progress: Minimum requirements for biodiversity in land use planning and IEM finalised

## Slide 36: ANNUAL PERFORMANCE SUMMARY : PROGRAMME 2
% Achieved | % Partially achieved | Exceeded Annual Targets
90% ( 9/10) | 10% (1/10) | 44% (4/9)
Chart: 
| On target | off target
Sales | 0.9 | 0.1

## Slide 37
PROGRAMME 3: OCEANS AND COASTS

## Slide 38: PROGRAMME 3: OCEANS AND COASTS
SO: Ocean and coastal environment protected and conserved |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Ocean management regime developed | Draft White paper on Ocean Management developed | Report on the analysis of legislative framework with implication on ocean governance in SA finalised | Progress: Report on analysis of legislative and institutional framework with implication on ocean governance in SA finalised
 |  | Implementation plan for the Ocean Management policy Developed | Progress: Implementation plan for the Ocean Management policy developed
Strategies and plans for management of ocean and coastal environment developed and implemented | National Ocean and Coast Spatial Plan (OCSP) framework submitted to 3D - Audit initiated for key datasets linking to fundamental elements of OCSP | National framework implemented | Progress: Nomination letters sent to relevant stakeholders for the establishment of a Technical Advisory Committee. Draft Committee terms of reference developed. Draft Implementation plan for Ocean and Coastal Spatial plan developed Challenges: Slow response by stakeholders in nominating members to serve on Advisory Committee Corrective Measures: Outstanding matters will be addressed and fast-tracked through the Operation Phakisa Delivery Unit

## Slide 39: PROGRAMME 3: OCEANS AND COASTS
SO: Ocean and coastal environment protected and conserved |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Strategies and plans for management of ocean and coastal environment developed and implemented | Draft National Coastal Management Programme (NCMP) | NCMP launched and implementation plan developed | Progress: The NCMP was launched on 14 March 2015 in East London. NCMP Implementation Plan developed
 | 6 of 25 updated local plans | Additional 1 plan updated | Progress: Knysna Zone local contingency plan reviewed and updated
 | 10 Regional oil spill contingency plans updated | One oil spill readiness exercise and one training session facilitated | Progress: Training workshop and oil spill readiness exercise for West Coast and Northern Cape region successfully undertaken in October 2014 in Veldrift
 | 20 estuary management plans developed | 5 estuary management plans developed | Progress: Estuarine Management Plans were developed as indicated below: uMngazi EMP developed Mngazana EMP developed Orange River Mouth EMP developed Durban Bay EMP under development Zinkwazi and Nonoti EMPs: Situation Assessment Reports (SAR) for the developed.

## Slide 40: PROGRAMME 3: OCEANS AND COASTS
SO: Ocean and coastal environment protected and conserved |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
 | Penguin Management Plan & Draft Shark Conservation Plan compiled | One new Draft protected Marine Species Plan (Turtle) | Progress: Draft Turtle management Plan developed
Percentage increase of coastline under MPA’s with partial or full protection | Full protection of 9.26% (324/3 600km) and partial protection of 13.5% (486/3600km) | Full protection of 9.5% (342/3 600km) and partial protection of 13.5% (486/3 600km) | Progress: 9,26% (333/3600km) of coastline is under full protection Addo MPA Declaration approved by the Executive Authority. Gazetting of the declaration of the Addo MPA will add 7,2km (0,2% of 3600km) of the coast length Betty’s Bay declaration is under consideration by the Executive Authority Cape Nature MPAs (Robberg, Goukamma) submission and regulations finalized Dwesa-Cwebe MPA –MPA resonation was gazetted for public comments, closed on

## Slide 41: PROGRAMME 3: OCEANS AND COASTS
SO: Ocean and coastal environment protected and conserved (Continued) |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage increase of coastline under MPA’s with partial or full protection | Full protection of 9.26% (324/3 600km) and partial protection of 13.5% (486/3600km) | Full protection of 9.5% (342/3 600km) and partial protection of 13.5% (486/3 600km) | Progress: 04 December 2014 and comments are being evaluated Namaqualand, Isimangaliso, Aliwal Shoal MPA have been identified as part of Operation Phakisa Oceans Economy project. Challenges: Consultation process in finalisation of MPAs took longer than anticipated Corrective measure: Betty’s Bay approval to be finalized in 2015/16. Declaration Addo MPA will be finalized in the first quarter of 2015/16

## Slide 42: PROGRAMME 3: OCEANS AND COASTS
SO: Ocean and coastal environment protected and conserved |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage increase of total area of Exclusive Economic Zone (EEZ) under protection and managed | 2 % (30 000/1 500 000 Km2 ) of EEZ protected | Draft monitoring proposal for Prince Edward Island developed | Progress: Draft declaration of Intent (outlining elements of the draft monitoring agreement with France) for the monitoring of Prince Edward Islands MPA has been compiled and finalized
Number of relief voyages (Antarctica and Islands) undertaken | 3 relief voyages undertaken | 3 relief voyages undertaken | Progress: 3 relief voyages were undertaken ( Marion islands , Gough , South African National Antarctic Expedition (SANAE) Voyage )
SO: Strengthened science policy interface |  |  | 
Ocean and coastal research projects survey completed and monitoring projects Undertaken | 3 surveys of priority habitats | 4 surveys of priority habitats | Progress: Robberg MPA and surrounding inshore priority areas resurveyed for benthic biodiversity and top predators Deep water survey off Walter Shoal undertaken) De Hoop MPA monitoring survey undertaken Pondoland MPA surveyed

## Slide 43: PROGRAMME 3: OCEANS AND COASTS
SO: Strengthened science policy interface |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Ocean and coastal research projects survey completed and monitoring projects Undertaken | Seabird population estimates for: • 12 species around SA (annually) • 1 Southern Ocean species (cumulative) | Seabird population estimates for: • 12 species around SA (annually) • 2 Southern Ocean species (cumulative) | Progress: Population estimates undertaken for all the 12 birds species and; 2 Southern Ocean species (Crozet and African Penguin)
 | 1 Coastal research project completed | 2 Coastal research projects completed | Progress: National Setback-line methods and recommendations (including estuaries) project plus supporting research studies (Coastal Vulnerability Assessment Phase 2) undertaken. National Wave height – (DEA – CSIR Coastal Vulnerability) Project.
Number of observational platforms contributing to an ocean and coastal observation and monitoring network | 4 Observational platforms deployed | 6 Observational platforms deployed | Progress: Buoys / moorings deployments: Nearshore Buoys deployed in Slangkop 4 Deep water Moorings in SAMBA (near Gough) - Elands Bay Buoy deployed Underwater Temperature Recorders (UTRs) serviced in Umkomaas and Amanzimtoti

## Slide 44: PROGRAMME 3: OCEANS AND COASTS
SO: Strengthened science policy interface |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of ecosystem process studies undertaken | 1 Integrated Ecosystem Project undertaken | 2 Multidisciplinary ocean functioning projects undertaken (in Benguela and Agulhas currents) | Progress: The Integrated Ecosystem Programme (IEP) multidisciplinary project undertaken ( Benguela Current) Challenges: Unavailability of the adequate ship, RV Algoa and lack of staff who were allocated in a different research cruise delayed the undertaking of the 2nd cruise to the 1st quarter in 2015/16 Corrective Measure: Multidisciplinary Cruise will be undertaken on the 4 -15 May 2015 in the Benguela Current region to monitor the seasonal variation of the ecosystem.

## Slide 45: ANNUAL PERFORMANCE SUMMARY : PROGRAMME 3
% Achieved | Partially achieved
81% (13/16) | 6% (3/16)
Chart: 
| On target | partial
Sales | 0.81 | 0.19

## Slide 46
PROGRAMME 4: CLIMATE CHANGE AND AIR QUALITY

## Slide 47: PROGRAMME 4: CLIMATE CHANGE AND AIR QUALITY
SO: Climate change impacts effectively managed |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of sectors for which Long Term Adaptation Scenarios (LTAS ) have been developed | • LTAS Phase 1 completed for 5 sectors (Water, Agriculture, Biodiversity, Marine Fisheries and Health). • 2 draft completed for 4 sectors (Human Settlements urban, coastal & rural, Disaster risk reduction) | Reports of phase 2 LTAS finalised for Human Settlement (Urban/ Rural/ Coastal) and Disaster Management sectors | Progress: LTAS Phase 2 Reports finalised covering human settlements, scenario planning, and disaster risk reduction sectors. Fact sheets completed and printed in all 7 reports. Phase 2 detailed reports in DEA website and printing finalised for Sub regional and scenario planning reports
Number of climate change adaptation studies conducted | Situational Analysis And Needs Assessment (SANAS) of provincial Climate Change response planning & adaptive capacity | Draft report of the Situational analysis and needs assessment (SANAS) of provincial CC response planning & adaptive capacity completed | Progress: Draft report of the Situational analysis and needs assessment (SANAS) completed

## Slide 48: PROGRAMME 4: CLIMATE CHANGE AND AIR QUALITY
SO: Climate change impacts effectively managed |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of Sector adaptation plans aligned with the National climate change response policy | Scoping report to support policy alignment for climate change adaptation, and draft sector adaptation plans | Recommendations for 4 sectors on mainstreaming climate change adaptation response measures into sector plans and policies (Human settlements – rural, urban and coastal, and disaster management) | Progress: Report on gap analysis/recommendations and policy alignment review for four adaptation sectors completed
National adaptation strategy developed and implementation facilitated | Long term adaptation scenarios and draft adaptation plans for key sectors | Framework for the National Climate Change Adaptation Strategy for South Africa developed | Progress: Framework for the National Climate Adaptation Strategy for South Africa completed
National Framework for Climate Services (NFCS) developed and implemented | Global Framework for Climate Services Roadmap for development of NFCS | Draft Framework for National Climate Services developed | Progress: Draft Framework for the National Climate Services developed

## Slide 49: PROGRAMME 4: CLIMATE CHANGE AND AIR QUALITY
SO: A fair contribution to the global effort to stabilize GHG concentrations in the atmosphere facilitated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of sector mitigation potential and impact studies conducted | 4 studies conducted | Draft National Carbon Sinks Atlas | Progress: Terms of reference for the appointment of as service provider developed and approved. Service provider for the project not appointed and planned annual target not achieved due challenges in accessing funds from the donor (DFID). Commitment received from GIZ to fund the project Challenges: DEA is awaiting the finalisation of the appointment of a service provider (CSIR). CSIR and GIZ in the process of finalising contractual and funding agreement. GIZ awaiting approval for the disbursement of funds from BMU head office in Germany. Corrective measures: Project will be concluded in the 2015/16 financial year

## Slide 50: PROGRAMME 4: CLIMATE CHANGE AND AIR QUALITY
SO: A fair contribution to the global effort to stabilize GHG concentrations in the atmosphere facilitated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of Climate Change Response Policy interventions implemented | Mapping existing relevant research, Planning and modelling processes concluded. A carbon budgets/ carbon tax report has been produced | Draft DEROs (Desired Emission Reduction Outcomes) for 5 Sectors] | Progress: Draft DERO report developed for 5 sectors
 |  | Draft Mix of measures for 5 sectors] | Progress: Draft Mix of measures framework developed
 |  | My 2050 Calculator Developed | Progress: My 2050 calculator developed
 | Framework for implementation of 3 flagships facilitated: • Public Works • Adaptation research • Waste Management | Flagship Framework coordinated and facilitated for 2 sectors: • Energy Efficiency • Transport | Progress: Framework of energy efficiency flagship developed. An overarching framework for flagships developed (including element of the transport sector flagship)
Number of sector mitigation plans aligned with the National Climate Change Response policy | Recommendations on alignment have been produced for the Public Transport and Waste Act | Guidelines for mitigation plans finalised | Progress: Final Mitigation Plans guideline prepared

## Slide 51: PROGRAMME 4: CLIMATE CHANGE AND AIR QUALITY
SO: Cleaner and healthy air |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
The National Air Quality Indicator (NAQI) | 0.972 | 1.135 | Progress: National Air Quality Indicator : 0.83
Number of air quality monitoring stations reporting to SAAQIS | 85 (72 Government owned) | 90 | Progress: 124 stations (100 Government-Owned + 24 Industry) reporting on SAAQIS.
Air Quality Act (AQA) Regulatory framework developed and implemented | 2 Draft offset policy developed | Emissions Offset Policy for AQM published | Progress: Emissions Offsets Guidelines finalised Challenge: Decision was taken to publish this as a guideline and not a policy – this means that the document produced will not go through cabinet and public consultations Corrective Measure: Guidelines have been processed for submission to the Executive Authority for approval and publication.

## Slide 52: PROGRAMME 4: CLIMATE CHANGE AND AIR QUALITY
SO: Cleaner and healthy air |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
AQA Regulatory framework developed and implemented | •S21 Amended •S23 small boilers •promulgated •Dust and modelling regs •2 Draft offset policy developed | Draft S23 – Small Scale Charcoal Plants Declared as Controlled Emitters] | Progress: Draft S23 – Intention to declare Small Scale Charcoal Plants as Controlled Emitters published for public consultation/comment.
 | •2 Priority Area AQMP •Waterberg- Bojanala AQMP under development(draft baseline assessment | 2014/15 Annual Plans of the National Priority Area AQMPs implemented (Vaal and Highveld) | Progress: 2014/15 Annual Plan for 3 AQMPs (Highveld and Vaal Triangle Airshed) implemented and an annual priority area progress report was produced and included in the 2014 NAQO report
 | •2 Priority Area AQMP •Waterberg- Bojanala AQMP under development(draft baseline assessment | Waterberg-Bojanala AQMP and threat assessment published in the gazette) | Progress: Waterberg-Bojanala AQMP approved for public comments

## Slide 53: ANNUAL PERFORMANCE SUMMARY : PROGRAMME 4
% Achieved | % Off Target | Exceeded Annual Targets
94% (16/17) | 6% (1/17) | 6% (1/16)
Chart: 
| On target | off target
Sales | 0.94 | 0.06

## Slide 54
PROGRAMME 5: BIODIVERSITY AND CONSERVATION

## Slide 55: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Percentage of land under conservation | 10.67% (13 016 461/121 991 200 ha of land under conservation) | 11.2%( 13 660 014/ 121 991 200 ha) | Progress: 11.3% under conservation (13 774 789 ha / 121 991 200 ha )
National Protected Area Expansion Strategy (NPAES) Reviewed and implemented | NPAES 2008. 5 Provincial expansion plans in place | NPAES Reviewed | Progress: NPAES reviewed

## Slide 56: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of additional stewardship sites established | Stewardship guidelines | One additional stewardship site established | Progress: Consultation facilitated and consensus reached between KwaZulu-Natal Ezemvelo Wildlife and Free State Province on the Provincial declaration process. Intent to declare Notice for one stewardship site in KZN published in the KZN Provincial Government Gazette. Challenge: Consultation with multiple stakeholders delayed finalisation of the process Challenge: Finalisation of the stewardship site to be concluded in 2015/16
Percentage of area of state managed protected areas assessed with a METT score above 67 % | 85 % of area of state managed protected areas assessed with a METT score above 67 % | 86 % of area of state managed protected areas assessed with a METT score above 67 % | Progress: 90% of area of state managed Protected Areas assessed with a METT score of 67% and above

## Slide 57: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of conservation and legislative tools to ensure the protection of species and ecosystems developed and implemented | Draft regulations for the registration of professional hunters, hunting outfitters and trainers developed | 14 conversation and legislative tools: Regulations for the registration of Professional Hunters and trainers Hunting Outfitters published for implementation | Progress: Draft regulations for the registration of Professional Hunters and Trainers Hunting Outfitters developed and published for public participation. Training workshop with provincial conservation authorities conducted and draft regulations finalised Challenge: Based on comments received during the public participation process (when the draft regulations were published for comments in the Gazette), Legal Services advised that the revised regulations be published for further public participation Corrective Measures: Regulations for the registration of Professional Hunters and Trainers Hunting Outfitters to be finalised in 2015/16

## Slide 58: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of conservation and legislative tools to ensure the protection of species and ecosystems developed and implemented | N/A | Review of Norms and standards for the management of elephants in South Africa initiated and amendments drafted | Progress: Draft amended/revised norms and standards for the management of elephants in South Africa developed

## Slide 59: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of conservation and legislative tools to ensure the protection of species and ecosystems developed and implemented | Comprehensive amendments to Threatened or Protected Species Regulations finalised and TOPS list reviewed | TOPS regulations published for implementation and guideline for implementation developed | Progress: Revised TOPS Regulations and species list finalised and submitted to Minister for approval to re-publish for public participation Challenge: Based on comments received during the public participation process, a number of new provisions were included and existing provisions were amended, which in both cases are of a more restrictive nature. Legal Services advised that the revised regulations be published for further public participation Corrective Measure: TOPS Regulations and species list will be finalised for implementation in 2015/16

## Slide 60: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of conservation and legislative tools to ensure the protection of species and ecosystems developed and implemented | Draft Amendment Regulations on Bioprospecting, Access and Benefit Sharing (BABS) Regulations developed and published for public participation | BABS Amendments Regulations approved by Inter-governmental structures | Progress: BABS Amendments Regulations approved by MINMEC
 |  | NEMBA review completed | Progress: NEMBA reviewed
 | NEMPAA ( National Environment Management : Protected Areas Act) Amendment Bill (MPAs) published for public comments (Phase 1) Stakeholder engagement on TFCAs and WHS to be incorporated in NEMPAA Amendment Bill (Phase 2) | Amendment Bill to incorporate MPAs into NEMPAA finalised | Progress: NCOP process completed and amendment Bill to incorporate MPAs into NEMPAA finalised
 |  | A draft Amendment Bill incorporating provisions relating to TFCAs and WHS reserves into NEMPAA developed | Progress: Draft Amendment Bill incorporating provisions relating to TFCAs and WHS reserves into NEMPAA developed

## Slide 61: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of conservation and legislative tools to ensure the protection of species and ecosystems developed and implemented | Draft norms and standards for the management of protected areas completed | Norms and standards for management of protected areas finalised | Progress: Norms and standards for the management of protected areas finalised and published for public participation Challenge: Extensive comments/ inputs required additional time to consider and to be incorporated in the final norms and standards Corrective Measure: Norms and standards for the management of protected areas will be published for implementation in 2015/16

## Slide 62: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of conservation and legislative tools to ensure the protection of species and ecosystems developed and implemented | Draft norms and standards for the declaration and inclusion of private nature reserves developed | Draft norms and standards for the declaration and inclusion of private nature reserves completed | Progress: 2nd draft of Norms and standards for declaration and inclusion of private nature reserves completed
 | Amendment of Regulations for Special Nature Reserves, National Parks and World Heritage sites completed. | Amendment of regulations for Special Nature Reserves, National Parks and World Heritage sites published for implementation | Progress: Regulations published in the Gazette for implementation
 | BMPs for Black Rhino, Albany Cycad and Pelargonium sidoides published in government gazetted. Norms and Standards for Biodiversity Management plans for Ecosystems finalised. | Draft BMP for 1 ecosystem developed | Progress: Draft BMP for one ecosystem ( Colbyn Valley Wetland) developed

## Slide 63: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of conservation and legislative tools to ensure the protection of species and ecosystems developed and implemented | Norms and Standards for Biodiversity Management plans for Ecosystems finalised | 2 Biodiversity Management Plans for species finalised for public participation (African Lion, White Rhino) ,and one BMP-S finalised for implementation (Bearded Vulture) | Progress: African Lion : Draft BMP for African Lion approved for public participation White Rhino : Draft BMP for White Rhino approved and published for public participation Bearded Vulture: BMP for Bearded Vulture target was finalised for implementation
 | Draft National Cycad Management Strategy | National Cycad Management Strategy and Action Plan approved | Progress: National Cycad Management Strategy and Action Plan approved
 |  | NBSAP review conducted | Progress: Draft NBSAP developed

## Slide 64: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Biodiversity Conserved, Protected and Threats Mitigated |  |  | 
Performance indicator | BASELINE | ANNUAL TARGET 2014/15 | Achievements/Challenges/Corrective measures
Number of tools to mitigate threats to biodiversity | NAP to combat land degradation | NAP review and alignment with the UNCCD 10 year Strategy and Framework finalised | Progress: NAP review and alignment with the UNCCD 10 year Strategy and Framework finalised. Implementation plan of the revised NAP developed.
 | Biodiversity Climate Change Adaptation Frameworks for 9 biomes developed | Draft Biodiversity Climate Change Adaptation Plans for 9 biomes developed | Progress: Draft Biodiversity climate change adaptation plans for 9 biomes developed.
Tools for the implementation of the Ramsar Convention developed and implemented | 20 management plans for Ramsar sites. | One Ramsar site designated | Progress: False bay Nature Reserve designated as Ramsar Site
 |  | Draft strategy to remove sites from the Montreux record developed | Progress: Draft strategy has been developed.

## Slide 65: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Fair Access and Equitable Sharing Of Benefits from Biological Resources Promoted |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Biodiversity Sector Transformation framework developed and implemented | Draft Biodiversity sector analysis | Biodiversity sector transformation framework finalised | Progress: Biodiversity Sector transformation framework has been finalised.
Number of sustainable natural resource based interventions and instruments identified, developed and implementation facilitated. | First Draft National Biodiversity Economy Development Strategy | National Biodiversity Economy Development Strategy finalised | Progress: Consultation finalised and first draft of the National Biodiversity Economy Development Strategy updated Challenge: Extensive and substantive comments inputs received during stakeholder consultation required additional time to process and incorporate Corrective Measure: Consultation finalised and inputs considered. Strategy will be finalised in 2015/16

## Slide 66: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Fair Access and Equitable Sharing Of Benefits from Biological Resources Promoted |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of sustainable natural resource based interventions and instruments identified, developed and implementation facilitated | 2 Biodiversity Economy development projects selected for future support | 2 Biodiversity Economy development projects supported for implementation | Progress: Communities supported in the development business plans for 2 Biodiversity Economy development projects: •Tyefu Aloe ferox harvesting •Balepye/Selwane Rhino farming projects
 | 2 cross border trails Operationalized | 1 cross border trail Operationalized | Progress: Desert Kayak cross border trail operationalized
 | 10 projects from the Trans Frontier Conservation Areas (TFCA) catalogue Implemented | 1 project from the TFCA investment catalogue Implemented | Progress: One project implemented (Sehlabathebe Lodge operational)

## Slide 67: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Fair Access and Equitable Sharing Of Benefits from Biological Resources Promoted |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of sustainable natural resource based interventions and instruments identified, developed and implementation facilitated | 4 natural resource based projects initiated (Awelani, Witsieshoek, People and Parks programme and Bushbuckridge) | 3 natural resource based projects implemented -Awelani, | Progress: Awelani lodge became operational in December 2014.
 |  | People and Parks programme | Progress: Implementation of the people and Parks programme reviewed, monitored and report prepared

## Slide 68: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Fair Access and Equitable Sharing Of Benefits from Biological Resources Promoted |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of sustainable natural resource based interventions and instruments identified, developed and implementation facilitated | 4 natural resource based projects initiated (Awelani, Witsieshoek, People and Parks programme and Bushbuckridge) | Implementation of the Bushbuckridge Master Plan (5 projects) facilitated | Progress: Implementation of five Bushbuckridge projects facilitated though the following interventions: •Tourism related projects: Business plan developed and project implementer has been appointed •African Honey Bee Project: 56 direct beneficiaries from 56 households in Bushbuckridge are benefiting •Bushbuckridge Fence project: The project manager has been appointed. The tender has been advertised, and the service provider has been recommended. Awaiting final confirmation from the adjudication committee)

## Slide 69: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Fair Access and Equitable Sharing Of Benefits from Biological Resources Promoted |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of sustainable natural resource based interventions and instruments identified, developed and implementation facilitated | 4 natural resource based projects initiated (Awelani, Witsieshoek, People and Parks programme and Bushbuckridge) | Implementation of the Bushbuckridge Master Plan (5 projects) facilitated | Progress (continued): •SMME development project: There is currently and agreement with KNP management to ring-fence contracts that will then be issued to this SMMEs once they finish with their training •Bushbuckridge Rural Enterprise and SMME Development Project: SMMEs are currently being trained by the University of Johannesburg

## Slide 70: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Strengthened Science Policy Interface |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions aimed at advancing the biodiversity science policy interface | Draft biodiversity research strategy | Biodiversity Research strategy finalised | Progress: Biodiversity Research Strategy has been approved
 | Intergovernmental Platform on Biodiversity and Ecosystem Services (IPBES) Established | National IPBES hub established | Progress: IPBES hub functional and launched at IPBES stakeholder Engagement Meeting-17 March 2015
 | Draft elephant research strategy | Elephant research strategy approved | Progress: Elephant Research Strategy was approved and published for implementation
 | Desertification Land Degradation and Drought (DLDD) research strategy | Phase 1: UNCCD DLDD land cover mapping impact indicator research finalised | Progress: UNCCD DLDD land cover mapping impact indicator research finalised

## Slide 71: PROGRAMME 5: BIODIVERSITY AND CONSERVATION
SO: Strengthened Science Policy Interface |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions aimed at advancing the biodiversity science policy interface | N/A | Report on the extent of MON810 insect resistance finalised | Progress: Report on the extent of insect resistance to MON810 finalised
 | N/A | 2 Science/policy input Reports compiled on Risk Analysis for intensive breeding in the wildlife sector; and State of play report on Predator control and conservation | Progress: 2 science/policy reports compiled (1) State of Play report (Predator control and conservation) (2) Risk analysis on intensive breeding

## Slide 72: ANNUAL PERFORMANCE SUMMARY : PROGRAMME 5
% Achieved | Partial Achievement | Exceeded Annual Targets
97% (35/36) | 3% (1/36) | 3% (1/35)
Chart: 
| On target | Work in progress
Sales | 0.97 | 0.03

## Slide 73
PROGRAMME 6: ENVIRONMENTAL PROGRAMMES

## Slide 74: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Improved socio-economic benefits within the environmental sector |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of Full Time Equivalents (FTEs) created | 16 706 | 35 936 | Progress: 33 318 Full Time Equivalents (FTEs) created Challenge: Some projects started late and resulted in beneficiaries working more than 23 days a month to catch up on work. These beneficiaries were excluded in accordance with EPWP reporting system validation rules Corrective Measure: 73 of 87 Implementing agents agreements have been signed and implementation will continue in 2015/16 financial year without the delay experienced in 2014/15

## Slide 75: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Improved socio-economic benefits within the environmental sector |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of Work Opportunities created (% of Women; % of Youth & % of People with Disabilities) | 63 378 (Women – 51%; Youth – 63% & People with Disabilities – 1, 86%) | Total 69 158 | Progress: 85 140 work opportunities created
 |  | (Women -55%;) | Progress: 85 140 work opportunities achieved. (Women- 53%)
 |  | Youth -60% | Progress: 85 140 (Youth – 70%)
 |  | People with Disabilities – 2%) | Progress: 85 140 (People with Disabilities – 1.66%)
Number of youths benefiting from the Youth Environmental Service | 963 | 900 | Progress: 900 Youths benefiting from the youth Environmental Service

## Slide 76: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Improved socio-economic benefits within the environmental sector |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Percentage of young people placed in exit Opportunities through Youth Environment Services (YES) programme | N/A | 75% | Progress: 39% (337/858) young people placed in exit opportunities after participation in the Youth Environmental Service (YES) Programme Challenge: lack of placement opportunities as employers prefer unemployed graduates over young people with only Senior certificate and one year training. Corrective Measure: Review the targets based on the baseline aligned to demand by the labour market.
Number of overnight visitor and staff accommodation units established | 104 | 22 | Progress: 33 (31 overnight visitor and staff accommodation units established and 2 units renovated)

## Slide 77: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Improved socio-economic benefits within the environmental sector |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of school desk equivalent | 22 424 | 120 000 | Progress: 160,090 school desk equivalent produced
Number of Small ,Medium and Micro-sized Enterprises ) SMMEs utilised (empowerment) | 2 611 | 2 210 | Progress: 2 210 SMMEs used

## Slide 78: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Ecosystem services restored and maintained |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of wetlands under rehabilitation | 96 | 115 | Progress: 115 wetlands under rehabilitation
Number of hectares of land where invasive alien plants treated/cleared (Initial Treatment) | - | 169 045 | Progress: 205 500 hectares of land where invasive alien plants treated/cleared
Number of hectares of land where follow up invasive alien plants treated/cleared (Follow up Treatment) | - | 560 339 | Progress: 556 722 hectares of land where follow up invasive alien plants treated/cleared
Number of hectares of degraded land under repair | 36 682 | 31 262 | Progress:\ 66 542 hectares of degraded land under repair
Number of kilometres of accessible coastline Cleaned | 2 203 | 2 113 | Progress: 2,113 kilometres of accessible coastline cleaned
Percentage of wild fires suppressed (provided there are not more than 2000) | 90 % | 90 % | Progress: 100% ( 3133/3133) fires suppressed)

## Slide 79: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Enhanced contribution to the environmental sector towards Sustainable Development and transition to a Green Economy |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of sustainable development tools/instruments developed and implemented | 4 policies and research strategies formulated South Africa Green Economy Modelling Report launched | Concept document for NSSD2 developed | Progress: NSSD2 concept document finalised
Number of Green Fund projects approved and implemented | • Green Fund budget allocation for 2012/13 & 2013/14 • 22 Green Fund implementation projects | 38 | Progress: 53 projects were approved for implementation.

## Slide 80: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Enhanced contribution to the environmental sector towards Sustainable Development and transition to a Green Economy |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of high- level environmental and sustainable development threat, weakness or opportunity early warning and/or response options researched and developed | Quarterly Environmental Threat, Weakness and Opportunity Scan (QETWOS) system established, and tested • 6 issues investigated – Shale gas carbon footprint; Peak phosphate; Environmental Offsetting; National Evaluations; MTSF 2014-2019; SIP 19 • 4 issue response options – Shale gas carbon footprint; National Evaluations; MTSF 2014-2019; and SIP 19 | Quarterly early warning and/or issue scanning Reports | Progress: 4 Quarterly Early Warning and/or issue scanning reports prepared and submitted to Management for consideration
 |  | 4 emerging issue response options formally submitted to top Management and approved responses developed | Progress: 4 emerging issue response options submitted to top management •SIP 19 Description document •Concerns around the apparent shallowness, narrow focus and the potentially dubious factual basis of the current national discourse on food and nutrition security •South Africa’s Response to Local and Global Change – Time for a new development approach •The Draft Environmental Offsetting Discussion Document

## Slide 81: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Enhanced contribution to the environmental sector towards Sustainable Development and transition to a Green Economy |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions for streamlining environmental authorisations finalised | 2 legal instruments evaluated and adjusted for comment | 1 legal instrument under evaluation/ adjustment/ development ((adoption of environmental instruments) | Progress: Discussion /concept document prepared and consulted process undertaken in intergovernmental fora Challenge: Delays in finalisation of financial provisioning regulations and focus on finalising EIA had impact on development of an adoption of environmental instrument tool. Corrective Measures: Draft regulations will be developed and finalised 2015/16

## Slide 82: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Enhanced contribution to the environmental sector towards Sustainable Development and transition to a Green Economy |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions for streamlining environmental authorisations finalised | 1 legal instrument finalized | 4 legal instruments gazetted for implementation (EIA, mine closure and financial provisioning regulations and revised listing notices) | Progress: •2 legal instruments gazetted for implementation (EIA regulations and revised listing notices) •Financial provisioning and mine closure regulations gazetted for public comment Challenge: Public consultation period on mine closure and financial provisioning regulations ended in December 2014, impacting on timeframe for consideration of comments. Corrective Measure: Financial provisioning and mine closure regulations will be finalised in 2015/16

## Slide 83: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Enhanced contribution to the environmental sector towards Sustainable Development and transition to a Green Economy |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions for streamlining environmental authorisations finalised | Interim registration board in place | Readiness plan for the registration of Environmental Assessment Practitioners Association of South Africa (ESPASA)developed | Progress: •Memorandum of Understanding including the work plan of EAPASA has been signed. •Section 24H regulations have been gazetted for comment are being finalised.
 | Inputs to Cabinet Report on hydraulic fracturing of shale gas | 1 initiative on hydraulic fracturing of shale gas coordinated and supported | Progress: Hydraulic Fracturing meeting held / attended and support provided. Inputs/comments submitted to Department of Minerals Resources on the draft of the “Proposed technical regulations for Petroleum Exploration and Exploitation.

## Slide 84: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Enhanced contribution to the environmental sector towards Sustainable Development and transition to a Green Economy |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions for streamlining environmental authorisations finalised | 3 Interventions for streaming environmental authorisations for Strategic Infrastructure Projects (SIP) and Industrial Policy Action Plan (IPAP) priorities under Development | 6 interventions for streamlining environmental authorisations for SIP and IPAP priorities developed | Progress: 5 Strategic Infrastructure Programmes (SIPs) interventions facilitated as follows: SIP 8 (2 SEAs – Wind and Solar) •Consultation on the Strategic Environmental Assessment (SEA) facilitated SIP 10 •Draft electricity grid expansion corridors finalised. SIP 16a •Draft sensitivity and electricity corridors map with site protocol finalised SIP 16b SKA Development SEA initiated and draft sensitivity map available 1 of the 6 planned intervention was finalised in 2013/14 (Matrix of environmental authorisation interventions for 18 SIPs and IPAP priorities )

## Slide 85: PROGRAMME 6: ENVIRONMENTAL PROGRAMMES
SO: Enhanced contribution to the environmental sector towards Sustainable Development and transition to a Green Economy (continued) |  |  | 
Performance indicator | Baseline | Annual Target 2014/15 | Achievements/Challenges/Corrective measures
Number of interventions for streamlining environmental authorisations finalised | 1 sector guideline developed (Ports sector guideline) | 1 sector guideline developed (mining review guideline) | Progress: Terms of reference for drafting mining guidelines has been finalised and request for proposals advertised Challenge: There was a need to delay a project due to financial constraints Corrective Measure: Planned work will be prioritised for finalisation in 2015/16

## Slide 86: ANNUAL PERFORMANCE SUMMARY : PROGRAMME 6
% Achieved | Partial Achievement | % Off Target | Exceeded Annual Targets
92% (23/25) | 4% (1/25) | 4% (1/25) | 29% (7/24)
Chart: 
| On target | Work in progress | off target
Sales | 0.92 | 0.04 | 0.04

## Slide 87
PROGRAMME 7: CHEMICALS AND WASTE MANAGEMENT

## Slide 88: PROGRAMME 7: CHEMICALS AND WASTE MANAGEMENT
SO: Less waste that is better managed |  |  | 
Performance Indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of Waste management instruments developed and implemented | Waste Act and Regulations National Waste Management Strategy | Health Care Risk Waste (HCRW) Management Regulations finalised | Progress: Draft regulations developed and recommendation for approval has been submitted to the Executive Authority for consideration Challenges: There are pending key issues between DEA and Department of Health and finalisation of the matters has delayed gazetting of the regulations Corrective Measures: The matter has been elevated to Ministerial level to be resolved. The process is being facilitated.
Number of Waste management instruments developed and implemented |  | Norms and Standards for the validation of the treatment efficacy and operation of a non- combustion technology used to treat health care risk waste finalised | Progress: Draft Norms and Standards developed and recommendation for approval has been submitted to the Executive Authority for consideration Challenges: There are pending key issues between DEA and Department of Health and finalisation of the matters has delayed gazetting of the regulations Corrective Measures: Elevated to Ministerial level to be resolved. The process is being facilitated.

## Slide 89: PROGRAMME 7: CHEMICALS AND WASTE MANAGEMENT
SO: Less waste that is better managed |  |  | 
Performance Indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of Waste management instruments developed and implemented | Waste Act and Regulations National Waste Management Strategy | Draft Import-Export regulations developed | Progress: Draft Import-Export regulations developed
Number of Waste management instruments developed and implemented |  | Draft Norms & Standards/Guidelines for Preparation of Waste Derived Fuels (WDF) developed | Progress: Best practice guideline for preparation of Waste Derived Fuel developed
Number of Waste management instruments developed and implemented |  | Draft Norms and Standards for waste sorting, shredding, grinding and bailing of general waste developed | Progress: Draft norms and standards developed

## Slide 90: PROGRAMME 7: CHEMICALS AND WASTE MANAGEMENT
SO: Less waste that is better managed |  |  | 
Performance Indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Percentage increase in waste being reused, recycled and recovered | 4 % of Waste Tyres recycled | 10 % | Progress: 25% of waste tyres recycled/used for energy recovery or re-used
Number of Integrated Industry Waste Management plans reviewed | An Integrated Industry Waste Tyre Management Plan Approved | 2 Integrated Industry Waste Management Plans reviewed | Progress: 2 Industry Management Plans reviewed ( e-waste plan and paper and packaging )
Percentage of unlicensed waste disposal sites authorised per annum | 4 waste management licences have also been processed.37 waste management application reports have been processed and submitted to Provinces | 80 % of unlicensed sites licensed | Progress: Survey to identify current unlicensed waste site undertaken, verification conducted and finalised, list of unlicensed site available (57 sites identified) .Process to appoint service provider is at an advanced stage. Funds secured and tender advertised closed in December 2014 Bid evaluation process will be conducted Challenges: Financial constraints and delays in securing funding for the projects has delayed achievement of the target. Corrective Measures: Funding has been secured and appointment of service providers is at an advanced stage. Licencing of waste sites will be finalised in the 2015/16 financial year
Number of buy-back centres established | 9 | 11 | Progress: 12 buy-back centres established

## Slide 91: PROGRAMME 7: CHEMICALS AND WASTE MANAGEMENT
SO: Less waste that is better managed |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of chemical management instruments developed and implemented | Multilateral Environmental Agreements (Stockholm, Rotterdam and Montreal) action plans implemented | National Implementation Plan for the Stockholm convention updated | Progress: National Implementation Plan for the Stockholm convention updated
Number of chemical management instruments developed and implemented |  | Draft Polychlorinated Biphenyl ( PCB) phase out plan for municipalities Developed | Progress: Draft PCB phase out plan developed
 |  | Study on impact of Minamata Convention on Mercury conducted | Progress: Terms of reference for undertaking of the study finalised and tender advertised in the Government Gazette and bid adjudication process undertaken Challenges: Financial constraints and delays in securing donor funds impacted on progress in the project Corrective Measures: Part of the required funding secured ( R3 million) and the remaining funds will be sourced from GEF Project prioritised for finalisation in 2015/16
Number of chemical management instruments developed and implemented |  |  | 

## Slide 92: PROGRAMME 7: CHEMICALS AND WASTE MANAGEMENT
SO: Less waste that is better managed |  |  | 
Performance indicator | Baseline | Annual target 2014/15 | Achievements/Challenges/Corrective measures
Number of chemical management instruments developed and implemented | Multilateral Environmental Agreements (Stockholm, Rotterdam and Montreal) action plans implemented | Draft National Chemicals Profile developed | Progress: Draft National chemicals profile developed. Draft policy discussion paper on chemicals management developed

## Slide 93: ANNUAL PERFORMANCE SUMMARY : PROGRAMME 7
% Achieved | Partial Achievement | Exceeded Annual Targets
69% (9/13) | 31% (4/13) | 13% (1/9)
Chart: 
| On target | Work in progress
Sales | 0.69 | 0.31

## Slide 94: SUMMARY OF OVERALL DEA PERFORMANCE
PROGRAMME | %ACHIEVED | Partial Achievement | % OFF TARGET | EXCEEDED ANNUAL TARGETS
ADMINISTRATION | 90% (47/52) | 4%(2/52) | 6% (3/52) | 43% (20/47)
LACE | 90% (9/10) | 10% (1/10) | - | 44% (4/9)
OCEANS AND COASTS | 81% (13/16) | 6% (3/16) | - | -
CC&AQM | 94% (16/17) |  | 6% (1/17) | 6% (1/16)
B&C | 97%% (35/36) | 3%(1/36) | - | 3% (1/36)
EP | 92% (23/25) | 4%(1/25) | 4% (1/25) | 29% (7/24)
C&WM | 61% (9/13) | 31% (4/13) | - | 13% (1/9)
DEA | 90% (152/169) | 7%(12/169) | 3% (5/169) | 24% (34/141)

## Slide 95: SUMMARY OF OVERALL DEA ANNUAL PERFORMANCE
%ACHIEVED | PARTIAL ACHIEVEMENT | % OFF TARGET | EXCEEDED ANNUAL TARGETS
90% (152/169) | 7%(12/169) | 3% (5/169) | 24% (34/141)
Chart: 
| Achieved | Partially Achieved | Off Target
Sales | 0.9 | 0.07 | 0.03