## Slide 1
Presentation to the Portfolio Committee on Cooperative Governance and Traditional Affairs
01 March 2015
COGTA Cumulative Performance Report 01 March to 31 December 2015
FY 2014/15

## Slide 2: PRESENTATION OUTLINE
Introduction
Part A: DCoG Cumulative Progress Performance (01 April to 31 December 2015)
Part B: State of Expenditure as at 31 January 2016

## Slide 3: Introduction
This performance report highlights actual progress against the planned targets set out in the Annual Performance Plan F/Y 2015/16.
A cumulative account of performance to date is provided covering progress from the 1st to the 3rd quarter. The likelihood of achieving the annual target by the end of the 4th quarter is also shown.
The State of Expenditure as at 31 January 2016 is also outlined

## Slide 4: 3rd Quarter Organisational dashboard
The Bar Chart shows that 70% (39 out of 56) of the planned targets were achieved while 27% (15 out of 56) were partially achieved, This level of performance is attributed to a number of factors such as the realignment of our functions to the B2B Programme. There is a high likelihood that the some of the 15 projects that are partially achieved will be achieved by the end of the financial year ending 30 March 2016. This is likely to bring the performance of the department to between 90 and 95% by the end of March 2016.
Chart: 
| Achieved | Partially Achieved | Not Due for Reporting
 | 39 | 15 | 2

## Slide 5: PART A: DCOG Cumulative Progress Performance (01 April to 31 December 2015)

## Slide 6: Programme One: Administration
Strategic Objectives
Improve information reliability and availability to support the strategic goals of the department by 2019;
Roll-out and monitor the implementation of the local government performance management system by 2019; and
Develop and implement an integrated monitoring and evaluation system for provincial departments of local government and municipalities by 2019

## Slide 7: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
1.1.1. Back to Basic interventions coordinated in identified Municipalities across all provinces (This report covers project 1.1.1, 2.1.1, 3.1.1, 4.1.1, 5.1.1 and 6.1.1) | Consolidation of progress reports | Back to Basics progress reports for all provinces have been consolidated. Since the 2nd quarter Action Plans for all dysfunctional municipalities are being implemented, and the 2nd phase is being implemented through the roll out of action plans. | Likely to be achieved Significant strides have been made in identifying challenges developing and implementing municipal specific action plans.
1.1.2 Four Back to Basics assessment reports submitted to Minister | Consolidate Back to Basics monthly assessment reports for Minister. | The quarterly assessment report covering the first 12 months of the Back to Basics monthly reporting (October 2014 to September 2015) is now finalised. | Likely to be achieved The consolidated Back to Basics assessment report will be submitted to the Minister for approval
1.1.3 2013/14 Municipal Systems Act section 48 developed 2013/14 Annual Municipal Performance Report | Consolidate Section 47 report from Provinces and develop draft Section 48. | The Section 48 report has not been finalised. Due to complexities at municipalities and floors in the legislative processes we have opted to develop the State of Local Government Report. | Likely to be achieved The State of Local Government offer a better insight of performance of municipalities.
1.1.4 Skills audit outcomes implemented as per the Human Resources plan | Develop Skills Audit Implementation Plan and conduct organisation wide skills audit. | The skills audit implementation plan is not developed pending approval of the organizational structure The organisational structure is still to be presented to the Minister for approval | Unlikely to be achieved We reorganised ourselves and implemented change management as a result this initiative had to be deferred to the new financial year 2016/17

## Slide 8: Programme Two: Policy Research and Knowledge Management
Strategic Objectives
The programme has the following predetermined objectives:
Build accountability in the Local Government Performance System through setting and enforcing clear performance standards by March 2019;
Provide efficient and effective corporate governance and administrative support services for COGTA to deliver on its mandate by March 2019; and
Strengthen the functionality of municipalities through the development and implementation of administrative institutional systems by March 2019.

## Slide 9: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
2.1.2 Local Government information hub is established to promote access to local government information | User specification document developed | Prototype of LG hub designed on SharePoint. Print Screen of the Catalogue of Information Sources published on the LG Hub Databases of the Information created and published on the LG hub | Likely to be achieved
2.1.3 Identify municipalities that are doing well in the five areas of back to basics | Number of case studies documented and published | A number of success stories have been documented amongst others, Metsimaholo and Matlosana | Likely to be achieved
2.1.4 Information Communication Technology enterprise architecture (EA) developed | 2.1.4 EA Repository implemented and configured Enterprise Architecture developed | The processes of appointing a service provider have been concluded however the EA could not be developed within the set timeframe | Unlikely to be achieved Due to internal delays this initiative had to be deferred to the new financial year 2016/17 .
2.1.5 B2B Dashboard on Municipal Performance management Information System Implemented | B2B dashboard monitored and maintained | Dashboard Developed and used to capture B2B info | 

## Slide 10: Programme 3:Governance and Intergovernmental Relations
Strategic Objectives
Build accountability for performance in the local government system through setting and enforcing clear performance standard by Mach 2019;
Structure IGR so that National and Provincial Government can support, monitor, intervene and enforce performance by March 2019;
Implement initiative to improve financial sustainability, revenue management and audit outcomes in local government by March 2019;
Promote public confidence in local government system through citizen engagement mechanisms by March 2019;
Strengthen anti-corruption measures and enforce applicable legislation and policies by March 2019; and
Promote good governance and an ethical culture and local government by March 2019

## Slide 11: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
3.1.2 Intergovernmental Monitoring Support Intervention Bill promulgated | Incorporate G & A and Ministers inputs into the draft Bill and submit | The revised IMSI Bill was submitted to the Minister in the 3rd Quarter for approval. | Unlikely to be achieved The promulgation is unlikely due to the need to the need to process through approval structures
3.1.3 Four reports on the implementation of outcome 9 presented to IGR structures | A report on the implementation of outcome 9 presented to IGR structures | The outcome 9 2nd quarter Progress report was developed and presented to the Technical Implementation Forum in September 2016, tabled and approved by Cabinet on 10 December 2015 | Likely to be achieved
3.1.4 Initiatives to influence the ability of municipalities to collect outstanding debt developed and implemented in 60 municipalities | Initiatives to influence the ability of municipalities to collect outstanding debt developed and implemented in 15 municipalities | Credit control and debt collection policies for 13 municipalities were evaluated to identify gaps. Two municipalities were assisted on the review of revenue enhancement strategy. | Likely to be achieved
3.1.5 A national campaign on improving the culture of payment implemented | A Campaigns on improving the culture of payment, anti-cable theft and illegal connections conducted in three provinces | The draft Campaign strategy was developed in the 3rd quarter , however the campaign will not be undertaken as its funding has been reprioritised into initiatives to improve debt collection in priority B2B municipalities | Unlikely to be achieved The payments campaign funding will be reprioritised into initiatives to improve municipal debt collection in priority B2B municipalities

## Slide 12: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
3.1.6. (58%) Unqualified audits for the 2014/15 audit | 3.1.6 All dysfunctional as well as municipalities with adverse and disclaimer opinions monitored to implement creditable audit action plans in response to the 2013/14 audit | In quarter 2, provinces conducted Annual Financial Statement (AFS) readiness assessments to ensure submission by 31 August. All municipalities in KZN, MP, NW, submitted AFS on time. Municipalities that did not submit are receiving support from a joint team of NT, Provincial Treasury and DCoG | Unlikely to be achieved The 2014/15 preliminary audit results were obtained from the AG on the 21 December 2015 to determine the disclaimers and adverse municipalities.
3.1.7. The functionality of MPAC's in all dysfunctional municipalities as well as municipalities with adverse and disclaimer opinions monitored and enforced | 3.1.7 All dysfunctional municipalities as well as municipalities with adverse and disclaimer opinions’ MPAC functionality monitored and enforced | As per MPAC capacity building plan, 2 training sessions were conducted in NW province to improve MPAC functionality in all municipalities. | Likely to be achieved
3.1.8 152 Municipalities assessed pertaining to compliance with the Municipal Property Rate Act and guidance provided to non-complying municipalities by 31 March 2016 | 3.1.8 Communicate findings and recommendations to non-compliant municipalities on corrective measure for the 2016/17 FY | Assessment of 86 (56.6%) of the 152 municipalities undertaken and letters to communicate findings prepared | Likely to be achieved

## Slide 13: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
3.1.9 Public participation regulatory framework piloted in 50 dysfunctional municipalities | 3.1.9 Draft framework piloted in 5 municipalities | Workshops on the draft compliance framework were held in municipalities within the Free State, Gauteng and Eastern Cape, Northern Cape, Mpumalanga and Western Cape. | Likely to be achieved
3.1.10 Conduct a nationwide citizen satisfaction survey | 3.1.10 Conduct survey and disseminate findings to the relevant sector departments/municipalities for intervention and publish results nationally. | The citizen satisfaction survey field-work has been completed and a draft report produced. | Likely to be achieved The findings will be disseminated to the relevant sector departments/municipalities for intervention and publish results nationally.
3.1.11Back to Basics priority municipalities supported to develop and implement citizen empowerment programmes | 3.1.11 Citizen empowerment programme Tool kit rolled-out in 14 "Back to Basic" priority municipalities Tool kit rolled-out in 13 "Back to Basic" priority municipalities | In the 2nd quarter consultation were undertaken in WC, MP, NC and GP. In the 3rd quarter 15 municipalities in attendance in Free State Province | Likely to be achieved All targeted B2B will be covered by end March 2016
3.1.12 Monitor the functionality of ward committees in line with the implementation of ward operational plans | 3.1.12 Convene a national evaluation session for outgoing councillors and ward committees to inform the next generation’s operations post 2016 local government elections | Workshops convened with all municipalities in the GP, EC, and FS on policies and structured community engagements plans and support provided to municipalities that have challenges and capacity to develop and implement community engagement plans. | Likely to be achieved This has a bearing on the next generation of councillors posts 2016 Local Government elections.

## Slide 14: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
3.1.13 Percentage (%) of municipalities implementing anti-corruption measures | Intensive monitoring of the "Not doing well" and the "At Risk" B2B Categories (70% of municipalities) Intensive monitoring of the all Categories of the municipalities | Elements of the Anti-Corruption Strategy implemented in identified B2B municipalities pending approval of the strategy. | Likely to be achieved Final approval of the Strategy as well as the Implementation Plan is pending
3.1.14 Annual progress report to minister of cases reported, investigated and prosecuted | Quarterly progress report on cases reported | A quarterly progress report regarding cases reported, investigated, and prosecuted for the period July to September and October to December 2015 has been prepared. the report covers progress on forensic investigations and municipal cases being investigated by the Directorate for Priority Crimes Investigation (DPCI), and cases reported through the National Anti-Corruption hotline. | Likely to be achieved The 4th quarterly report will form basis for the development of the Annual Report. The project will be achieved
3.1.15 Local Government Tribunal | Planned for 2017/18 | Not due for Reporting as it is planned for implementation in 2017/18, However legal opinion on the establishment of a Local Government Anti-Corruption Tribunal suggest that DCoG is not the ideal institution to carry out this initiative. | Planned for 2017/18 This project will be removed from the APP 2016/17
3.1.16 Local Government code of Good practice developed | The project was not initiated since the beginning of the financial year | The project was not initiated since the beginning of the financial year | This project will be removed from the APP 2016/17

## Slide 15: Programme 4 : National Disaster Management Centre
Strategic Objectives
Improve the system of disaster management and fire services across government by March 2019;
Build accountability for performance in Local Government System through setting and enforcing clear performance standard by March 2019; and
Develop a disaster management and fire services monitoring and evaluation system by March 2019

## Slide 16: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
4.1.2 First Draft Bill on Fire Services prepared | 4.1.2 Draft Bill on Fire Services consulted with key stakeholders First Draft Bill on Fire Services finalised | Consultation session on the Draft Bill was held with key stakeholders on 02 December 2015. | Likely to be achieved Currently integrating comments received during the consultation held during December 2015.
4.1.3 National disaster management and fire services advocacy and public awareness campaigns facilitated in 9 provinces | 4.1.3 Advocacy and Public Awareness campaigns facilitated in 2 Provinces & Hold a National International Day for Disaster Reduction (IDDR) in 1 province Advocacy and Public Awareness campaigns facilitated in 3 Provinces | Supported the Northern Cape, the North west and Gauteng provinces towards commemoration of respective provincial IDDR's. - Hosted the National IDDR in collaboration with the Eastern Cape Province and the Chris Hani District Municipality in Queenstown. - Conducted a drought awareness campaign in collaboration with the Kwazulu-Natal Provincial Disaster Management Centre in the UMkhanyakude District Municipality | Likely to be achieved In the 4th quarter the centre will brief the NDMAF on the progress made in the implementation of the DM M&E Framework and the Implementation Plan on and thereafter, a report will be compiled for sign-off by the Head of the National Centre. The database is updated as and when disasters are declared
4.1.4 Report on the implementation of disaster management M&E Framework | 4.1.4 Update the database as and when disasters are declared during 2015/16 for all provinces Report on the implementation of Disaster Management band Fire Services M&E Framework produced by 31 March 2016 for KZN, MP and WC | Database for all provinces updated as and when disasters were declared during 2015/16 financial year. | Likely to be achieved The Chief Directorate will brief the NDMAF on the progress made in the implementation of the DM M&E Framework and the Implementation Plan on 18 February 2015 and thereafter, a report will be compiled for sign-off by the Head of the National Centre. The database is updated as and when disasters are declared

## Slide 17: Provincial and Municipal Government Support
Strategic Objectives
Strengthen the functionality of municipalities through the development and implementation of administrative institutional systems by March 2019;
Facilitate and coordinate capacity building initiatives in order to build capable municipalities by March 2019;
Build accountability for performance in the Local Government system through setting and enforcing clear performance standards by March 2019;
Promote good governance and an ethical culture in Local Government by March 2019; and
Facilitate the restructuring of cities space economy through changes in land use planning and management by March 2019

## Slide 18: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
5.1.2 Four Quarterly report on corrective actions taken to enforce compliance with competency requirements as prescribed in the MSA and its Regulations | 5.1.2 A report on number municipalities monitored and assisted in filling of posts with competent municipal managers and s56 managers | 23 priority municipalities were identified Mpumalanga (4), KZN (5), Limpopo (4), Western Cape (1), Eastern Cape (3), Free State (2), North West (2) and Northern Cape (2). During the reporting period 42 Senior Manager posts were advertised, 10 were not compliant to the prescribed requirement and municipalities have been advised to issue erratum. | Likely to be achieved The 3rd quarter reports on municipalities that have been assisted to fill vacant posts have been developed. The final report will be produced by end financial year. The project will there been achieved as planned.
5.1.3 Report on the status of appointment of competent and suitably qualified municipal manager and s56 managers | 5.1.3 All serving and newly appointed municipal managers and section 56 managers subjected to competency assessment. Competency assessment report and recommendations for dealing with senior managers who do not meet requirements compiled. | The total number of competent and suitably qualified section 56 managers who meet the relevant skills, expertise, competency and qualifications as prescribed in the Regulations has increased from 189 from the previous quarter to 200. | Likely to be achieved A report on the status of appointment of competent and suitable qualified municipal managers is been generated . The project will be achieved.

## Slide 19: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
5.1.4 Four 4 Quarterly report on corrective actions taken to enforce compliance with competency requirements as prescribed in the MSA and its Regulations | 5.1.4 A report on the number of corrective actions taken to enforce compliance with competency requirements as prescribed in the Municipal Systems Act and Regulations | A total of 38 appointments were made in contravention of the Systems Act. 23 corrective measures have been taken by the MECs responsible for local government between July and December 2015. Letters were written through the Minister to the MECs of the affected 5 municipalities to instituted corrective measures | Likely to be achieved A report in this regard is been generated and will be available by end of the financial year.
5.1.5. Guidelines on roles and responsibilities of office bearers and delegation framework developed | 5.1.5 Finalize guidelines and delegation framework Implement guidelines and delegation framework | Draft guidelines have been developed and consulted with provinces, presented to the Ministers. | Unlikely to be achieved To facilitate implementation, the roles and responsibilities of office bearers have to be regulated
5.1.6 Preparations for the 2016 local government elections facilitated | 5.1.6 Consultations with stakeholders Report on preparation for Local government elections developed | Meeting of the Technical Task Team on Municipal Elections held on 12 June 2015. Meeting of the Municipal Demarcation Transition Committee held on 29 October 2015 | Likely to be achieved

## Slide 20: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
5.1.7 Amend Local Government Laws Amendment Bill | 5.1.7 Certification by Chief State Law Adviser introduce the Local Government Laws Amendment Bill into Parliament Local Government Laws Amendment Bill presented to Cabinet | Pre-certification obtained from the OCSLA. The LGLAB has been changed to the Municipal Structures Amendment Bill. | Likely to be achieved
5.1.8 Progress on concept paper and business plan to establish a local government skills development institute (Local Government Learning Centre) | 5.1.8 Local Government Skills Development Institute (Local Government Learning Centre) launched Alignment and incorporation of existing management training programmes into the institute (Learning Centre) including roll-out Design and curriculum development of training programmes) | Discussion are planned with SALGA and DPSA to eliminate duplications and find common ground for a more effective Learning centre and the correct placement thereof | Unlikely to be achieved This project will be partially achieved by the end of the financial year

## Slide 21: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
5.1.9 Capacity building strategies and interventions plans for councillors and officials implemented | 5.1.9 Capacity building strategies and intervention plans for Councillors and Officials implemented, progress monitored and reported | A draft National Capacity Building Framework (NCBF) Model incorporating capacity building strategy for both elected and appointed officials developed for further consultation | Unlikely to be achieved The strategy will be implemented in the next financial year
5.1.10 Batho Pele Service Standards Framework for Local Government adopted and implemented | At least 6 provinces fully implementing Batho Pele Service Standards Framework for Local Government Agenda and presentations for the development of Batho Pele service standards framework for local government in Limpopo all 9 provinces fully implementing Batho Pele Service Standards Framework for Local Government | Four (4) provinces (KwaZulu-Natal, Gauteng, Western Cape and Limpopo) developed the Batho Pele Service Standards and supported municipalities to develop Batho Pele Service Charters. This is in addition to the three provinces supported in the first six months of the financial year. | Likely to be achieved The project will be achieved against the target. Nine Municipalities that fully implemented Batho Pele service standards framework for Local Government

## Slide 22: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
5.1.11. Eight Cities and towns supported to develop long term strategies and SDFs. | 5.1.11 (4 and 3) | Approval obtained from the World Bank to support the development of a toolkit for strengthening planning in intermediate cities | Unlikely to be achieved Projects reconceptualised to focus on the development of a toolkit for strengthening planning
5.1.12. Twelve districts supported to develop integrated development plans (IDP) that reflect sectional and spatial convergence by target date | 5.1.12 Four Districts supported to develop IDP | Engagement held with five districts in Kwa-Zulu Natal, Free State and Gauteng province (UThungulu, UMkhanyakude, Lejweleputswa, Thabo Mofutsanyane, West Rand districts) on the development of integrated development plans (IDP) that reflect sectional and spatial convergence. Four were supported in quarter 2 | Likely to be achieved
5.1.13 Annual Oversight Report on the state of governance | Oversight Report | The initiative to develop an Annual Oversight Report on the state of governance has not been done, however the report on State of Local Government will give insight in the state of governance of municipalities | Likely to be achieved

## Slide 23: PROGRAMME FIVE: INFRUSTRUTURE AND ECONOMIC DEVELOPMENT
Build accountability for performance and local government system through setting and enforcing clear performance standards by March 2019;
Provide and maintain 1 million work opportunities through building capacity of participants and establishing strategic partnership by March 2019;
Coordinate and implement sustainable infrastructure development and maintenance initiatives in order to improve the quality of service and extend infrastructure to unserved communities by March 2019;
Facilitate private sector through the implementation of innovative programmes that stimulate Local Economics by end March 2019; and
Support the implementation of sustainable infrastructure development and maintenance initiatives in order to improve the quality of service and extend infrastructure to unserved communities by March 2019

## Slide 24: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
6.1.2 Inter- Ministerial Committee(IMC) resolutions implemented | IMC Resolutions Implemented | IMC (IMTT) meetings held on 18 and 24 November 2015 Technical IMC held on 9 December 2015 In the progress of formulating a Cabinet Memorandum on the IMTT | Likely to be achieved This project will be achieved in carrying the agenda of the IMC Cabinet pronouncements
6.1.3 Identified municipalities monitored to reduce the % of households with Infrastructure but no service | Identified municipalities monitored to reduce the % of households with Infrastructure but no service | 1 of 27 Districts Municipality assessments concluded and those for Amatole DM, Sekhukhune, Umzinyathi, Bojanala are in progress Ten municipalities monitored to reduce % of households with infrastructure but no services | unlikely to be achieved Diagnostic on the Amathole District and the results have been shared with the municipality. We are on track to complete the diagnostics on the first ten districts by the end of the calendar year. The plan is to complete the remaining 17 districts will be completed by the end of 2017 This project was reconceptualised after being transferred to MISA The focus is now on conducting thorough diagnostic assessment in identified district municipalities

## Slide 25: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
6.1.4 Identified municipalities monitored to reduce the % of households without Infrastructure for basic service | Identified municipalities monitored to reduce the % of households without Infrastructure for basic service | (25%) 100 000 (32%) 130 000 Diagnostic on the Amathole District and the results have been shared with the municipality. We are on track to complete the diagnostics on the first ten districts by the end of the calendar year. The plan is to complete the remaining 17 districts will be completed by the end of 2017 | Unlikely to be achieved This project was reconceptualised after being transferred to MISA. The focus is now on conducting thorough diagnostic assessment in identified district municipalities
6.1.5 Forty Five (45) of Municipalities supported to develop Infrastructure assets registers | Municipalities supported to develop Infrastructure assets registers | In quarter 2 Technical support was provided in 8 municipalities: Siyancuma, letsemeng, Naledi, uMzinyathi, Dr Ruth Mompati, Pisley ka Seme and Merafong In Quarter 3 Technical support provided to the following targeted local municipalities: Thulamela, Greater Tubatse, Mogalakwena, Kopanong, Masilonyana, Sundays River, Makana, Randfontein, Kannaland, Prince Albert | Likely to be achieved This project was reconceptualised after being transferred to MISA

## Slide 26: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
6.1.6 Fifty municipalities supported to capture the Infrastructure assets in the Municipal Infrastructure Performance Management Information System (MIPMIS) by target date | 15 municipalities | MIPMIS rolled out to the following 20 targeted municipalities: Hantam, Richterveld, Capricorn, Molemolle, Aganang LM, Setsoto, Phumelela, Nketoana, Mantsopa LM,Umhlabuyalingana, Mzumbe, Ezingolweni, Umkhanyakude, Impendle, Amathole, Amajuba, City of Matlosana, Tlokwe, Marquassi Hills, Nyandeni | Likely to be achieved This project is being implemented through MISA
6.1.7 Forty Five (45) municipalities supported to spend at least 7% of operational budgets on maintenance of Infrastructure | 15 municipalities | Technical support provided to targeted local municipalities; Mkhondo, City of Matlosana, Randfontein and Amahlathi | Likely to be achieved This project is being implemented through MISA

## Slide 27: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
6.1.8. 45 Municipalities supported to develop operations and maintenance plans | 15 Municipalities | Technical support provided to the following targeted local municipalities: Mkhondo, City of Matlosana, Randfontein and Amahlathi. | Partially Achieved The annual target was revised to 21 municipalities instead of 45 and the quarterly target to 10 instead of 15 ensuing the structural changes in the Department
6.1.9 70 Municipalities supported to update their indigent registers | Undertake assessment of indigent registers in the 35 municipalities communicate findings and recommendations to targeted municipalities on corrective measures to update their indigent registers | Assessment of indigent registers were undertaken in targeted 35 municipalities | Likely to be achieved
6.1.10 Ten 10 municipalities supported to implement programmes in partnership with the private sector | 5 Municipalities | Engagement with five districts in Kwa-Zulu Natal, Free State and Gauteng province (UThungulu, UMkhanyakude, Lejweleputswa, Thabo Mofutsanyane, West Rand districts) | Likely to be achieved

## Slide 28: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
6.1.11 Additional 10 000 (197 000 cumulative) work opportunities provided | Additional 2500 (194 500 cumulative) work opportunities provided Additional 2500 (197 000 cumulative) work opportunities provided 197 000 work opportunities provided by 31 March 2015 | 5095 additional work opportunities provided for the 3rd Quarter | Likely to be achieved
6.1.12 (10 additional municipalities) with CWP sites established by 31 March 2016 | 6.1.12 (3 additional municipalities) with CWP sites 2 additional municipalities with CWP sites | 11 additional municipalities with CWP Sites established; and an additional 8 Municipalities have Council Resolutions that approve the establishment of CWP Sites | Likely to be achieved

## Slide 29: PROGRESS ON THE ACHIEVEMENT OF PREDETERMINED OBJECTIVES
Annual Target | Q3 Targets | Cumulative progress (Q1 to Q3) | Likelihood of Achievement 4th Quarter Target
6.1.13 (100% )Participants and relevant stakeholders trained | (75%) participants and relevant stakeholders trained 100% participants and relevant stakeholders trained | 4676 participants and 47 LRCs were trained in Quarter 3 FY 2015/16 | Likely to be achieved
6.1.14 (5 partners ) with public, private sector and civil organisations established | One partnership with public, private sector and civil organisations established | Two partnerships formed with Reggio Emilio municipality located in Italy. Department of Small Business Development (DSBD) where they provided training to CWP at the Erasmus site in Tshwane. 18 CWP cooperatives have been registered through this partnership | Likely to be achieved

## Slide 30
Part B: STATE OF EXPENDITURE AS AT 31 JANUARY 2016

## Slide 31: STATE OF EXPENDITURE: ANALYSIS PER PROGRAMME AS AT 31 JANUARY 2016

## Slide 32: STATE OF EXPENDITURE: ANALYSIS PER ECONOMIC CLASSIFICATION AS AT 31 JANUARY 2016

## Slide 33: EXPENDITURE ANALYSIS PER ECONOMIC CLASSIFICATION AS AT 31 JANUARY 2016 (Cont.)

## Slide 34: STATE OF EXPENDITURE AS AT 31 JANUARY 2016 (Cont.)
OVERALL EXPENDITURE
The total expenditure of the Department amounts to R49,520 billion at the end of 31 January. The total amount spent represents a 69,9 per cent spending rate of the total appropriation.
The main reasons for the lower spending against the projections are:
• The withholding of Municipal Infrastructure Grant funds; and
The uncertainty with regard to the release of the Disaster Relief grants.

## Slide 35: EXPENDITURE ANALYSIS PER ECONOMIC CLASSIFICATION AS AT 31 JANUARY 2016 (Cont.)
    COMPENSATION OF EMPLOYEES
R’000
Budget (2015/16): R271 777
Preliminary Actual expenditure (31 January): R215 421 (79.3 per cent spent)
Variance R 56 356
The spending is less than the target of 83 per cent for a ten-month period.
The under-spending is mainly due to the delays experienced with the filling of some posts in the CWP functional areas and general turn-over rate of staff.

## Slide 36
    GOODS AND SERVICES: R’000
Budget (2015/16): R2 539 693
Actual expenditure (31 January): R1 938 580 (76,3 per cent spent)
Variance R 601 113
The spending is less than the target of 83 per cent for a ten-month period.
The main reason for the under-expenditure is the delays in the payment of claims from CWP Implementation Agents.
EXPENDITURE ANALYSIS PER ECONOMIC CLASSIFICATION AS AT 31 JANUARY 2016 (Cont.)

## Slide 37: EXPENDITURE ANALYSIS PER ECONOMIC CLASSIFICATION AS AT 31 JANUARY 2016 (Cont.)
    TRANSFERS AND SUBSIDIES
R’000
Budget (2015/16): R67 997 386
Actual transfers (31 January): R47 357 218 (69.6 per cent spent)
Variance R20 640 168
The spending is less than the target of 83 per cent for an ten-month period.
The under-spending is mainly due to the uncertainty with regard to the payment of disaster relief grants and withholding of Municipal Infrastructure Grants (MIG) in respect of some municipalities.

## Slide 38: EXPENDITURE ANALYSIS PER ECONOMIC CLASSIFICATION AS AT 31 JANUARY 2016 (Cont.)
    PAYMENTS OF CAPITAL ASSETS
R’000
Budget (2015/16): R6 521
Actual expenditure (31 January): R8 213 (125.9 per cent spent)
Variance (R1 692)
The spending is higher than the target of 83 per cent for an ten-month period.
The spending reflect a 25.9 per cent over-spending based on the budget allocation of R6.5 million. The over-spending is mainly due to the procurement of critical office equipment.

## Slide 39: Response to Recommendations raised by the Portfolio Committee
The Budgetary Review and Recommendations Report (BRRR) of the Committee for the 2013/14 and 2014/15 financial years highlighted key recommendations related to performance information of the Department of Cooperative Governance (DCoG).
More effort should be put on ensuring that the performance indicators implemented by the Department and its entities are Specific, Measurable, Achievable, Reliable and Time-bound; and
The Department should meet with Auditor-General to ensure that they share the same understanding with respect to the expected standards of compliance with reporting requirements.
Subsequent to the engagement with the Committee held on 14 October 2015
A team comprising of planning, monitoring and evaluation technical expects from across CoGTA (Department of Cooperative Governance, Department of Traditional Affairs and the Municipal Infrastructure Support Agent) was established to attend to all performance information related matters.
The forum held Three working session between October and December 2015 to subject all Draft APP FY 2016/17 targets to the SMART criteria (Specific, Measurable, Attainable, Realistic and Time Bound)
We have also established the Internal Controls Committee to deal with finance and governance related matters
Engagements were held with the Office of the AG with the recent one having taken place on 11th of February 2016.The forum will continuously do the work up until there are noticeable improvement on the management of performance information.
39
Notes: 24 October was engagement on BRRR

## Slide 40: Conclusion
Despite the challenges experienced in the reconfiguration of reporting lines as a result of the restructuring process, some stability is being maintained, there is a high likelihood that the majority of the 20 projects that have been partially achieved will be achieved by the end of the financial year ending 30 March 2016. When adding these to the 29 projects that are achieved, the performance of the department will increase to between 80 and 85% by the end of March 2016.
Some of the above actions were not progressed due to a decision to redeploy resources to pressure point activities in pursuit of the B2B programme implementation.
The context for pursuing planned initiatives at a wider scale has also changed considerably in that the external environment is become much more difficult. There are cost containment measures resulting from a weak domestic economy coupled with systematic failures or weaknesses in pursuit of the developmental local government.
The main challenges over the coming years will be to progress and implement these priorities We however, believe that, within this budgetary parameters and limited staffing resources, some improvement will be realised through the implementation of the 2nd phase of the B2B programme and related tactics like the application of the 80/20 paleo rule.

## Slide 41
THANK YOU!