## Slide 1: USDG PRESENTATION City of Tshwane Portfolio Committee on Human Settlements
Tues, 12 April 2016: COJ, COT, EKURHULENI, NMB, BCM
Wed, 13 April 2016: MANGAUNG, ETHEKWINI, CAPE TOWN

## Slide 2: 1. MTSF RESPONSE

## Slide 3: ACHIVEMENTS MADE AGAINST THE 2011/16 IDP
KPI | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 (to March 2016)
CRU’S | 104 | 92 | 104 | 48 | -
Title Deeds | 3 372 | 3 450 | 6 902 | 4 485 | 3 090
Social housing | - | - | 160 | 86 | 118
Houses built | 400 | - | 973 | - | -
Land acquisition | - | - | 1 | 3 | 2 (by June)
Roads constructed | 49.1km | - | 79.046km | 24.86km | -
Water connections | 4 200 (2000) | 9 845 (2000) | 1 675(2000) | 7 464 (2000) | -
Sewer connections | 4 200 | 9 845(1000) | 1 675(1000) | 7 464 (1000) | -

## Slide 4: CONTRIBUTION TOWARDS MTSF TARGETS
MTSF TARGET 2019 | National 5 yr MTSF Target for Metro | Annual MTSF Target | 2014/15 Achieved | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 5 yr MTSF (Less or more)
750 000 households in informal settlements upgraded to Phase 2 of the Informal Settlements Upgrading Programme | 15869 households upgraded in informal Settlements | 6750 | 7625 | 5669 | 3000 | 2900 | 4300 | 15869
Individual households: Water Sanitation Electricity | 63208 | 12641 | 4935 | 10641 | 18287 | 17252 | 12093 | 63208
 | 63208 | 12641 | 4935 | 10641 | 18287 | 17252 | 12093 | 63208
 | 69437 | 13887 | 17180 | 12891 | 12550 | 8162 | 18654 | 69437
Shared services (number of households benefiting) Water Sanitation | 7982 households | 2000 | 0 | 2000 | 2400 | 1200 | 2382 | 7982
Title Deeds: 563 000 for new developments Pre-1994 housing stock Post-1994 housing stock | 17230 (Free holding) | 2469 | 2500 | 2700 | 3000 | 3500 | 4000 | 17230
 | 8298 (sectional tittle) | 972 | 492 | 1200 | 1500 | 1800 | 2500 | 8298
10 000 of hectares of well-located land | 470 hectares | 120 | 10 | 150 | 100 | 110 | 200 | 470
City of Tshwane: MTSF

## Slide 5: 2. 2016/17 - 2018/19 TARGETS

## Slide 6: 2.1A 2016/17 - 2018/19 LAND
PROPERTY NAME | SIZE | REGION | PLANNED INTERVENTION | Internal valuations | External valuations
Remainder of Portion 39 of the farm Strydfontein 306 JR | 12.1589 ha | 1 | Mixed integrated development to accommodate Region 1 housing backlog | R1 200 000.00 | R1 950 000.00
2. Remaining extent of the farm Klipeiland 524-JR (Cultura Park X 8) | 70.0318 ha | 7 | Mixed integrated development to accommodate Region 7 informal settlements | R14 250 000.00 | R191 000 000 .00
3. Remainder of Portions 29 , portions 30 to 38 Pienaarspoort 339-JR | 89.4 ha | 6 | Mixed integrated development | R22 500 000.00 | R13 400 000.00
4. Remainder of Portion 5 Pienaarspoort 338-JR | 7.4 ha | 6 | Expansion to accommodate Mamelodi informal settlements | In progress | In progress
5. Portion 48 of the farm Uitzicht alias Rietvalei 314 - JR | 130 ha | 3 | Mixed integrated development to accommodate Atteridgeville informal settlements | In progress | In progress

## Slide 7: 2.1A 2016/17 - 2018/19 LAND
POTENTIAL PRIVATE PARTNERSHIPS |  |  |  |  | 
PROPERTY NAME | SIZE | REGION | PLANNED INTERVENTION | Internal valuations | External valuations
Portions 12 & 13 Knopjeslaagte 385-JR | 109 ha | 4 | Mixed integrated development to accommodate Region 4 housing backlog | Will be conducted as soon as there is an agreement on the percentage to be sold to the City. | Will be conducted as soon as there is an agreement on the percentage to be sold to the City

## Slide 8: 2.2A 2016/17 - 2018/19 INFORMAL SETTLEMENTS UPGRADING
The Upgrading of Informal Settlements Plan 2016/17 – 2018/19, and demonstrate:
  Existence of strategy to upgrade settlements incrementally and in-situ with an eye to formalise and integrate them within the urban core; and
  Existence of settlement plans and readiness to implement settlement plans in 2016/17 - 2018/19;
The City has adopted the Re Aga Tshwane Programme ( almost aligned to the NUSP) and offers serviced stands ( water & sewer up to 250m²) with the following:
  Outside toilet with washing line
  Stand pipe
  Electricity connection
  Waste removal (bin)
  3 pre-approved building plans (for those that can immediately start with building)
  Title Deeds
Benefit: proof of address and municipal account (revenue, reduce unaccounted for water & electricity due to illegal connection)

## Slide 9: 2.2B 2016/17 - 2018/19 USDG TARGETS: INFORMAL SETTLEMENTS
Number of informal settlements targeted for upgrading - 10
Number of informal settlements targeted for upgrading with upgrading plans - 10
Number of households living in informal settlements targeted for upgrading –app. 6 000.
Number of informal settlements in situ upgraded (services provided): -4
Number of informal settlements targeted for formalisation (services and tenure provided) through relocation and in situ upgrading -10
Number of households living in informal backyard rental agreement
Number of household living in informal settlements provided with essential services( water, sanitation and electricity) – approximately 7000

## Slide 10: 2.5 2016/17 - 2018/19 USDG TARGETS: MEGA PROJECTS
REGION | Number of units | Estimated costs | Planned allocation 2016/17 | Planned allocation 2017/18 | Planned Allocation 2018/19
Region 1&2 | 43 600.00 | 12 426 000 000.00 | 393 440 150 | 370 854 550 | 235 968 275
Region 3 | 36 550.00 | 10 416 750 000 | 254 702 588 | 497 183 175 | 378 552 831
Region 4 | 20 595.00 | 5 973 315 000 | 255 907 425 | 190 620 850 | 102 736 750
Region 5&6 | 22 366.00 | 4 325 742 000 | 176 481 750 | 124 670 938 | 114 550 938
Region 7 | 10 000.00 | 2 850 000 000 | 224 516 188 | 244 934 188 | 250 334 188
Total | 163 111.00 | 44 541 807 000 | 1 337 298 100 | 1 285 017 850 | 1 026 781 231

## Slide 11: REGION 1 & 2 PROJECTS/ TSHWANE NORTH DEVELPOMENT NODE
Project name & size | Priority | Overall Budget | Progress and Interventions required
Soutpan (Phase 1 – 8) Size: 16 600 | Short term | 4 731 000 000.00 | Bulk infrastructure and top structures required. Contractor appointed and on site.
Hammanskraal West Ext 2,3,4 Size: 7 000 | Short term | 1 995 000 000.00 | Planning in progress; request bulk funding
Winterveldt URP Size: 20 000 | Medium term | 5 700 000 000.00 | Presidential Urban Renewal Programme Project. Contractor on site. Bulk infrastructure and top structures required
Sterkwater Size: 30 000 | Long term | 0.00 | Environmental issues and the City will no longer acquire the land.
TOTAL: 43 600 |  | 12 426 000 000.00 | 

## Slide 12: REGION 1& 2 PROJECTS/ TSHWANE NORTH DEVELPOMENT NODE
PROJECT NAME | DATA | PROJECT SIZE / PROJECTIONS | 2016/17 FY | 2017/18 FY | 2018/19 FY
1. Soutpan Phase 1 - 7 | Stands/Services | 16 600 | 200 | 500 | 500
 | Houses |  | 100 | 150 | 200
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 2 910 041 254 | R 21 364 950 | R 40 742 675 | R 46 190 025
 | Bulk water | Soutpan ext 2 - 1000 stands | R 20 000 000 |  | 
 | Water reticulation |  |  | R 10 000 000 | 
 | Bulk Sewer |  | R 15 000 000 |  | 
 | Sewer reticulation |  |  | R 10 000 000 | 
 | Roads and stormwater |  |  | R 22 500 000 | R 26 200 000
 | Budget Estimates (USDG) | R 103 700 000 | R 35 000 000 | R 42 500 000 | R 26 200 000

## Slide 13: REGION 1& 2 PROJECTS/ TSHWANE NORTH DEVELPOMENT NODE
PROJECT NAME | DATA | PROJECT SIZE / PROJECTIONS | 2016/17 FY | 2017/18 FY | 2018/19 FY
3. Hammanskraal West Ext 2, 3 &4 | Stands/Services | 7 000 | - | - | -
 | Houses |  | 100 | 250 | 300
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 1 227 125 830 | R 103 868 375 | R 34 670 938 | R 41 605 125
 | Budget Estimates (USDG) | R 0 | R 0 | R 0 | R 0
4. Winterveldt URP | Stands/Services | total 20 000 |  |  | 
 | Houses |  | 200 | 250 | 300
 | Units |  | 100 | 150 | 150
 | Budget Estimates (HSDG) | R 3 506 073 800 | R 53 986 750 | R 74 045 938 | R 110 980 125
 | Bulk Water reservoir | As planned in the 5 year plan | R 93 000 000 |  | 
 | Water reticulation |  |  | R 44 000 000 | 
 | Bulk sewer |  |  | R 55 000 000 | 
 | Sewer reticulation |  | R 34 000 000 | R 34 895 000 | 
 | Roads and stormwater |  | R 44 540 000 | R 45 000 000 | R 10 993 000
 | Budget Estimates (USDG) | R 361 428 000 | R 171 540 000 | R 178 895 000 | R 10 993 000
 | TOTAL HSDG | R 7 643 240 884 | R 179 220 075 | R 149 459 550 | R 198 775 275
 | TOTAL USDG | R 465 128 000 | R 206 540 000 | R 221 395 000 | R 37 193 000

## Slide 14: REGION 3 PROJECTS – Tshwane West and Central Development Node
 | Project name | Priority | Overall Budget | Progress and Interventions required
Tshwane West Node | Lotus Garden West Size: 4 000 | Short term | 1 425 000 000.00 | Contractor appointed.
 | Fortwest Ext 4 & 5 Size: 7 492 | Short term | 1 995 000 000.00 | Contractor appointed , work in progress
 | Danville/Elandspoort Ext 3 Size: 2 000 | Short term | 570 000 000.00 | Contractor on site- top structures
 | Zandfontein Size: 4008 | Short term | 2 308 500 000.00 | Contractor appointed
 | Lady Selbourne Size: 4 300 | Short term | 1 425 000 000.00 | Contractor appointed, Land claims delaying the implementation of project. Bulk infrastructure and top structures required
Tshwane Central | Capital Park; Vermuelen Point; Kruger Park; Townlands Size: 9 450 | Long term | 2 693 250 000.00 | Rental/ Social housing units. Planning in progress
 | TOTAL: 36 550 |  | 10 416 750 000.00 | 

## Slide 15: REGION 3 PROJECTS – Tshwane West Development Node
PROJECT NAME | DATA | PROJECT SIZE / PROJECTIONS | 2016/17 FY | 2017/18 FY | 2018/19 FY
1. Lady Selbourne | Stands/Services | 5 000 | - | - | -
 | Houses |  | 50 | 100 | 100
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 876 518 450 | R 10 234 188 | R 15 988 375 | R 18 988 375
 | Water reticulation | R 86 000 000 | R 10 000 000 | R 33 000 000 | R 43 000 000
 | Sewer Reticulation | R 86 000 000 | R 10 000 000 | R 33 000 000 | R 43 000 000
 | Roads and stormwater | R 165 000 000 |  | R 66 000 000 | R 72 600 000
 | Budget Estimates (USDG) | R 337 000 000 | R 20 000 000 | R 132 000 000 | R 158 600 000
2. Danville/Elandspoort Ext 3 | Stands/Services | 2 700 | 600 | 1 000 | 1 000
 | Houses |  | 50 | 400 | 375
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 473 319 963 | R 33 748 100 | R 89 874 500 | R 86 407 406
 | Budget Estimates (USDG) | R 0 | R 0 | R 0 | R 0
3. Lotus Gardens West | Stands/Services | 5 000 |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 876 518 450 | R 4 600 000 | R 1 200 000 | R 2 000 000
 | Water reticulation | R 90 000 000 | R 30 000 000 | R 60 000 000 | 
 | Sewer Reticulation | R 90 000 000 | R 30 000 000 | R 60 000 000 | 
 | Roads and stormwater | R 151 800 000 | R 66 000 000 | R 59 400 000 | R 26 400 000
 | Budget Estimates (USDG) | R 331 800 000 | R 59 400 000 | R 0 | R 0

## Slide 16: REGION 3 PROJECTS – Tshwane West Development Node
PROJECT NAME | DATA | PROJECT SIZE / PROJECTIONS | 2016/17 FY | 2017/18 FY | 2018/19 FY
4. Fortwest Ext 4 & 5 | Stands/Services | 7 492 | 300 | 300 | 300
 | Houses |  | - | - | 200
 | Units |  | - | - | -
 | Budget Estimates (HSDG) | R 1 313 375 245 | R 12 120 300 | R 10 320 300 | R 38 057 050
 | Bulk Water | R 30 000 000 | R 20 000 000 |  | 
 | Water reticulation | R 92 000 000 | R 50 000 000 |  | 
 | Sewer Reticulation | R 115 000 000 | R 50 000 000 |  | 
 | Roads and stormwater | R 247 236 000 | R 50 000 000 | R 100 000 000 | R 53 236 000
 | Budget Estimates (USDG) | R 484 236 000 | R 0 | R 0 | R 0
5. Zandfontein | Stands/Services | 4 008 |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 702 617 190 | R 600 000 | R 6 400 000 | R 6 000 000
 | Water reticulation | R 100 200 000 | R 40 000 000 | R 50 200 000 | 
 | Sewer reticulation | R 100 200 000 | R 40 000 000 | R 50 200 000 | 
 | Roads and stormwater | R 90 000 000 |  | R 50 000 000 | R 40 000 000
 | Budget Estimates (USDG) | R 290 400 000 | R 80 000 000 | R 150 400 000 | R 40 000 000
6. Kirkney / Andeon | Stands/Services | 1 700 |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 298 016 273 | R 0 | R 0 | R 0
 | Water reticulation | R 42 500 000 | R 17 000 000 | R 20 500 000 | 
 | Sewer Reticulation | R 42 500 000 | R 17 000 000 | R 20 500 000 | 
 | Roads and stormwater | R 78 500 000 |  | R 50 000 000 | R 28 500 000
 | Budget Estimates (USDG) | R 163 500 000 | R 34 000 000 | R 91 000 000 | R 28 500 000
 | Total HSDG Region 3 | R 4 540 365 571 | R 61 302 588 | R 123 783 175 | R 151 452 831
 | Total USDG Region 3 | R 1 606 936 000 | R 193 400 000 | R 373 400 000 | R 227 100 000

## Slide 17: REGION 3 PROJECTS – Tshwane Central Development Node
PROJECT NAME | DATA | PROJECT SIZE / PROJECTIONS | 2016/17 FY | 2017/18 FY | 2018/19 FY
1. Capital Park | Stands/Services | - |  |  | 
 | Houses |  |  |  | 
 | Units |  | - | - | -
 | Budget Estimates (HSDG) | R 0 | R 0 | R 0 | R 0
 | Budget Estimates (USDG) | R 0 | R 0 | R 0 | R 0
2. Vermuelen Point | Stands/Services | 9 450 |  |  | 
 | Houses |  |  |  | 
 | Units |  | 100 | 150 | 150
 | Budget Estimates (HSDG) | R 2 845 404 450 | R 32 250 000.00 | R 47 375 000.00 | R 47 375 000.00
 | Budget Estimates (USDG) | R 0 | R 0 | R 0 | R 0
3. Kruger Park | Stands/Services | - |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 0 | R 0 | R 0 | R 0
 | Budget Estimates (USDG) | R 0 | R 0 | R 0 | R 0
4. Townlands | Stands/Services | - |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 0 | R 0 | R 0 | R 0
 | Budget Estimates (USDG) | R 0 | R 0 | R 0 | R 0
 | Total HSDG | R 2 845 404 450 | R 32 250 000 | R 47 375 000 | R 47 375 000

## Slide 18: REGION 4 PROJECTS – TSHWANE SOUTH
Project Name | Priority | Overall Budget | Progress and Interventions required
Olievenhoutbosch 27, 36 and 60 Size: 5 959 | Short term | 1 698 315 000.00 | Contractor on site – Ext 27 & 60 and land acquisition in progress for Ext 36. Top structures required.
Various privately owned farm land earmarked for acquisition Size: 15 000 | Medium term | 4 275 000 000.00 | Land identification and assessment in progress
TOTAL: 20 959 |  | 5 973 315 000.00 | 

## Slide 19: REGION 4 PROJECTS – TSHWANE SOUTH
PROJECT NAME | DATA | PROJECT SIZE PROJECTIONS | 2016/17 FY | 2017/18 FY | 2018/19 FY
1. Olivenhoutbosch 60, 27,36 | Stands/Services | 5 959 | 250 | - | -
 | Houses |  | 420 | 190 | 200
 | Units |  | 250 | 250 | 
 | Budget Estimates (HSDG) | R 1 044 634 689 | R 73 547 425 | R 62 820 850 | R 27 736 750
 | Roads and stormwater (60) |  | R 24 200 000 |  | 
2. Olivenhoutbosch 27 | Top structures | 1 800 | R 75 000 000 | R 75 000 000 | R 75 000 000
 | Road and storm water |  | R 83 160 000 | R 52 800 000 | 
 | Total HSDG | 1 044 634 689 | 148 547 425 | 137 820 850 | 102 736 750
 | Total USDG | 160 160 000 | 107 360 000 | 52 800 000 | -

## Slide 20: REGION 5 & 6 PROJECTS – TSHWANE EAST
Project name | Priority | Overall Budget | Progress and Interventions required
Land acquisition Transnet: Portion 52 and remainder of Portion 47 of Pienaarspoort 339 , remainder of 19, 20, 21, Remainder of portion 30; 33 of Franspoort Size: 7 188 | Medium term | To be determined | Negotiations with Transnet in progress. Bulk infrastructure required
Nellmapius Ext 4 and 22 Size: 6 178 | Short term | 1 760 730 000.00 | Services installations in progress
Habitech: Nellmapius Ext 24, Heathely 25, 26 *Portion 27&28 and other of Heathely Farm Size: 5 000 | Short term | 1 425 000 000.00 | Contractor appointed, work in progress.
Portions 3;12;15;17 &45 of Pienaarspoort Size: 4 000 | Short term | 1 140 012 000.00 | Planning in progress. Bulk infrastructure required.
TOTAL: 22 366 |  | 4 325 742 000 | 

## Slide 21: REGION 5& PROJECTS – TSHWANE EAST
PROJECT NAME | DATA | PROJECT SIZE / PROJECTIONS | 2016/17 FY | 2017/18 FY | 2018/19 FY
1. Nellmapius Ext. 4 | Stands/Services | 4 298 |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 753 455 260 | R 0 | R 0 | R 0
 | Budget Estimates (USDG) | R 0 | R 0 | R 0 | R 0
2. Nellmapius Ext 21 | Stands/Services | 2 500 |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 438 259 225 | R 0 | R 0 | R 0
 | Water reticulation |  | R 5 000 000 |  | 
 | Sewer reticulation |  | R 6 000 000 |  | 
 | Roads and stormwater |  | R 10 000 000 | R 28 745 000 | 
 | Budget Estimates (USDG) | R 59 197 500 | R 28 745 000 | R 0 | R 0
3. Nellmapius Ext. 22 | Stands/Services | 1 880 |  |  | 
 | Houses |  | 100 | 150 | 150
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 329 570 937 | R 63 868 375 | R 70 802 563 | R 70 802 563
 | Budget Estimates (USDG) | R 0 | R 0 | R 0 | R 0
4. Nellmapius Ext. 24 | Stands/Services | 2 568 |  |  | 
 | Houses |  | 50 | 50 | 50
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 450 179 876 | R 6 934 188 | R 6 934 188 | R 6 934 188
 | Water reticulation |  | R 25 000 000 |  | 
 | Sewer reticulation |  | R 25 000 000 |  | 
 | Roads and stormwater |  | R 20 000 000 | R 40 000 000 | R 29 880 000
 | Budget Estimates (USDG) | R 162 300 000 | R 76 934 188 | R 46 934 188 | R 36 814 188
 | Total HSDG | R 1 971 465 298 | R 70 802 563 | R 77 736 750 | R 77 736 750
 | Total USDG | R 221 497 500 | R 105 679 188 | R 46 934 188 | R 36 814 188

## Slide 22: REGION 7 - TSHWANE FAR EAST
Project name | Priority | Estimated Budget | Progress and Interventions required
Zithobeni Ext 8, 9 and Zithobeni Heights Size: 9 000 | Short term | 2 565 000 000.00 | Contractor on site for Ext 8, 9 and Heights. Top structures required for Zithobeni 9 in 2015/16 FY. Bulk infrastructure required for Zithobeni Heights and the surrounding areas.
Rama City Size: 2 000 | Medium term | 285 000 000.00 | Contractor on site. Funding for topstructures required
TOTAL: 10 000 |  | 2 850 000 000.00 | 

## Slide 23: REGION 7 - TSHWANE FAR EAST
PROJECT NAME | DATA | PROJECT SIZE / PROJECTIONS | 2016/17 FY | 2017/18 FY | 2018/19 FY
1. Zithobeni Ext 8 & 9 | Stands/Services | 4 000 |  |  | 
 | Houses |  | 50 | 50 | 50
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 701 214 760 | R 6 934 188 | R 6 934 188 | R 6 934 188
 | Bulk sewer (9) | R 45 000 000 | R 25 000 000 |  | 
 | Roads and stormwater (8+9) | R 126 000 000 | R 42 582 000 |  | R 24 000 000
 | Water reticulation (8) | R 36 000 000 |  | R 10 000 000 | R 20 000 000
 | Sewer reticulation (8) | R 36 000 000 |  | R 10 000 000 | R 20 000 000
 | Budget Estimates (USDG) | R 243 000 000 | R 67 582 000 | R 20 000 000 | R 64 000 000
2. Zithobeni Heights | Stands/Services | 3 962 |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 694 553 220 | R 0 | R 0 | R 0
 | Bulk water | R 300 000 000 | R 100 000 000 | R 100 000 000 | R 100 000 000
 | Water reticulation | R 79 240 000 | R 20 000 000 | R 29 000 000 | 
 | Sewer reticulation | R 79 240 000 | R 20 000 000 | R 20 000 000 | 
 | Roads and stormwater | R 98 000 000 |  | R 33 000 000 | R 59 400 000
 | Budget Estimates (USDG) | R 556 480 000 | R 140 000 000 | R 182 000 000 | R 159 400 000
3. Rama City | Stands/Services | 1 000 |  |  | 
 | Houses |  | - | - | -
 | Units |  |  |  | 
 | Budget Estimates (HSDG) | R 175 303 690 | R 0 | R 0 | R 0
 | Water reticulation | R 18 000 000 | R 5 000 000 | R 13 000 000 | 
 | Sewer ewticulation | R 18 000 000 | R 5 000 000 | R 13 000 000 | 
 | Roads and stormwater | R 51 100 000 |  | R 10 000 000 | R 20 000 000
 | Budget Estimates (USDG) | R 87 100 000 | R 10 000 000 | R 36 000 000 | R 20 000 000
 | Total HSDG | R 1 571 071 670 | R 6 934 188 | R 6 934 188 | R 6 934 188
 | Total USDG | R 886 580 000 | R 217 582 000 | R 238 000 000 | R 243 400 000

## Slide 24
2.7B 2017/18 - 2018/19 HSDG TARGETS
Note: The business plans for 2017/18- 2018/19 have not yet been finalised with GDHS

## Slide 25: 2.7 B 2016/17 HSDG TARGETS
Project name | Targeted units | Budget
Fortwest Ext 4 | 100 | R11 094 700
Fortwest Ext 5 | 150 | R16 642 050
Zandfontein | 100 | R11 094 700
Thorntreeview | 100 | R11 094 700
Fortwest Ext | 100 | R11 094 700
Ga-Tsebe | 50 | R5 547 350
Kopanong | 100 | R11 094 700
Kudube ext 9 | 100 | R11 094 700
Mabopane EW | 100 | R11 094 700
Mabopane Erf 29355 | 50 | R5 547 350

## Slide 26: 2016/17 - 2018/19 HSDG TARGETS
Project name | Targeted units | Budget
Nellmapius x21 | 100 | R11 094 700
Nellmapius x 24 | 50 | R5 547 350
Timberlands – social housing units | 100 | R11 094 700
Townlands – social housing units | 100 | R11 094 700
Boyzen- social housing units | 100 | R11 094 700
Olievenhoutbosch x60 | 100 | R11 094 700
Refilwe manor | 100 | R11 094 700
Thembaview Ext 1 | 100 | R11 094 700
Zithobeni Ext 1 | 100 | R11 094 700
Chantelle x39 social units | 100 | R11 094 700
Sunnyside erf | 130 | R14 423 110
Fortwest ext | 100 | R11 094 700

## Slide 27: HSDG allocation 2015/16 FY
R86 656 000 gazetted for the following projects :-
Refilwe Manor : 100
Zithobeni x 9 : 307
Kudube x 9 : 100
Olievenhoutbosch x 60 : 100
Mamelodi Erf 29355 : 74
TOTAL :781
NB: Expenditure to date is R41 655 006
Invoices received R22 000 000

## Slide 28
Project Name | Target of 2016/17 | Target 15/16 | Completed Foundations | Actual Wallplates | Actual Roofed | Actual Completed
Refilwe Manor | 518 | 100 | 102 | 102 | 100 | 2
Zithobeni Ex 9 | 800 | 307 | 550 | 301 | 204 | 2
Kudube x 9 | 300 | 100 | 22 | - | - | -
Olievenhoutbosch x 60 | 759 | 200 | 63 | 22 | 2 | -
Mamelodi Erf 29355 | 150 | 74 | 74 | 48 | 2 | -
 | 2527 | 781 | 811 | 473 | 308 | 4
Progress to date:
Construction of Top-structures

## Slide 29: Social Housing Projects
Programme/Project | Region | Total No. of Units | FY 2016/17 | FY 2017/18 | FY 2018/19 | FY 2019/20
Townlands Project: | 3 | 900 | 100 | 350 | 450 | -
Sunnyside Erf 708 & 709 | 3 | 260 | 130 | 130 | - | -
Chantelle X39 | 1 | 1107 | 100 | 407 | 300 | 300
Fort West Ext 4 | 3 | 400 | 100 | 300 | - | -
Timberland Project: | 3 | 320 | 0 | 120 | 200 | -

## Slide 30: 2016/17 HSDG: Existing contractual obligations with Province
Refilwe Manor : 418
Zithobeni x 9 : 493
Kudube x 9 : 200
Olievenhoutbosch x 60 : 559
Mamelodi Erf 29355 : 76
TOTAL : 1746
NB: indicative HSDG R203 033 000

## Slide 31: 3. FINANCIAL PERFORMANCE 2015/16: CAPITAL BUDGET BREAKDOWN
Funding Source | Adjusted Budget | YTD Adjusted Expenditure Projections 31 March 2016 | YTD Actual Expenditure 31 March 2016 | Variance (Actual vs Adjusted Projection) | Actual as % of Adjusted Expenditure Projection | Actual as % of Adjusted Budget
 | R'000 | R'000 | R'000 | R'000 | % | %
Council Funding | 170 945 | 42 990 | 6 388 | (36 602) | 14.9% | 3.7%
Public Transport Infrastructure and Systems Grant (PTIS) | 770 609 | 502 618 | 466 968 | (35 650) | 92.9% | 60.6%
Neighbourhood Development Partnership Grant (NDPG) | 62 619 | 33 784 | 42 251 | 8 466 | 125.1% | 67.5%
USDG (replaces MIG)- Urban Settlements Development Grant | 1 537 550 | 774 979 | 889 429 | 114 450 | 114.8% | 58.4%
Intergrated National Electrification Programme (INEP) | 37 001 | 18 375 | 12 988 | (5 388) | 70.7% | 35.1%
Capital Replacement Reserve | 13 806 | 1 493 | 2 157 | 664 | 144.5% | 15.6%
Other Contributions | 1 773 | 1 674 | 883 | (791) | 52.8% | 49.8%
Financial Management Grant (FMG) | 250 | 22 | 22 | 0 | 100.0% | 8.7%
Community Library Services (CLS) | 7 551 | 3 462 | 4 187 | 725 | 120.9% | 55.4%
Borrowings | 1 200 000 | 678 795 | 582 841 | (95 955) | 85.9% | 48.6%
Public Contributions & Donations | 150 000 | 91 118 | 74 766 | (16 352) | 82.1% | 49.8%
Social Infrastructure Grant | 38 682 | 10 435 | 7 220 | (3 214) | 69.2% | 18.7%
LG SETA Discretionary Allocation | 18 407 | 4 879 | 405 | (4 474) | 8.3% | 2.2%
Total | 3 995 193 | 2 164 625 | 2 090 505 | (74 121) | 96.6% | 52.3%

## Slide 32: 4. FINANCIAL PERFORMANCE: USDG 2015/16
Department | Project Name | Current Budget 2015/16 | Cumulative Expenditure Projection | Cumulative Capex Actual | Actual expenditures | Cumulative Committed | Cumulative Capex Expenditure Projection Not/ (Over) Spent | % Cumulative Capex Expenditure Projection Not/ (Over) Spent
Energy & Electricity | Electricity for All | 91 344 858 | 54 731 358 | 54 399 066 | 60% | 22 550 018 | 332 292 | 1%
 | Tshwane Public Lighting Programme | 30 991 045 | 20 921 602 | 17 517 634 | 57% | 7 597 284 | 3 403 968 | 16%
Sub - total |  | 122 335 903 | 75 652 959 | 71 916 700 | 59% | 30 147 302 | 3 736 260 | 0
Housing & Human Settlement | Water Provision | 174 208 170 | 83 188 498 | 81 635 346 | 47% | 4 877 393 | 1 553 152 | 2%
 | Sewerage | 149 834 769 | 43 608 306 | 39 125 979 | 26% | - | 4 482 326 | 10%
 | Roads and Stormwater | 258 921 070 | 142 441 495 | 142 677 796 | 52% | 5 290 327 | -236 300 | 0%
 | Project Linked Housing | 100 000 000 | 36 082 884 | 95 082 884 | 95% | - | -59 000 000 | -164%
Sub - total |  | 682 964 679 | 305 321 183 | 358 522 005 | 51% | 10 167 720 | -53 200 822 | -2
Water & Sanitation | Refurbishing of Water Networks and Backlog Eradication | 180 815 293 | 79 653 362 | 98 147 616 | 54% | - | -18 494 254 | -23%
Sub - total |  | 180 815 293 | 79 653 362 | 98 147 616 | 54% | - | -18 494 254 | -0
Transport | Flooding Backlogs: Sosh & Winterveldt Area | 347 460 678 | 194 697 331 | 250 134 792 | 72% | 8 422 960 | -55 437 461 | -28%
 | Flooding Backlogs: | 4 000 000 | 2 305 442 | 1 905 442 | 48% | 1 304 449 | 400 000 | 17%
 | Mabopane Station Modal Interchange | 27 000 000 | 14 429 014 | 14 434 172 | 53% | 577 | -5 158 | 0%
Sub - total |  | 378 460 678 | 211 431 787 | 266 474 406 | 70% | 9 727 986 | -55 042 619 | -0
Office of the City Manager | RE - AGA - Tshwane | 154 218 000 | 101 730 829 | 94 368 329 | 61% | 54 304 034 | 7 362 500 | 7%
Sub - total |  | 154 218 000 | 101 730 829 | 94 368 329 | 61% | 54 304 034 | 7 362 500 | 0
Total |  | 1 532 794 553 | 773 790 120 | 889 429 056 | 58% | 104 347 042 | -115 638 936 | -2
 | Adjusted budget | 1 537 550 333 | 773 790 120 | 889 429 056 | 58% |  |  | 

## Slide 33: 5. NON-FINANCIAL PERFORMANCE: USDG 2015/16
Project Name | Item intervention | Project Outputs 2015/16 |  | Non-financial progress Q2
Kudube 9 | Construction of roads | 3 | 74,75 | Engineering designs submitted and provisionally approved pending the results of a WULA
Thorntreeview | Construction of roads | 8 | 90 | 70% Roadbed completed,62% of storm water trenches excavated, 58% of pipes laid. On track
Mabopane EW | Construction of roads | 2 | 12 | Waiting for approval of designs
Olievenhoutbosch 60 | Construction of roads | 3 | 77 | The stream crossing design and costing approved. Awaiting final approval of roads. Plans in place to shift funding to other roads projects

## Slide 34: 5. NON-FINANCIAL PERFORMANCE: USDG 2015/16
Fortwest 4&5 | Construction of roads | 7 | 07 | Contract on site Site establishment completed - Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill
Soshanguve X5 | Construction of roads | 4 | 37 | Contract on site Site establishment completed Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill
Soshanguve X12 | Construction of roads | 3 | 39 | Contractor on site - Site establishment completed - Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill
Soshanguve X13 | Construction of roads | 3 | 39 | Contractor on site -Site Establishment completed Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill
Zithobeni Ext 8&9 | Construction of roads | 3 | 102 | Contractor on site - Site establishment complied, Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill and V Drains

## Slide 35: 5. NON-FINANCIAL PERFORMANCE: USDG 2015/16
Rama City | Nr of stands in settlements provided with sewer reticulation | 100 | 4,32 | Excavation ,bedding pipe laying and blanket on progress
Kudube 9 | Nr of stands in settlements provided with sewer reticulation | 100 | 74,75 | 1490 stands water lines connections completed, negotiations with house owners regarding the moving /relocation of obstructions
Mabopane Ext 1 | Nr of stands in settlements provided with sewer reticulation | 150 | 20,21 | Excavation, bedding, laying of pipes in progress
Kopanong | Nr of stands in settlements provided with sewer reticulation | 300 | 37,39 | Excavations and laying of main sewer pipes (5011m) in progress
Kirkney / Andeon South | Nr of stands in settlements provided with sewer reticulation | 200 | 55 | Layout plan to be revised

## Slide 36: 5. NON-FINANCIAL PERFORMANCE: USDG 2015/16
Garsfontein | Nr of stands in settlements provided with sewer reticulation | 100 | 46 | Objections from the Residents Committee on the TRU – Legal department addressing this matter
Zithobeni Heights | Nr of stands in settlements provided with sewer reticulation | 200 | 74 | Setting out, clearing &grubbing exaction ,bedding ,pipe laying in progress
Zandfontein | Nr of stands in settlements provided with sewer reticulation | 150 | 55 | Project still at planning stage, Awaiting approval of layout plan – plans in place to shift funding t other projects
Soutpan (phase 2) | Nr of stands in settlements provided with sewer reticulation | 100 | 25 | Setting out ,clearing &grubbing, excavation, bedding, pipe laying, backfilling and vavle chamber in progress
Lotus Gardens | Nr of stands in settlements provided with sewer reticulation | 300 | 7 | Site clearance for explosives in progress
Fortwest 4&5 | Nr of stands in settlements provided with sewer reticulation | 300 | 7 | Excavations, laying of pipes, backfilling, fitting, pressure tests/ commissioning
Zithobeni 8&9 | Nr of stands in settlements provided with sewer reticulation | 50 | 102 | Contractor at 60% completion stage

## Slide 37: 5. NON-FINANCIAL PERFORMANCE: USDG 2015/16
Refilwe Manor Ext 9 | Waste water treatment plant | 1.00 | 99,100 | 
Refilwe Manor Ext 9 | Construction of 1.5KL/day sewer pump station | 1.00 | 99,100 | Contractor on site with the construction of sewer pump station – 30% completion stage
Rama City | Nr of stands in settlements provided with water reticulation | 100 | 4,32 | Excavation, bedding, pipes laying and blanket in progress
Kudube 9 | Nr of stands in settlements provided with water reticulation | 100 | 74,75 | 1490 stands water lines connections at 90% completion stage .negotiations with house owners regarding the moving /relocation of obstructions
Mabopane Ext 1 | Nr of stands in settlements provided with sewer reticulation | 150 | 20,21 | Excavation, bedding, laying of pipes in progress
Kopanong | Nr of stands in settlements provided with water reticulation | 300 | 37,39 | Excavations and laying of main sewer pipes (12 700m) in progress

## Slide 38: 5. NON-FINANCIAL PERFORMANCE: USDG 2015/16
Olievenhoutbosch 60 | Nr of stands in settlements provided with water reticulation | 100 | 77 | Contractor on site
Kirkney / Andeon South | Nr of stands in settlements provided with sewer reticulation | 200 | 55 | Excavation ,bedding, pipe laying in process
Garsfontein | Nr of stands in settlements provided with water reticulation | 100 | 46 | Project still planning. Addressing the objections by residents committee – plans on place to shift funding to other performing projects
Zithobeni Heights | Nr of stands in settlements provided with water reticulation | 200 | 102 | Setting out, clearing &grubbing exaction ,bedding ,pipe laying in progress. Challenges with boulders on site that require blasting
Zandfontein | Nr of stands in settlements provided with water reticulation | 150 | 55 | Awaiting approval of layout plan – plans in place to shift funding to performing projects
Soutpan (phase 2) | Nr of stands in settlements provided with water reticulation | 100 | 25 | Setting out ,clearing &grubbing, excavation, bedding, pipe laying, backfilling and vavle chamber in progress
Lotus Gardens | Nr of stands in settlements provided with water reticulation | 300 | 07 | Site clearance currently in progress(Clearing the site of explosives by specialist company)
Fortwest 4&5 | Nr of stands in settlements provided with water reticulation | 300 | 07 | Project is progress well

## Slide 39
Project Name | Areas & No of Households benefitting | Annual Target outputs | Non-Financial Actual Progress |  | 
HOUSING: INTERNAL SERVICES |  |  |  |  | 
Kudube 9 | 74,75 | 3 | Engineering designs submitted and provisionally approved pending the results of a WULA |  | 
Thorntreeview | 90 | 8 | Roaded ,layers ,curbing ,asphalt ,finishing ,storm water trenches excavated ,storm water pipes laid, mainholes constructed |  | 
Mabopane EW | 12 | 2 | Waiting for approval of designs |  | 
Olievenhoutbosch 60 | 77 | 3 | The stream crossing design and costing approved. Awaitinng final approval of roads. Plans in place to shift funding |  | 
Zithobeni Heights | 102 | 3 | Contractor on site - Site establishment complied, Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill and V Drains |  | 
Fortwest 4&5 | 07 | 7 | Contract on site Site establishment completed - Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill |  | 
5.2 2015/16 DETAILED PROJECT PROGESS
HOUSING: INTERNAL SERVICES
No Internal Services are planned for 2015/16 with USDG in COT

## Slide 40
Project Name | Areas & No of Households benefitting | Annual Target outputs | Non-Financial Actual Progress |  | 
HOUSING: INTERNAL SERVICES |  |  |  |  | 
Soshanguve X5 | 37 | 4 | Contract on site Site establishment completed Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill |  | 
Soshanguve X12 | 39 | 3 | Contract on site Site establishment completed Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill |  | 
Soshanguve X13 | 39 | 3 | Contract on site Site establishment completed Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill |  | 
Zithobeni Ext 8&9 | 102 | 3 | Contractor on site - Site establishment complied, Clearing & Grubbing, Box –cutting, Roadbed, lower Selected Layer, Rock Fill and V Drains |  | 
5.2 2015/16 DETAILED PROJECT PROGESS
HOUSING: INTERNAL SERVICES

## Slide 41
Project Name | Areas & No of Households benefitting | Annual Target outputs | Non-Financial Actual Progress |  | 
HOUSING: INTERNAL SERVICES |  |  |  |  | 
Rama City | 4,32 | 100 | Excavation ,bedding pipe laying and blanket on progress |  | 
Kudube 9 | 74,75 | 100 | 1490 stands water lines connections completed, negotiations with house owners regarding the moving /relocation of obstructions |  | 
Mabopane Ext 1 | 20,21 | 150 | Exacavation,bedding, laying of pipes in progress |  | 
Kopanong | 37,39 | 300 | Excavations and laying of main sewer pipes (5011m) in progress |  | 
Kirkney/Andeon South | 55 | 200 | Finalizing of rates |  | 
Garsfontein | 46 | 100 | Objections from the residents Committee on the TRU- Legal Department addressing this matter |  | 
5.2 2015/16 DETAILED PROJECT PROGESS
HOUSING: INTERNAL SERVICES

## Slide 42
Project Name | Areas & No of Households benefitting | Annual Target outputs | Non-Financial Actual Progress | Budget | Expenditure
HOUSING: INTERNAL SERVICES |  |  |  |  | 
Zithobeni Heights | 102 | 200 | Setting out, clearing &grubbing exaction ,bedding ,pipe laying in progress |  | 
Zandfontein | 55 | 150 | Project still at planning stage, turnkey ,Awaiting of layout plan –plans in place to shift funding other projects |  | 
Soutpan (phase 2) | 25 | 100 | Setting out ,clearing &grubbing, excavation, bedding, pipe laying, backfilling and vavle chamber in progress |  | 
Lotus Gardens | 07 | 300 | Site clearance for explosives in progress |  | 
Fortwest 4&5 | 07 | 300 | Excavations, laying of pipes, backfilling, fitting, pressure tests/ commissioning |  | 
Zithobeni 8&9 | 102 | 50 | Contractor at 60% completion stage |  | 
5.2 2015/16 DETAILED PROJECT PROGESS
HOUSING: INTERNAL SERVICES

## Slide 43
MTSF TARGET 2019 | ACTUAL DELIVERY PROGRESS |  |  |  |  | 
 | 2014/15 Q4 | 2015/16 |  |  |  | Total to date
 |  | Q1 | Q2 | Q3 | Q4 | 
750 000 households in informal settlements upgraded to Phase 2 of the Informal Settlements Upgrading Programme |  |  |  |  |  | 
Individual households (metered): Water Sanitation Electricity | 8000 |  |  |  |  | 
 | 3000 |  |  |  |  | 
 | 9161 houses electrified | 683 houses electrified | 795 houses electrified | 203 houses electrified |  | 1681 houses electrified
Shared services (number of households benefiting) Water Sanitation |  |  |  |  |  | 
Title Deeds: 563 000 for new developments Pre-1994 housing stock Post-1994 housing stock |  | 778 | 1283 | 1029 |  | 
10 000 of hectares of well-located land | 3 land parcels | - | - | 142 ha |  | -
6. PERFORMANCE SUMMARY: USDG 2015/16

## Slide 44
Project Name | Areas & No of Households benefitting | Annual Target outputs | Non-Financial Actual Progress | Budget | Expenditure
LAND ACQUISITION |  |  |  |  | 
Temporary residential units-Garsfontein | Garsfontein | - | - | R41 000 000 | R36 082 884
Roodepoort 504 JR | Region 7 | 142ha | Transfer in process (end May) | R59 000 000 | R59 000 000 (R31mill at in 16/17)
 |  |  |  | R100 000 000 | R 95 082 884
5.1 2015/16 DETAILED PROJECT PROGRESS
LAND ACQUISITION

## Slide 45
5.3 2015/16 DETAILED PROJECT PROGRESS
ROADS & STORMWATER
Project name | Benefiting ward | Annual targets in km | Non financial progress | Budget
Major Stormwater System, Mamelodi X 8 | 17 | Detail Designs, Wula and EIA | Consultant will only be appointed during the fourth quarter | 20 000 000
Major Stormwater Systems: Klip/Kruisfontein | 35, 36, 90 | Construction of 0.3km stormwater | Consultant will only be appointed during the fourth quarter | 15 000 000
Shova Kalula Bicycle Project | 9, 19, 24 | Construction of 6km cycle path | Consultant will only be appointed during the fourth quarter | 1 000 000
Mabopane Station Modal Interchange | 29 | Construct 25,176m² precast brick paving, 174 foodstalls, 2 guard houses, 2 ablution blocks, 1 admin building and 14 668 m² canopy for 30 new taxi bays and 13 new bus bays | Progress of contractor not satisfactory and scope reduced | 1 000 000
Block W - Stormwater Drainage | 25, 26 | Construction of 0,3km stormwater | Consultant will only be appointed during the third quarter | 5 000 000
Major S/Water Drainage System: Majaneng | 74, 75 | Construction of 0.3km stormwater | Consultant will only be appointed during the third quarter | 15 000 000
Major S/Water Drainage Channels: Ga-Rankuwa | 30, 31, 32 | Review of designs and obtain EIA & WULA | Consultant will only be appointed during the fourth quarter | 237 176 350
Stormwater Drainage Systems in Ga-Rankuwa View | 30, 31, 32 | Review of designs and obtain EIA & WULA | Consultant will only be appointed during the fourth quarter | 1 000 000
Internal Roads: Northern Areas | 12, 19, 20, 21, 22, 30, 31, 32 | Review of designs and obtain EIA & WULA | Consultant will only be appointed during the third quarter | 10 000 000
Flooding Backlogs: Stinkwater & New Eersterust Area | 8, 13, 14, 74, 75, 76, 95 | Construct 2 km of Bulk Stormwater Drainage | Consultant will only be appointed during the fourth quarter | 12 000 000
Flooding Backlogs: Sosh & Winterveldt Area | 11, 26 ,29, 88 ,94 | Construction of 11.5km roads and 16.5km stormwater drainage and 1,5km sidewalks | Project ongoing from previous financial year | 10 000 000
Flooding Backlogs: Mabopane Area | 19, 20, 21, 22 | Review of designs and obtain EIA & WULA | Consultant will only be appointed during the fourth quarter | 300 000

## Slide 46
5.3 2015/16 DETAILED PROJECT PROGRESS
ROADS & STORMWATER
Project name | Benefiting ward | Annual targets in km | Non financial progress | Budget
Flooding Backlogs: Mamelodi, Eersterust & Pta Eastern Area | 15, 16, 17, 18, 23, 28, 38, 40, 67, 97 | Pipe jacking: 0.005km stormwater | Consultant will only be appointed during the fourth quarter | 6 000 000
Flooding Backlog: Network 2F, Kudube Unit 6 | 8, 74, 75, 76 | Construction of 0.68km of bulk stormwater drainage system | Consultant will only be appointed during the third quarter | 20 000 000
Flooding backlog: Network 5A, Matenteng | 8, 13, 14, 74, 75, 76, 95 | Construct 1 km of internal roads | Consultant will only be appointed during the third quarter | 2 000 000
Flooding Backlog: Network 2H, Kudube Unit 7 | 8, 13, 74, 75, 76 | Apply and obtain EIA & WULA | Consultant will only be appointed during the third quarter | 15 000 000
Flooding Backlog: Network C5, C6, C11 & C13, Atteridgeville | 51, 62, 63, 68, 72 | Construct 2km closed bulk stormwater drainage system | Consultant will only be appointed during the third quarter, but contractor performing well | 1 000 000
Flooding Backlogs: Soshanguve South & Akasia Area | 89, 39 | Construct 0,3km of bulk stormwater drainage system | Consultant for phase 2 will only be appointed during the third quarter, but contractor on phase 1 performing well | 6 000 000
Flooding Backlog: Network 2B, Ramotse | 73, 74 | Relocation of 10 residents and review of designs | Consultant will only be appointed during the fourth quarter | 12 000 000
Flooding Backlog: Network 2D, New Eersterust x 2 | 8, 13, 14, 95 | Construct 2 km of bus route | Consultant will only be appointed during the fourth quarter | 6 000 000
Upgrading of Mabopane Roads dealing with Red Soils | 12, 19, 20, 21, 22 | Review of designs and obtain EIA & WULA | Consultant will only be appointed during the fourth quarter | 2 000 000
Upgrading of Road from gravel to tar in Zithobeni Ward 5 & 6 | 102 | Review designs and construction of 0.375km internal roads and stormwater drainage | Consultant will only be appointed during the fourth quarter | 20 000 000
Upgrading of Road from gravel to tar in Ekangala Ward 8,9 & 10 | 103, 104 | Review designs and construction of 0.75km internal roads and stormwater drainage | Consultant will only be appointed during the fourth quarter | 10 000 000
Upgrading of Road from gravel to tar in Ekangala Ward 8,9 & 11 | 105 | Review designs and construction of 0.375km internal roads and stormwater drainage | Consultant will only be appointed during the third quarter | 55 000 000
Refurbishing of Water Networks and Backlog Eradication | 20,22,30,31,32 | Installation bulk feeder pipelines and bulk pipeline in different locations | Consultant will only be appointed during the third quarter | 

## Slide 47
Project Name | Areas & No of Households benefitting | Annual Target outputs | Non-Financial Actual Progress | Budget | Expenditure
WATER AND SANITATION DEPARTMENT |  |  |  |  | 
Refurbishing of Water Networks and Backlog Eradication | Stinkwater Extenstions 2 to 8 (6000 Households) | 2300m New Bulk Pipeline Shoshanguve DD to stinkwater | The contractor has already installed 50% of the bulk pipeline. The pipe line will be operational by the end of June 2016 | 73,634,412 USDG 25,894,412 | 11,331,608 USDG 10,194,059.00
 | New Waterborne sewer and Toilets: Ekangala block A and F | Installation of Pipelines and Construction of 912 Toilet Structures | The project is progressing well the work is anticipated to be completed in June 2016 | 22,571,311 | 19,530,647
 | Extension of the Temba Water Purification Plant | Completion Civil Construction and Commencement of the mechanical component installation | Civil works are currently at 71% and anticipated to be completed by end of August 2016 and Some of the Mechanical components have been delivered as from March 2016 | 236,974,329 USDG 122418890 | 157,230,446 USDG 58,590.334
5.4 2015/16 DETAILED PROJECT PROGRESS
WATER AND SANITATION INFRASTRUCTURE

## Slide 48
5.6 2015/16 DETAILED PROJECT PROGESS
Re-AGA Tshwane
Project Name | Project Outputs 2015/16 | Benefiting Ward | Non- financial progress Q2
Nellmapius x 21 – sewer reticulation | Sewer reticulation |  | Pipe length installed = 4.9km Households connected = 442
Nellmapius x 24 - water reticulation | Water reticulation |  | Pipe length installed = 10 km Household connections = 1
Nellmapius x 24 – sewer reticulation | Sewer reticulation |  | Pipe length Installed = 7 km Household connected = 533
Nellmapius x 6 - sewer reticulation | Sewer reticulation |  | Pipes length installed = 2.5 km Household connected = 11
Mahube Valley x 2 – water reticulation | Water reticulation |  | 154 stands reticulation, busy with house connections
Mahube Valley x 2 – sewer reticulation | Sewer reticulation |  | 129 stands reticulated, busy with the design of the connection point and toilet top structures
Nellmapius x 21 – sewer reticulation | Sewer reticulation |  | Pipe length installed = 4.9km Households connected = 442
Nellmapius x 24 - water reticulation | Water reticulation |  | Pipe length installed = 10 km Household connections = 1
Nellmapius x 24 – sewer reticulation | Sewer reticulation |  | Pipe length Installed = 7 km Household connected = 533
Nellmapius x 6 - sewer reticulation | Sewer reticulation |  | Pipes length installed = 2.5 km Household connected = 11
Mahube Valley x 2 – water reticulation | Water reticulation |  | 154 stands reticulation, busy with house connections
Mahube Valley x 2 – sewer reticulation | Sewer reticulation |  | 129 stands reticulated, busy with the design of the connection point and toilet top structures

## Slide 49
Project Name | Benefiting Areas/Wards |  | Annual Target outputs | Non-Financial Actual Progress | Budget | Expenditure | % Expenditure
Electricity-for-All | 48, 90, 10, 11, 15, 17, 93, 97 | Provide new electricity connections to a total of 4200 houses |  | New electricity connection provided to a total 1729 households through electrification. | R 91 344 858 | R58 098 096 | 63.6%
Installation of streetlights and High masts | 17, 24, 55, 66, 99 & 105 | Install a total of 1450 new streetlights and 13 new high masts |  | 1416 streetlights and 15 high masts installed and energized | R 30 991 045 | R 17 775 747 | 57.3%
Totals |  | Electrify 4200 houses, install new 1450 streetlights an 13 high masts |  | 1729 houses electrified, 1416 streetlights and 15 high masts installed. | R 122 336 903 | R 75 873 843 | 62%
5.7 2015/16 DETAILED PROJECT PROGRESS
ELECTRICITY

## Slide 50
Name of Informal Settlement | Service provided | No of Households to benefit | Annual Target | Budget | Expenditure
INFORMAL SETTLEMENT UPGRADING |  |  |  |  | 
5.10 2015/16 DETAILED PROJECT PROGESS
INFORMAL SETTLEMENTS

## Slide 51
Project Name | Annual Target | Number of title deeds issued | Budget | Expenditure
TITLE DEEDS ISSUED |  |  |  | 
Title deeds are recorded per month/quarter/annual; city wide. | 80% of title deeds received | Q1 = 778 | R0.00 Provincial mandate | R0.00 Provincial mandate
Title deeds are recorded per month/quarter/annual; city wide. | 80% of title deeds received | Q2 = 1283 | R0.00 Provincial mandate | R0.00 Provincial mandate
Title deeds are recorded per month/quarter/annual; city wide. | 80% of title deeds received | Q3 = 1029 | R0.00 Provincial mandate | R0.00 Provincial mandate
2015/16 DETAILED PROJECT PROGESS
TITLE DEEDS

## Slide 52
2015/16 DETAILED PROJECT PROGESS
TITLE DEEDS (2)
Challenges:
Uncollected because of unresolved estates, illegal sales & occupations, untraceable beneficiaries
Mitigating factors:
Constant issuing of calling letters to beneficiaries.
Political public events to issue title deeds
Consumer education on the importance of a title deed
oIssuing of referral letters to the Master of the High Court for resolution of estates
Advertise on local print media to call for collection of title deeds.
Title Deeds in the cross-border areas
Over 300 title deeds available in the NWHC Cross-Border areas & currently held by the North West Province in anticipation of joint-issuing between the 2 Provinces. Engagement between the 2 provinces on matters related to this project needs to be fast-tracked.

## Slide 53: CHALLENGES AND INTERVENTIONS
Delays in approval of beneficiaries on HSS
The City has offered to assist in capturing the subsidy forms.
Numerous disruptions on site - projects stopped by community members.
Engagements with ward councillors and through the platform provided by the War Room
Heavy rainfall
Contractors have been requested to source additional teams and work over weekends
CRU’s funding
Utilisation of HSDG to fund Top Structure or combination of USDG and HSDG

## Slide 54: 7. LINK BETWEEN USDG & HSDG
USDG – Housing Internal Services: Project Name | 2014/2015 | HSDG – Top Structure: Project Name | 2014/2015
Refer to 15/16 projects (multi-year) | - | - | -
No HSDG funding allocated to the City in 2014/15 fy

## Slide 55
END