## Slide 1: BUFFALO CITY METROPOLITAN MUNICIPALITY
Urban Settlement Development Grant (USDG)
3RD Quarter 2015 / 2016

## Slide 2: OVERVIEW
The preparation of the third quarter USDG performance report is done in line with the grant framework as stipulated in the Division of Revenue Act for 2015 and section 71 of the Municipal Finance Management Act.
The USDG utilizes, as a Framework, the Built Environment Performance Plan(BEPP) that is consistent with the Integrated Development Plan and the Service Delivery and Budget Implementation Plan of Buffalo City Metropolitan Municipality (BCMM).
The report presents both financial and non-financial performance and expenditure up to 31 March 2016.
The presentation reflects what the City has achieved since the beginning of the 2015/2016 financial year.

## Slide 3
FINANCIAL PERFORMANCE

## Slide 4
FUNDING SOURCE | 2015/2016 CAPITAL BUDGET | 2015/2016 ADJUSTMENT BUDGET
Own Funding | 529 796 867 | 600 806 117
DoE(Integrated National Electrification Programme) | 30 000 000 | 30 000 000
Electricity Demand Side Management Grant | 13 000 000 | 13 000 000
Department of Sport, Recreation, Arts & Culture | 0 | 8 014 208
Infrastructure Skills Development Grant | 100 000 | 100 000
Department of Local Government and Housing | 0 | 9 036 112
Neighbourhood Development Partnership Grant | 20 000 000 | 0
Financial Management Grant | 0 | 120 000
Urban Settlement Development Grant | 679 784 100 | 659 541 863
Leiden c/o | 0 | 458 860
Human Settlement Development Grant | 94 400 000 | 69 800 000
Human Settlement Development Grant-MPCC | 13 068 500 | 0
TOTAL PER FUNDING | 1 380 149 467 | 1 390 877 160
CAPITAL BUDGET BREAKDOWN

## Slide 5
CAPITAL BUDGET BREAKDOWN
Others : Grants e.g. LGTA, BCMET, DEDEAT, DSRAC etc.
Chart: 
| Own Funding | DoE (INEP) | DSRAC | DLGTH | EDSMG | FMG | ISDG | LEIDEN | NDPG | USDG | HSDG | HSDG-MPCC
Total Budget | 600806117.11 | 30000000 | 8014207.63 | 9036112 | 13000000 | 120000 | 100000 | 458860 | 0 | 659541863 | 69800000 | 0

## Slide 6
SERVICE | BUDGET | 2015/16 ADJUSTMENT BUDGET | Q1 | Q2 | Q3 | %
Water | 51 000 000 | 59 500 000 | 4 267 839 | 27 742 395 | 36 614 614 | 62%
Waste Water | 190 000 000 | 186 000 000 | 0 | 62 883 577 | 103 364 937 | 56%
Electricity | 25 500 000 | 25 500 000 | 1 137 912 | 11 044 362 | 12 475 656 | 49%
Roads and Stormwater | 185 000 000 | 229 017 741 | 4 615 477 | 69 798 349 | 92 198 760 | 40%
Human Settlements (Internal Services) | 119 074 000 | 118 424 000 | 40 872 255 | 62 124 371 | 88 397 923 | 75%
Transport Planning | 30 000 000 | 40 000 000 | 2 113 580 | 13 012 522 | 19 471 633 | 49%
Waste Management / Refuse | 21 710 100 | 47 856 153 | 6 739 999 | 21 119 838 | 26 921 672 | 56%
Social Amenities | 42 200 000 | 26 795 205 | 2 353 572 | 14 086 574 | 13 588 979 | 51%
Public Safety | 6 000 000 | 500 000 | 0 | 0 | 0 | 0%
Local Economic Amenities | 10 000 000 | 0 | 0 | 0 | 0 | 0%
EPMO | 32 647 900 | 21 942 309 | 6 808 496 | 14 425 421 | 17 408 327 | 53%
TOTAL | 713 132 000 | 755 535 408 | 69 144 131 | 296 472 411 | 410 442 501 | 54%
USDG PER SERVICE As at 31 March 2016

## Slide 7
2015/2016 USDG DoRA Allocation | R 713,132,000
Transfer to Date | R 713,132,000
EXPENDITURE AS AT 31 MARCH 2015 | 
Expenditure | R 410 442 501
Which is 58% of the transferred funds | 58%
Which is 54% of the allocated funds | 54 %
Which is a Variance of R...... | R 416 659 590
SYNOPSIS
FINANCIAL PERFORMANCE

## Slide 8
Chart: 
| Q1.1 | Q1.2 | Q1.3 | Q2.1 | Q2.2 | Q2.3 | Q3.1 | Q3.2 | Q3.3 | Q4.1 | Q4.2 | Q4.3
14/15 USDG EXP | 2285768.79 | 35710711.67 | 52092905.76 | 134566386.71 | 170968677.8 | 278118788.22 | 293258238.33 | 293258238.33 | 407601986.32 | 447751280 | 457439244 | 557375710
1st Budget Adjustment 14/15
2nd Budget Adjustment 14/15
USDG Projections 2015/16 | 35656600 | 71313200 | 106969800 | 156889040 | 206808280 | 249596200 | 306646760 | 363697320 | 427879200 | 520586360 | 613293520 | 713132000
Current Expenditure | 1854080.18 | 32614059.67 | 64766200.92 | 151736623.53 | 213436566 | 296472411 | 313779371.37 | 346063587.2 | 410442501
TOTAL USDG EXPENDITURE as at
31 MARCH 2016

## Slide 9
NON FINANCIAL & FINANCIAL PERFORMANCE

## Slide 10
IMMEDIATE RESULTS INDICATORS | Q1 | ACHIEVED | Q2 | ACHIEVED | Q3 | aCHIEVED | Q4 | ANNUAL TARGET 2015/2016
No of ha of land procured and suitable for Greenfields development | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2ha
Number of dwelling units developed | 350 | 251 | 450 | 266 | 500 | 103 | 400 | 1700
Number of households in informal settlements targeted for upgrading : In-Situ | 400 | 407 | 500 | 249 | 550 | 103 | 511 | 1961
Number of households in informal settlements upgraded (services provided) : Relocated | 350 | 374 | 525 | 450 | 425 | 87 | 400 | 1700
Number of Title deeds transferred to eligible beneficiaries | 1459 | 0 | 1550 | 0 | 1645 | 0 | 1184 | 5 838
HUMAN SETTLEMENT DEVELOPMENT

## Slide 11
Greenfields Projects | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
Amalinda Co- Op | 4 800 000 | 1 800 000 | 42 625 | 42 625 | 42 625 | 1%
Amalinda Fairlands | 300 000 | 300 000 | 0 | 0 | 0 | 0%
Ilitha North 177 Units | 4 000 000 | 1 500 000 | 0 | 19 279 | 19 279 | 0.48%
Mdantsane Zone 18 CC Phase 2 | 8 500 000 | 3 500 000 | 79 119 | 668 914 | 668 914 | 19%
Potsdam Ikhwezi Block 1 | 200 000 | 200 000 | 12 000 | 168 494 | 197 964 | 99%
Potsdam Ikhwezi Block 2 | 200 000 | 200 000 | 74 800 | 74 800 | 74 800 | 37%
Potsdam North Kanana | 200 000 | 200 000 | 0 | 0 | 0 | 0%
Reeston Phase 3 Stage 2 | 5 000 000 | 13 000 000 | 0 | 0 | 0 | 0%
Reeston Phase 3: Stage 3 | 5 000 000 | 5 000 000 | 4 331 178 | 4 588 783 | 4 983 074 | 99%
Sunny South | 100 000 | 6 800 000 | 0 | 18 481 | 486 469 | 7%
Tyutyu Phase 3 | 500 000 | 250 000 | 0 | 0 | 0 | 0%
HOUSING : INTERNAL SERVICES

## Slide 12
Greenfields Projects | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
Block Yard TRA | 0 | 1 000 000 | 0 | 0 | 0 | 0%
Manyano & Tembelihle | 0 | 1 000 000 | 0 | 0 | 0 | 0%
Second Creek | 0 | 3 500 000 | 0 | 0 | 0 | 0%
Informal Settlement Upgrading |  |  |  |  |  | 
Cluster 1 (Masibambane; Masibulele; Velwano; Ilinge and Dacawa) | 25 000 000 | 33 750 000 | 12 092 941 | 21 890 590 | 33 750 000 | 100%
Cluster 2 (Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe) | 13 024 000 | 3 524 000 | 2 535 226 | 3 520 744 | 1 184 539 | 9%
Cluster 3 (Fynbos Informal 1, Fynbos Informal 2, Ndancama) | 25 350 000 | 41 350 000 | 21 704 365 | 27 090 755 | 41 350 000 | 100%
TOTAL | 119 074 000.00 | 116 874 000 | 40 872 255 | 88 268 859 | 82 757 664 | 71%
HOUSING : INTERNAL SERVICES

## Slide 13
IMMEDIATE RESULTS INDICATORS | Q1 | ACHIEVED | Q2 | ACHIEVED | Q3 | ACHIEVED | Q4 | ANNUAL TARGET 2015/2016
KMs of paved roads to be resurfaced | 3 | 0.2 | 5 | 6.5 | 7 | 7.33 | 10 | 25
KMs of gravelled roads maintained | 100 | 133 | 150 | 185.93 | 150 | 180.011 | 200 | 600
KMs of roads gravelled | 5 | 0.2 | 15 | 83 | 15 | 52.5 | 15 | 50
KMs of storm water drainage installed in addition to current ones | 0 | 0 | 3 | 8 | 3 | 5.44 | 4 | 10
Number of existing BCMM bridges rehabilitated | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 3
Number of new bus terminals or taxi ranks to be constructed | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2
Number of new bus / taxi stops to be constructed | 1 | 0 | 1 | 3 | 0 | 2 | 0 | 2
ROADS & TRANSPORT

## Slide 14
PROJECT | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
Quenera Beacon Bay Link Road | 20 000 000 | 20 000 000 | 1 278 715 | 10 663 794 | 12 735 994 | 63%
Upgrading of Mdantsane Roads | 60 000 000 | 60 000 000 | 2 526 928 | 14 849 293 | 14 534 319 | 24%
KWT Roads | 10 000 000 | 10 000 000 | 0 | 3 147 126 | 6 710 363 | 67%
Gonubie Main Road | 10 000 000 | 10 000 000 | 0 | 1 885 137 | 2 574 154 | 26%
Rural Roads | 30 000 000 | 30 000 000 | 0 | 25 779 330 | 29 142 935 | 97%
Fleet Street | 20 000 000 | 30 000 000 | 809 835 | 12 432 650 | 13 649 189 | 68%
RDP Roads - Inland, Midlands and Coastal | 15 000 000 | 15 000 000 | 0 | 1 008 883 | 4 357 074 | 29%
Rehabilitation of BCMM Bridges and Stormwater | 5 000 000 | 5 000 000 | 0 | 32 137 | 418 506 | 8%
Procurement of Graders for Rural Roads - Yellow Fleet | 15 000 000 | 15 000 000 | 0 | 0 | 8 076 226 | 54%
Mdantsane Roads |  | 14 815 569 |  |  | 0 | 0%
Urban Roads |  | 19 202 172 |  |  | 0 | 0%
TOTAL | 185 000 000 | 229 017 741 | 4 615 477 | 69 798 349 | 92 198 760 | 40%
ROADS PROJECTS

## Slide 15
PROJECT | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
Integrated Transport Plan Implementation | 30 000 000 | 30 000 000 | 2 113 580 | 7 330 785 | 12 657 193 | 42%
TOTAL | 30 000 000 | 30 000 000 | 2 113 580 | 7 330 785 | 12 657 193 | 42%
TRANSPORT PROJECTS

## Slide 16
IMMEDIATE RESULTS INDICATORS | Q1 | ACHIEVED | Q2 | ACHIEVED | Q3 | ACHIEVED | Q4 | ANNUAL TARGET 2015/2016
No of additional water service points to be installed for informal settlement dwellers within a 200m radius | 0 | 0 | 3 | 4 | 3 | 8 | 4 | 10
Number of formal domestic customers receiving water services | 107714 | 107473 | 107489 | 107457 | 107714 | 107695 | 107 714 | 107 714
No of consumer units provided with access to a free basic level of potable water, by means of an individual HH supply or standpipe within 200m | 0 | 0 | 0 | 0 | 500 | 346 | 1000 | 1500
Reduction in backlog in the no. of consumers units with access to free basic level of potable water | 0 | 0 | 258 | 0 | 715 | 346 | 1503 | 950
WATER

## Slide 17
PROJECT | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
Bulk Water Provision |  | 5 000 000 | 0 | 0 | 0 | 0%
Project 1 : Water Supply Coastal Areas and backlog eradication | 20 000 000 | 23 500 00 | 1 209 648 | 7 535 995 | 14 291 188 | 61%
Project 2 : KWT and Bhisho Infrastructure (Water) |  |  |  |  |  | 
 | 7 000 000 | 7 000 000 | 1 841 824 | 1 611 053 | 5 127 367 | 73%
Project 3 : Amahleke Water Supply | 3 000 000 | 3 000 000 | 798 209 | 1 041 995 | 2 133 216 | 71%
Project 4: Augmentation of Water Treatment | 17 000 000 | 17 000 000 | 0 | 9 820 527 | 13 811 851 | 81%
Project 5 : Upgrade Water Networks | 4 000 00 | 4 000 000 | 0 | 507 025 | 1 250 992 | 31%
TOTAL | 51 000 000 | 59 500 000 | 3 849 681 | 20 516 605 | 36 614 614 | 62%
WATER PROJECTS

## Slide 18
IMMEDIATE RESULTS INDICATORS | Q1 | ACHIEVED | Q2 | ACHIEVED | Q3 | ACHIEVED | Q4 | ANNUAL TARGET 2015/2016
Number of additional sanitation service points (toilets) to be installed for informal settlement dwellers | 0 seats (1 274) | 8 seats (1 282) | 15 seats (1 289) | 62 seats (1490) | 15 seats (1 304) | 29 seats (1 519) | 10 seats (1 314) | 40 seats (1 314)
Number of additional households to be provided with sewer connections | 162 063 (+306) | 162 068 (+257) | 162 369 (+306) | 162 072 (297) | 162 675 (+306) | 162997 (+306) | 162 981 (+306) | 162 981 (+1 224)
Reduction of backlog in the provision of basic sanitation services (above RDP standards) | 61 505 (-306) | 62 581 (-257) | 61 199 (-306) | 62 577 (1 378) | 61 893 (-306) | 60 533 (-306) | 60 587 (-306) | 60 587 (-1 224)
SEWERAGE

## Slide 19
PROJECT | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP Q.3 | %
Waste Water Infrastructure Capacity - KWT Regional Scheme | 31 400 000 | 31 400 000 | 0 | 1 587 023 | 4 597 735 | 15%
Reeston Phase 3 Bulk Services Sewer | 50 000 000 | 45 000 000 | 0 | 17 202 178 | 22 548 123 | 50%
Mdantsane Infrastructure | 4 500 000 | 2 000 000 | 0 | 293 729 | 492 333 | 25%
Diversion of Amalinda & Wilsonia effluent to Reeston | 1 500 000 | 1 500 000 | 0 | R 374 052 | 363 177 | 25%
Sanitation Backlog Eradication | 56 500 000 | 0 | 0 | 27 126 662 | 0 | 0%
Ablution Blocks | 3 000 000 | 3 000 000 | 0 | 1 345 102 | 2 784 811 | 93%
Berlin Sewer | 15 000 000 | 15 000 000 | 0 | 3 200 875 | 4 101 025 | 27%
Hoodpoint Marine Outfall | 1 000 000 | 1 000 000 | 0 | 0 | 0 | 0%
Gqozo Village | 15 000 000 | 15 000 000 | 0 | 11 250 846 | 10 365 713 | 69%
West Bank Restitution | 5 000 000 | 5 000 000 | 0 | 432 346 | 3 157 573 | 63%
Quenera Works | 7 100 000 | 7 100 000 | 0 | 70 765 | 4 649 544 | 1%
TOTAL | 190 000 000 | 126 000 000 | 0 | 62 883 577 | 53 060 033 | 42%
SANITATION PROJECTS

## Slide 20
IMMEDIATE RESULTS INDICATORS | Q1 | ACHIEVED | Q2 | ACHIEVED | Q3 | ACHIEVED | Q4 | ANNUAL TARGET 2015/2016
Number of additional RDP households living in formal areas provided with electricity connections | 0 | 0 | 0 | 0 | 300 | 0 | 1200 | 1500
Number of additional high mast lights installed | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
Number of additional street lights installed | 25 | 50 | 25 | 67 | 25 | 67 | 25 | 100
Number of informal households with access to basic electricity | 0 | 200 | 0 | 1 104 | 150 | 160 | 850 | 1000
ELECTRICITY

## Slide 21
PROJECT | BUDGET |  | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
INEP Electrification Programme - Counterfunding | 5 000 000 |  | 5 000 000 | 1 012 482 | 850 048 | 1 862 530 | 37%
Electrification of Informal Dwelling Areas within BCMM | 15 000 000 |  | 15 000 000 | 0 | 7 847 752 | 10 613 126 | 60%
Street Lighting and High masts - Informal Settlements | 3 500 000 |  | 3 500 000 | 0 | 0 | 0 | 0%
Replacement and Refurbishment of Bulk ELECT Infrastructure | 2 000 000 |  | 2 000 000 | 0 | 0 | 0 | 0%
TOTAL | 25 500 000 | 25 500 000 |  | 1 137 912 | 11 044 362 | 12 475 656 | 49%
ELECTRICITY PROJECTS

## Slide 22
IMMEDIATE RESULTS INDICATORS | Q1 | ACHIEVED | Q2 | achieved | Q3 | achieved | Q4 | ANNUAL TARGET 2015/2016
Number of additional areas provided with access to weekly refuse removal | 0 | 7 Areas | 4 Areas (4) | 4 Areas | 8 Areas (4) | 0 | 10 Areas (2) | 10 Areas
Number of waste minimisation projects initiated / upgraded | 2 | 0 | 3 | 0 | 3 | 3 | 3 | 3
Number of informal settlements with solid waste removal service | 2 | 5 | 5 | 5 | 10 | 10 | 10 | 30
SOLID WASTE MANAGEMENT

## Slide 23
PROJECT | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
Waste Management Facilities Programme | 1 000 000 | 0 | 0 | 0 |  | 0%
Construction and Rehabilitation of Waste Cells | 20 710 100 | 34 654 917 | 6 739 999 | 21 119 838 | 26 921 672 | 97%
TOTAL | 21 710 100 | 34 654 917 | 6 739 999 | 21 119 838 | 26 921 672 | 78%
WASTE MANAGEMENT
LAND
Project | Budget | Expenditure | %
Land acquisition | 0 | 0 | 0%

## Slide 24
IMMEDIATE RESULTS INDICATORS | Q1 | ACHIEVED | Q2 | achieved | Q3 | ACHIEVED | Q4 | ANNUAL TARGET 2015/2016
Number of new community halls | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Number of community halls upgraded | 2 | 1 | 3 | 3 | 4 | 7 | 2 | 11
Number of sport fields and stadia developed | 0 | 0 | 0 | 0 | 3 | 1 | 3 | 6
Number of community swiming pools developed | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2
Number of new cemeteries developed | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2
Number of cemeteries upgraded | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 3
Number of safety and emergency facilities developed | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Number of markets to be upgraded | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
SOCIO-ECONOMIC AMENITIES

## Slide 25
PROJECT | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
Development and Upgrading of Community Halls - War Memorial Hall, Egoli Community Hall, Continuation of KWT Town Hall, 5 NU Halls Mdantsane and Carnegie Hall. | 6 000 000 | 6 000 000 | 1 145 849 | 5 421 749 | 5 574 637 | 90%
Construction of Nompumelelo Hall | 8 000 000 | 4 300 000 | 0 | 85 456 | 4 245 | 1%
Upgrading of NU2 Pool – Mdantsane | 7 500 000 | 2 500 000 | 0 | 0 | 0 | 0%
Upgrading of Waterworld | 5 000 000 | 3 000 000 | 15 354 | 714 389 | 963 503 | 32%
Upgrading of Dimbaza and Zwelitsha Stadium | 2 700 000 | 2 700 000 | 0 | 0 | 0 | 0%
Upgrading of Floodlights at Victoria Grounds, Bhisho Stadium, Ginsberg stadium, Sisa Dukashe Stadium, Alfred Schoeman Stadium, North End Stadium, Jan Smuts Stadium, Amalinda Stadium, and Gompo Stadium | 3 000 000 | 3 000 000 | 0 | 510 187 | 367 840 | 17%
SOCIAL AMENITIES PROJECTS

## Slide 26
PROJECT | BUDGET | ADJUSTMENT BUDGET | EXP. Q1 | EXP. Q2 | EXP. Q3 | %
Fencing of Sports Fields | 500 000 | 2 500 000 | 0 | 347 923 | 322 446 | 70%
Upgrading of Phakamisa and Mount Coke Sports Fields | 1 500 000 | 1 500 000 | 0 | 1 436 842 | 1 297 889 | 96%
Development and Upgrading of Cemeteries (Inland, Midland and Coastal) | 8 000 000 | 8 000 000 | 1 192 369 | 5 570 028 | 6 430 798 | 70%
KWT Traffic Building | 6 000 000 | 500 000 | 0 | 0 | 0 | 0%
TOTAL | 48 200 000 | 34 000 000 | 2 353 572 | 14 086 574 | 13 997 855 | 29%
SOCIAL AMENITIES PROJECTS

## Slide 27
IMMEDIATE RESULTS INDICATORS | q1 | ACHIEVED | Q2 | achieved | Q3 | Q4 | ANNUAL TARGET 2015/2016
Number of jobs created under Expanded Public Works Programme & other municipal programmes | 225 | 156 | 235 | 289 | 260 | 825 | 1545
JOB CREATION

## Slide 28
INFORMAL SETTLEMENTS &
TITLE DEEDS

## Slide 29
Name of Informal Settlement | Service Provided | Annual Target 2015/2016 | Actual Progress 1 July 2015 to March 2016 | Budget | Expenditure
CLUSTER 1 Masibambane; Masibulele; Velwano; Ilinge and Dacawa | Internal Services | 480 | 207 | 25 000 000 | 12 092 941
CLUSTER 2 Chris Hani 3; Winnie Mandela; Deluxolo Village; Sisulu Village; Francis Mei; Mahlangu Village, Mathemba Vuso, Gwentshe | Internal Services | 250 | 183 | 13 024 000 | 7 226 788
CLUSTER 3 Fynbos 1; Fynbos 2; Ndancama | Internal Services | 300 | 142 | 25 350 000 | 21 704 365
INFORMAL SETTLEMENTS

## Slide 30: LINK BETWEEN USDG & HSDG
USDG is used for the construction critical bulk infrastructure and the provision of internal services linked to approved housing projects.
HSDG is used for the construction of top structures on serviced sites as prepared by the USDG in the urban areas and on top structures only in rural areas.

## Slide 31: LINK BETWEEN USDG & HSDG
USDG – Housing Internal Services | 2015/2016 | HSDG – Top Structure | 2015/2016
Reeston Phase 3 Stage 2 | 13 000 000 | Reeston Phase 3: Stage 2 | 13 000 000
Reeston Phase 3 Stage 3 | 5 000 000 | Reeston Phase 3 Stage 3 | 62 804 569
Mdantsane Zone 18 CC Phase 2 | 3 500 000 | Mdantsane Zone 18 CC Ph. 2 | 0
West Bank Restitution | 0 | __ | 
Sunny South | 6 800 000 | Sunny South | 7 500 000
Amalinda Co- Op | 1 800 000 | Amalinda Co- Op | 0
Amalinda Fairlands | 300 000 | Amalinda Fairlands | 0
Ilitha North 177 Units | 1 500 000 | Ilitha North 177 Units | 0
__ |  | Ilitha - Eradication of Wooden Houses to Formal Houses | 10 380 294

## Slide 32: LINK BETWEEN USDG & HSDG
USDG – Housing Internal Services | 2015/2016 | HSDG – Top Structure | 2015/2016
Block Yard TRA | 1 000 000 | Block Yard TRA | 0
Manyano & Tembelihle | 1 000 000 | Manyano & Tembelihle | 0
Second Creek | 3 500 000 | Second Creek | 0
Braelyn Ext 10 | 800 000 | Braelyn Ext 10 | 800 000
Disaster Project Tsholomnqa | 0 | Disaster Project Tsholomnqa | 7 500 000
Cluster 1 | 33 750 000 | Cluster 1 | 75 519 030
Cluster 2 | 3 524 000 | Cluster 2 | 10 000 000
Cluster 3 | 41 350 000 | Cluster 3 | 45 861 424

## Slide 33: LINK BETWEEN USDG & HSDG
USDG – Housing Internal Services | 2015/2016 | HSDG – Top Structure | 2015/2016
Potsdam Ikhwezi Block 1 & 2 | 200 000 | Potsdam Ikhwezi Block 1 | 0
Potsdam North Kanana | 200 000 | __ | 
Potsdam Village Phase 1 & 2 | 700 000 | Potsdam Village Phase 1 & 2 | 0
__ |  | Dimbaza 110 Units | 500 000
Tyutyu Phase 3 | 250 000 | Tyutyu Phase 3 | 0
Peelton Cluster | 700 000 | Peelton Cluster | 20 000 000
Reconstruction of Storm Damaged Houses | 0 | Reconstruction of Storm Damaged Houses | 17 500 000
DVRI Pilot Project | 0 | DVRI Pilot Project | 1 501 683

## Slide 34
MEDIUM TERM STRATEGIC FRAMEWORK (MTSF) RESPONSE

## Slide 35
Programme | Stand Costs | Annual Target | Annual Costs | 5-Year Target | Total Cost *
Upgrading of Informal Settlements Programme | ±R43,626 per site for basic services as per quantum | 3 796 | R165,604,296 | 18 980 | R828,021,480
MTEF BUDGET ALLOCATION
Funding Source | 2015/2016 Budget | 2016/2017 Budget | 2017/2018 Budget
USDG (Capital) | 755,535,408 | 715,222,100 | 758,942,100
HSDG (Capital) | 94,400,000 | 106,300,000 | 65,000,000
TOTAL | 849,935,408 | 821,522,100 | 823,942,100
Note : DoRA USDG 2015/16 : R 755 535 408 HSDG 2015/16 : R 94 400 000
USDG 2016/17 : R731 499 000 HSDG 2016/17 : R106 300 000
USDG 2017/18 : R774 202 000 HSDG 2017/18 : R65 000 000

## Slide 36
MTSF TARGET 2019 | ACTUAL DELIVERY PROGRESS |  |  |  |  | 
 | 2014/15 Q4 | 2015/16 |  |  |  | Total to date
 |  | Q1 | Q2 | Q3 | Q4 | 
18 980 Households in informal settlements upgraded to Phase 2 of the Informal Settlements Upgrading Programme | 1729 | 407 | 249 | 0 | 0 | 656
Individual households: Water Sanitation Electricity | 1400 | 109 | 43 | 81 | 0 | 233
 | 1082 | 275 | 297 | 271 | 0 | 843
 | 517 | 200 | 1 104 | 160 | 0 | 1 464
Shared services (no. of households benefiting) Water Sanitation | 143 | 109 | 4 | 8 | 0 | 193
 | 448 | 80 | 62 | 10 | 0 | 152
Title Deeds: 7 560 for new developments Pre-1994 housing stock Post-1994 housing stock | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0
 | 0 | 0 | 0 | 0 | 0 | 0
62.4 hectares of well-located land | 3.7 | 0 | 0 | 0 | 0 | 0
CONTRIBUTION TOWARDS MTSF TARGETS

## Slide 37
MUNICIPAL HUMAN
SETTLEMENT GRANT (MHSG)

## Slide 38
Category | Description | 2015/16 Planned Target (Number) | Budget 2015/16 | Expenditure 2015 /16 |  | 
 |  |  |  | Q1 | Q2 | Q3
Capacity | Compensation of Employees | 10 | 3 167 134 | 0 | 0 | 2 181 251
 | Training of Staff and Workshops | 8 | 500 000 | 0 | 44 107 | 144 980
 | Consultants |  | 2 000 000 | 0 | 0 | 0
 | Professional/ Technical Services | 5 | 2 235 866 | 0 | 0 | 0
 | Research (Housing Needs Demand Register) |  | 0 | 0 | 0 | 0
Support | Office Management | 10 offices | 1 100 000 | 0 | 0 | 0
 | Risk Management |  | 0 | 0 | 0 | 0
 | Systems (Name of System) | 1 system | 250 000 | 0 | 0 | 0
 | TOTAL |  | 9 253 000 | 0 | 44 107 | 2 326 231
MUNICIPAL HUMAN SETTLEMENTS GRANT

## Slide 39
FIVE YEAR USDG TARGETS

## Slide 40: Improve, develop and maintain the condition of BCMM infrastructure

## Slide 44
CHALEENGES AND REMEADIAL MEASURES

## Slide 45
Challenges | Remedial Measures Taken
Technical challenges due to SCOA implementation resulted in delay in procurement processes and expenditure performance during first quarter | SCOA implementation issues are being addressed and a service provider is on site assisting the municipality
Budget shortfall for critical infrastructure projects to unlock human settlement development (Bulk sewer tunnel project to unlock Amalinda Junction) | Bids for expression of interest for the financial institutions are under evaluation to be followed by request for quotations from the qualifying bidders
Backlog in evaluation of bids impacting expenditure pattern | BCMM has established 3No. Bid Evaluation Committees
Conclusion of funding agreements for human settlement projects where the Provincial HS Department requested for additional information | BCMM is addressing the information shortages in order for expenditure incurred to be paid
CHALLENGES & REMEDIAL MEASURES

## Slide 46
Challenges | Remedial Measures Taken
Zwelitsha WWTW project was delayed by Arbitration process | Construction has started resumed and contract end date is in 2017/1 financial year
Late start of projects than anticipated | Mid year budget adjustment has now benn approved by Council, project of long lead time to deliver was taken out from the budget and replaced by those ready to commence
Community service delivery strikes delaying project implementation | Established a task team to attend to community concerns and improve response time.
Underperforming service providers due to various reasons (capacity, cash flows, expired SARS certificates) affecting expenditure | Recovery plans requested from service providers and terminating the contracts would be done should interventions not materialize
CHALLENGES & REMEDIAL MEASURES

## Slide 47
THANK YOU