## Slide 1: Gauteng Department of Human Settlements Presentation 4th Quarter Report
April 2016

## Slide 2: 2015/16 PERFORMANCE
A. ACTUAL PERFORMANCE INFORMATION PER HOUSING PROGRAMME

## Slide 3: 2015/16 MTSF Picture per Programme *BAS: The expenditure information is not yet final and can still change!!
 | Planned Annual Target 1 April ‘15 to 31 March 2016 |  |  | Actual Delivery to date 1 April’15 to 31 March 2016 |  |  | Variance | 
MTSF PICTURE PER PROGRAMME | Total Planned Sites | Total Planned Units | Total Budget Allocation | Sites | Units | Total Expenditure | Sites | Units
TOTAL IRDP | 3843 | 2979 | 574 535 011 | 1797 | 1017 | 439 487 | -2046 | 1962
2.2a Integrated Residential Development Programme :Phase 1:Planning and Services | 3843 | 0 | 215 280 038 | 1797 | 0 | 227 481 | -2 046 | 0
2.2c Integrated Residential Development Programme :Phase 2:Top Structure Construction | 0 | 2979 | 357 754 973 | 0 | 953 | 212 006 | 0 | -2 026
2.3a People's Housing process | 0 | 0 | 0 | 0 | 64 | 0 | 0 | +64
UISP TOTAL | 9435 | 15370 | 2 271 901 070 | 2622 | 8946 | 2 262 742 | 6365 | -6255
2.2b Integrated Residential Development Programme :Phase 1:Planning and Services INFORMAL SETTLEMENTS | 7935 | 0 | 526 080 495 | 1 346 | 0 | 456 189 | 6 589 | 0
2.2d Integrated Residential Development Programme :Phase 2:Top Structure Construction INFORMAL SETTLEMENTS | 0 | 12 317 | 1 300 367 789 | 0 | 8 429 | 1 281 000 | 0 | -3 888
2.2e Integrated Residential development Programme :Phase 4:Top Structure Construction (INFORMAL SETTLEMENTS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3b People's Housing Process INFORMAL SETTLEMENTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 Informal Settlement Upgrading | 1500 | 3053 | 445 452 786 | 1 276 | 686 | 525 553 | -224 | -2 367

## Slide 4: 2015/16 MTSF Picture per Programme *BAS: The expenditure information is not yet final and can still change!!
 | Planned Annual Target 1 April ‘15 to 31 March 2016 R |  |  | Actual Delivery to date 1 April’15 to 31 March 2016 |  |  | Variance | 
SOCIAL AND RENTAL HOUSING INCLUDING CRU TOTAL | 0 | 1111 | 346 693 969 | 0 | 1008 | 70 165 | 0 | -103
3.1 Institutional Subsidies | 0 | 420 | 123 398 778 | 0 | 0 | 5 365 | 0 | -420
3.2b Social Housing: Capital Grants for rental housing (Funded by NDoH) | 0 | 490 | 86 394 900 | 0 | 973 | 0 | 0 | +483
3.3b Community residential units (CRU) Constructed | 0 | 201 | 136 900 291 | 0 | 35 | 73 800 | 0 | -166
RURAL HOUSING TOTAL | 0 | 215 | 8 466 600 | 0 | 0 | 16 316 | 0 | -690
4.1 Farm Worker Housing Assistance | 0 | 115 | 23 389 974 | 0 | 0 | 16 316 | 0 | -115
4.2 Rural Housing: Communal land rights | 0 | 100 | 6 466 600 | 0 | 0 | 0 | 0 | -100
SUBSIDIES TOTAL | 90 | 1293 | 102 668 620 | 0 | 822 | 209 745 | 0 | -475
1.1a Individual housing subsidies (R0 - R3 500) credit linked | 0 | 0 | 1 500 000 | 0 | 4 | 0 | 0 | 0
1.1b Individual housing subsidies (R0 - R3 500) Non - Credit Linked | 0 | 0 | 0 | 0 | 0 | 200 726 | 0 | 0
1.2 Housing finance linked Individual subsidies (FLISP)-(R3 501 - R7 000) | 90 | 1 293 | 101 168 620 | 0 | 818 | 9 019 | -90 | -475
2.5a Consolidation Subsidies (Excluding Blocked Projects) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 5: 2015/16 MTSF Picture per Programme
 | Planned Annual Target 1 April ‘15 to 31 March 2016 R |  |  | Actual Delivery to date 1 April’15 to 31 March 2016 R |  |  | Variance | 
5. PRIORITY PROJECTS | 1623 | 3314 | 461 368 562 | 5 629 | 2 417 | 372 720 | +4 006 | -897
6. PROVINCIAL SPECIFIC PROGRAMMES | 0 | 1071 | 334 225 142 | 0 | 318 | 37 153 | 0 | -753
TOTAL NATIONAL MTSF TARGET | 14991 | 25353 | 4 097 858 874 | 10 148 | 14 528 | 3 408 325 | -4843 | -10 825
Emergency Housing Programme (new units) | 0 | 0 | 204 476 608 | 0 | - | 0 | - | -
Military Veterans | 0 | 0 |  | 0 | 32 | 0 | 0 | +32
Title Deeds Backlog (Pre-1994) | 0 | 4 000 | 51 000 000 | 0 | 2 846 | 38 925 | 0 | 331
Title Deeds Backlog (Post-1994) | 0 | 6 000 |  | 0 | 6 041 |  |  | 
Title Deeds (New Developments) | 0 | 0 |  | 0 | 0 |  |  | 
Total | 14991 | 25353 | 4 353 335 582 | 10 148 | 14 560 | 3 447 250 | -4 843 | -10 793
Total targets | 40 344 24 708 -15 636 |  |  |  |  |  |  | 

## Slide 6: MINING TOWNS
 | Planned Annual Target 1 April ‘15 to 31 March 2016 |  |  | Actual Delivery to date 1 April’15 to 31 March 2016 |  |  | Variance | 
PROGRAMMES FOR MINING TOWNS | Total Planned Sites | Total Planned Units | Total Budget Allocation R’000 | Sites | Units | Total expenditure R’000 | Sites | Units
Westonaria Khutsong X3 | - | 115 | 60 862 | 0 | 0 | 0 | 0 | 115
Randfontein Mohlakeng X11 Construction of roads Bulk Water Reservoir | - | - | 52 000 | 0 | 0 | 0 | 0 | -0
Merafong Bekkersdal Afghanistan X & Z Section- Rehabilitation of Sewer Network | - | 80 | 50 000 | - | -0 | 96 719 | - | 0
Mogale City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | - | 195 | 162 862 | 0 | - | 96 719 | - | 115

## Slide 7: PROGRAMMES PROPOSED NOT TO BE FUNDED BY THE HSDG
 | Planned Annual Target 1 April ‘15 to 31 March 2016 |  |  | Actual Delivery to date 1 April’15 to 31 March 2016 |  |  | Variance | 
PROGRAMMES PROPOSED NOT TO BE FUNDED BY THE HSDG | Total Planned Sites | Total Planned Units | Total Budget Allocation | Sites | Units | Total expenditure | Sites | Units
1.5a Rectified RDP Stock 1994-2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5b Rectification of Housing Stock (pre 1994) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 Blocked Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.12 Housing Chapters of IDP's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 Project Linked Subsidies (current commitments approved up to 31/03/07) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5b Consolidation Subsidies (Blocked Projects) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.6 Emergency Housing Assistance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3a Community Residential Units (CRU) Converted/Upgraded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emergency (existing units) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 8: PROGRAMMES THAT NEED ADDITIONAL FUNDING
 | Planned Annual Target 1 April ‘15 to 31 March 2016 |  |  | Actual Delivery to date 1 April’15 to 31 March 2016 |  |  | Variance | 
PROGRAMMES THAT NEED ADDDITIONAL REPORTS | Total Planned Sites | Total Planned Units | Total Budget Allocation | Sites | Units | Total expenditure | Sites | Units
1.3 Enhanced Extended Discount Benefit Scheme (EEDBS) | 0 | 0 | 51 000 | 0 | 00 | 38 925 | 0 | 0
1.4 State Asset Maintenance Programme | 0 | 0 | 46 500 | 0 | 0 | 131 331 | 0 | 0
1.6 Social and Economic Facilities | 0 | 0 | - | 0 | 0 | - | 0 | 0
1.8 Operational Capital Budget | 0 | 0 | 248 992 | 0 | 0 | 239 004 | 0 | 0
1.11a Land parcels procured(IHAHSD) | 0 | 0 | - | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 346 492 | 0 | 0 | 409 260 | 0 | 0

## Slide 9: OTHER PROGRAMMES TO BE FUNDED
 | Planned Annual Target 1 April ‘15 to 31 March 2016 |  |  | Actual Delivery to date 1 April’15 to 31 March 2016 |  |  | Variance | 
OTHER PROGRAMMES THAT ARE TO BE FUNDED | Total Planned Sites | Total Planned Units | Total Budget Allocation R”000 | Sites | Units | Total expenditure R”000 | Sites | Units
1.10 NHBRC enrolment (related to grant) | 0 | 0 | 34 000 | 0 | 0 | 10 579 | 0 | 0
3.2a Social Housing: Operational Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 Accredited Municipalities (level 1 & 2): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Disaster Relief | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 34 000 | 0 | 0 | 10 579 | 0 | 0

## Slide 10: MINING TOWNS
 | Planned Annual Target 1 April ‘15 to 31 March 2016 |  |  | Actual Delivery to date 1 April’15 to 31 March 2016 |  |  | Variance | 
PROGRAMMES FOR MINING TOWNS | Total Planned Sites | Total Planned Units | Total Budget Allocation R’000 | Sites | Units | Total expenditure R’000 | Sites | Units
Westonaria Khutsong X3 | - | 115 | 60 862 | 0 | 0 | 0 | 0 | 115
Randfontein Mohlakeng X11 Construction of roads Bulk Water Reservoir | - | - | 52 000 | 0 | 0 | 0 | 0 | -0
Merafong Bekkersdal Afghanistan X & Z Section- Rehabilitation of Sewer Network | - | 80 | 50 000 | - | -0 | 96 719 | - | 0
Mogale City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | - | 195 | 162 862 | 0 | - | 96 719 | - | 115

## Slide 11: 2016/17 DELIVERABLES AND BUDGETS
B. PLANNED TARGETS AND BUDGETS PER HOUSING PROGRAMME

## Slide 12: MTSF 2016 PLANNED TARGETS
The Department received an allocation of R5,022,669,000 for 2016 – 2017 FY , the department is requested to focus on the following :
Adherence to the MTSF Targets & Outputs
Key Programmes (FLISP , Social & Rental Housing, UISP,IRDP and Title Deeds.
Relevant Protocols to be entered into with HDA- for the acquisition of land
And finally the alignment of the HSDG and USDG business plans
For the 2016 – 2017 Business Plan ,extensive engagements have been undertaken with the respective municipalities of Gauteng to ensure alignment primarily with the IDP’s MIG & USDG. The state of readiness of the projects have been scrutinized and have reached a satisfactory level for implementation, projects that require final appointments of contractors will be managed by Supply Chain Management ensuring all outstanding projects to be awarded contractors and valid contracts by the end of April 2016.

## Slide 13
Ekurhuleni | Sites | Units | Budget | %
 | 337 | 4862 | R 643,609,365 | 70.94%
 | 1500 | 1377 | R 222,196,658 | 24.25%
 | 0 | 0 | R 41,410,000 | 4.81%
Total | 1,837 | 6,239 | R 907,216,023 | 100%
Tshwane | Sites | Units | Budget | % of total budget allocation
 | 310 | 6320 | R 690,659,950 | 51.71%
 | 1070 | 1780 | R 237,294,730 | 30.32%
 | 0 | 0 | R 65,000,000 | 16.41%
 | 0 | 0 | R 12,700,000 | 1.56%
Total | 1,380 | 8,100 | R 1,005,654,680 | 100%
LEGEND
Project Ready for construction /Contractor & PRT on Site
Projects require SCM, Process dealing with contracts and IPW’s
Projects Under Planning
Projects delivering Bulk Infrastructure
Project Readiness Matrix - SUMMARY
Joburg | Sites | Units | Budget | %
 | 2150 | 4875 | R 774,481,029 | 71.96%
 | 222 | 1797 | R 196,851,076 | 18.29%
 |  |  | R 15,000,000 | 1.39%
 | 0 | 0 | R 89,885,195 | 8.35%
TOTAL | 2372 | 6672 | R 1,076,217,300 | 100%
NB. Targets and Budget will adjust from Amber to Green,
once awarding and contracting is concluded

## Slide 14
Sedibeng | Sites | Units | Budget | % of total budget allocation
 | 923 | 3508 | R 453,916,719 | 62.99%
 | 2266 | 1513 | R 278,655,097 | 27.44%
 |  |  | R 17,731,484 | 6.06%
 |  |  | R 29,696,700 | 3.50%
TOTAL | 3189 | 5021 | R 780,000,000 | 100%
GDHS | Sites | Units | Budget | %
 | 5625 | 21557 | R 2,913,926,809 | 61.21%
 | 6203 | 8616 | R 1,184,113,918 | 20.23%
 |  |  | R 191,624,507 | 3.82%
 |  |  | R 171,316,052 | 3.56%
OPSCAP,NHBRC, EEDBS, Assests, Flood Repair |  |  | R 425,333,851 | 8.47%
Head Office GPF |  | 1229 | R 136,353,863 | 2.71%
Grand Total | 11,828 | 31,402 | R 5,022,669,000 | 100%
Project Readiness Matrix - SUMMARY
LEGEND
Project Ready for construction /Contractor & PRT on Site
Projects require SCM, Process dealing with contracts and IPW’s
Projects Under Planning
Projects delivering Bulk Infrastructure
NB. Targets and Budget will adjust from Amber to Green,
once awarding and contracting is concluded
West Rand | Sites | Units | Budget | % of total budget allocation
 | 2050 | 3254 | R 474,289,607 | 36.57%
 | 1000 | 887 | R 145,573,229 | 52.30%
 | 0 | 0 | R 64,319,887 | 9.30%
 |  |  | R7,710,560 | 1.84%
Total | 3,050 | 4,141 | R 691,893,283 | 100%

## Slide 15: MTSF PLANNED TARGETS
MTSF PICTURE PER PROGRAMME | Total Sites | Budget for Sites | Total Units | Budget for Units | Total Allocation per programme
TOTAL IRDP ( Incremental Housing Programme) | 9,243 | 663,182,672 | 22,928 | 2,703,267,803 | 3,366,450,475
2.2a Integrated Residential Development Programme :Phase 1:Planning and Services | 2,677 | 139,891,190 | - | - | 139,891,190
2.2c Integrated Residential Development Programme :Phase 2:Top Structure Construction | - | - | 4,920 | 588,059,461 | 588,059,461
2.3a People's Housing process |  |  |  |  | 
UISP TOTAL |  |  |  |  | 
2.2b Integrated Residential Development Programme :Phase 1:Planning and Services INFORMAL SETTLEMENTS | 5,396 | 425,302,872 | - | - | 425,302,872
2.2d Integrated Residential Development Programme :Phase 2:Top Structure Construction INFORMAL SETTLEMENTS | - | - | 13,681 | 1,616,705,427 | 1,616,705,427
2.4 Informal Settlement Upgrading | 1,170 | 70,249,170 | 4,327 | 478,863,355 | 549,112,525

## Slide 16: MTSF PLANNED TARGETS
MTSF PICTURE PER PROGRAMME | Total Sites | Budget for Sites | Total Units | Budget for Units | Total Allocation per programme
SOCIAL AND RENTAL HOUSING INCLUDING CRU TOTAL | - | - | 4,002 | 587,790,463 | R 587,790,463
3.1 Institutional Subsidies | - | - | 2,723 | 306,338,010 | 306, 338,010
3.2b Social Housing: Capital Grants for rental housing (Funded by NDoH) | - | - | 550 | 61,020,850 | 61,020,850
3.3b Community residential units (CRU) Constructed | - | - | 729 | 211,609,163 | 211,609,163
RURAL HOUSING TOTAL | 300 |  | 500 |  | 53,834,708
4.1 Farm Worker Housing Assistance | 300 | 16,350,308 | 300 | 36,484,400 | 52,834,708
4.2 Rural Housing: Communal land rights | 0 | 0 | 200 | 1,000,000 | 1000,000
SUBSIDIES TOTAL |  |  |  |  | 
1.2 Housing finance linked Individual subsidies (FLISP)-(R3 501 - R7 000) | 0 | 0 | 893 | 56,318,758 | 56,318,758

## Slide 17: MTSF PLANNED TARGETS
MTSF PICTURE PER PROGRAMME | Total Sites | Budget for Sites | Total Units | Budget for Units | Total Allocation per programme
5. PRIORITY PROJECTS | 2,285 | 146,641,110 | 2,682 | 310,741,466 | 457,382,576
6. PROVINCIAL SPECIFIC PROGRAMMES |  |  | 397 | 128,159,327 | 
TOTAL NATIONAL MTSF TARGET | 11,828 | 1,005,130,171 | 31402 | 4,017,538,829 | 5,022,669,000
Emergency Housing Programme (new units) ring-fenced | - | - | - | - | 47,379,000
Military Veterans |  |  | 836 | 97,044,277 | 97,044,277
Title Deeds Backlog (Pre-1994) |  |  | 7461 | 51,000,000 | 51,000 ,000
Title Deeds Backlog (Post-1994) |  |  | 78,795 |  | Require additional to accommodate the backlog
Total |  |  |  |  | 
Total Housing Opportunities | 43 230 |  |  |  | 

## Slide 18: MINING TOWNS
PROGRAMMES FOR MINING TOWNS | Total Planned Sites | Budget for Sites | Total Planned Units | Budget for Units | Total Budget Allocation per programme
PRIORITY PROJECTS West Rand | 935 | 44,869,341 | 986 | 111,663,908 | 156,533,249
PROVINCIAL SPECIFIC PROGRAMMES West Rand |  |  | 287 | 98,317,476 | 98,317,476
TOTAL | 935 | 44,869,341 | 1273 | 209,981,384 | 254,850,725
Kokosi Ext 7 - Sewer Outfall Line
Sewer Rehabilitation Project - Bekkersdal
R 54,319,887
R 10,000,000
Inclusive of the following for Revitalisation of Mining Towns

## Slide 19: PROGRAMMES PROPOSED NOT TO BE FUNDED BY THE HSDG
PROGRAMMES PROPOSED NOT TO BE FUNDED BY THE HSDG | Total Planned Sites | Budget for Sites | Total Planned Units | Budget for Units | Total Allocation per programme
1.5a Rectified RDP Stock 1994-2002 | - | - | - | - | -
1.5b Rectification of Housing Stock (pre 1994) | - | - | - | - | -
1.9 Blocked Projects | - | - | - | - | -
1.12 Housing Chapters of IDP's |  |  |  |  | 
2.1 Project Linked Subsidies (current commitments approved up to 31/03/07) | - | - | - | - | -
2.5b Consolidation Subsidies (Blocked Projects) | - | - | - | - | -
3.3a Community Residential Units (CRU) Converted/Upgraded | - | - | - | - | 8,822,440
Emergency Programme (existing units) | - | - | - | - | 
TOTAL |  |  |  |  | 
Notes: CRU converted/upgtaded have contractual commitments. A minimum amount of budget has been put aside for the said projects for ensuring registration on BAS in case of Ministerial approval . Management of risk of non-payment ot service providers based on commitments as cited e.g. Sethoga hostel, Thokoza hostel, KwaMasiza and Sharpeville, Boipatong

## Slide 20: PROGRAMMES THAT NEED ADDDITIONAL REPORTS
PROGRAMMES THAT NEED ADDDITIONAL REPORTS | Total Sites | Budget for Sites | Total Units | Budget for Units | Total Allocation per programme
1.3 Enhanced Extended Discount Benefit Scheme (EEDBS) | - | - | - | - | 51,000,000
1.4 State Asset Maintenance Programme | - | - | - | - | 46,500 ,000
1.6 Social and Economic Facilities | - | - | - | - | 
1.8 Operational Capital Budget | - | - | - | - | 251,133 ,450
1.11a Land parcels procured(IHAHSD) | - | - | - | - | -
Total |  |  |  |  | 

## Slide 21: OTHER PROGRAMMES THAT ARE TO BE FUNDED
OTHER PROGRAMMES THAT ARE TO BE FUNDED | Total Sites | Budget for Sites | Total Units | Budget for Units | Total Allocation per programme
1.10 NHBRC enrolment (related to grant) | - | - | - | - | 27,099,243
3.2a Social Housing: Operational Support | - | - | - | - | -
1.7 Accredited Municipalities (level 1 & 2): | - | - | - | - | -
Disaster Relief | - | - | - | - | -
Total |  |  |  |  | 

## Slide 22: THANK YOU
“We have come a long way – Celebrating 20 Years of Freedom!”