Directorate: Strategic Management, Monitoring and Evaluation,

Private Bag X 896,

Regent Place, 66 Queen Street,

Pretoria: Tel: 012 304 5175

ORGANISATIONAL PERFORMANCE REVIEW REPORT

QUARTER 4: 2015/16 FINANCIAL YEAR

QSRM DATE: 25 APRIL 2016

TABLE OF CONTENTS

1.	INTRODUCTION	3

2.	LIST OF PROGRAMMES AND PEFORMANCE INFORMATION	4

2.1	PROGRAMME 1: ADMINISTRATION	4

2.1.1	PROGRAMME PERFORMANCE GRAPH	4

2.1.2 SERVICE DELIVERY MAIN ACHIEVEMENTS	5

2.1.3	PERFORMANCE INFORMATION	7

2.2	PROGRAMME 2: ACTIVE NATION	8

2.2.1	PROGRAMME PERFORMANCE GRAPH	8

2.2.2	SERVICE DELIVERY MAIN ACHIEVEMENTS	9

2.2.3	PERFORMANCE INFORMATION	10

PROGRAMME 3: WINNING NATION	13

2.3.1	PROGRAMME PERFORMANCE SUMMARY	13

2.3.2	SERVICE DELIVERY ACHIEVEMENTS	14

2.3.3	PERFORMANCE INFORMATION	15

2.4	PROGRAMME 4: SPORT SUPPORT	17

2.4.1	PROGRAMME PERFORMANCE GRAPH	17

2.4.2	SERVICE DELIVERY MAIN ACHIEVEMENTS	18

2.4.3	PERFORMANCE INFORMATION	19

2.5	PROGRAMME 5: INFRASTRUCTURE SUPPORT	21

2.5.1	PROGRAMME PERFORMANCE	21

2.5.2	SERVICE DELIVERY ACHIEVEMENTS	21

2.5.3	PERFORMANCE INFORMATION	22

# INTRODUCTION

Framework for Strategic Planning and Annual Performance Plan (August 2010) states that the purpose of quarterly performance reports provide progress updates on the implementation of an institution APP in the previous quarter, with particular reference to monitoring delivery against quarterly performance targets. Quarterly performance report provides the Accounting Officer, Executive Authority and National Treasury with information on performance against plans. According to the timeframes stated in the Framework, reports must be prepared within 30 days after the end of the quarter. Changing of planned targets should not be made during reporting.

The purpose of the report is to give an overview of what transpired in the fourth quarter of the financial year (2015/16). The report reflects mainly performance against key strategic objectives and annual performance indicators as reflected in the Department’s Annual Performance Plan (APP) and to a lesser extent, the Operational plan for 2015/16.

The report also gives a consolidation of quarterly performance and its contribution to the annual performance. The quarter 4 performance is reflective of the annual performance for each programme.

# 2.	LIST OF PROGRAMMES AND PEFORMANCE INFORMATION

## PROGRAMME 1: ADMINISTRATION

### PROGRAMME PERFORMANCE GRAPH

There were 8 targets to be achieved during the quarter under review. Two targets were not achieved and 6 were achieved.

### 2.1.2 SERVICE DELIVERY MAIN ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Sub-programme | Quarter 4 |
| --- | --- |
| Management | Managed and quality assured Risk management reports; Executive Monthly reports; and Task team Reports Coordinated the development and submission of documents for: Portfolio Committee and NCOP meetings (and also attended the meetings as invited) as well as the Risk management Committee meeting. Coordinated the hosting of the following committees’ meetings: HeadCom, ManCo, as well as the Operations Management, and followed up decisions of these committees to ensure implementation of decisions. Followed up decisions of the Study Cluster and Cabinet meetings to the extent they affected SRSA. Coordinated a meeting and prepared report on the Commonwealth Games 2022, preparations. |
| Internal Audit | Internal Audit None |
| Communication and Marketing | All undertaken events were provided with marketing and communication support. |
| Corporate Services | Human Resources For this quarter, twenty seven (27) employees were trained in various courses. Again, the unit has over-achieved in terms of this item, as the target was twenty (10). Out of the total trained, five employees were being trained for the first time. |
|  | Legal Services None |
|  | Labour Relations None |
|  | Government Information Technology None |
|  | Office Accommodation: None |
| CFO’s Office | Finance: Managed the finances such that the set target of >99% spending was achieved. SCM: (incl. Fleet, Facilities and Security Management) - None |
| Strategic Support | 1. QPR Quarter 3 report was presented at the QSRM meeting and follow up MANCO meeting. Submission to DPME and National Treasury was done within the set timeframe. A presentation of the QPR was developed and presented by DG to the portfolio committee. 2. Outcome 14 Relentlessly engaged with the Presidency to obtain confirmation of Cabinet approval of the Outcome 14 revisions. Drafted a comprehensive memo to the Dept. of Arts and Culture (DAC) outlining the dissatisfaction of SRSA with the slow progress made in this regard. Convened a meeting with officials from the DAC and the Presidency and on 20 January to discuss the MTSF revisions proposed by SRSA, and the implications thereof for the 2016/17 Annual Performance Plan. Represented the DG at the Outcome 14 DG’s Technical Implementation Forum in Cape Town on 12 February 2016 and again on 18 February in Pretoria. Prepared and presented SRSA’s revisions to the MTSF. Proposals were accepted by the Forum and were submitted to DAC for inclusion in the Cabinet Memo. 3. 2016/17 Annual Performance Plan Updated the APP following input from Presidency on draft two of the Plan, ahead of printing and tabling of the report. Updating included aligning the 2016 ENE selected performance indicators with those in the draft APP and drafted the expenditure analysis per programme. Prepared a powerpoint presentation linking the APP targets with the approved ENE in preparation for the DG’s engagement with the Minister on 25 February; DG’s presentation to the Portfolio Committee; and CD: SS’ presentation to Deputy Minister. Tabled the APP in Parliament. Prepared Technical Indicator Descriptions for all the indicators in the 2016/17 APP. 4. Operational plans The Operational Plan Guidelines were updated and the template was reviewed for updates. The 2016/17 Annual Performance Plan was perused and all the relevant outputs were extracted per programme and compiled to assist the managers to develop their 2016/17 operational plans. 5. Conditional Grant Framework Strategic Alignment Presented a Powerpoint presentation detailing the customized sector indicators and the selected conditional grant indicators at the Conditional Grant Workshop on 16 February. 6. 2016 ENE Engaged with National Treasury and replied to ad-hoc queries in preparation for submission of the final ENE (non-financial chapter). Consulted line function Chief Directors to agree upon selected performance indicators and collaboratively adjusted targets following January budget cuts. Also contributed to editing of the final 2016 ENE and confirmed the performance indicators to ensure alignment with the Outcome indicators and to the 2016/17 APP. 7. Public entity support Reviewed the BSA 2016/17 APP and provided formal written feedback. SAIDS did not provide the correct documentation for review. 8. Customized Sector Indicators Received the published Customized Sector Indicators for 2016/17 from DPME and communicated them to all nine provinces. The provinces were also informed in writing that all five customized indicators need to be included in their provincial APPs for 2016/17. 9.MPAT Attended MPAT KPA Coordinators Challenge Workshop on 8 February. Uploaded all the additional documentation supporting the areas challenged. 10. Additional work requested Representatives of the Chief Directorate were seconded to the School Sport Task Team to provide the Results and Monitoring functions at the Port Elizabeth Championship held in March 2016. |

### PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan.

| Programme Performance Indicator | Annual Target 2015/16 | Quarter 4 | Preliminary Information | Actual Performance | Status of Achievement | Cumulative Total | Reason for deviation | Corrective Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sup-programme: Administration |
| Strategic objective: Strategic leadership, management and support services. |
| 1.1 Approved MTEF Human Resource Plan. | 1 | - | Achieved in the first quarter. | Achieved in the first quarter. | Achieved | 1 | None | None |
| 1.2 Moderation for performance assessments concluded for previous cycle by 30 June. | 100% | - | - | No Target | Achieved | 100% | None | None |
| 1.3 Number of employees trained. | 60 | 10 | 27 | 27 Newly trained =5 | Achieved | 127 | Increased need for skills development | None |
| 1.4 Number of client satisfaction surveys conducted. | 1 Internal | - | 1 | 1 | Achieved | 1 | The target couldn’t be achieved in quarter 3 | None |
| 1.5 Approved procurement plan. | 1 | - | - | - | Achieved | 1 | None | None |
| 1.6 Budget spent (%) | > 99% | > 99% | - | > 99% | Achieved | > 99% | None | None |
| 1.7 Creditor payment age (days) | 30 | 30 | 30 | >30 | Not Achieved | >30 | System(BAS) challenges, especially w.r.t. transaction speed | None |
| 1.8 Quarterly APP targets met (%) | 100% | 100% | - | 79% | Not Achieved | 79% | This target won’t be achieved as long as there is no 100% achievement | Removed from the 2016/17 APP because it doesn’t add value. |

## PROGRAMME 2: ACTIVE NATION

### PROGRAMME PERFORMANCE GRAPH

*There were 10 targets to be achieved by the programme during the quarter under review.

Six targets were achieved, 4 were not achieved.

### SERVICE DELIVERY MAIN ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Programme | Quarter 4 |
| --- | --- |
| Active Nation | Active Recreation & Community Sport: None |
|  | Community Sport None |
|  | School Sport: The school sport programme implemented two successful National Championships in March 2016, in Port Elizabeth (Eastern Cape) and Bloemfontein (Free State). All provinces were represented. |
|  | Provincial sport support and coordination None |

    - PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan

| Programme Performance Indicator | Annual Target 2015/16 | Quarter 4 | Preliminary Information | Actual Performance | Status of Achievement | Cumulative Total | Reason for deviation | Corrective Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-programme: Active Recreation. |
| Strategic objective: Active recreation programmes implemented. |
| 2.1 Number of close-out reports produced. | 5 Close-out reports on: Youth Camp Move for Health Day Golden Games Big Walk Recreation Day | 3 GG BW NRD | 3 | 3 | Achieved | 5 YC –Q3 M4H-Q2 GG –Q4 BW-Q4 NRD–Q4 | None | None |
| Sub-programme: Community Sport. |
| Sport participation opportunities provided to communities. |
| 2.2 Number of close-out reports produced. | 2 Close-out reports on: Indigenous Games Nelson Mandela Sport and Culture Day | No target | - | 1 | Achieved | 2 67 Minutes of Mandela celebrated in Cannavon and Atteridgeville-Q2 IG -Q3 | Nelson Mandela Day celebration achieved in Q2 is only reported in this quarter | None |
| 2.3 Number of participants in sport and recreation promotion campaigns and events. | 11 700 Participants from 2.1 & 2.2 above. | 11 700 | - | 11 804 | Achieved | 11 804 M4H; IG; BW; YC; NRD; AMGD: | Increased interest in SRSA events | None |
| Sub-programme: School Sport. |
| Strategic Objective: School sport programmes supported. |
| 2.4 Number of close-out reports produced. | 1 Close out report for National School Sport Championship | 1 | - | 3 | Achieved | 3 | See note below | None |
| 2.5 Number of participants in the school sport programme. | 12 000 | 12 000 | - | 10 106 | Not Achieved | 10 106 | See note below | None |
| Sub-programme: Provincial sport support and coordination. |
| Strategic Objective: Provincial sport development programmes supported. |
| Funded from Conditional Grant: |
| 2.6 Number of people actively participating in organised sport and active recreation events. | 2 371 680 | 639 615 | - | 0 | Not achieved | 102 219 | Q4 reports from provinces being verified | Update the status once Q4 reports are verified |
| 2.7 Number of learners participating in school sport tournaments at a district level. | 37 441 | 11 360 | - | 0 | Achieved | 57 518 | See note below | Update the status once Q4 reports are verified |
| 2.8 Number of schools, hubs and clubs provided with equipment and/or attire as per the established norms and standards. | 6 520 | 2058 | - | - | Not Achieved | 1 671 | Q4 reports from provinces being verified | Update the status once Q4 reports are verified |
| 2.9 Number of athletes (learners) supported by the sports academies (% increase also reflected). | 8 275 | 815 | - | 2 067 | Not Achieved | 6 089 | Q4 reports from provinces being internally audited | Update the status once Q4 internal audit is finalised |
| 3.0 Number of sport academies supported. | 32 | 5 | - | 35 | Achieved | 35 | Intensified follow-up of provinces for evidence | None |

2.2 The recognition of the ideals that former President, Dr Nelson Mandela stood for, is done in various ways by the Department, with each year bringing its own version, be it a sports and culture day, or engagement of communities w.r.t sport development, where sport clinics are conducted, or sport equipment and attire is given to hubs, clubs or schools, or even inviting sports people to go and do some act of goodness in a community, like painting and so forth. Although activities related to the Nelson Mandela Day took place in Carnavon and Atteridgeville in Q3, the involvement of various structures delayed the submission of the final report. The performance is thus only reported in Q4.

2.4 Two Autumn championships were held in addition to the Summer 2015 one. This is the new approach going forward.

2.5 Management took a decision in-year to reduce the target in line with available resources, following the cut of financial contribution from the Lottery. Following engagement of National Treasury, the target could however not be changed.

2.6 – 2.9: reports from provinces being verified/internally audited. Once done, the info from the reports will be added to the q4 achievement totals.

2.7 Target already achieved. However Q4 has not yet been included because reports from provinces are being internally audited.

## PROGRAMME 3: WINNING NATION

Purpose: Support the development of elite support.

### PROGRAMME PERFORMANCE SUMMARY

There were 7 targets to be achieved by the programme. Six targets were achieved, and 1 target was not achieved.

### SERVICE DELIVERY ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Sub-programme | Quarter 4 |
| --- | --- |
| Scientific Support | None |
| Major Events | 1. Achievements against APP indicator targets: None 2. Achievements against other projects not captured as APP indicator targets: No major achievements to report on |

### PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan

| Programme Performance Indicator | Annual Target 2015/16 | Quarter 4 | Preliminary Information | Actual Performance | Status of Achievement | Cumulative Total | Reason for deviation | Corrective Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-programme: Scientific Support. |
| Strategic objective: Scientific support services coordinated for athletes. |
| 3.1 Number of SASCOC MOU progress reports evaluated. | 4 | 1 | 0 | 4 | Achieved | 4 | None | None |
| 3.2 Number of athletes supported through the Ministerial Bursary Sports Programme. | 40 | 5 | - | 42 | Achieved | 52 | The last intake increased the number beyond 40 | None |
| 3.3 Number of athletes supported through the scientific support programme. | 40 | 5 | - | 20 | Achieved | 43 29 [6 residential + 23 +14] | Increased need for scientific support | None |
| Strategic objective: Government responsibility towards anti-doping supported. |
| 3.4 Number of drug-free support agencies supported. | 4 RADO WADA CDA SAIDS | 1 | 1 | 1 RADO | Achieved | 4 | None | None |
| Sub-programme: Major Events Support. |
| Strategic objective: Approved major events supported. |
| 3.5 Number of major international events receiving intra-governmental support per year. | 4 | - | - | 0 | Not Achieved | 0 | Supported events not EA/Cabinet approved | None |
| Strategic Objective: Sport Tourism to South Africa promoted. |
| 3.6 Number of national & international sporting events, exhibitions or conferences used to showcase SA as a sports tourist destination. | 1 Olympic & Paralympic Games – Rio Ekhaya status report. | 1 | 1 | 1 | Achieved | 1 | None | None |
| Sub-programme: Recognition Systems. |
| Strategic objective: Achievements in the sport and recreation sector acknowledged. |
| 3.7 Number of recognition and honouring events. | 3 | - | - | - | Achieved | 4 | None | None |

3.7. Cumulative: G-Sport recognition, IAAF achievers [TNA Bkfst], Sport Awards, and AM Green Jacket (AMGJ).

## PROGRAMME 4: SPORT SUPPORT

Purpose: Develop and maintain an integrated support system to enhance the delivery of sport and recreation.

### PROGRAMME PERFORMANCE GRAPH

* There were 7 targets to be achieved by the programme during the quarter under review. All targets were achieved.

### SERVICE DELIVERY MAIN ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

| Sub-programme | Quarter4 |
| --- | --- |
| Sport and Recreation Service Providers 7 sport bodies received financial support during the quarter under review. This takes the cumulative total to 65. |
| Number of Bilateral exchanges implemented None |
| Multilateral engagements supported: None |

### PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan

| Programme Performance Indicator | Annual Target 2015/16 | Quarter 4 | Preliminary Information | Actual Performance | Status of Achievement | Cumulative Total | Reason for deviation | Corrective Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-programme: Sport and Recreation Service Providers. |
| Strategic objective: Good governance supported. |
| 4.1 Number of Federations pledging support for the Code of Conduct. | 20 | 5 | 20 | 20 | Achieved | 23 | See note below | None |
| Strategic objective: Sport and recreation bodies supported. |
| 4.2 Number of sport and recreation bodies receiving financial and non-financial support per year. | 60 | - | - | 7 | Achieved | 65 | Improved cooperation from federations | None |
| 4.3 Number of world class athletes under 18 years supported. | 80 | 80 | 92 | 92 | Achieved | 115 | See note below | None |
| 4.4 Percentage increase in support of world class athletes under 18 years of age. | Establish baseline | - | R585, 439.00 | R585, 439.00 | Achieved | R1, 258,531.24 | None | None |
| Strategic objective: Transformation programmes implemented and monitored. |
| 4.5 Number of consolidated National Federation Transformation Progress Reports produced. | 1 | No Target | 1 | 1 | Achieved | 1 | None | None |
| Sub-programme: International relations. |
| Strategic objective: Strategic bilateral relations managed and strengthened. |
| 4.6 Number of bilateral exchanges implemented. | 3 | 1 |  | 1 | Achieved | 4 Cuba; India, High performance visit by HPC to Jamaica Russia | None | None |
| Participation in strategic multilateral relations managed. |
| 4.7 Number of status reports detailing multilateral engagements supported. | 4 | 1 | 1 | 1 | Achieved | 4 | None | None |

## 4.1 The cooperation of the federation gained momentum earlier than anticipated

## 4.2 Federations that were paid twice such as Boxing, Netball, and Handball are while counted in the quarter achievements, not counted double in the cumulative total.

4.3 Federations’ growing need to develop young athletes for international duty. The athletes are from among others, Aerobics; Baseball; Canoeing; Chess; Surfing; Weightlifting; Table Tennis

4.7 The multilateral engagements relate to: AUSC Region 5; UNESCO; CABOS; and 5th Session of the conference of parties.

## PROGRAMME 5: INFRASTRUCTURE SUPPORT

Purpose: Regulate and manage the provision of sport and recreation facilities.

    - PROGRAMME PERFORMANCE GRAPH

There was 2 targets scheduled to be achieved by the programme and they were both achieved.

### SERVICE DELIVERY ACHIEVEMENTS

The table below illustrates the summarised main achievements of the programme.

Quarter 4

Sub-programme: Sport and Recreation facility planning.

After struggling to do so, in the previous financial year, the first phase of the Facilities Audit was conducted in the form of a facilities count. A sample of the facilities reported as counted, were verified by a team of SRSA officials, who visited all the provinces in March 2016. The verification process registered a 100% match.

### PERFORMANCE INFORMATION

The table below illustrates the performance of the programme against the Annual Performance Plan

| Programme Performance Indicator | Annual Target 2015/16 | Quarter 4 | Preliminary Information | Actual Performance | Status of Achievement | Cumulative Total | Reason for deviation | Corrective Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sub-programme: Sport and Recreation facility planning. |
| Access to sport and recreation facilities optimised. |
| 5.1 Number of provinces with a facility audit completed | 9 | 9 | - | 9 | Achieved | 9 | None | None |
| Sub-programme: Sport and recreation facility management. |
| Technical and management support provided. |
| 5.2 Number of post-support reports produced. | 12 | 3 | 3 | 10 | Achieved | 13 | See note below | None |

5.2 With the appointment of an engineer, more technical support was provided to municipalities.

2.6 OVERALL ACHIEVEMENT

:

There were 34 targets scheduled to be achieved by the programme and 27 were achieved and 7 were not achieved. This is 79% achievement.

…000…

# Text boxes

PROGRAMME 3: WINNING NATION

PROGRAMME 4: SPORT SUPPORT

PROGRAMME 2: ACTIVE NATION

PROGRAMME 5: INFRASTRUCTURE SUPPORT

OVERALL ACHIEVEMENT FOR Q4, 2015/16

PROGRAMME 1: ADMINISTRATION