## Slide 1: INFRASTRUCTURE PROGRAMME
State of legacy projects and infrastructure maintenance projects
Presented by: Act Director-General
Date: September 2016

## Slide 2: OUTLINE OF THE PRESENTATION
PURPOSE OF THE PRESENTATION
ALLOCATION AND EXPENDITURE AS AT 31 JULY 2016
FUNDED MAINTENACE AND UPGRADING PROJECTS IN 2016/17 FINANCIAL YEAR
INFRASTRUCTURE IMPROVEMENT PLAN
CONCLUSION

## Slide 3: PURPOSE
To brief the Portfolio Committee for Arts and Culture on the state of the infrastructure programme in the DAC

## Slide 4: INTRODUCTION
The DAC has an Infrastructure Development Unit (IDU) that oversees construction, maintenance and payment of municipal services of the DAC infrastructure portfolio.
The construction of buildings is mainly done by DPW and some projects were done by IDT.
The private leasing portfolio is managed by entities themselves.
The IDU is faced with the challenge of the limited capacity: it consists of a Director and three recently appointed Project Managers to implement the infrastructure programme. The challenges faced were:
  Under expenditure
  Poor project management
  Limited monitoring and verification of work done
  Deliberations to resolve infrastructure challenges take place at the strategic level.
  Areas which require improvement were identified and processes for interventions were initiated. These are outlined in the slides with challenges and interventions.

## Slide 5: ALLOCATION AND EXPENDITURE AS AT 31 JULY 2016

## Slide 6: EXPENDITURE AS AT 30 JULY 2015
PROGRAMME | APPROPRIATION | EXPENDITURE | %
Arts and Culture Promotion and Development | R134 547 000 | 0 | 0
Heritage Promotion and Preservation (Heritage Institutions Infrastructure work) | R173 036 000 | R43 092 026 | 25%
Institutional Governance (Legacy Projects) | R252 549 000 | R27 165 097 | 11%
TOTAL | R 560 132 000 | R70 257 123 | 13%

## Slide 7: EXPENDITURE AS AT 30 JULY 2015
* August reconciliation still underway

## Slide 8: FUNDED maintenance AND UPGRADING projects

## Slide 9: 2016/17 INFRASTRUCTURE PROJECTS cont…
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Artscape Space Optimization project – upgrading of the foyers and theatres. | 14 750 000 | 0 | Design stage
Market Theatre Foundation | 24 687 000 | - | -
Upgrading of Laager Theatre | 1 028 918 | 0 | Planning stage
Upgrading and Refurbishment of the Windybrow Heritage House | 20 000 084 | 0 | Design Stage
Installation Back-up Generators | 3 658 000 |  | Planning stage

## Slide 10: 2016/17 INFRASTRUCTURE PROJECTS cont…
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Performing Arts Centre of the Free state | 30 000 000 | - | -
Mechanical Ventilation & Air Conditioning System | 30 000 000 | 0 | Design stage
The Playhouse Company | 13 818 406 |  | 
Installation of Back-up Generators | 13 818 406 |  | Planning stage
State Theatre | 4 800 000 | - | -
Refurbishment of foyer and ablutions | 4 000 000 |  | Construction stage
Replacement of stage lighting equipment | 8 000 000 |  | Planning stage

## Slide 11: 2016/17 INFRASTRUCTURE PROJECTS cont…
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Incubator | 2 000 000 | - | -
Polokwane Performing Arts Centre | 2 000 000 | 0 | Feasibility stage
Community arts centres | 23 992 000 | - | -
Upgrading of Community Art Centres | 12 000 000 | 0 | Planning phase
Construction of Community Art Centres | 11 991 823 | 0 | Planning phase

## Slide 12: 2016/17 INFRASTRUCTURE PROJECTS cont…
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Cultural precincts | 12 500 000 | - | -
Red Location | 2 500 000 | 0 | Design stage
Other Cultural precincts | 10 000 000 | 0 | Planning
South African Roadies Association | 5 000 000 | 0 | Planning
Upgrading of public spaces | 3 000 000 | 0 | Planning
Total for ACPD | 134 547 000 | 0 | 

## Slide 13: 2016/17 INFRASTRUCTURE PROJECTS cont…
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Afrikaans Taal Museum en-monument | 2 000 000 | 228 971 | 
Construction of workers change room | 2 000 000 | 228 971 | Tender Stage
Ditsong Museums of South Africa | 5 128 000 | 575 786 | 
Repairs and Maintenance Mechanical and electrical work status quo report | 2 089 000 | 575 786 | Construction stage
Sammy Marks Museum - Construction renovation & Upgrading | 347 794 | 0 | Construction stage

## Slide 14: 2016/17 INFRASTRUCTURE PROJECTS cont…
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Repairs and Maintenance programme :Civil and structural(Cultural History) | 2 609 949 | 0 | Construction stage
Luthuli Museum | 500 000 | - | -
Construction of Resource Centre with Exhibition Space, Ablution Facilities and offices | 5 00 000 | 0 | Tender stage

## Slide 15: 2016/17 INFRASTRUCTURE PROJECTS cont…
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
National English Literary Museum | 50 041 000 | 22 424 767 | Practical competition. (competition certificate will be handed over upon payment of outstanding invoices)
Construction of the NELM building | 50 041 000 | 22 424 767 | 
Nelson Mandela Museum | 6 750 000 | 232 174 | Practical competition. (competition certificate will be handed over upon payment of outstanding invoices)
Upgrading of Bhunga | 500 000 | 232 174 | 

## Slide 16
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Facilities management and maintenance of the buildings | 1 750 000 | 0 | Design
Iziko Museums of South Africa | 75 288 000 | 19 630 328 | 
Installation of the integrated system | 288 000 | 0 | Construction stage
Construction of a storage structure in the court yard | 75 000 000 | 19 630 328 | Construction stage
2016/16 INFRASTRUCTURE PROJECTS cont…

## Slide 17
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Robben Island Museum | 15 429 000 | - | -
Desalination Plant Maintenance/Sewer Reticulation & Upgrades | 1 344 000 | 0 | Design stage
Restoration of the Blue stone Quarry and Walkways | 8 520 199 | 0 | Design stage
Harbour Precinct Project | 5 564 994 | 0 | Design stage
2016/17 INFRASTRUCTURE PROJECTS cont…

## Slide 18
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
South African Library for the Blind | 1 036 000 | - | -
Upgrading and Refurbishment of the Josie Wood Building and the Hemming Street House(Site clearance) | 1 036 000 | 0 | Design stage
National Library (Pretoria Campus) | 16 864 000 | - | -
Facilities Management Contract | 16 864 000 | 0 | Design stage
Total | 173 036 000 | - | -
2016/17 INFRASTRUCTURE PROJECTS cont…

## Slide 19
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
National Archives | 93 972 000 |  | 
National Archive (Pretoria) OLD Building remedial work | 48 933 782 | 17 178 253 | construction stage
National Archive (Pretoria) Upgrading of fire protection system | 45 038 064 |  | construction stage
Archie Gumede | 2 883 000 |  | Procurement
Delvillewood | 10 000 000 |  | Construction stage
2016/17 INFRASTRUCTURE PROJECTS cont…

## Slide 20
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
Gumtree Mill | 180 000 | 0 | Planning
Ingquza Hill Museum | 7 000 000 | 0 | Phase 1 practical completion
Enyokeni Cultural Precinct | 29 150 000 | 0 | Planning
OR Tambo Memorial | 3 000 000 | 0 | planning stage
Raymond Mhlaba Statue | 2 000 000 | 0 | Procurement
Sarah Baartman Centre | 48 500 000 | 9 986 844 | construction stage
Vlakplaas | 2 000 000 | 0 | Planning
2016/17 INFRASTRUCTURE PROJECTS cont…

## Slide 21
PROJECT | BUDGET | EXPENDITURE TO DATE | STATUS
JL Dube House | 6 014 000 | 0 | Construction stage
Liberation Heritage Route | 29 150 000 | 0 | Planning
Voortrekker Monument | 1 500 000 | 0 | Infrastructure maintenance
National Heritage Monument | 5 000 000 | 0 | Under implementation
Isandlwana | 6 000 000 | 0 | Planning stage
Information Management System for Infrastructure (IMSI) | 2 700 000 | 0 | Planning stage
Khoe & San Heritage Sites | 3 500 000 | 0 | Planning stage
Total for Institutional Governance | 252 549 000 | - | -
2016/17 INFRASTRUCTURE PROJECTS cont…
*IMSI is not an infrastructure project but a project management software / IT tool

## Slide 22: CHALLENGES AND INTERVENTIONS

## Slide 23: INFRASTRUCTURE IMPROVEMENT PLAN
Challenge | Intervention | Progress to date | Timeframe
Infrastructure projects were managed all over the department. Roles and Responsibilities amongst the Programmes were not clarified. | Centralisation of the management of infrastructure projects | Structure to Centralise the Infrastructure Portfolio is being developed but not yet finalised and implemented. The draft Terms of Reference have been developed | 
2 officials were managing infrastructure and office accommodation projects worth more than R500m and R100m respectively. Poor project management. Limited monitoring & verification of work done. | Increase technical capacity | 3 Construction Project Managers and 1 Property Manager were appointed. | 31 July 2016

## Slide 24: INFRASTRUCTURE IMPROVEMENT PLAN cont…
Challenge | Intervention | Progress to date | Timeframe
Escalated estimates and increased scope of work by Implementing Agents, e.g DPW Lack of determination re value for money. | Establishment of the OMNIBUS for the Professional Service Providers, i.e Architects, Engineers, Quantity Surveyors . | Terms of Reference were approved by Bid Adjudication Committee. The Advert is ready and will be placed out by 30 September 2016. | 31 March 2016
Delays due to unclear processes, e.g funding criteria, definition of the infrastructure projects, requirements for funding etc. | Development of the infrastructure policy. | Infrastructure policy was approved . (Terms of Reference are attached) | 30 June 2016

## Slide 25: INFRASTRUCTURE IMPROVEMENT PLAN cont…
Challenge | Intervention | Progress to date | Timeframe
The draw down schedule and necessary documentation required before the transfers are processed as stipulated by DAC policy were not submitted in the 1st quarter. | Work shops were conducted on required documentation and templates were developed . | The following institutions with outstanding documentation were visited: Artscape, War Museum, Robben Island Museum and PACOFS. All the transfers which were due in the 1st quarter will be completed before end of the 2nd quarter. | 30 September 2016
Approved infrastructure plan for MTEF period to avoid delays on implementation, under spending and ad hoc funding. | Development of the User Immovable Asset Management Plan (UAMP). | 2016 MTEF UAMP was approved and allocation letters approving funding for 3 years were forwarded to the institutions. | 31 January 2016

## Slide 26: INFRASTRUCTURE IMPROVEMENT PLAN cont…
Challenge | Intervention | Progress to date | Timeframe
Lack of functional structure in the DAC to oversee the implementation of infrastructure programme. | Establishment of the Infrastructure Committee with members at executive level. | Terms of Reference were developed and approved by Infrastructure Committee. | July 2016
Lack of Integrated Technology System to manage and monitor the budget amongst the Programmes and Finance Directorate. | Development of the Information Management System ( in the interim the unit will be able to use the MS Project to monitor projects) | Specifications for phase 1 which will concentrate on alignment and sharing of information amongst Programmes and Finance This will include generating reports and attaching supporting documentation electronically. | 31 March 2016

## Slide 27: INFRASTRUCTURE IMPROVEMENT PLAN cont…
Challenge | Intervention | Progress to date | Timeframe
DAC couldn’t transfer funds committed for IDT projects pending the competition of the financial reconciliation which was received on 22 July 2016. | Appointment of Rubiquant Quantity Surveyors to assess the IDT expenditure incurred on all DAC legacy projects. | Rubiquant has submitted a preliminary report indicating possible overcharging on professional fees and materials. ADG has engaged IDT CEO on the preliminary report, requesting access to project sites and documents by Rubiquant to finalise the investigation. The lawyers of the two entities have met to finalise legal matters pertaining to court cases against IDT for non-payment of fees | End October

## Slide 28: CONCLUSION
Under expenditure will be reduced by end of the third quarter.
The Department has identified projects which will not spend as envisaged and shifted funds to projects which require additional funding. These virements will be approved by National Treasury on completion of the adjustment period in October 2016.
Infrastructure projects oversight has been strengthened with new capacity brought on board..

## Slide 29: ENKOSI