## Slide 1
7 September 2016
The Compensation Commissioner for Occupational Diseases (CCOD)
Presentation to
Portfolio Committee on Health
Progress in addressing challenges at the CCOD – Financial Statements

## Slide 2: Overview
Initial Status
Challenges and improvements
Timetable for submission of Financial reports
Unaudited Financial Statements

## Slide 3: Overview
Initial Status
Challenges and improvements
Timetable for submission of Financial reports
Unaudited Financial Statements

## Slide 4: Financial Statements – Initial Status
Financial Statements outstanding since 2010/11 FY
2010/11FY Submitted to AGSA and disclaimed. Not submitted to parliament
Processing in the Accounting system limited to 2011/12 FY
Accounts prepared manually in Excel after 2011/12 FY on a cash basis
No balance sheet reconciliations
Financial Statements not reconciled to Trial Balance (2009/10 FY)
No defined list of controlled mines (Revenue)

## Slide 5
Manual interest calculations (Debtors)
Payment rejections without detail (Creditors)
Manual payment records
No reporting functionality in the Administration system
No support for the Mineworkers compensation system (2004)
No data management
No document management
No reconciliation of payments between administration and accounting system
Manual calculation of claims benefits
Financial Statements – Initial Status

## Slide 6
Manual calculation of interest on claims
Manual payment procedures for settlement of claims
Upgrades to hardware/software required for accounting system
No process flow documentation available
Financial Statements – Initial Status

## Slide 7: Overview
Initial Status
Challenges and improvements
Timetable for submission of Financial reports
Unaudited Financial Statements

## Slide 8: Financial statement Challenges
Complexity of Actuarial valuation
  Unique methodology
  Complex data requirements
  Multiple claims data sources (MCS, TEBA, Ku-Riha, Agendas, Payments)
Lack of detail on rejected payments to claimants
Delays in procurement of new software
Limitations with the previous Accounting Software
  Multi-year processing not possible
  Processing/calculations manual in nature
Availability of Government Gazettes (Controlled Mines)

## Slide 9
Financial statement Improvements
  Actuarial valuators appointed in Quarter 3 of 2015/16 FY
  Data for Actuarial valuation - Integrity checks and data clean-up completed in July 2016
  Actuarial report - Due September 2016
  Revenue
  Register of controlled mines and works approved by Risk committee
  Risk assessment matrix created and analytics performed
  Inspection of mines leading to submission of outstanding assessments
Expenditure
  Reconciliation of payments between cashbooks and administration system
  Review of accounts payable detail to allocate payments and rejections

## Slide 10: Financial Statements Improvements
Accounting system
  Pastel Evolution implemented
  2011/2012 FY transactions loaded into Pastel Evolution
  Cashbook entries loaded for review
  Risk shifts loaded from template for review
  Live processing in progress for revenue
Business processes mapped

## Slide 11: Financial Statements Improvements
Tools provided
  Interest calculation model – Levy revenue and claims payables
  Benefit calculator
  Internet Banking to facilitate payments
  Risk Shift upload tool for revenue processing
  Risk assessment matrix for analytics

## Slide 12: Financial Statements Improvements
Audit preparation
  Audit team appointed by Auditor General of South Africa in March 2016
  Regular meetings with Finance team and Audit team
  Regular meetings with Finance team and Actuarial Valuation team
  Audit Strategy to be approved at Audit and risk committee meeting on 15 September 2016
  Audit for 2011/12 FY in progress

## Slide 13: Overview
Initial Status
Challenges and improvements
Timetable for submission of Financial reports
Unaudited Financial Statements

## Slide 14: Financial Statement - Timelines
Year | Action | Status / Start Date | Target Date
2010-11 | Actuarial Valuation | In progress | 15 September 2016 – Draft Report on liabilities
 | AFS update | In progress | 1 week after Actuarial Valuation / Confirmation of Certified Claims
 | Audit | In progress | Update will be provided during assignment - KPMG
 | Calculation / Confirmation of movement in claims / payments | 1 August 2016 | 15 September 2016
 | Submit Financial Statements / Approval of AFS by ARC |  | 30 September 2016
2011-12 | Actuarial Valuation | In progress | 15 September 2016 – Draft report on liabilities
 | AFS update | In progress | 2 weeks after Actuarial Valuation / Confirmation of Certified Claims
 | Calculation / Confirmation of movement in claims / payments | 1 August 2016 | 15 September 2016
 | Submit Financial Statements / Approval of AFS by ARC |  | 30 September 2016

## Slide 15
Year | Action | Status / Start Date | Target Date
2012-13 | Actuarial Valuation | In progress | 15 September 2016 – Draft report on liabilities
 | Bulk loading of transactions | Complete | 31 July 2016
 | Review / Audit preparation | 1 August 2016 | 31 October 2016
 | AFS preparation | 1 November 2016 | 14 November 2016
 | Audit | 1 November 2016 | Update will be provided during assignment
 | Calculation / Confirmation of movement in claims / payments | 15 September 2016 | 30 September 2016
 | Submit Financial Statements / Approval of AFS by ARC |  | 31 December 2016
2013-14 | Actuarial Valuation | In progress | 15 September 2016 – Draft report on liabilities
 | Bulk loading of transactions | 1 August 2016 | 31 October 2016
 | Review / Audit preparation | 1 November 2016 | 31 December 2016
 | AFS preparation | 1 January 2017 | 14 January 2017
 | Audit | 1 January 2017 | Update will be provided during assignment
 | Calculation / Confirmation of movement in claims / payments | 15 September 2016 | 30 September 2016
 | Submit Financial Statements / Approval of AFS by ARC |  | 28 February 2017
Financial Statement - Timelines

## Slide 16
Year | Action | Status / Start Date | Target Date
2014-15 | Actuarial Valuation | In progress | 15 September 2016 – Draft report on liabilities
 | Bulk loading of transactions | 1 November 2016 | 31 December 2016
 | Review / Audit preparation | 14 January 2017 | 14 March 2017
 | AFS preparation | 15 March 2017 | 31 March 2017
 | Audit | 14 March 2017 | Update will be provided during assignment
 | Calculation / Confirmation of movement in claims / payments | 15 September 2016 | 30 September 2016
 | Submit Financial Statements / Approval of AFS by ARC |  | 31 May 2017
2015-16 | Actuarial Valuation | In progress | 15 September 2016 – Draft report on liabilities
 | Bulk loading of transactions | 15 Jan 2017 | 15 Mar 2017
 | Review / Audit preparation | 15 Mar 2017 | 15 May 2017
 | AFS preparation | 15 May 2017 | 31 May 2017
 | Audit | 15 May 2017 | Update will be provided during assignment
 | Calculation / Confirmation of movement in claims / payments | 15 September 2016 | 30 September 2016
 | Submit Financial Statements / Approval of AFS by ARC |  | 31 July 2017
Financial Statement - Timelines

## Slide 17: Financial Statement Timelines
Year | Action | Status / Start Date | Target Date
2016-17 | Actuarial Valuation | In progress | 15 September 2016 – Draft report on liabilities
 | Bulk loading of transactions | 15 Mar 2017 | 15 April 2017
 | Review / Audit preparation | 15 April 2017 | 15 June 2017
 | AFS preparation | 15 June 2017 | 30 June 2017
 | Audit | 15 July 2017 | Update will be provided during assignment
 | Calculation / Confirmation of movement in claims / payments | 15 June 2017 | 30 June 2017
 | Submit Financial Statements / Approval of AFS by ARC |  | 31 August 2017

## Slide 18: Financial Statements - Status

## Slide 19: Overview
Initial Status
Challenges and improvements
Timetable for submission of Financial reports
Unaudited Financial Statements

## Slide 20
UNAUDITED FINANCIAL STATEMENTS OF THE COMPENSATION FUND

## Slide 21: Revenue
Statement of financial performance | Unaudited amount (’000) |  |  | Target (‘000) | Actual (‘000) | % Deviation from target
 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2015/16 | 2015/16
Levy income | 286 316 | 269 202 | 260 939 | 296 795 | 310 208 | 4,52%
Interest received | 114 230 | 130 851 | 172 104 | 201 170 | 210 854 | 4,81%
Transfers received | 2 916 | 3 062 | 3 215 | 3 363 | 3 363 | 0
Total revenue | 403 462 | 403 115 | 436 258 | 501 328 | 524 425 | 4,61%

## Slide 22: Expenditure
Statement of financial performance | Unaudited amount (’000) |  |  | Target (‘000) | Actual (‘000) | % Deviation from target
 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2015/16 | 2015/16
Administration costs | 7 839 | 7 724 | 7 411 | 7 839 | 7 571 | -3,42%
Claims payments including pensioners | 108 966 | 136 862 | 158 508 | 164 066 | 63 392 | -61,36%
Total expenditure | 116 805 | 144 586 | 165 919 | 171 905 | 70 963 | -58,72%

## Slide 23: Assets
Statement of financial performance | Unaudited amount (’000) |  |  | Target (‘000) | Actual (‘000) | % Deviation from target
 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2015/16 | 2015/16
Investments | 2 229 267 | 2 606 886 | 2 963 136 | 3 163 067 | 3 349 193 | 5,88%
Accounts receivable | 3 017 | 29 578 | 40 488 | 27 338 | 18 508 | -32,30%
Cash and cash equivalents | 169 797 | 74 618 | 58 995 | 60 000 | 122 351 | 103,92%
Total assets | 2 402 081 | 2 711 082 | 3 062 619 | 3 250 405 | 3 490 052 | 7,37%

## Slide 24: Liabilities
Statement of financial performance | Unaudited amount (’000) |  |  | Target (‘000) | Actual (‘000) | % Deviation from target
 | 2012/13 | 2013/4 | 2014/15 | 2015/16 | 2015/16 | 2015/16
Surplus/(deficit) | 842 673 | 1 353 934 | 1 891 950 | 2 176 824 | 2 121 962 | -2,52%
Provisions | 1 554 807 | 1 311 395 | 1 143 645 | 1 054 021 | 1 349 455 | 28,03%
Accounts payable and other payables | 4 601 | 45 753 | 27 024 | 19 560 | 18 635 | -4,73%
Total | 2 402 081 | 2 711 082 | 3 062 619 | 3 250 405 | 3 490 052 | 7,37%

## Slide 25
Thank You
kistnb@health.gov.za