## Slide 1: STATUS OF HOUSING DELIVERY
MILITARY VETERANS HOUSING ASSISTANCE
NOVEMBER 2016

## Slide 2: RELATIONSHIP BETWEEN THE DMV & THE DHS
Memorandum of Understanding
Concluded 7 Feb 2012 by the Deputy Ministers of the DMV & DHS
To assists Milvets with housing related difficulties based on the merit of each case
Service Level Agreement
Signed with all the HOD’s of Provincial Department of Human Settlement.
Gives effect to the MoU
To provide Housing sector skills training to Milvets
To provide housing to Milvets based on agreed specifications
To upgrade/repair dilapidated properties of Milvets
DMV qualifying criteria and selection process applies.
PDHS built houses to the specification and bill the DMV an amount equivalent to the Top-Up
DMV provide a list of eligible beneficiaries
Build houses are handed to the beneficiaries by the DMV
Monitoring of implementation of MoU and the SLA involves oversight by the Portfolio

## Slide 3: GOVERNANCE STRUCTURE
Political Steering Committee
Chairpersons: Deputy Ministers of the Department of Human Settlements and Department of Military Veterans
Accounting Officers Forum
Chairpersons: Directors General of the Department of Human Settlements and Department of Military Veterans
Operational Task Team
Chairpersons: Relevant DDG’s from Department of Human Settlements and Department of Military Veterans
Composition: Deputy Ministers of the DMV and the DHS
Frequency of meetings: Once per quarter
Roles and responsibilities: To provide political direction on the roll-out of the Military Veterans Housing Assistance Initiative
Roles and responsibilities: Serve as a decision making body and provide strategic. Guide and co-ordinate the roll-out of the Programme.
Frequency of meetings: Once per quarter
Frequency of meetings: Bi-monthly
Composition: Two Directors General, Provincial HOD of Human Settlement, DMV & DHS DDG’s responsible for the program and Secretariats
Roles and responsibilities: Effective implementation of the program
Composition: Officials responsible for the Programme from DMV and DHS, Provincial Project Managers and Coordinators, Stakeholder Management DHS/DMV, Beneficiary administration DHS/DMV, Capacity building & Skills Development (DMV), Secretariat
Request the Portfolio Committee to exercise oversight

## Slide 4: PROJECT PERFORMANCE TO DATE
Total transfers to date R51,760,000.00
Houses built 132.
Remaining Balance R33,034,000.00
Provinces without a single delivery:
Limp, KZN, WC
The DMV’s annual housing target as per the Annual Performance Plan (APP) is the provision of 1000 houses.
NDHS has committed to assist the DMV with tracking utilization of funds that were transferred to the Provincial DHS.
PROVINCE | 2013/2014 |  | 2014/2015 |  | 2015/16 |  | 2016/17 | 
 | Top-Up @ R72,000 per unit | TARGETS/ (DELIVERED) | Top-up @ R64,053 per unit | TARGETS/ (DELIVERED) | Top-up @ R78,000 per unit | TARGETS/ (DELIVERED) | Top-up @ R78,000 per unit | TARGETS/ (DELIVERED)
EASTERN CAPE | R0 | 0 (0) | R3,010,000 | 46(0) | R0 | 104 (52) | R5,304,000 | 200 (1)
FREE STATE | R7,200,000 | 100 (0) | R7,686,000 | 120(0) | R0 | 220 (30) | R0 | 137 (0)
GAUTENG | R0 | 0(0) | R0 | 0(0) | R0 | 363 (7) | R0 | 833 (14)
KWAZULU NATAL | R3,600,000 | 50(0) | R7,686,000 | 120(0) | R0 | 280 (0) | R0 | 250 (0)
LIMPOPO | R0 | 0(0) | R0 | 0(0) | R0 | 175 (0) | R0 | 200 (0)
MPUMALANGA | R0 | 50(0) | R13,528,000 | 155(0) | R0 | 126 (34) | R0 | 150 (0)
NORTH WEST | R3,746,000 | 52(2) | R0 | 0(0) | R0 | 163 (7) | R0 | 142 (0)
NORTHERN CAPE | R0 | 0(0) | R0 | 0(0) | R0 | 105 (0) | R0 | 50 (0)
WESTERN CAPE | R0 | 0(0) | R0 | 0(0) | R0 | 120 (0) | R0 | 150 (0)
TOTAL | R14,546,000 | 205 (2) | R31,910,000 | 441 (0) | R0 | 1,656 (130) | R5,304,000 | 2,112 (15)
Portfolio Committee to exercise oversight over the project performance on the three spheres of Government.

## Slide 5: REASONS FOR PROJECT UNDERPERFORMANCE
High rejection rate of potential housing beneficiaries
  In Chatty 491 (Nelson Mandela Bay Municipality) , 224 Milvets applied, only 71 (32%) were approved on the NDHS’s(National Department of Human Settlement) HSS (Housing Subsidy System).
  In KZN, 739 Milvets applied, only 215 (29%) were approved on the NDHS’s HSS.
  Reasons for rejections includes:
    Combined household income exceed the prescribed threshold.
    Previous property owner
  Cause:
    DHS erroneously subject Milvets to an HSS qualifying criteria (Low cost housing qualifying criteria).
    The Portfolio Committee to assist with the monitoring and implementation of the proposed solution.
  Proposed Solution:
    DHS was requested to reconfigure HSS to align it to the DMV qualifying criteria as per the regulations.
  Why hasn’t these proposal implemented?
    DHS prefers that for each case rejected DMV must write a letter to DHS to request a system over-ride.
    This is both impractical and incorrect as it presupposes that the rejected Milvets do not meet the qualifying criteria and a special consideration is proposed for them.
  How wide spread is the rejection:
    All provincial DHS offices complains about the high rejection rate.

## Slide 6: REASONS FOR PROJECT UNDERPERFORMANCE
Lack of project prioritization at construction level
  In Nellmapius (City of Tshwane), 1800 low costs houses are built, DMV’s houses constitute 5% (98) of these houses. Of this houses, 14 houses have been allocated to Milvets, 84 are expected to be built by end March 2017.
  Cause:
    DHS project managers prefers to focus on the bigger project rather than waste time on the smallest “unit of the projects”.
    That is, project managers would rather succeed on the 95% of the project than on the 5%
Random housing projects not informed by demand
  In Lukhanji (Chris Hani Municipality), 200 housing project was approved, but there are fewer than 200 NSF Milvets within the vicinity of Lukhanji.
  Cause:
    Limited DMV influence in project identification and prioritization
    Inability DHS to initiate small scale projects that would targets Milvets who own sites or prefers to have their houses built in the rural areas.

## Slide 7: REASONS FOR PROJECT UNDERPERFORMANCE
Non-adherence to the approved floor plan
  In Mpumalanga, poor quality material is utilized to build for military veterans.
  Some of the specifications are ignored, such as: in-house toilets, fencing around the yard
  Floor plan changed without consultation with the DMV and the NDHS.
  Deviation from the norms and standards agreed to by the DMV and the DHS.
  Cause:
    PDHS (Provincial Department of Human Settlement) account to NDHS, however the NDHS does not seem to have influence on provinces
Lack of Capacity within the DMV
  Only one permanent official is tasked with overseeing housing delivery within the DMV. (2 other junior officials are interns)
  The tasked official does not have any Building Sector related experience
  In comparison, the NDHS has one director for every three province.
  Cause:
    Poor organizational planning
  Planned Solution
    A Chief Director post has been advertised and expected to be filled during the current financial period.
    A Director post has been advertised and is in the process of being filled.
    Strengthening monitoring and evaluation together with the DHS.

## Slide 8: HOUSING PROJECTS EXPECTED TO BE ALLOCATED IN THE NEAR FUTURE
HOUSING LOCATION | NO. OF UNITS BEING BUILT | EXPECTED ALLOCATION DATE | EXPECTED INVOICE FROM DHS | STATUS
Evaton, Gauteng | 5 Units | December 2016 | R 440 000,00 | 5 Houses were previously built as low cost housing and are currently being modified for occupation by the Milvets.
Lufhereng, Gauteng | 30 Units | February 2016 | R 2,640 000,00 | 30 Houses are various stages of constructions.
Nellmapius, Gauteng | 14 Units | 13 October 2016 | R 1,936 000,00 | 14 Houses have been built and beneficiaries allocated. However all the beneficiaries have not taken occupation due to the fact that water and electricity had not been installed at the time of allocation At completion, the project is aimed at yielding 98 houses.
Golden Gardens, Gauteng | 20 Units | January 2016 | R 1 760 000,00 | 20 houses have been built and are estimated to be at 80% completion.
Chatty 491, Eastern Cape | 30 Units | December 2016 | R 0,00 (A top-up transfer of R5,304,000 was made in April 2016 for these houses) | 26 Houses are at completion level and are expected to be handed-over to the beneficiaries in December 2016.
Kimberley, Northern Cape | 30 Units | December 2016 | R 1 672 000,00 | 30 house are at completion level and will be handed over to the beneficiaries before year end. The project was delayed by the lack of electricity and bulk water
Grand Total | 129 Units |  | R 8 448 000,00 | 
Request for oversight visit by the Portfolio Committee

## Slide 9: STRATEGIC INTERVENTIONS
Provision of emergency housing assistance
  NDHS and the DMV agreed to allocate low cost (RDP’s) to Milvets who are destitute in areas where there are low costs houses without DMV projects.
Improvement in funds Transfers to the Provinces
  Funding model has been developed with guidance from the National Treasury.
Provision of assistance to Milvets who wish to purchase their own houses
  DMV encourages and provides financial assistance to Milvets who wish to purchase properties that are being sold privately for the value that is equivalent to the housing benefits as guided by the policy.
Critical repairs
  Provision of critical repairs to dilapidated properties that are owned by Milvets provided that the concerned Milvets have not received subsidy from the state before.
Building Assistance to Milvets with sites
  Prioritization of building assistance to Milvets who own serviced sites