## Slide 1
MILITARY VETERANS STATUS / PROGRESS REPORT
BRIEFING TO PARLIAMENT PORTFOLIO COMMITTEE
09 NOVEMBER 2016

## Slide 2: TABLE OF CONTENTS
2
Purpose
BACKGROUND
ACHIEVEMENTS TO DATE
ACTIVE PROJECTS & STATUS
PIPELINE PROJECTS
CHALLENGES & INTERVENTIONS
SUMMARY

## Slide 3
3
PURPOSE

## Slide 4: PURPOSE
4
The purpose of this presentation is to present the Eastern Cape status, progress and challenges the Department is encountering in delivering housing benefits to Military Veterans

## Slide 5
5
BACKGROUND

## Slide 6: Background
6
Military Veterans Act , Housing Act amongst others guide roll-out of the programme in the Province.
Programme implemented in line and in compliance to the DMV database
Dedicated Directorate established to oversee implementation of the Military Veterans assistance programme.
Current number of veterans in the Province stands at 631.
Implementation approach: new projects, extend scope of running projects or individual subsidy route

## Slide 7
7
KEY ACHIEVEMENTS TO DATE

## Slide 8: Key Achievements to date
8
43 military veterans housed at Wells Estate through a project-linked subsidy.
9 military veterans took occupation of their homes in Mayfield, Makana.
Individual beneficiaries assisted with housing using the individual subsidy route, such as Mgabela family in Tsholomnqa, Twebe family in Dimbaza, Hina family in New Brighton, Qalani family in Zwide, Merile family in KwaZakhele, Jack family in Uitenhage.
Sound relations with key stakeholders, in particular the Provincial Military Veterans Steering Committee.

## Slide 9
9
ACTIVE PROJECTS & STATUS

## Slide 10: Active projects and status
10
Municipality | Project Name | Beneficiaries Approved | Contractor Appointed (yes/no) | Units Completed
Chris Hani | Lukhanji (200) | 67 | Yes | 66
O.R. Tambo | O.R Tambo (57) | 53 | Yes | - (various stages: 8 @ roof level, 24 @ wall plate, 28 @ slab)
Nelson Mandela Metro | Chatty 491 | 70 | Yes (Military Veterans Cooperative) | 1 (various stages: 14 @ roof level, 15 @ wall plate, 39 @ slab)

## Slide 11
11
PIPELINE PROJECTS

## Slide 12: Pipeline projects
12
Municipality | Project Name | Beneficiaries Approved | Contractor Appointed | Units Completed
Buffalo City Metro | BCMM 42 | 27 | Yes | -
Buffalo City Metro | BCMM 179 | - | No | -

## Slide 13
13
CHALLENGES & INTERVENTIONS

## Slide 14: Challenges & interventions
14
CHALLENGES | INTERVENTIONS
Department of Military Veterans database is not updated regularly, is not consistent and excludes other Military Veterans. | The Province is continuously engaging with the Department of Military Veterans as the custodians of the database so that they update the database and ensure that it is all -inclusive and consistent. Working with the National Department of Human Settlements, Department of Military Veterans and the local Chapter of SANMVA, the Province is continuously implementing a drive in the areas where the projects are located to resolve problems related to the military veteran beneficiaries

## Slide 15: Challenges & interventions (cont…)
15
CHALLENGES | INTERVENTIONS
Military Veterans who earn above the threshold are rejected on HSS | This is a policy bottleneck, and in this regard the Province is engaging with the Department of Military Veterans and National Department of Human Settlements to find solutions in this regard.
Military Veterans who previously benefitted are rejected on HSS | This is a policy bottleneck, and in this regard the Province is engaging with the Department of Military Veterans and National Department of Human Settlements to find solutions in this regard.
Dependents of deceased Military Veterans are not considered at present | Department of Military Veterans has undertaken to review the Policy to include dependents of military veterans.

## Slide 16
16
SUMMARY

## Slide 17: Summary
17
Despite all the challenges, Province is committed to the roll-out of the military veterans assistance programme in the Province.
Resolution of the policy bottlenecks is key in realizing the above commitment