## Slide 1: Report to portfolio committee
Second Quarter Report 2016/17

## Slide 2
Performance Indicator/ Measure | Annual Targets for 2016/17 | Milestones | Actual Achievement | Reasons for variance | Corrective action | Progress to date
Number of designation requests submitted to Minister per year | Four designation requests submitted to Minister per year | Q2: Two designation requests submitted to Minister | Nil designation requests submitted to Minister | There were delays in obtaining data on historic expenditure and procurement plans from procuring entities resulting in target not being achieved. Note: The following designations were finalised from the previous financial year: Wheelie Bins. Water meters were not accepted previously as 2015/16 achievements should be acknowledged. | To be finalized in Q3. | One designation proposal was submitted to Minister in Q3; Steel Products and Components for Construction. the dti still busy with consolidation of designation proposals as well as stakeholder engagements, the work will be completed in Q4. Note: Fire Trucks Instruction Note is published by National Treasury.
Strategic Goal 1

## Slide 3
Performance Indicator/ Measure | Annual Targets for 2016/17 | Milestones | Actual Achievement | Reasons for variance | Corrective action | Progress to date
Value (Rand) of Innovative venture supported from approved enterprises | R50m | 8m | 0 (Cumulatively above target R20.76 m against R18m) | No applications processed to support innovative ventures due to delay in the due diligence process | Proactive targeted workshops to be held with stakeholders and appoint due diligence experts | (Cumulatively above target R20.76 m against R18m to date) The process of appointing due diligence experts is being finalized by the Bid Adjudication Committee
Strategic Goal 1

## Slide 4
Performance Indicator/ Measure | Annual Targets for 2016/17 | Milestones | Actual Achievement | Reasons for variance | Corrective action | Progress to date
Progress reports on five priority development areas in SACU, SADC FTA, | Progress reports produced on implementation of agreed work programme and projects for priority development areas in SACU, SADC FTA. | Progress report produced on implementation of agreed work programme on development areas in SACU, SADC FTA | SACU There was no progress on the agreed work programme SADC FTA Progress report on the implementation of the SADC Trade Protocol developed | SACU Ministers have to approve the Report of the Retreat that was held in June 2016 as a basis for further engagement | Confirmation of suitable dates for a Council meeting is crucial to this process | Progress to be provided at the end of quarter 3.
Strategic Goal 2

## Slide 5
Performance Indicator/ Measure | Annual Targets for 2016/17 | Milestones | Actual Achievement | Reasons for variance | Corrective action | Progress to date
Number of Socio-Economic Impact Assessment System (SEIAS) reports (previously RIA reports) developed for Minister’s approval | Two SEIAS reports on Companies and Copyright/Performers Protection Amendment Acts developed for Minister’s approval | Q2: First draft SEIAS reports on Companies, and Copyright/Performers Protection Amendment Acts developed | 1st draft SEIAS Report which is preliminary work (research and consultations) on the amendments to the Companies Amendment Act were done while waiting for the Bill to be revised. Copyright/ Performers Protection achieved in the 1st quarter due to the Cabinet programme. | Amendments to the Bill not yet effected, therefore 1st draft SEIAS Report cannot be completed | As soon as the Amendments to the Bill have been effected the SEIAS report will be completed. | Progress to be provided at the end of quarter 3.
Strategic Goal 4

## Slide 6
Performance Indicator/ Measure | Annual Targets for 2016/17 | Milestones | Actual Achievement | Reasons for variance | Corrective action | Progress to date
Number of Evaluation reports developed for Ministers approval | Two evaluation reports on Consumer Protection Act (Exemptions and Industry Codes) and Companies Act (Cost of doing business) developed for Minister’s approval | First draft evaluation reports on Consumer Protection Act (Exemptions and Industry Codes) and Companies Act (Cost of doing business) developed | First draft evaluation reports on Consumer Protection Act (Exemptions and Industry Codes) and Companies Act (Cost of doing business) were not developed | The evaluation on the Consumer Protection Act scope had to be amended due to legislative provisions. The project on the evaluation of the Companies Act was presented to BAC on 12 August 2016 but it was not approved. | The CPA project Terms of Reference have been revised and the necessary approvals are being requested due to the change in scope for the project. The Companies Act evaluation project concerns raised by the BAC have been addressed and documents have been submitted to the BAC for their consideration again. | Progress to be provided at the end of quarter 3.
Strategic Goal 4

## Slide 7
Performance Indicator/ Measure | Annual Targets for 2016/17 | Milestones | Actual Achievement | Reasons for variance | Corrective action | Progress to date
Number of Bills developed for Minister's approval | Two Bills on Companies Amendment and Copyright/Performers Protection Act developed for Minister’s approval | Two (1st drafts) Bills on Companies Amendment and Copyright/Performers Protection Act) developed for approval | Revised the Memorandum on the Objects of the Copyright and Performers Protection Bill Commenced with the drafting of the Companies Amendment Bill | Companies Amendment Act could not be reviewed as the Liquor and Gambling Bills were prioritised. | Finalising a policy directive for the Amendment of the Companies Act and will communicate same with Legislative Drafting once ready | Progress to be provided at the end of quarter 3.
Number of regulations developed for Minister’s approval and published | Four regulations on Liquor, Companies, Gambling and Copyright developed for Minister’s approval and published | Four (First draft) regulations on Liquor, Gambling, Copyright and Companies developed | Four (First draft) regulations on Liquor, Gambling, Copyright and Companies were not developed | Regulations were not developed because the Bills have not yet been approved by Cabinet. | A request to postpone to the next financial year has been submitted to the DGs office. | Progress to be provided at the end of quarter 3.
Strategic Goal 4

## Slide 8
Performance Indicator/ Measure | Annual Targets for 2016/17 | Milestones | Actual Achievement | Reasons for variance | Corrective action | Progress to date
Number of multi-media awareness campaigns on key sectors of IPAP and the dti strategic projects | 22 | 6 | 3 | Challenges with media buying process | Approval granted to carry media buying via GCIS | Memorandum of Understanding (MOU) to procure through GCIS approved. GCIS has started the procurement process.
Strategic Goal 5

## Slide 9
THANK YOU