## Slide 1: Presentation to the PCD&MV – Dashboard on BRRR Department of Military Veterans
Name: Max Ozinsky
Designation: Acting Director General
Date: 08 March 2017

## Slide 2: PRESENTATION LAYOUT
The aim of the presentation
Progress Report on Dashboard Issues (BRRR Recommendations)

## Slide 3: The Aim of the Report
To brief the Portfolio Committee on Defence and Military Veterans (PCD&MV) on the issues identified in the Dashboard

## Slide 4: Progress Report on Dashboard Issues
Serial no. | Issues raised in the Dashboard as at 23.11.2016 | Progress report to date
1 | The Department was told to ensure that its reports on SLA’s and MOU’s need to be as complete as possible, thus listing both the in-year numbers as well as the cumulative number of the SLA’s and MOU’s, when it reports to the Committee. | The SES Branch has concluded Memorandum of Understanding with the following Departments and Entities: Department of Defence, Department of Social development, Department of Housing, Department of Basic Education Department of Human Settlement, and National Student Financial Aid Scheme (NSFAS)
2 | The Department should submit a report on progress regarding the MPAT at the next meeting, preferably when it reports on the performance of the Second Quarter for FY 2016/17. | The respond was disseminated and responded to the Committee on the 22.02. 2017

## Slide 5: Progress Report on Dashboard Issues
Serial no. | Issues raised in the Dashboard as at 23.11.2016 | Progress report to date
3 | A Skills Audit is essential to properly plan training and the Department was requested to present a report on this at the next meeting, especially as the vacancies and skills gaps in the service delivery programmes are detracting it from functioning optimally. | The DMV has briefed the committee on this matter on the 22.02. 2017
4 | The Committee recommended that the Consequence Management regime of the DMV be strengthened and that it should report at the next meeting on the cases and steps taken against persons who were found to be responsible for instances of Irregular and wasteful expenditure and other serious transgressions | The DMV has briefed the committee on this matter on the 22.02. 2017

## Slide 6: Progress Report on Dashboard Issues
Serial no. | Issues raised in the Dashboard as at 23.11.2016 | Progress report to date
5 | The Committee wants clarity on the exact number of the people employed at the DMV and these statistics should be inclusive of contracts workers, interns etc and it should report back at the next meeting. | The DMV has briefed the committee on this matter on the 22.02. 2017
6 | The Department should at its next meeting with the Committee report on its disciplinary cases i.e. the numbers, offences, outcomes etc | The department is the process of finalizing this report and has targeted the 15 March 2017 as the completion date.
7 - 12 | These items will be presented on the 10.03.2017 as they belong to the JSCD as planned. | 
13 | The Department was requested to report back on progress to overhaul the SCM and Procurement processes in the Department in total with the assistance of National Treasury and the DPSA | There is a continuous consultation with the Office of the Chief Procurement Officer (OCPO) and other stakeholders who may contribute positively towards overhauling the DMV SCM. The Deputy Director SCM commenced work on the 01 February 2017 and has already started identifying and fixing the SCM processes. The Contract post for SCM Director has been advertised and due HR processes will commence as soon as the advert closes. All other items identified by AGSA have been added onto in the Action plan and are being addressed.

## Slide 7: Progress Report on Dashboard Issues
Serial no. | Issues raised in the Dashboard as at 23.11.2016 | Progress report to date
14 | The Committee was informed that some of the funds “parked” at NSFAS, has since been utilised for the current academic year and it was encouraged to ensure that these funds were properly accounted for and utilised. | Funds are correctly accounted for Quarterly, statements and breakdown of expenditure is provided. Funds that were not transferred to NASFAS in previous years have been used to pay for Education Support in this Academic year
15 | The Department should give feedback on efforts to improve the relationship with SITA | The DMV has briefed the committee on this matter on the 22.02. 2017
16 | The Committee recommended that the Department should prioritise the Database through enhancing its verification processes with military veteran organisations such as SANMVA and the assistance of the TSI to make progress on this issue. | This is part of the plan of work of the department in the coming months. A Standard Operating Procedure (SOP) will be finalized in this month for the database

## Slide 8: Progress Report on Dashboard Issues
Serial no. | Issues raised in the Dashboard as at 23.11.2016 | Progress report to date
17 | The Call centre challenges should be prioritised, especially since the Department has indicated that some of the functions will migrate from SITA to DMV. It should report to the Committee on this, with a view a joint meeting with both parties to assist addressing these issues. | The DMV has briefed the committee on this matter on the 22.02. 2017
18 | The Committee recommended that the DMV looks into the challenges around the pay-out of Burial support funds as a matter of urgency to ensure that the last respects are paid to military veterans in a dignified manner. | The DMV is implementing the recommendations of the Portfolio Committee in the following ways: Where paperwork is all complete and families urgently require funds, a request is made for overnight payment of funds into the account of the deceased’s family. Where the time between the finalization of paperwork and the execution of the funeral is too close to make payment on time for the funeral, contact is made with undertakers to execute the funeral whilst the final administrative processes are concluded. At present, the DMV is managing to pay out the funeral benefit within one week where all administrative matters are in order

## Slide 9: Progress Report on Dashboard Issues
Serial no. | Issues raised in the Dashboard as at 23.11.2016 | Progress report to date
19 | The Committee wants the Department to report on a quarterly basis on progress with housing and the transport benefit, in which the Department performed poorly in previous years. | The Department has in co-operation with the Department of Human Settlement, established a national task team to provide strategic direction on the housing provisioning and to enhance the monitoring and evaluation of the housing programme. The department has developed a “Housing needs database” consisting of 3,895 former NSF members who will be provided with housing opportunities. For the 2016/17FY, the lists of beneficiaries consists of 1,421 former NSF members and various housing projects are underway to build houses. In addition to providing housing opportunities to destitute military veterans, the Departments has strengthened its administrative systems to provide financial assistance towards the settlement of mortgage loans within the prescripts of the Military Veterans Benefits Regulations (MVBR) of 2014. The transport benefit is still inactive, however the DMV is facilitating the process of entering into MoU with the Department of Transport.

## Slide 10: Progress Report on Dashboard Issues
Serial no. | Issues raised in the Dashboard as at 23.11.2016 | Progress report to date
20 | The Department was urged to ensure that all systems are in place to ensure that it is able to exist independently from the Department of Defence. | Through addressing AGSA issues and continuous interaction with National Treasury, systems are being put in place and that will give assurance to the principals that DMV is ready to exist independently of Department of Defence. This is being achieved through formalization and enforcement of policies, standard operating procedures and robust governance structures.
21 | The Department was requested to report to the Committee on its new structure as soon as it has been approved by the Executive Authority. | As advised by the Committee, the department will report on this item only when structure is approved.

## Slide 11: Thank you!
End.