Department of Government Communication and Information System

Fourth Quarter Actual Performance Report

(01 January – 31 March 2017)

The pulse of communication excellence in government

TABLE OF CONTENTS

1.	INTRODUCTION	3

2.	OVERVIEW OF THE ORGANISATIONAL ENVIRONMENT	3

3.	SERVICE DELIVERY ENVIRONMENT	5

4.	2016/17 FOURTH QUARTER ACTUAL PERFORMANCE	6

5.	AUDIT  OF PERFORMANCE INFORMATION BY THE INTERNAL AUDIT	7

6.	RECONCILIATION OF QUARTERLY ACHIEVEMENTS AND EVIDENCE	9

7.	CONCLUSION	9

ANNEXURE A: 2016/17 FOURTH  QUARTER ACTUAL PERFORMANCE REPORT	10

ANNEXURE B:  2016/17 FOURTH QUARTER EXPENDITURE REPORT	35

LIST OF ACRONYMS AND ABBREVIATIONS	40

# INTRODUCTION

  - The Treasury Regulations Section 5.3.1, require the Accounting Officer of an institution to establish procedures for quarterly reporting to the Executive Authority to facilitate effective performance monitoring, evaluation and corrective action.

  - Quarterly performance reports function as an ‘early warning system’ to alert departments to areas of weak performance, potential challenges and where corrective action is required. This in-year monitoring report also serves as an oversight tool to the Department of Planning, Monitoring and Evaluation and National Treasury and, as a management tool for departments.

  - The 2016/17 Fourth Quarter Actual Performance Report provides audited and validated performance information against the planned targets for the fourth quarter for the 2016/19 Annual Performance Plan. The detailed performance report is attached as Annexure A.

  - The report provides an overview of the organisational environment which indicates the internal operations during the fourth quarter of the 2016/17 financial year. The service-delivery environment provides a description of developments in the external environment of the organisation that may have impacted either the demand for the department’s services or the department’s ability to deliver those services.

  - The 2016/17 fourth quarter expenditure report has been attached as Annexure B, to provide a summary of expenditure against the allocated budget for all programmes.

# OVERVIEW OF THE ORGANISATIONAL ENVIRONMENT

  - As of the 30 March 2017 the GCIS received the new Executive Authority, Minister of Communications Ms Ayanda Dlodlo and Deputy Minister of Communications Ms Tandi Mahambehlala.

  - The departmental value of innovation requires the creation of new ideas and processes. As part of living to this value, Human Resource Management (HRM) has introduced an e-EPMDS system. The system will enable employees to complete performance agreements and reviews/assessments electronically. This system will be convenient, improve the efficacy of the organisation and contribute to a paperless environment.

  - In the period under review, the department had a vacancy rate of 9.27 %. This was exacerbated by the high number of vacant positions at senior management level. Twelve  senior management  posts were vacant during the reporting period and these are the Director-General (GCIS), Deputy Director-General of the Intergovernmental Coordination and Stakeholder Management, Deputy Director-General: Content Processing and Dissemination, Chief Director: Media Engagement, Director: Rapid Response, Provincial Directors for the  North West and Free State, Chief Director and the  Director for the Social and G&A Clusters, Director: Human Resource Development, Director: Vuk’uzenzele. The department also has a secondment of the Chief Director: Products and Platforms since 2014. Currently, the department is at an advanced stage of finalising the filling of these vacant posts.

  - The Employment Equity statistics for the quarter under review were as follows:

- Africans were at 83%, over represented by 8%.

- Coloured 7% and under represented by 2%.

- Indians at 2% and under represented by 2%.

- Whites at 6% and under represented by 5%.

- Female at SMS level at 44% and under represented by 6%. However females at all levels were at 57%; and

- Disability below 2%.

  - In line with the department’s retention strategy in the period under review, five internal appointments were made.  The five appointments comprise of three assistant directors, one human resource practitioner and one project administrator.

  - The department complied with the legislative requirements of National Treasury, DPME and the DPSA by submitting the following documents:

- The third quarter 2016/17 interim financial reporting was compiled and submitted to National Treasury on 31 January 2017.

- The 2017-2020 APP was tabled in Parliament on 14 March 2017.

- The third quarter 2016/17 preliminary performance report was submitted to the National Treasury, DPME and the Executive Authority in 31 January 2017 and was presented to the Portfolio Committee on Communications on 14 March 2017.

- Approved 2017/18 Gender Mainstreaming Plan and the 2016/17 second bi-annual report was submitted to the DPSA on 28 February 2017.

# SERVICE DELIVERY ENVIRONMENT

  - The department conducts ongoing public opinion research and analysis of media coverage. This is to gain an understanding of   the communication environment and guides the government messaging to the citizens.

During the fourth quarter, the second bi-annual media content analysis report on the economy was produced and presented to Management Committee (MANCO). Five cluster reports were produced and presented to Manco and shared with the Chief Directorates: Clusters.

These reports provide insights that are useful in developing communication strategies for communicators .The second biannual government communication monitoring and evaluation report which focused on the communications of the Department of Small Business Development was produced and presented to Manco.

3.2	The department continued to provide strategic communication and ensured that the National Development Plan (NDP) is communicated to the public. A National Development Plan Izimbizo events on Education, took place from the 25 February 2017 and were held across all Provinces. The events were in line with the NDP, which identified education, training and innovation as central to creating a better South Africa by 2030.

3.3	14 communication strategies for communication campaigns, projects and programmers were developed to encourage citizens’ participation in the implementation of government communication programmes. 402 development communication projects and 482 community and stakeholder liaison visits were implemented during the fourth quarter, where various public information campaigns were implemented in different methods, including community radio talk-shows, community media newspapers, seminars, workshops, door to door visits, taxi and mall awareness campaigns, dialogues, and meetings.

3.4 The department produces different communication products to meet the information needs of different target audiences. During the quarter under review, 17 editions of communication products were published. These includes; four editions of Vuk’uzenzele newspaper, two editions of the Public Sector Manager (PSM) magazine, one GovComms newsletters, 11 electronic My District Today and one Insight Newsletter.

3.5 The Media Connect workshop that was held at Ster Kinekor on Friday, 10 March 2017, heightened the awareness of the Vuk’uzenzele mobile application and the newspaper. The workshop was attended by specialists from various fields of work such as Human Resources and Media and Communications. The publication currently has a print run of over 850 000 copies per edition and it is distributed to members of the public at no cost. Moreover, the newspaper is available in all official languages and in braille.

3.6 The department provided media production services in support of other government departments. 685 requests for media production services were provided, these included photographic, video and graphic design services. Through the GCIS’s in-house media bulking service designed to save advertising costs for government, whilst maintaining the visibility of government’s communication campaigns, 85 media buying campaigns were approved. 67 are being implemented, 6 are completed, and 12 were approved but not implemented. The cost of the advertising was R79 116 673.15 for which departments paid R69 813 489.61 and saved R9 303 183.54 (average 11.76% saving achieved) R7 829 191.17. About 11.21% of the advertisement spent in the fourth quarter was allocated to community media.

# 2016/17 FOURTH QUARTER ACTUAL PERFORMANCE

4.1	The department had 51 targets for the fourth quarter of 2016/17 financial year. 49 (96%) targets were achieved and two (4%) targets were not achieved. Programme 1 achieved 100% of the planned targets, Programme 2, achieved 96% and 4% of the targets were not achieved while Programme 3 achieved 94% and 6% were not achieved. We should note that of the 49 targets achieved, 12 of them were overachieved during the quarter under review. The detailed performance report has been attached as Annexure A.

The table below provides departmental actual performance per programme.

| Programme | Q4 targets | Achieved | Not achieved |
| --- | --- | --- | --- |
| Administration | 10 | 10 | 0 |
| Content Processing and Dissemination | 23 | 22 | 1 |
| Intergovernmental Coordination and Stakeholder Management | 18 | 17 | 1 |
| Total | 51 | 49 | 2 |

# AUDIT  OF PERFORMANCE INFORMATION BY THE INTERNAL AUDIT

5.1	The audit of performance information for the third quarter of 2016/17 identified 10 targets that were misstated. Nine targets had negative variances while one had a positive variance. The negative variances were caused mainly by duplications in the evidence and in some instances inability to produce the means of verification as recorded in the technical indicator descriptor.

5.2	Nine targets with a negative variance are as follow:

| Sub-Programme | Performance Indicator | Variance |
| --- | --- | --- |
| Communication Services Agency | Number of media-buying campaigns | Negative variance of 4. 71 implemented media-buying campaigns were reported and 67 verified. |
|  | Number of photographic products and services provided | Negative variance of 3. 160 photographic products and services were reported and 157 were verified. |
|  | Number of video products and services | Negative variance of 2. 154 video products and services were reported and 152 were verified. |
|  | Number of radio products and services provided. | Negative variance of 1. 86 radio products and services were reported and 65 were verified. |
|  | Number of graphic designs implemented | Negative variance of 1. 129 graphic designs were reported and 128 were verified. |
|  | Number of Corporate Identity services provided | Negative variance of 2. 156 corporate identity services reported and 154 implemented. |
| Provincial and Local Liaison | Number of development communication activations aligned to the GCP | Negative variance of 1. 403 development activations were reported and 402 were verified. |
|  | Number of community and stakeholder liaison visits undertaken | Negative variance of 2. 484 visits reported and 2 were verified. |
| Media Engagement | Number of engagements between government officials and senior journalists on the government PoA and policy issues held | Negative variance of 3. 10 media engagements reported and 7 were verified. |

5.2	One target with a positive variance is as follow:

| Sub-Programme | Performance Indicator | Variance |
| --- | --- | --- |
| Media Engagement | Number on post-Cabinet media briefings and/or statements issued after ordinary Cabinet meeting | Positive variance of 1. Three Post-Cabinet media statements were reported and four were verified. |

# RECONCILIATION OF QUARTERLY ACHIEVEMENTS AND EVIDENCE

  - The final review of the quarterly achievements was conducted to ensure that reported achievements in the annual report are accurate and valid. During the review process there were more evidence for the indicator: Number of Community and Stakeholder Liaison Visits Undertaken was discovered.

This resulted in amendments on the validated figures for third and fourth quarter. Although 370 Community and Stakeholder Liaisons visits were verified, there was supporting evidence for 421. In the same light, 641 visits were reported but there was supporting evidence for 634.

# CONCLUSION

7.1 The department has achieved 96% of the planned targets during the fourth quarter of 2016/17. The target on the marketing events for the Thusong Programme that was not achieved will be achieved by off-setting against some of the over-achievements for the year and the annual target will thus be fully achieved. The target on social media was reconciled to reflect non-achievement because of lack of evidence as recorded in the technical indicator descriptor.

7.2	Management has also provided proper oversight and control, and ensured that the identified risk relating to verification of evidence is properly monitored. As a result most managers verified the evidence against the reported achievements performance report, as noted by the Internal Auditors.

# ANNEXURE A: 2016/17 FOURTH  QUARTER ACTUAL PERFORMANCE REPORT

| Programme/ Sub-Programme/ Performance Indicators | 2016/17 Annual Target as per Annual Performance Plan (APP) | Quarter 4 Progress | Comments |
| --- | --- | --- | --- |
|  |  |  | Reason for Deviation | Corrective Action |
|  |  | Quarter 4 Target as per APP | Quarter 4 Output – Actual | Deviation (Actual) | Deviation (%) |  |  |
| Programme 1: Administration |
| Sub programme: Strategic Management |
| Strategic management processes and procedures implemented | 2017-2020 APP and tabled in Parliament according to prescribed legislation | The revised 2017-2020 APP tabled in Parliament according to prescribed legislation | 2017-2020 APP was tabled in Parliament on 14 March 2017. | None | 0% | None | None |
| Strategic management processes and procedures implemented | Four approved quarterly performance reports submitted to National Treasury, DPME and Executive Authority according to prescribed legislation | Third quarter 2016/17 performance report submitted to National Treasury, DPME and Executive Authority according to prescribed legislation | Third quarter 2016/17 preliminary performance report was submitted to the National Treasury, DPME and the Executive Authority in 31 January 2017. | None | 0% | None | None |
| Strategic management processes and procedures implemented | Departmental Annual Report tabled in Parliament within National Treasury guidelines and legislative time frames | No target |
|  | Four progress reports on implementation of risk-mitigation plans produced | Third quarter 2016/17 progress report on implementation of risk-mitigation plans produced | The 3rd quarter risk mitigation reports were produced, presented and approved by Manco in 17 February 2017. They were also presented to the Audit Committee 0n 20 March 2017. | None | 0% | None | None |
| Sub programme: Human Resources |
| MTEF HRP implemented | Annual adjusted HRP and HRP implementation report submitted to the DPSA | No target |
| Sub programme: Information Management and Technology |
| IMT governance implemented | Four reports on the availability of IT Infrastructure presented to the IM&T SC | One report on the availability of IT Infrastructure presented to the IM&T SC | 2016/17 third quarter report on the availability of IT Infrastructure was presented to IM&T Steering Committee on the 27th January 2017. | None | 0% | None | None |
| IMT governance implemented | Four reports on IM systems development presented to the IM&T SC | One report on IM systems development presented to the IM&T SC | 2016/17 third quarter report on IM Systems development was presented to IM&T Steering Committee on the 27 January 2017. | None | 0% | None | None |
| Sub programme: Finance, Supply Chain Management and Auxiliary Services |
| Annual financial statements prepared and issued within legislated prescripts | Annual financial statements prepared and issued within legislated prescripts | Third quarter 2016/17 interim financial reporting compiled and submitted to National Treasury | The third quarter 2016/17 interim financial reporting was compiled and submitted to National Treasury on 31 January 2017. | None | 0% | None | None |
| Sub programme: Internal Audit |
| Performance compliance, financial audit conducted | Updated risk-based internal audit plan and 2016/17 operational plan approved | Review the 2016/17 operational plan and develop 2017/18 operational plan | Reviewed the 2016/17 operational plan and developed 2017/18 operational plan | None | 0% | None | None |
| Performance compliance, financial audit conducted | Four progress reports on performance, compliance, financial audit conducted | One progress report on performance, compliance, financial audit conducted | One progress report on performance, compliance, financial audit conducted. | None | 0% | None | None |
| Programme 2: Content Processing and Dissemination |
| Sub programme: Products and Platforms |
| Number of editions of Vuk’ uzenzele newspaper published per year | 21 editions of Vuk’uzenzele newspaper published annually | Four editions of Vuk’uzenzele newspaper published per quarter | Four editions of Vuk’uzenzele newspaper were published in the quarter | None | 0% | None | None |
| Number of editions of GovComms published annually | Four editions of GovComms published annually | One edition of GovComms published | One edition of GovComms was published | None | 0% | None | None |
| Number of editions of PSM magazine published annually | 11 editions of PSM magazine published annually | Two editions of PSM magazine published | Two editions of PSM magazine were published | None | 0% | None | None |
| An annual edition of 2015/16 SAYB and Pocket Guide to South Africa published, and 4 000 DVDs produced | One annual edition of 2015/16 SAYB and Pocket Guide to South Africa published | No target |
| Number of language services requests completed | 1 500 language services requests completed | 300 language services requests completed | 389 language services requests completed | Target overachieved by 89 | +30% | More requests for language services were received. | None |
| News updates on key government programmes and activities | Daily news updates on key government programmes and activities (excluding public holidays, weekends and holiday periods) | Daily news updates on key government programmes and activities (excluding public holidays, weekends and holiday periods) | Daily news updates on key government programmes and activities, 1. Stories published daily during the quarter: 823. 2. Twitter: Grew from 91 000 in the last quarter to 99 300. Facebook – Grew from 18 480 in the last quarter to 20 011 likes | None | 0% | None | None |
| Updated content on the www.gov.za website as per items received (excluding public holidays, weekends and holiday periods) | Daily content updates to the www.gov.za website as per items received (excluding public holidays, weekends and holiday periods) | Daily content updates to the www.gov.za website as per items received (excluding public holidays, weekends and holiday periods) | Daily content updates to the www.gov.za website: Published: 1 085 speeches, statements and advisories; 11 opinion pieces; 652 documents Posted 6 354 tweets and 704 Facebook messages | None | 0% | None | None |
| Number of reports on social media accounts performance as per weekly content plans | 12 reports per year on social media accounts performance as per weekly content plans | Three monthly reports on social media accounts performance as per weekly content plans | Three monthly reports on social media accounts performance as per weekly content plans were not developed. | Target underachieved by three reports | -100% | Reports were done however the target failed on the technical indicator descriptor to get Manco approval. | None |

| Programme/ Sub-Programme/ Performance Indicators | 2016/17 Annual Target as per Annual Performance Plan (APP) | Quarter 4 Progress | Comments |
| --- | --- | --- | --- |
|  |  | Quarter 4 Target as per APP | Quarter 4 Output (Actual) | Deviation (Actual) | Deviation (%) | Reason for Deviation | Corrective Action |
| Sub programme: Policy and Research |
| Number of cluster reports on priorities produced | Two reports per cluster produced biannually | Five cluster reports biannually | Five cluster reports were produced and presented to Manco on 10 March 2017. The approved cluster reports were submitted to Chief Directorates: Cluster Support. | None | 0% | None | None |
| Number of Pulse of the Nation reports produced | Two Pulse of the Nation reports produced annually | No target |
| Number of reports on government communication monitoring and evaluation produced | Two reports on government communication monitoring and evaluation produced | One report on government communication monitoring and evaluation produced | The 2nd Biannual government communication monitoring and evaluation report focusing on communications of in Department of Small Business Development was produced following interactions with the department. The report was presented and approved by Manco on 10 March 2017. | None | 0% | None | None |
| Number of Insight newsletters published | Four Insight newsletters published | One Insight newsletters published | One Insight newsletters published during March. | None | 0% | None | None |
| Number of media content analysis reports produced | Two media content analysis reports produced | One media content analysis report produced | The 2nd Biannual media content analysis report focusing on Economy as a priority of government was produced and presented to Manco on 24 February. Manco approved the report. | None | None | 0% | None |
| Percentage of requested key messages produced. (excluding weekends, public holidays and holiday periods) | Produce 100% of key messages requested. (excluding weekends, public holidays and holiday periods) | Produce 100% of key messages requested. (excluding weekends, public holidays and holiday periods) | Produced 33 (100%) sets of key messages as per requests. | None | 0% | None | None |
| Percentage of opinion pieces produced (excluding weekends, public holidays and holiday periods) | Produced 100% of opinion pieces requested (excluding weekends, public holidays and holiday periods) | Produce 100% of opinion pieces requested (excluding weekends, public holidays and holiday periods) | Produced 28 (100%) opinion pieces as per requests | None | 0% | None | None |
| Sub programme: Communication Service Agency |
| Number of approved media-buying campaigns implemented | 250 approved media-buying campaigns implemented | 60 approved media-buying campaigns implemented | 85 media buying campaigns were approved, where 67 are implemented, 6 are completed, 12 were approved but not implemented. The cost of the advertising was R79 116 673.15 for which departments paid R69 813 489.61 benefitted from R9 303 183.54 savings (average saving achieved was 11.76%) R7 829 191.17 (11.21%)of the fourth quarter ad spend was allocated to community media | Target overachieved by 7 | +12% | More media buying campaigns were briefed in by Departments | None |
| Number of photographic products and services provided | 500 photographic products and services provided | 100 photographic products and services provided | 157 photographic products and services were provided of these 82 were for The Presidency, 13 were for the GCIS, 28 were for other government departments and 34 were for related parties | Target overachieved by 57. | +57% | More requests for photographic coverage were received than planned. | None |
| Number of video products and services provided | 520 video products and services provided | 105 video products and services provided | 152 video shoots were conducted. These 71 for The Presidency, 7 for the GCIS, 58 for other government departments and 16 for related parties. | Target overachieved by 47 | +45% | More request for video coverage were received than planned. | None |
| Number of radio products and services provided | 200 radio products and services provided | 40 radio products and services provided | 85 radio products and services were provided. 3 were live link-ups of government events, 30 were phone in programmes, 1 was for the production of adverts and 51 were recordings of government events. | Target overachieved by 45 | +113% | More requests for radio products and services were received than planned. | None |
| Number of graphic designs completed | 500 graphic designs completed | 100 graphic designs completed | 128 Graphic designs were completed. 1 was for The Presidency, 76 for the GCIS, 32 for other government departments and 19 were for related parties. | Target overachieved by 28 | +29% | More requests for graphic designs were received than anticipated when setting the target. | None |
| Number of Corporate Identity (CI) services provided | 340 Corporate Identity services provided | 100 Corporate Identity services provided | 154 corporate identity services were provided. 1 for assistance with the protocol on the display of official photographs, 27 for advice on corporate identity and 126 for corporate identity quality control. | Target overachieved by 54 | +54% | More requests for CI approvals were received than planned. | None |
| Percentage of approved marketing services requests implemented | 30 approved marketing services requests implemented | 100% of approved marketing services requests implemented | 34 (100%) approved marketing services requests implemented. | None | 0% | None | None |
| Number of GCIS print products distributed | 22 print products produced by the GCIS distributed (21 editions of Vuk’uzenzele and one edition of the Pocket Guide to South Africa | Five GCIS print products distributed | Five GCIS products distributed: 4 x editions of Vuk'uzenzele distributed and 1 x edition of the Pocket Guide | None | 0% | None | None |
| Programme 3: Intergovernmental Coordination and Stakeholder Management |
| Sub programme: Clusters |
| Number of GCPs developed for the clusters | Five Government Communication Programmes (GCP) 2016/17 developed | Implementation of the 2016/17 GCP. Review of 2016/17 GCP | 12 reports on the implementation of the 2016/17 GCP were developed for the Clusters and presented to the DGs cluster. 2016/17 GCPs reviewed. | None | 0% | None | None |
| Percentage of communication strategies developed for cluster campaigns/projects/programmes (based on demand) | 100% of communication strategies developed for cluster campaigns/projects/ programmes (based on demand) | 100% of communication strategies developed for cluster campaigns/projects/programmes (based on demand) | 14 (100%) requests to assist with communication strategies developed for cluster campaigns/projects/programmes were received and implemented. | None | 0% | None | None |
| Number of Government Communicators’ Forums (GCF) coordinated | 2 Government Communicators’ Forums coordinated | One GCF coordinated | Two meetings were held with government communicators and chiefs of staff to plan for the Imbizo Focus Week and Imbizo on Education including feedback from Inter-Ministerial Committee on Publicity and Information. | Target overachieved by one. | 50% | One meeting to plan for Imbizo on Focus Week during the third quarter of 2016/17. | None |
| Number of Internal Communicators’ Forums (ICF) coordinated | 2 Internal Communicators’ Forums coordinated | One ICF coordinated | One ICF held in February 2017. | None | 0% | None | None |
| Number of reports on government communication training produced | Four reports on government communication training produced per year | One report on government communication training produced per quarter | Produced one quarterly report on government communication training | None | 0% | None | None |
| Percentage of communication projects implemented (based on demand) | 100% of communication projects implemented | 100% of communication projects implemented | 15 (100%) communication projects implemented in with cluster priorities. | None | 0% | None | None |
| Sub programme: Provincial and Local Liaison |
| Number of reports on support to the functioning of government communication system produced (provincial and local level) | Four reports on support to the functioning of government communication system produced (provincial and local level) | One report on support to the functioning of government communication system produced (provincial and local level) | One report on the support to the functioning government communication system produced (provincial and local level) | None | 0% | None | None |
| Number of development communication activations aligned to the GCP | 1 200 development communication activations aligned to the GCP per year | 240 development communication activations aligned to the GCP | 402 development communication activations aligned to the GCP | Target overachieved by 162. | +68% | 43 Back to School Izimbizo and high demand of Post SONA (203) events and Human Rights Day (69). | None |
| Number of marketing events for Thusong programme held | 486 marketing events for Thusong programme held per year | 121 marketing events for Thusong programme held | 108 marketing events for Thusong programme held | Target underachieved by 13. | -11% | The number Izimbizo and DTT events held which required the redeployment of staff | None - Annual target reached during the 3rd quarter. The total marketing events to date is 552 |
| Number of community and stakeholder liaison visits undertaken | 1 800 community and stakeholder liaison visits undertaken per year | 360 community and stakeholder liaison visits undertaken | 482 community and stakeholder liaison visits undertaken | Target over achieved by 122. | +34% | Increased stakeholder engagements for preparations 42 Imbizo and DOC campaigns | None |
| Number of reports on Izimbizo events held | Four reports on the number of Izimbizo events held per year | One report on Izimbizo events held per quarter | One report on the 42 Izimbizo events held by political principals. | None | 0% | None | None |
| Number of electronic My District Today newsletters published | 44 electronic My District Today newsletters published per year | 10 electronic My District Today newsletters published | 11 electronic My District Today newsletters published | Target overachieved by 1 | +10% | Economic issues that emerged in the communication environment | None |
| Sub programme Media Engagement |
| Number of engagements between government officials and senior journalists on the government PoA and policy issues held | 16 engagements between government officials and senior journalists on the government PoA and policy issues held per year | Four engagements between government officials and senior journalists on the government PoA and policy issues held | 7 engagements between government officials and senior journalists held | Target overachieved by 3 | +75% | Developments in the media environment as well as adhoc projects. | None |
| Number on post-Cabinet media briefings and/or statements issued after ordinary Cabinet meeting | 18 post-Cabinet media briefings and/or statements issued after ordinary Cabinet meeting per year | Three post-Cabinet media briefings and/or statements issued after ordinary Cabinet meeting per quarter | Three post-Cabinet media briefings/ four statements issued | Target overachieved by one statement. | +33% | One statement was issued without a briefing | None |
| Number of biweekly Rapid Response reports for the minister produced (excluding December and January) | 24 biweekly Rapid Response reports produced for the Minister (excluding December and January) | Five biweekly Rapid Response reports for the minister produced (excluding December and January) | 6 biweekly Rapid Response reports for the minister produced (excluding December and January) | Target overachieved by 1 | +20% | Communicating issues emerging from the media environment. | None |

# ANNEXURE B:  2016/17 FOURTH QUARTER EXPENDITURE REPORT

| PROGRAMME | TOTAL BUDGET | ACTUAL EXPENDITURE | % SPENT | BUDGET AVAILABLE |
| --- | --- | --- | --- | --- |
|  | R'000 | R'000 |  | R'000 |
| PROGRAMME 1: ADMINISTRATION | 149 394 | 147 359 | 100% | 2 035 |
| Personnel | 62 237 | 60 204 | 97% | 2 033 |
| Operational | 87 157 | 87 155 | 100% | 2 |
| Management | 1 341 | 1 342 | 100% | -1 |
| Chief Financial Officer | 62 966 | 62 964 | 100% | 2 |
| Information Management and Technology | 12 916 | 12 916 | 100% | - |
| Internal Audit | 2 903 | 2 904 | 100% | -1 |
| Human Resources Management and Development | 4 018 | 4 018 | 100% | - |
| Internal communication | 2 506 | 2 505 | 100% | 1 |
| Strategic Management | 507 | 506 | 100% | 1 |

| PROGRAMME | TOTAL BUDGET | ACTUAL EXPENDITURE | % SPENT | BUDGET AVAILABLE |
| --- | --- | --- | --- | --- |
|  | R'000 | R'000 |  | R'000 |
| PROGRAMME 2: CONTENT PROCESSING AND DISSEMINATION |  |  |  |  |
| Personnel | 77 807 | 77 607 | 100% | 200 |
| Operational | 57 223 | 57 223 | 100% | - |
| Management | 319 | 319 | 100% | - |
| Research and media monitoring | 8 076 | 8 076 | 100% | - |
| Printing of communication products | 17 985 | 17 985 | 100% | - |
| Development of electronic content | 2 307 | 2 307 | 100% | - |
| Media Buying and Distribution | 19 600 | 19 600 | 100% | - |
| Media Production | 8 936 | 8 936 | 100% | - |

| PROGRAMME | TOTAL BUDGET | ACTUAL EXPENDITURE | % SPENT | VARIANCE |
| --- | --- | --- | --- | --- |
|  | R'000 | R'000 |  | R'000 |
| PROGRAMME 3: INTERGOVERNMENTAL COORDINATION AND STAKEHOLDER MANAGEMENT | 120 084 | 117 157 |  |  |
| Personnel | 81 594 | 78 725 | 96% | 2 869 |
| Operational | 19 238 | 19 216 | 100% | 22 |
| Management | 426 | 426 | 100% | - |
| Media engagement | 2 581 | 2 579 | 100% | 2 |
| Cluster supervision | 1 373 | 1 365 | 99% | 8 |
| Development and communication of outreach programmes | 14 858 | 14 846 | 100% | 12 |

# LIST OF ACRONYMS AND ABBREVIATIONS

| APP | Annual Performance Plan |
| --- | --- |
| AU | African Union |
| CI | Corporate Identity |
| DIRCO | Department of International Relations and Cooperation |
| DoC | Department of Communications |
| DPME | Department of Planning Monitoring and Evaluation |
| DPSA | Department of Public Service and Administration |
| GCF | Government Communicator’s Forum |
| GCIS | Government Communication and Information System |
| GCP | Government Communication Programme |
| HRP | Human-Resource Plan |
| ICF | Internal Communicator’s Forum |
| ICT | Information and Communication Technology |
| IT | Information Technology |
| IM&T | Information Management and Technology |
| IM | Information Management |
| IPAP | Industrial Policy Action Plan |
| MANCO | Management Committee |
| PoA | Programme of Action |
| PPP | Public Participation Programme |
| PSM | Public Sector Manager |
| SAYB | South Africa Year Book |
| SCM | Supply Chain Management |

# Footnotes

Indicators without targets are not calculated in the report.