## Slide 1: FOURTH QUARTER YTD EXPENDITURE AND PERFORMANCE REPORTING FOR THE FINANCIAL YEAR 2016/17
BRIEFING TO THE STANDING COMMITTEE ON FINANCE
20 June 2017

## Slide 2
Q4 YTD 2016/17 EXPENDITURE

## Slide 3: FINANCIAL OVERVIEW: ACTUAL EXPENDITURE 2016/17
Chart: ACTUAL EXPENDITURE 2015/16 vs 2016/17
| Compensation of Employees | Goods and Services | Payment of Capital Assets | Payment of Financial Assets | Transfer and Subsidies
Actual Expenditure (R'000) 2015/16 | 732744 | 1093166 | 33210 | 5846273 | 31644334
Actual Expenditure (R'000) 2016/17 | 786431 | 1594078 | 46379 | 4001228 | 21790666

## Slide 4: Q4 2016/17 ACTUAL EXPENDITURE OUTCOMES PER PROGRAMME
Programmes | Adjusted Budget R'(000) | Virement/shifts R'000 | Final Budget R'(000) | Actual Outcome R'(000) | Variance R'(000) | % Spend | 
1. Administration | 467 416 | (3 000) | 464 416 | 436 312 | 28 104 | 93.9% | 
2. Eco Pol, Tax, Fin Reg & Res | 150 161 | 6 400 | 156 561 | 151 182 | 5 379 | 96.6% | 
3. Public Finance & Budget Man | 294 483 | – | 294 483 | 281 778 | 12 705 | 95.7% | 
4. Asset & Liability Management | 113 129 | – | 113 129 | 110 146 | 2 983 | 97.4% | 
5. Financial Acc and SCM Systems | 1 216 758 | 35 000 | 1 251 758 | 1 228 858 | 22 900 | 98.2% | 
6. International Financial Relations | 4 977 977 | (16 349) | 4 961 628 | 4 955 753 | 5 875 | 99.9% | 
7. Civ & Mil Pen, Cont to Funds | 4 462 642 |  | 4 462 642 | 4 400 159 | 62 483 | 98.6% | 
8. Tech Sup & Dev Finance | 2 612 688 | (22 051) | 2 590 637 | 2 478 432 | 112 205 | 95.7% | 
9. Revenue Administration | 9 363 676 | – | 9 363 676 | 9 363 676 | – | 100.0% | 
10. Fin Intel & State Security | 4 812 487 | – | 4 812 487 | 4 812 487 | – | 100.0% | 
Total National Treasury | 28 471 417 | – | 28 471 417 | 28 218 782 | 252 635 | 99.11% | 

## Slide 5: SIGNIFICANT VARIANCES AND REASONS (1/5)
The main contributors to the under-spending of R252.6 million are Transfers (R152.4 million) and Operational Expenditure (R100.2 million) as follows:
R152.4 million under-spending on transfers:
R57.3 million surpluses on Jobs Fund grant disbursement, the funds transferred to the Jobs Fund Partner were not fully spent and had to be returned to NT;
R32.1 million representing an under-spending on the Neighbourhood Development Partnership Grant (NDPG) direct grant. Funds were withheld as the Mbombela Municipality did not spend all funds transferred in November 2016;

## Slide 6: SIGNIFICANT VARIANCES AND REASONS (2/5)
R32 million representing an under-spending on Special Pensions due to a decline in membership as a result of attrition and members opting for Non-Statutory Forces (NSF). Variance between budget and actual expenditure is inevitable due to the nature of this account, i.e. a reduction in numbers usually as a result of resignation, retirement or death;
R28.2 million representing an under-spending on Injury on Duty (IoD) due to challenges experienced in obtaining the outstanding awards that are in the employers’ possession. The Compensation Fund issues two awards in respect of IoD, one being a copy issued to GPAA and the original to the employer department. Therefore, GPAA only process payments upon receipt of the original award from the employer department; and
R2.8 million on other various transfers within the department.

## Slide 7: SIGNIFICANT VARIANCES AND REASONS (3/5)
7
R100.2 million under-spending on operational budget:
R27.3 million saving which was mainly the funding which was earmarked for the resolution 3 of 2009 within Corporate Services of R12.5 million which was not approved nor implemented. The remaining R14.8 million relates to the under-spending subsequent to EXCO’s decision to freeze certain vacant positions within the department in order to remain within the current expenditure ceiling set;
R14.3 million representing an under-spending on the Jobs Fund operational expenditure. The cumulative under-spending is mainly due to monthly delays in submission of the cost recovery invoices which were to be issued by Government Technical Advisory Centre (GTAC) which administers the payments on behalf of Jobs Fund within National Treasury;
Notes: ECFF – Employment Creation Facilitation Fund
POBF – Political Office Bearers Fund
NDPG – Neighbourhood Development Partnership Grant
CSP – Cities Support Programme
IDIP – Infrastructure Delivery Improvement Programme

## Slide 8: SIGNIFICANT VARIANCES AND REASONS (4/5)
R7 million surpluses on NDPG (Indirect Grant). Funds were initially transferred to GTAC but returned later in March 2017 due to delays in municipal procurement of service providers;
R7 million unspent funds mainly on transversal systems resulting from a lower than expected spending on development and maintenance of the software systems;
R5.8 million unspent funds mainly on consultancy services within the Specialised Audit Services unit for the forensic investigations related cost. The unit receives invoices for services rendered, which highly depends on the number of cases under investigation;

## Slide 9: SIGNIFICANT VARIANCES AND REASONS (5/5)
R5.5 million representing an under-spending on the procurement of a generator for the department for the purpose of managing business continuity during the power outages that happens in the city. Facilities Management experienced delays in sourcing a service provider. As a result, the generator will be procured in the new financial year; and
R33.3 million saving realised from various items mainly due to the implementation of cost containment measures on items such as, amongst others stationery, training and travel costs.

## Slide 10: Q4 2016/17 ACTUAL OUTCOMES VS BUDGET PER CLASSIFICATION
Chart: 
| Compensation of Employees | Goods and Services | Payment of Capital Assets | Payment of Financial Assets | Transfers and Subsidies



Item Classification | Adjusted Budget R'(000) | Virement/shifts R'000 | Final Budget R'(000) | Actual Outcome R'(000) | Variance R'(000) | % Spend
Compensation of Employees | 815 716 | (1 949) | 813 767 | 786 431 | 27 336 | 96.6%
Goods and Services | 1 678 248 | (22 051) | 1 656 397 | 1 594 078 | 62 319 | 96.2%
Payment of Capital Assets | 56 893 | – | 56 893 | 46 379 | 10 514 | 81.5%
Payment of Financial Assets | 4 001 235 | – | 4 001 235 | 4 001 228 | 7 | 100.0%
Transfers and Subsidies | 21 919 325 | 24 000 | 21 943 125 | 21 790 666 | 152 459 | 99.3%
Sub-Total National Treasury | 28 471 417 | - | 28 471 417 | 28 218 782 | 252 635 | 99.1%
Provincial Equitable Share | 410 698 585 | – | 410 698 585 | 410 698 585 | – | 100.0%
Debt Service cost | 147 689 225 | – | 147 689 225 | 146 500 577 | 1 188 648 | 99.2%
Fuel Levy | 11 223 831 | – | 11 223 831 | 11 223 831 | – | 100.0%
National Revenue Fund Payments | 1 221 393 | – | 1 221 393 | 1 778 016 | (556 623) | 145.6%
Sub-Total Statutory Transfers | 570 833 034 | – | 570 833 034 | 570 201 009 | 632 025 | 99.9%
Overall National Treasury | 599 304 451 | - | 599 304 451 | 598 419 791 | 884 660 | 99.9%

## Slide 11: Q4 2016/17 ACTUAL OUTCOMES VS BUDGET PER CLASSIFICATION
Chart: 
| Compensation of Employees | Goods and Services | Payment of Capital Assets | Payment of Financial Assets | Transfers and Subsidies



Chart: Final Budget vs Actual outcomes
| Compensation of Employees | Goods and Services | Payment of Capital Assets | Payment of Financial Assets | Transfers and Subsidies
Final Budget R'(000) | 813767 | 1656197 | 56893 | 4001235 | 21943325
Actual Outcome R'(000) | 786431 | 1594078 | 46379 | 4001228 | 21790666
Chart: Variance
| Compensation of Employees | Goods and Services | Payment of Capital Assets | Payment of Financial Assets | Transfers and Subsidies
Variance R'(000) | 27336 | 62319 | 10514 | 7 | 152459
% Spend | 0.96641 | 0.96238 | 0.8152 | 1 | 0.99305
% Variance

## Slide 12: SUMMARY OF VIREMENT/SHIFTS IMPLEMENTED

## Slide 13
Q4 YTD PERFORMANCE INFORMATION REPORT
ANNUAL PERFORMANCE PLAN 2016/17

## Slide 14: Q4 YTD 2016/17:QUARTER-ON-QUARTER COMPARISON PERFORMANCE ACHIEVED BY TOTAL NUMBER OF INDICATORS
Chart: 
| Q1 | Q2 | Q3 | Q4
Achieved | 0.7459 | 0.7018 | 0.7063 | 0.7561
Partially Achieved | 0.2131 | 0.2018 | 0.2098 | 0.1402
Not Achieved | 0.041 | 0.0965 | 0.0839 | 0.1037

## Slide 15: Q4 YTD 2016/17: PERFORMANCE ACHIEVED BY TOTAL NUMBER OF INDICATORS
Chart: 
| Achieved | Partially Achieved | Not Achieved | Not yet due for reporting | Total
Department of National Treasury | 124 | 23 | 17 | 0 | 164
Quarter | Achieved | Partially Achieved | Not Achieved | Not yet due for reporting | Total
Q4 | 75.6100% | 14.02% | 10.37% | 0% | 100%
Q3 | 70.63% | 20.98% | 8.39% | 13% | 100%
Q2 | 70.18% | 20.18% | 9.65% | 30% | 100%
Q1 | 74.59% | 21.31% | 4.10% | 26% | 100%

## Slide 16: Q4 YTD 2016/17: PERFORMANCE ACHIEVED BY PROGRAMME BY INDICATORS
Chart: 
| Programme 1- Administration | Programme 2 - Economic Policy,Tax and Financial Sector Policy | Programme 3 - Public Finance and Budget Management | Programme 4 - Assets and Liability Management | Programme 5 - Financial Accounting and Supply Chain Management Systems | Programme 6 - International Financial Relations | Programme 7 - Civil Military Pensions, Contributions to Funds and Other Benefits | Programme 8 - Technical Support and Development Finance Programme Management
Achieved | 0.73333 | 0.85714 | 0.87879 | 0.95 | 0.625 | 0.5 | 0.5 | 0.75
Partially Achieved | 0.2 | 0.071429 | 0.090909 | 0.05 | 0.125 | 0.33333 | 0.5 | 0.20833
Not Achieved | 0.066667 | 0.071429 | 0.030303 | 0 | 0.25 | 0.16667 | 0 | 0.041667
Not yet due for reporting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 17: Q4 YTD 2016/17: PERFORMANCE ACHIEVED BY PROGRAMME BY INDICATORS AS A NUMBER
Division | Administration | Economic Policy | Tax and Financial Sector Policy | Budget Office | Intergovernmental Relations | Public Finance | Assets and Liability Management | Office of the Accountant General | Office of the Chief Procurement Officer | International Financial Relations | Civil Military Pensions, Contributions to Funds and Other Benefits | Technical Support and Development Finance Programme Management
Total number of targets due in this quarter | 15 | 9 | 5 | 11 | 18 | 4 | 20 | 29 | 19 | 6 | 4 | 24
Achieved | 11 | 8 | 4 | 10 | 17 | 2 | 19 | 18 | 12 | 3 | 2 | 18
Partially Achieved | 3 | 0 | 1 | 1 | 0 | 2 | 1 | 6 | 0 | 2 | 2 | 5
Not Achieved | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 5 | 7 | 1 | 0 | 1

## Slide 18: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P1: Corporate Services | Percentage completion of the business continuity plan | 100% | 90% | Under-performance is attributed to operational changes resulting in approval of governance documents not being concluded.
P1: Corporate Services | MPAT score achieved on risk management standard | 4 | 3 | Under-performance is attributed to failing to meet newly introduced prescriptive administrative compliance evidence requirements.
P1: Corporate Services | Percentage savings on goods and services expenditure | 5% | 0.5% | Under-performance is attributed to service providers not being in a position or unwilling to negotiate prices as a result of stressed economic factors as well as recently introduced OCPO travel framework limiting departmental level negotiation on travel and accommodation.
P1: Corporate Services | Percentage implementation of ERM annual plan | 100% | 80% | Under-performance is attributed to delayed responses from internal stakeholders.

## Slide 19: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P2:Tax And Financial Sector Policy | Publish tax proposals in annual budget review | Prepare tax proposals for 2018 Budget | Tax proposals presented to the Minister in December 2016. | Under-performance is attributed to the delay in the approval process.
P2:Tax And Financial Sector Policy | Number of economic policy analyses, research, assessment and advice on macroeconomics including government policy proposals developed | 420 | 116 | Under-performance is attributed to restructuring of this area of work, having ended daily reports and reduced the number of monthly reports to align needs of principals better to available resources.
P3:Budget Office | Number of reports produced on review and implementation of the cost-of-living adjustment (COLA) costing model | 4 | 3 | Under-performance is attributed to challenges relating largely to data accessibility and limited resource availability.

## Slide 20: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P3:Public Finance | Percentage adherence to timelines for sectoral analysis and advice for policy framework development | 100% | 98.9% | Under-performance is attributed to three correspondences having required consultations which went beyond the reporting period.
P3:Public Finance | Number of monthly expenditure feedback to departments | 480 | 277 | Underperformance attributed to delays in addressing queries by departments these included not providing feedback within the stipulated 15-day period and delays in addressing technical errors in the reporting template.
P3:Inter governmental Relations | Publication of Local Government Budgets and Expenditure Review | 1 | 0 | Underperformance attributed to budget constraints and not securing technical support for the analysis of the chapters.
P4:Assets and Liability Management | Number of reports on the management of government’s contingent liabilities and counterparty risk | 6 | 5 | Under-performance is attributed to the data and the report on contingent liabilities that had been incorporated into the budget review having not changed between presenting the budget and the FLC meeting and as such negating the need to prepare a new quarterly report .

## Slide 21: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P5:Office of the Accountant-General | Number of assessments conducted of IA and state of readiness for quality assurance reviews and adoption of best practice to assess compliance with PFMA, MFMA and international professional practice standards | 12 | 4 | Under-performance is attributed to delays in client’s responses.
P5:Office of the Accountant-General | Number of institutions whose audit committees have been provided with support | 10 | 2 | Under-performance is attributed to realignment of planning to better align with resource constraints.
P5:Office of the Accountant-General | Number of knowledge sharing forums on IA and risk management facilitated through formal platforms | 6 | 4 | Under-performance is attributed to delay in submission of documentation
P5:Office of the Accountant-General | Number of strategic support plans for government entities struggling at the lower levels of IA and risk management implementation, in line with the FMCMM | 6 | 5 | Under-performance is attributed to realignment of planning to better align with resource constraints.

## Slide 22: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P5:Office of the Accountant-General | Number of public sector officials supported or trained on risk management | 400 | 398 | Under-performance is attributed to delay in submission of documentation
P5:Office of the Accountant-General | Review and updating of e-learning module | 1 | 0 | Under-performance is attributed to current capacity constraints.
P5:Office of the Accountant-General | Improved FMCMM | Develop a web-based FMCMM model | The FMCMM questions have been revised and include questions from level 1 to 6, which are applicable to national and provincial departments, constitutional institutions and schedule 3(a) and 3(c) public entities | . The IT department has confirmed that the space is now available on the server to host the revised FMCMM.
P5:Office of the Accountant-General |  | Conduct one FMCMM assessment | The National Treasury has identified CGROW model at the Western Cape Treasury (WCPT) as a web based platform to host the FMCMM. The National Treasury held a meeting with the WCPT and it was agreed the platform can be shared with to host the FMCMM. | Awaiting confirmation of donor funding"

## Slide 23: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P5:Office of the Accountant-General | Percentage compliance with the banking services for national government: •Daily bank reconciliation of NRF •Electronic verification of supplier banking details within four working days | 100% | 93% | Under-performance is attributed to system disruptions post internal systems upgrade.
P5:Office of the Accountant-General | Number of generic solution configuration templates completed | 1 | 0 | Under-performance is attributed to activities required for the configuration of template rescheduled to the 2017/18 financial year due to protracted contracting with service providers.
P5:Office of the Accountant-General | Number of IFMS comprehensive implementation strategies published | 1 | 0 | Under-performance is attributed to the implementation strategy having been completed but not published.
P5:Office of the Chief Procurement Officer | Number of procurement bills drafted and published for comment | 1 | 1 procurement bill drafted | Underperformance is attributed to the draft Procurement Bill having been developed, however it has not yet been published for comment.

## Slide 24: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P5:Office of the Chief Procurement Officer | Number of systems for publishing procurement spend data developed | 1 | 0 | Underperformance is attributed to budget constraints.
P5:Office of the Chief Procurement Officer | Number of proposals for strategic sourcing opportunities | 3 | 0 | Underperformance is attributed to restructuring of this work area.
P5:Office of the Chief Procurement Officer | Number of sourcing strategies for identified commodities/procurement categories developed | 4 | 2 | Underperformance attributed to not all Provincial Departments of Health having provided the requisite data. Spend analysis at lowest item level could not be done. As BAS and Vulindlela data available is not sufficient information to conduct a spend analysis exercise.

## Slide 25: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P5:Office of the Chief Procurement Officer | Number of sourcing strategies for identified commodities/procurement categories implemented | 4 | 0 | Underperformance is attributed to implementation of Health related projects listed having been delayed. Strategic Sourcing projects run over three phases. Phase one commenced in October 2016 and not April-May 2016 as initially envisaged, due to a protracted tender, evaluation and award process for the appointment of the service provider. In respect of Travel and Accommodation challenges experienced with benefits tracking as departments seem to have difficulties to report in the format as prescribed by the Cost Containment Instruction. Departments seem to not fully understand the Minimum Bid Specifications and have challenges correctly applying the stipulations.
P5:Office of the Chief Procurement Officer | Number of on-boarding, monitoring and benefits tracking on sourcing strategies | 3 | 0 | Underperformance is attributed to the lack of information or data as there is no tracking system in place .
P5:Office of the Chief Procurement Officer | Number of reviews of current PRS model conducted | 1 | 0 | Underperformance is due to the cancellation of the project.
P5:Office of the Chief Procurement Officer | Number of e-SCM performance management modules established | 1 | 0 | Underperformance is attributed to system development should be aligned with performance management framework, in the absence of the framework the system cannot be developed.

## Slide 26: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P6:International Financial Relations | Number of interventions to increase South Africa’s presence within institutions of particular strategic value | 3 | 0 | Under-performance is attributed to constraints in budget not allowing for funding of the placement of Directors at SADC nor advisors to increase capacity in the Constituency Office at the AfDB
P6:International Financial Relations | Number of initiatives to expand relations with key strategic partners | 3 | 2 | Under-performance attributed to delays in stakeholder inputs as well as approval processes still underway.
P6:International Financial Relations | Percentage implementation of assessments of initial conditions and projects and plans to accelerate regional integration | 75% | 50% | Under-performance is attributed to delays in partner departments delivery as well as in-principle approval processes still underway.
P7:Civil And Military Pensions. Contributions to Funds and Other Benefits | Percentage of benefits paid within liable dates | 100% | 95% | Under-performance is attributed to non-submission of payment documents in time by approved clients.

## Slide 27: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P7:Civil And Military Pensions. Contributions to Funds and Other Benefits | Percentage compliance with NT SLA | 100% | 83% | Under-performance is attributed to 3 findings remaining unresolved on the Compliance Audit and 2 out of 14 external audit findings still to be resolved.
P8:Technical and Management Support and Development Finance | Number of technical advisory projects supported | 100 | 84 | Under-performance is attributed to this output being determined by user demand.
P8:Technical and Management Support and Development Finance | Number of municipalities and provincial treasuries assisted through MFIP II | 49 | 34 | Under-performance is attributed to resignations in the Provincial Treasury (2) and municipalities (5) since the beginning of the year.
P8:Technical and Management Support and Development Finance | Number of projects confirmed within integration/spatial transformation zones | 12 | 4 | Under-performance is attributed to delay in submission of documentation

## Slide 28: Q4 YTD 2016/17: INDICATORS NOT ACHIEVED WITH REASONS
PROGRAMME DIVISION | INDICATOR | TARGET | ACTUAL | REASON FOR NOT ACHIEVING
P8:Technical and Management Support and Development Finance | Number of Jobs Fund projects approved (cumulative) | 130 | 125 | Under-performance is attributed to Agriculture funding round (5th call) not yielding the anticipated number of new projects. The assessment of the Innovation funding round (6th call) has been finalised and the Jobs Fund Investment Committee has approved 21 projects, taking the total approved to 125 projects.
P8:Technical and Management Support and Development Finance | New jobs contracted (cumulative) | 150 000 | 136 069 | Under-performance is attributed to project withdrawals post contracting.
P8:Technical and Management Support and Development Finance | Value of grant funding disbursed (cumulative) | R4 462m | R3 734m | Target adjusted upward in 2017/18 APP
P8:Technical and Management Support and Development Finance | Number of technical assistants (TAs) deployed to provide capacity for infrastructure development | 34 | 12 | Under-performance attributed to user demand

## Slide 29: Q4 YTD 2016/17: PERFORMANCE HIGHLIGHTS
22 instructions issued in line with policy interventions and proposed designated products or categories to enhance SCM policy significantly above the targeted 9 P5: OCPO
437 officials from provincial treasuries trained in preparing provincial consolidated financial statements, revenue fund statements and implementation of GRAP standards ; above the 250 planned P5:OAG
1295 national and provincial officials trained in building public financial management competencies
P5:OAG
41 forensic investigation and special performance audit reports, above the target of 25
P5: OAG
74 cases referred and supported to law enforcement agencies/Anti-corruption Task Team for criminal investigation, above the target of 25 P5: OAG
MODERNISE SCM POLICIES AND PROCEDURES
66 national institutions and 9 provincial treasuries workshopped on IA and risk management guidelines; above the 20 and 5 planned respectively P5:OAG
IMPROVE FINANCIAL MANAGEMENT GOVERNANCE AND COMPLIANCE ACROSS ALL SPHERES AND ENTITIES IN GOVERNMENT GIVING EFFECT TO THE PFMA AND MFMA

## Slide 30: Q4 YTD 2016/17: PERFORMANCE HIGHLIGHTS
439 graduates in training for professional registration in engineering, town planning, geographic information systems and project management
P8: GTAC
459 Catalytic projects approved above the planned 360 (accumulative)
P8: GTAC
90 087 placements (jobs fund) contracted (cumulative) P8:GTAC
98.9% of funded positions filled and 98.9% of staff retained P1: Admin
IMPROVED INFRASTRUCTURE PLANNING, MANAGEMENT AND SKILLS DEVELOPMENT
FACILITATION OF EMPLOYMENT CREATION AND INCLUSIVE GROWTH
PROMOTION OF URBAN INTEGRATION AND NEIGHBOURHOOD DEVELOPMENT
ADVANCING NT SERVICE DELIVERY
28 Transactional advisory projects registered, 10 capital project advisory work and 31 performance and expenditure reviews performed; Above the planned 12,5 and 10 respectively P8: GTAC
1793 officials trained on the Infrastructure Delivery Management toolkit
P8: GTAC
224 089 training opportunities contracted above the planned 160 000 (cumulative) P8:GTAC
Vetting files completed by priority group and submitted to SSA P1: Admin

## Slide 31: THANK YOU
BRIEFING TO THE STANDING COMMITTEE ON FINANCE
20 JUNE 2017