## Slide 1: Presentation for SCOPA
15 August 2017

## Slide 2: A: PURPOSE

## Slide 3: Purpose
The purpose of this presentation is to provide SCOPA with a progress report on:
  Implementation of the legislative mandate of SASSA and the extent to which the mandate has been implemented;
  Key Event Schedule to ensure the continuation of social assistance grants payments beyond April 2018; and
  Proposed insourcing of the payment function over an estimated period of 3 to 5 years;

## Slide 4: B: LEGISLATIVE MANDATE AND STATISTICAL BREAKDOWN

## Slide 5: Key SASSA Objectives
As stated in Chapter 2 Section 3 of Act No. 9, 2004: SOUTH AFRICAN SOCIAL SECURITY AGENCY ACT, 2004, are:
Act, eventually, as the sole agent that will ensure the efficient and effective management, administration and payment of social assistance
(b) Serve as an agent for the prospective administration and payment of social security; and
(c) render services relating to such payments.

## Slide 6: SASSA Service Offering
Social Grants
Social Relief Of Distress
ALL Means-tested except for FCG
Child Support Grant
Family Distress (no maintenance , breadwinner dead, incarcerated less than 6 months, medically unfit & not on UIF, etc.)
Disability Grant
Care Dependency Grant
Older Persons Grant
Grant-in-Aid
War Veteran Grant
Foster Care Grant
Report from Social Worker
Disaster Relief (house burnt down, etc.)
Other (assist in malnutrition children and rare cases of school uniform & other desperate situations)
1
2
3
1
2

## Slide 7: Statistical Breakdown Per Province

## Slide 8: C: CONTEXT AND FRAMEWORK

## Slide 9: Scope of Work
The Current Scope of Work entails the following:
Management, Administration and Payment of social assistance to 17.3 million Beneficiaries.
  Management and Administration Functions are largely in-sourced;
  Payment Functions is out-sourced;
(b) SASSA in in a process to further execute administration and payment of social security; and

## Slide 10: HIGH LEVEL SEQUANCE OF EVENTS: CONSTITUTIONAL COURT
In 2012 SASSA, supported by DSD, embarked on a partnership Payment Service Providers (PSP)utilising a tender process.
This process resulted in the appointment of CPS and a consortia of service providers who included Grindrod Bank, Net1, UEPS, and Fidelity Security Services.
The tender process was challenged by competing Payment Services Providers in a litigation.
This resulted in the Constitution Court declaring the tender invalid.
However, SASSA was granted relief for a limited time by the Constitutional Court to make amends through the issuance of a new tender.
SASSA could not comply with the order due to non-responsive bids received
In the meantime CPS was allowed to continue with the payment function till 31st March 2017

## Slide 11: Compliance with Constitutional Court Judgement
Urgent Court application lodged by Black Sash supported by various interested parties
Judgement handed down 17 March 2017
In line with order of court, current contract with CPS was extended for period of 12 months, under same terms and conditions, with additional requirement to protect beneficiary data
Matters resolved:
  Addendum with CPS signed 31 March 2017
  Payment taking place monthly, without disruption since 1 April 2017

## Slide 12: Compliance with Constitutional Court Judgement
SASSA submitted its first quarterly report to the Constitutional Court on the 20 June 2017;
The report was due on the 17 June 2017, which was a public holiday, hence the filing on the 20 June 2017;
Condonation received from the Court to file on the 20 June 2017.

## Slide 13: Panel of Experts
The independent panel of experts were appointed by the Constitutional Court appointed and their maiden meeting was on the 14 June 2017
SASSA has engaged with the panel of Experts on: 14 June, 7 and 24 July 2017
Documents requested were provided;
SASSA not clear of the scope and extent of the work of the panel;
SASSA proposed DPSA rates and still awaits feedback from panel;
SASSA need to finalise the rates and hours to in order to submit a budget bid the National Treasury.

## Slide 14: D1: PHASE 1 END 31 March 2018

## Slide 15: PHASE 1: CURRENT UNTIL 31 MARCH 2018
Capacity
Capability
Change Management Programme (Systems, Processes, People)
1
4
5
2
3
SASSA’s ROLE
Building Capability, Capacity in Systems, Processes, People
Manage Data Migration from Service Provider
Open Corporate Bank Accounts
Possible Direct Transfers to Beneficiaries with Commercial Banks
Roll-Out of Biometric Management System
Management Of Regulation 26A deductions
6
PSP’s ROLE
Overall Beneficiary Data Migration
Payment of Beneficiaries Until 31 March 2018
1
2

## Slide 16: Payment Model
SASSA in consultation with the Department of Social Development resolved that a Hybrid model be implemented, which will include:
  Insourcing certain components of the payment process
  Procuring services of a payment service provider as an interim solution through a combination of government to government and a competitive bidding process;
  Engaging with other organs of state involved in the payment space for possible collaboration in line with approved prescripts; and
  Continuing with efforts to build internal capacity to take over the responsibility for payments over time

## Slide 17: Summary of SASSA Plan
CURRENT
Outsourcing all components of the payment process
TRANSITION
Hybrid
Mixture of insourced and outsourced services
FUTURE
In-house processing of payments by SASSA
April 2017 – March 2018
April 2018 – March 2021
From April 2021

## Slide 18: Current projects undertaken
Key aspects which SASSA will phase-in between 2017 - 2018 include:
  Corporate bank account (s)
  Direct transfers to beneficiaries in commercial bank accounts inclusive of Walvis Bay beneficiaries;
  Biometric Identity User Management system
    to minimize fraud,
    and the same hardware will be used for beneficiary biometric enrolment
    Integration testing with SOCPEN in November 2017
  Management of Regulation 26A direct deductions (October 2017); and
  Migration of DATA from current service provider

## Slide 19: Progress: SASSA Corporate Accounts (s)
OBJECTIVE | PLANNED INTERVENTIONS | PROGRESS
The objective is for SASSA to take ownership of the main account | PMG account re-activated (30 September 2017) | Confirmation from SARB and National Treasury on the requirements and time frames
Manage direct transfers to beneficiaries in commercial banks | Dedicated user codes for SASSA through Bankserv SOCPEN reports enhancements to align to new user codes Develop framework to manage dormant accounts SARB issued requirements for adjustment for payment files. Confirmation of accounts involved (1.6 million) Quality Assurance in process | 
SASSA Social Assistance Bank Account (Holding Account) - October /November 2017 | Incorporated in the RFP as part of acquiring sponsor bank | 

## Slide 20: Progress: Regulation 26A Deductions
OBJECTIVE | INTERVENTIONS | PROGRESS
Insourcing Management of Regulation 26A direct deductions (funeral policy premiums) | SASSA will be taking responsibility for this activity prior to the remainder of the payment function being brought in-house. October 2017 | SASSA investigated a process to ensure compliance to the legislation
 |  | BAC approval for the process was granted
 |  | SOCPEN enhancements in process
 |  | Engagement with local service providers completed.
 |  | Registering of the service providers currently in process.

## Slide 21: Progress: Migration of Beneficiary Data
OBJECTIVE | INTERVENTIONS | PROGRESS
Securing Beneficiary Data | Beneficiary profile (Masterfile) | Beneficiary profile data stored inhouse in SOCPEN Payment files are sent back to SASSA on monthly basis with reconciliations Phase-out: Letter will be sent to CPS to retrieve all beneficiary information on conclusion of the contract
 | Biometric Data | Monthly Migrations (100% up to date)
 | Payment Transactions data | Beneficiary Grant Payment; Biometric scanned images, Beneficiary Transactional data, Customer Care data, FICA data, etc

## Slide 22
Data Set | Brief Description | Who Owns It | Custody/Storage | Migration Plan
Beneficiary Grant Payment Data | The payment file that is generated by SOCPEN to effect payment to beneficiaries The payment reconciliation that is regenerate by CPS to confirming the payments that were effected. | SASSA | SASSA (SOCPEN) | Transmitted to Service Provider monthly in form of payment file Transmitted to SASSA monthly in form of reconciliation file
Beneficiary Biometric Data | Beneficiary Biometric images captured at registration/ enrolment | SASSA | SASSA | Transferred to SASSA on a weekly/monthly basis
Beneficiary Transactional Data | These are transactional data sets that are effected by the beneficiary and CPS on the beneficiary bank accounts. These include: where and when the beneficiaries withdraw their cash; number of withdrawals; bank charges; and any other transactional activity between Beneficiary and the bank. | Grinrod/ Beneficiary SASSA ownership of this data still needs to be clarified as legally it’s a different relationship between a Beneficiary and a bank | CPS/Grinrod | This data has not yet been availed. The format and frequency to be agreed will based on the analysis of the data structures, as well as agreement on the ownership.
Biometric Data Migration: Details

## Slide 23
FICA Data | These are FICA related scanned documents pertaining to a beneficiary entering into relationships with banks of their choice | CPS/ Grinrod Bank | CPS | There are legal challenges regarding the ownership of this data set as it involves third party relationship
Beneficiary/ Customer Master Data | All Beneficiary Data relating to any form of interaction with SASSA or Service Provider via Call Centre or any other point of interaction | SASSA | CPS | This data has not yet been availed. We expect that this data will be transferred to SASSA by November 2017 and residual data will be transferred at the end of the contract.
Beneficiary Voice Data | These are the voice prints of the Beneficiary recorded during the enrolment and registration process. | SASSA | CPS | Limited data was received. This data is not currently used by SASSA.
Biometric Data Migration: Details

## Slide 24: Key Elements to be Out-sourced: Payment Services required
Account Management
  Holding Bank Account
  Special Disbursement Accounts
Card Body Production
  Payment Card Production
  Card Distribution
Provision of payment
  Provision of Electronic Payment
  Cash Payment Services

## Slide 25: D2: SAPO ENGAGEMENT & PAYMENT SERVICES PROCUREMENT

## Slide 26: SAPO Workshop and Process to be Followed
Workshop held on 17 May 2017;
SAPO presented it service offering;
SASSA’s EXCO resolved to partner with SAPO in the payment of social grants:
Deviation from the bidding process obtained from the National Treasury on the following conditions:
    SASSA amend the Demand Plan
    To provide SAPO with the Request for Proposal,
    SASSA should go out on tender for all other services that SAPO cannot perform.

## Slide 27: Timelines for Procurement of SAPO Services
RFP developed and approved on the 20 July 2017
RFP issued to SAPO 24 July 2017 (close procurement )
Bid Document due on the 07 August 2017
Evaluation: 14 – 25 August 2017
  Technical Due diligence
  Evaluation Committee
Adjudication and awarding 31 August 2017
Contracting by 8th September 2017
  setting up and development by 10th October 2017
Testing from 1st November 2017

## Slide 28: Procurement of ‘other’ Services
In case non or not all payment services required can be offered by SAPO then the Open Procurement Processes will unfold as follows;
Revised RFP will be advertised 08 September 2017;
Tender closes on the 05 October 2017;
Evaluation concluded on the 19 October 2017;
Adjudication and Awarding 26 October 2017;
Contracting: 03 November 2017;
    Setting up & Development Nov & Dec 2017
    Testing from the 01 January 2018

## Slide 29: Summary of Procurement of Payment Services
Procurement of Payment Services
SAPO
Request for deviation (29/06/2017) and response (04/07/2017)
RFP submitted to SAPO (24/07/2017)
Closing date: 07/08/2017)
Competitive Bidding Process
Will commence after evaluation of SAPO proposal
Evaluation & Due Diligence
(From the 14 – 25 August)

## Slide 30: E: PHASE 2 FRAMEWORK END 31 March 2021

## Slide 31: PHASE 2: CURRENT UNTIL 31 MARCH 2021
Capacity
Capability
Change Management Programme (Systems, Processes, People)
1
4
5
2
3
1
2
Possible Phasing Out of Interim Payment Arrangements
3
Introduction of New SASSA Card
Management of New SASSA Card
Collaboration with Other Spheres of Government
Management of New Payment Arrangement Mechanisms
Management of Biometric Management System
SASSA’s ROLE
PSP’s ROLE
Roll-Out of Interim Payment Arrangements
Management of Interim Payment Arrangement

## Slide 32
Sponsoring Bank
Payment Service Provider/s
Large
Solution Integrator
&
Cash Distribution & PayPoint SP
Integrated Grant Admin & Payment
SASSA Data
Integrated
Customer Care & CRM Platform
Grant Admin SYSTEMS
Grant Payment SYSTEMS
3rd Party Banking & Payment Systems
Biometric Authentication, Verification & Proof of Life
Data Services & Integration
Integration
Auxiliary Role
SASSA APPROACH

## Slide 33: Business Continuity & Transition Payment
It is imperative that a well-managed exit from CPS is taken into account and planned for as phase-out and phase-in:
Possible Card life extension and phase-out
  New SASSA card roll out project will take place alongside the card life extension project
  If extended, the life of the card should be replaced in the shortest possible time
A new SASSA payment Card
  New SASSA card will be managed by the new service provider while remaining the property of SASSA
  the card will address all SASSA goals and objectives for the business value sought.

## Slide 34: Issues and risks
Risk/ Issue | Mitigation action
Delay in issuing new SASSA beneficiary cards | Current card life extension
Confusion amongst beneficiaries | GCIS coordinated communication with beneficiaries
Uncertainty amongst employees | Implement change programme

## Slide 35: E: PHASE 3 OF THE FRAMEWORK END 31 March 2023

## Slide 36: PHASE 3: CURRENT FROM 1 APRIL 2021
Capacity
Capability
Change Management Programme (Systems, Processes, People)
1
2
3
SASSA’s ROLE
SASSA as the sole agent for the management, administration and payment of social assistance
SASSA serving as an agent for the prospective administration and payment of social security
SASSA rendering services relating to social assistance and social security payments
PSP’s ROLE
Diminishing Role of Payment Service Providers
Non Core Functions remain Outsourced
1
2

## Slide 37: SASSA’s Intent
  SASSA seeks to develop a payment solution for the future, wholly and efficiently controlled and managed by SASSA and fully responsive to the needs of the beneficiaries in line with Chapter 2, section 3 of the SASSA Act, 2004 as amended .
  The approach that SASSA seeks will be an incremental transition towards a desired future state where SASSA Owns, Operates and Delivers a Constantly Improving “One Stop” Grant Administration and Payment Service.
  This will be implemented in a phased manner that takes into account the limited capability, capacity and budget of SASSA.
  The SASSA payment insourcing plan is informed by the outcomes by the Ministerial Advisory Committee and insourcing plan developed by SASSA supported by research of the Workstreams, CSIR and other expertise sourced.

## Slide 38: Key Strategic Objectives
Reduce Cost
  Cost-to-collect and Inconvenience to the Beneficiary
  Cost-to-pay
Improve Performance
  Improved beneficiary experience
  Improved Grant Administration and Payment
  Improved customer care and relationship management
Improve Compliance
  Improve transparency and accountability by both SASSA and Suppliers
  Improved compliance with SASSA and Social Assistance Act by both SASSA and Suppliers
Reduce Risks
  Improved risk management & fraud prevention
  Improved Controls & Information Assurance
  Improved Data governance

## Slide 39: Recommendation
It is recommended that SCOPA notes:
  Legislative mandate of SASSA and the extent to which the mandate has been implemented.
  Key Events Schedule to ensure the payment of social assistance grants as from April 2018; and
  Proposed Framework towards SASSA taking the payment function in-house over an estimated period of 3 to 5 years

## Slide 40
I Thank you
Nelson Mandela: “After climbing a great hill,
one only finds that there are many more hills to climb.”