## Slide 1: ENYOKENI CULTURAL PRECINCT PROJECT
DATE: 12/09/2017

## Slide 2: PRESENTATION OUTLINE
Purpose
Background
Terms of reference and brief
Scope of work and budget as per instruction letter
Project Master Plan and Scope
Progress from master plan to phase 1 scope of work
Phase 1 final approved scope of work
Summary of project financials
DAC project management office (PMO) background

## Slide 3: 1. purpose
To provide the status update on the progress of the development of Enyokeni Cultural Precinct Project to date.
3

## Slide 4: 2. BACKGROUND
On the 31 August to 1st September 2013 the DAC had a meeting with His Majesty King Goodwill Zwelithini to discuss the Bhambatha Project.
At this meeting His Majesty requested the DAC to assist with capital funding for the construction of the Cultural Arena to host culturally significant ceremonies and functions.
On 15 October 2013 the Bhambatha Project follow-up meeting was held between DAC, Zondi Family and the Royal House in Nongoma
Her Majesty the Queen requested the feedback from DAC regarding the request by His Majesty for funding of the 2014 Reed Dance Ceremony, 2013 First Fruits Ceremony, and the Capital Funding for Cultural Arena.
The King requested DAC to assist with capital funding for the construction of the Cultural Arena for cultural significant ceremonies and functions as Reed Dance Ceremony (uMkhosi woMhlanga)
DAC responded by indicating that the Department will discuss the request from His Majesty. However, it would be recommended that the Royal Household submits the formal request in writing to the Department.
The DAC eventually received a letter requesting the above on the 23 October 2013

## Slide 5: 2. BACKGROUND (Cont)
The Department of Arts and Culture (DAC) launched the Enyokeni Cultural Precinct project on the 29th April 2014.
The year of 2014 was the significant year of the celebration of the 30th anniversary of the revival of the Royal Reed Dance Ceremony. The Reed Dance ceremony witnessed massive growth in number of participants from 500 in 1984 to almost 50 000 in 2013.
Enyokeni Cultural Precinct project is a multi-cultural activities and heritage precinct intended for the promotion and preservation of arts, culture and heritage through hosting various cultural heritage festivities and ceremonies that are of great significance to the nation.
The precinct serves as a pilot in keeping with the Intangible Cultural Heritage draft Policy to support various traditional communities to protect and promote vast indigenous knowledge and help in transmitting it from one generation to the next in partnership with traditional authorities across South Africa.

## Slide 6: 3. TERMS OF REFERENCE AND BRIEF
The MOA outlines the terms of reference in terms what is expected of both IDT and DAC.
The instruction letter outlines the brief of the project scope.
The IDT received an appointment letter from the DAC dated 08 November 2013 for the implementation of Heritage and Library Projects.
The Department of Arts and Culture (DAC) and the IDT entered into a Memorandum of Agreement (MOA) in January 2014.
The scope of the MOA was to implement short term and long term infrastructure delivery related to the following programs:
  1.Establishment of a Project Management Office (PMO)
  2. Libraries and Community Centres
  3. Heritage Projects
  4. Facilities Management
The DAC issued a letter of instruction to the IDT to proceed with urgent implementation of Enyokeni Cultural Precinct in particular dated 12 March 2014.

## Slide 7: 4. SCOPE OF WORK AND BUDGET AS PER INSTRUCTION LETTER
Bulk Earthworks
Parking and Access Roads
Infrastructure: Accommodation; 50 000 Maidens and 2000 guests
Ablution Facilities
5 Catering Facilities and Equipment
The initial total budget allocated for the project construction was R100m excluding professional fees and IDT Management Fees.

## Slide 8: 5. PROJECT MASTER PLAN AND SCOPE
The original master plan was developed and planned to be implemented in two phases.
The scope of the master plan comprised of:
  Refurbishment of the existing pavilion (Arena) for performances- including seating, compaction of the soil and re-grassing; paving; fencing and gates.
  Practicing Field and temporary maiden sleeping area with fencing and gates.
  Construction of the accommodation infrastructure housing 50 000 maidens with ablutions and industrial kitchen;
  Construction of a multifunctional cultural dome (Amphitheatre) to accommodate 2000 people
  Construction of the New Water reservoir,
  water and electricity reticulation;
  Royal square (17 000m2)
  Widened walkways and upgrading of access road within precinct vicinity;
On the 8th April 2014 the final original master plan was presented to the Project Steering Committee and the King

## Slide 9: 6. PROGRESS FROM MASTER PLAN TO PHASE 1 SCOPE OF WORK
On the meeting of the 8th April 2014, the Steering Committee requested changes due to budget constraints.
On the 10th April 2014, the revised changes were presented to the Steering Committee by the Project Team.
The Steering Committee requested that 04 pods out of 16 (and left with 12 pods) be removed and substituted by the addition of the VIP facility (Amphitheatre) and Reed Presentation Wall for Phase 1.
On the 11th April 2014 the revised phase 1 plan was submitted to the IDT.
On the 21st May 2014 the appointed environmental specialist submitted the environmental screening report to the KZN department of Agriculture and Environmental Affairs in Pietermaritzburg.
The pods were reduced from 12 to 6 due to environmental screening report which indicated the extent of the disturbed areas allowed to be constructed on.
On the 4th July 2014 the project team presented to the steering committee that only 2 pods out of 6 could be constructed due to poor and bad soil conditions, additional costs to spoil and borrow pit licensing as per contractor’s programme.
On the 5th July 2014 the project steering committee instructed the project team to remove all pods from Phase 1 due to the above identified issues and due to 2 pods being not sufficient to significantly accommodate required number of maidens.

## Slide 10: 7. PHASE 1 FINAL APPROVED SCOPE OF WORK
The final approved and completed scope of work for Phase 1 was grouped as follows:
  Work Package 1 A – Arena
    New paving to areas adjacent to existing pavilion;
    Security lighting around the arena;
    Flood light mounted on top of the pavilion;
    Weatherproof 60m single phase power to provide temporary power to the tents at the temporary accommodation area.
    Reshaping arena with new sub-soil drainage and earth embankment to direct storm water;
    Sloping seating and finished with grass removed from the existing arena;
    Construction of the razor mesh fencing to Arena with 3 gates

## Slide 11: 8. SUMMARY OF PROJECT FINANCIALS
Work Package | Description | Final Account For | Professional | IDT Management | Estimated Total | Expenditure To | Estimated Amounts
 |  | Construction | Fees | Fees | Work Package Cost | Date | Still To be Paid
01A | Arena Fields | R 16 268 636,89 | R 4 513 435,38 | R 831 282,89 | R 21 613 355,16 | R 18 773 983,33 | R 2 839 371,83
01B | VIP Area | R 37 949 636,95 | R 10 528 431,80 | R 1 939 122,75 | R 50 417 191,51 | R 43 793 825,89 | R 6 623 365,61
01C | Royal Square | R 28 170 296,68 | R 7 815 332,93 | R 1 439 425,18 | R 37 425 054,80 | R 32 508 481,43 | R 4 916 573,37
01D | Earth Works | R 2 353 541,39 | R 652 946,96 | R 120 259,53 | R 3 126 747,88 | R 2 715 983,34 | R 410 764,54
01E | Water Services | R 17 364 294,31 | R 4 817 405,47 | R 887 267,99 | R 23 068 967,77 | R 20 038 370,40 | R 3 030 597,37
01F | Electrical Services | R 3 981 981,32 | R 1 104 727,80 | R 203 468,36 | R 5 290 177,48 | R 4 595 200,66 | R 694 976,82
 | Totals | R 106 088 387,54 | R 29 432 280,34 | R 5 420 826,72 | R 140 941 494,60 | R 122 425 845,06 | R 18 515 649,54

## Slide 12: 9. DAC PROJECT MANAGEMENT OFFICE (PMO) BACKGROUND
In terms of clause 3.1.1 of the signed MOA between the DAC and the IDT, the IDT had to establish the Project Management Office (PMO).
The terms of reference for the PMO were as follows:
  An invitation to qualified and experienced Professional Service Providers (PSPs)
  The PSPs were to set up a PMO
  Provide Project Management Services
  Coordinate Project Planning
  Coordinate Project Design
  Produce a Project Recovery Plan
  Produce a Plan for the c

## Slide 13
    END