## Slide 1: Operation Phakisa report PRESENTATION TO THE Portfolio Committee ON RURAL DEVELOPMENT AND LAND REFORM 10 OCTOBER 2017

## Slide 2: Operation PHAKISA :
The DRDLR in collaboration with DAFF were mandated to implement an Operation Phakisa for the sector.
The intention of Phakisa is about finding better ways to implement the Restitution Mandate.
A facilitated Phakisa Mini Lab was conducted, and recommendations for fast tracking settlement of claims are in place.
Acceleration strategy
An acceleration strategy has been adopted for the settlement of the remaining land claims submitted before the cut-off date of 1998.
New Commission:
Ministers Budget Policy Speech of 19 May 2017. Move towards transforming the Land Claims Commission into a Chapter 9 Institution. An Operating Model have been developed for the Autonomous Commission as well as an interim model.

## Slide 3: Outcomes of the Mini Phakisa
  Develop an operating model that will assist the Commission to be better poised to deal with its current and future challenges of backlog resolution
1
  Redesign the claim process to facilitate the fast tracking of the claims in backlog
2
  Propose key capabilities required to support the redesigned process.
3
  Proposed governance structures that will guide the Commission’s internal operations and its interaction with other institutions that impact its operations.
  .
4
  High level implementation plans to guide the Commission to implement the proposals.
  .
5
Notes: Create a shared understanding of the challenges affecting the land restitution process, the causes of these and prioritise the most pertinent challenges.
Understand and analyse the Previous and Current initiatives to clear the backlog.
Analyse the current settlement options and explore potential alternatives.
Agree on the Design principles that will guide the Solution Design
Explore potential solutions to improve the process and the enablers.

## Slide 4
The table below reflect a total of 6558 outstanding claims as at 30 June 2017 as per the Restitution Business Process. The alignment of claims in terms of the Restitution Business Process is an on-going process.
OUTSTANDING CLAIMS AS AT 30th JUNE 2017
(LODGMENTS - 31ST DECEMBER 1998 IN TERMS OF THE RESTITUTION BUSINESS PHASE)
Province | Phase Two | Phase Three | Phase Four | Total outstanding as at 30th June 2017
 | Screening and Categorisation | Determination of Qualification in terms of Section 2 of the Restitution Act | Negotiations | 
Eastern Cape | 168 | 0 | 497 | 665
Free State | -14 | 0 | 13 | 13
Gauteng | 47 | 0 | 144 | 191
KwaZulu Natal | 103 | 115 | 1644 | 1862
Limpopo | -184 | 0 | 519 | 499
Mpumalanga | 1174 | 0 | 1181 | 2355
Northern Cape | -57 | 0 | 151 | 148
North West | -102 | 0 | 135 | 133
Western Cape | 353 | 0 | 339 | 692
Total | 1820 | 115 | 4623 | 6558
Note:
A total of 25 claims were researched, i.e. LP (20), NC (3) and NW (2) irrespective of the negative totals reflected under Phase 2. For FS there was no research. This will therefore balance the figure of 1845 minus the 25 researched, giving a total of 1820. However the 25 was considered for the total outstanding claim count resulting in 6558 (i.e. 6607 minus 49 settlements)

## Slide 5
ACCELERATION PLAN FOR THE SETTLEMENT OF CLAIMS lodged 31 December 1998

## Slide 6
As a strategy to accelerate, streamline and standardise the settlement of the remainder outstanding claims, the Commission has undertaken to identify the following:
All remainder outstanding claims in terms of rural or urban (district based);
The type of rights lost, e.g. registered and unregistered rights;
The commodity type (e.g. conservation, forestry, mining etc) of all phased settlements;
The commodity types for outstanding claims (pure);
Prioritise the settlement of State land claims;
Regional champions for each commodity type.
All role players, stakeholders and/or investment partners during the options workshops, who then become part of the settlement in line with RETM.
STRATEGY TO ACCELERATE THE SETTLEMENT OF CLAIMS

## Slide 7: Proposed Operating Model – Option 1
The operating model demonstrates clear requirements for each function with links only proposed to enhance collaboration
Support Services
Office of the Commissioner
Claims Coordination
Department of Rural Development and Land Reform
Strategy
Human Resources
Finance
Settlement Sign - Off
Information Management
Claim Authorisation
Pre – Settlement Management
Information Management
IT Services
Procurement
Contact Centre
Quality Assurance
Stakeholder Management
Office of the Commissioner - National
Provincial Offices
Legal
(Restitution)
Quality Assurance
Legal (Restitution)
Permanent functions
Temporary functions - for a finite period
Change Management
Restitution Policy
Monitoring & Evaluation
Deployed functions
Claim Settlement
Function complementarity
New or revised functions
Actuarial Planning
Communications
Provincial Coordination
Notes: Risk and audit needs authority/clout to work across functions, not from support services as it might be marginalised if a bottom-up approach is taken. Risk & Audit should be seen as a governing capability more than a support capability to drive good practice

## Slide 8: Proposed Operating Model – Option 2
The Operating model has a governance or advisory structure that enables the organisation to participate in activities such as investments
Commissioner
Operations
Fund Management
Governance / Advisory Structure
Contact centre
Actuarial planning
Support Services
Human Resources
Communications
Project management
Co-ordination services
Investment
Management
Minister
IT Services
Strategy
Monitoring and Evaluation
Procurement
Stakeholder Engagement
Finance
Legal
Information Management
Quality Assurance
Office of the Commissioner - National
Provincial Offices
Governance Structures
Secretariat
Restitution Policy
Pre – Settlement Management
Information Management
Quality Assurance
Legal
(Restitution)
Change Management
Permanent functions
Temporary functions - for a finite period
New or revised functions

## Slide 9: Proposed Operating Model – Option 3
The model makes provision for the Commission to be accountable only to Parliament. It also has an operational focus with the CEO at the helm of operational oversight
Support Services
CEO
Operations
Parliament
Strategy
Human Resources
Information Management
Pre – Settlement Management
Information Management
IT Services
Procurement
Contact Centre
Quality Assurance
Stakeholder Management
Office of the Commissioner - National
Provincial Offices
Legal
(Restitution)
Quality Assurance
Legal (Restitution)
Finance
Governance
Revenue Management
Finance
Actuarial Planning
Commissioner(s)
Change Management
Monitoring and Evaluation
Restitution Policy
RLCC – (X4)
Office of the Ombud
Claim Sign Off
Communications
Permanent functions
Temporary functions - for a finite period
New or revised functions

## Slide 10: 3 feet plan progress

## Slide 11
INITIATIVE: FAST TRACKING THE SETTLEMENT OF OUTSTANDING RESTITUTION CLAIMS IN A SUSTAINABLE MANNER
Activity | 3 feet Activity Progress
CONDUCT AND FINALIZE ALL OUTSTANDING RESEARCH (916) BY 31 DECEMBER 2017 | As of 30 September 2017, 269 from 916 target research reports has been approved. Acceleration implementation plan by Commission are currently being implemented. Policy on untraceable claimants has been developed, SABC Radio & TV, Commercial Print (newspaper adverts), Commercial Radio and TV, Community Radio & TV, Outdoor Production, Creative and Diversity Print on untraceable claimants – all adverts are currently running.
CONDUCT AND FINALIZE OUTSOURCING VERIFICATION IN THE NEXT 48 MONTHS | Draft verification policy has been completed. Claimant Verification of community claimants to be outsourced due to the complexity of the claims. This will involve staff re-deployment. This initiative is depended on the completion of the departmental re-engineering project. Progress on this will be tracked by checking the number of claims verified over a period of time- ongoing.

## Slide 12
INITIATIVE: FAST TRACKING THE SETTLEMENT OF OUTSTANDING RESTITUTION CLAIMS IN A SUSTAINABLE MANNER
Activity | 3 feet Activity Progress
SETTLE AND FINALIZE ALL OUTSTANDING CLAIMS (6558) in the next 48 months | As of 30 June 2017, 6558 claims where outstanding of which 1820 are on Phase two : screening phase, 115 Phase 3: determination of qualification and 4623 Phase 4: negotiations. 2152 claims will be settled and finalize in the next 24 months. The Hybrid Settlement Option and Models are linked to the three on-going state holder engagement dialogues. Written delegations to Provinces for Research reports, Gazette Notices, Section 42Ds, Sale and Settlement Agreements is in progress and linked to the approval of an operating model. The Commission is looking at the option of appointing Regional Land Claims Commissioners per Province. This activity to finalize all claims (Transfer of land / Payment of financial Compensation) This is ongoing.
RE-DESIGN RESTITUTION BUSINESSS PROCESS | Commission’s business process reviewed as part of the Restitution mini Phakisa A preferred Commission interim operating and long term model have been established towards chapter 9 institution. Implementation of the operating model, once approved, will be on an ongoing basis. Project Charter has been developed between CRLR and G-Tech. Details project plan will be finalised soon.

## Slide 13: Implementing Phakisa Outcomes

## Slide 14: Implementing Operation Phakisa Outcomes
1. A project management unit (PMU) will direct, field technical support and coordinate the approach using work streams 2. The PMU will chaired by the DLCC supported by the GTAC team leader Members will be GTAC technical advisors and officials from the CRLR PMU will be organised into work streams focusing on: Operations management; Change and People management; Funding options and Piloting funding options; and Organisational form. 3. A project charter will be concluded between the GTAC and the CRLR by 30 December 2017

## Slide 15
  THANK YOU