## Slide 1
BRIEFING BY DPW & PMTE ON THE PRESTIGE PROGRAMME WITH FOCUS ON PARLIAMENT AND THE WORK OF THE PARLIAMENTARY VILLAGES MANAGEMENT BOARD (PVMB)
South Africa Works because of Public Works
Presentation to the Portfolio Committee
on Public Works
24 October 2017
OFFICE OF THE DIRECTOR-GENERAL

## Slide 2
PURPOSE OF THE PRESENTATION
To brief the Portfolio Committee on the Prestige Programme with focus on Parliament and the work or functions of the Parliamentary Villages Management Board (PVMB).

## Slide 3
CONTENTS PAGE
Section | Slide No
Section A – Projects within Parliament Precinct | 4 – 6
Section B – Work or Functions of the Parliamentary Villages Management Board (PVMB) | 7 – 8
Section C – Challenges – Pending issues for Discussion by the Board | 9 – 10
Section D – Considerations and Conclusion | 11 – 12

## Slide 4
Section A
Projects within Parliament Precinct

## Slide 5
PROJECTS WITHIN PARLIAMENT PRECINCT
S/N | Project Title | Project Manager | Start Date | Completion Date | Budget | Progress / Status
1. | Marks Building: External Repairs and Renovations - Work entails the roof replacement / water proofing, repairs to sandstone walls, replacement of windows, repairs to windows and repairs to cooling towers - (WCS 050720, Status 5B). The Construction Company. Contract period: 18 months. | Greg Rowe. | 07/03/2016 | 25/05/2018 | R36,055,339.09 | Project commenced. Requirement: SSA approval requires that SAPS provides escorts.
2. | NCOP: Total refurbishment including HVAC, Electrical and Electronic installations (WCS 044232, Status 5B). Nolitha Construction. Contract period: 24 months. | Eric Williams & Babalwa Ntshonyana . | 11/05/2017 | 17/04/2019 | R102,112,409.00 | Project commenced however, Chairperson of NCOP and Deputy Chairperson’s offices will be attended to over the December recess period.
3. | Parliamentary Precinct: Maintenance Contract for Security / Access Control on the Parliamentary Precinct (WCS 047084, Status 5B) Messrs EOH Security Services. Contract period: 36 months. | Heine Smith | 01/11/2016 | 30/10/2019 | R47,445,090.00 | Maintenance control for access control doors. Project ongoing
4. | 90 Plein Street Lift modernisation and refurbishment. WCS 052134 - Status 5B. (Contract period: 18 months). | Mark Kirschner | 28/09/2017 | March 2019 | R9.2 million | Site handover established 28th September 2017. A bank of 4 lifts to be attended to at a time.

## Slide 6
PROJECTS WITHIN PARLIAMENT PRECINCT
S/No | Project Title | Project Manager | Start Date | Completion Date | Budget | Status
5. | 90 Plein 6th Floor: Total redesign/refurbishment (WCS 045650, Status 5) Prema-Raciti is the recommended contractor. Contract period 8 months. | Mark Kirschner | Extended to 16/11/2017 | 2018 (date to be confirmed) | R25,929,329.00 | Commencement of project dependent on Justice family court vacating 6th floor. DOJ & CD relocation planned for November 2017.

## Slide 7
Section B
Work or Functions of the Parliamentary Villages Management Board (PVMB)

## Slide 8
Work or Functions of the Parliamentary Villages Management Board (PVM)
Background
The Parliamentary Villages Management Board is established by the Parliamentary Villages Management Board Act,1998 (Act No 96 of 1998):
  according to the Parliamentary Villages Management Board Act,1998 (Act No 96 of 1998), the Minister of Public Works appoints Members of the Board,
  the Director General of Public Works shall be the Chairperson of the Board;
  Three residents, of whom two shall be Parliamentarians, and one shall be a Sessional Official from each parliamentary village (Acacia, Laboria & Pelican Park);
Work or Functions of the Parliamentary Villages Management Board (PVMB)
  The Board shall provide transport from and to parliamentary villages for residents who are in Cape Town;
  Observe any tariff fixed by the Minister with the concurrence of Minister of Finance and Minister of Transport in respect of any service referred to in paragraph(a), and shall be subject to such direction as the Minister may issue after consultation with the Board;
  Perform such duties as the Minister may determine.

## Slide 9
Section C
Challenges

## Slide 10
Challenges
All the currently serving Members were appointed in 2015 and according to the Act, Board Members must be appointed annually. The challenge has been that, Members of the Board are drawn from Residence committees which are also supposed to be elected annually but tenants seldom attend meetings. This has resulted in Board Members serving for a term of Parliament.
The Parliamentary Villages Management Board to date has held a series of meetings, the first meeting was on the 03rd June 2015 and the last meeting was held on the 06 May 2016.
In 2015 the Board met on a monthly basis and now it meets quarterly .
For the whole of 2016 and early 2017, the Board did not meet quorum and that has resulted in the Board resolving to hold its meetings on a Wednesday. This was due to Plenary starting at 15:00 on the day as compared to holding meetings on Fridays as some Members had challenges with flights.
Since the change, the last Board meeting met the quorum, the following meeting which was set for the 06th September 2017 had to be postponed owing to last moment cancellation.

## Slide 11
Pending issues for Discussion by the Board
Gym facilities
Transport matters
Renovation of members’ residences
Proposed amendment of the Act.
The definition of dependants
The role of Parliament with respect to Transport

## Slide 12
Section D
Considerations and Conclusion

## Slide 13
Considerations and Conclusion
According to the act, the substance of the work for the Board is the provision of transport and as the programme for Members of Parliament is compiled by Parliament they are better positioned to manage the transport.
The following proposed functions (which are relevant and lacking in the PVMB Act) should be performed by the Board :
  allocation of residences within the parliamentary villages,
  appointment of residents committees for each parliamentary village,
  ensure the provision of security services at parliamentary villages,
  provision for the keeping and maintenance of parliamentary villages.
The Board should report to Parliament annually on its activities and management of funds allocated to the Board.
The PVMB Act is also silent on the Minister’s powers to make regulations.
Consideration should be given to repeal the act and allow Parliament to manage the transport and the Department of Public Works to execute its mandate of providing accommodation in consultation with Parliament.

## Slide 14: Thank You
National Department of Public Works (NDPW)
Head Office: Public Works CGO Building Cnr Bosman and Madiba Pretoria Central Private Bag X65 Pretoria 0001
Website: http://www.publicworks.gov.za