## WCS20170612
FINANCIAL YEAR | CLIENT DEPT | OFFICE TYPE | CATEGORY TYPE | PROJECT TYPE | PROVINCE | OFFICE | TYPE | MUNICIPALITY | DESCRIPTION | WCS NO | PROJECT NO | CATEGORY CODE | CATEGORY | STATUS | STATUS TYPE | ASSET TYPE | ASSET TYPE DESCRIPTION | INFRA CLASS | INFRA CLASS DESCRIPTION | FINANCIAL TENDER DATE | FIRST DELIVERY DATE | TENDER NO | CONTRACT PERIOD | RETENSION | CONTRACTOR ORIGINAL ALLOCATION | CONTRACTOR LATEST ALLOCATION | CONTRACTOR NEW ALLOCATION | CONTRACTOR EXPENDITURE PREVIOUS YEARS | CONTRACTOR EXPENDITURE CURRENT YEAR | CONTRACTOR CASH FLOW AMOUNT | CONTRACTOR CASH FLOW YEAR 2017/2018 | CONTRACTOR CASH FLOW YEAR 1 | CONTRACTOR CASH FLOW YEAR 2 | CONTRACTOR CASH FLOW YEAR 3 | CONTRACTOR CASH FLOW YEAR 4 | CONSULTANT AUTHORISATION | CONSULTANT ORIGINAL ALLOCATION | CONSULTANT LATEST ALLOCATION | CONSULTANT NEW ALLOCATION | CONSULTANT EXPENDITURE PREVIOUS YEARS | CONSULTANT EXPENDITURE CURRENT YEAR | CONSULTANT CASH FLOW AMOUNT | CONSULTANT CASH FLOW YEAR 2017/2018 | CONSULTANT CASH FLOW YEAR 1 | CONSULTANT CASH FLOW YEAR 2 | CONSULTANT CASH FLOW YEAR 3 | CONSULTANT CASH FLOW YEAR 4 | KAM MANAGER | PROJECT MANAGER | RAMP | ENDOWMENT PROPERTY | LITIGATION IND
2017 | DEFENCE | R | CAPITAL WORKS | PACE | FREESTATE | BLOEMFONTEIN | DEFAULT | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,,MOBILISATION CENTRE,ERECTION OF PROTECTION WALLS AND EXTENDED ROOFING | 048244 | 048244 | 85RAFS | DEFENCE: CAPITAL: LEDGER: FS | 7 | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2011/12/21 | 2014/03/06 | BL11050 | 8 | 319911.26 | 0 | 0 | 0 | 2959555.5 | 0 | 4534060.44 | 1574505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PERUMAL V | MARITE L | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | FREESTATE | BLOEMFONTEIN | DEFAULT | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,,MOBILISATION CENTRE,UPGRADING OF BUILDINGS 1175, 1176, 1178, 1179, 1181, 1182, 1184 & 1185 | 048245 | 048245 | 85RAFS | DEFENCE: CAPITAL: LEDGER: FS | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/12/19 | 2017/12/08 | BL16/049 | 8 | 55930.1 | 0 | 0 | 2483772 | 1239779.29 | 573842.83 | 3723552.29 | 2483772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PERUMAL V | MARITE L | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | FREESTATE | BLOEMFONTEIN | DEFAULT | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,,BLOEMSPRUIT AIR FORCE BASE,UPGRADE AND REFURBISHMENT OF SICK BAY COMPLEX | 052154 | 052154 | 85RAFS | DEFENCE: CAPITAL: LEDGER: FS | 5B | 1 - COMMITMENTS | 004 | AIR FORCE BASE | 03 | REFURB & REHAB CAPITAL | 2015/02/06 | 2016/10/03 | 049920 | 17 | 1050968.75 | 0 | 0 | 7923339 | 9799511.08 | 983428.36 | 17722850.53 | 7923339 | 0 | 0 | 0 | 0 | 3390183.44 | 0 | 0 | 216992 | 2260999.62 | 0 | 3390183.44 | 216992.09 | 0 | 0 | 0 | 0 | DE KLERK CCE | MARITE L | N | N | Y
2017 | DEFENCE | R | CAPITAL WORKS | PACE | FREESTATE | BLOEMFONTEIN | DEFAULT | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,,3 MILITARY HOSPITAL,UPGRADING AND EXTENSIONS TO HOSPITAL: CONSULTANTS PAYMENT ON LY | 045310 | 045267 | 85RAFS | DEFENCE: CAPITAL: LEDGER: FS | 4 | 3 - WORKS IN PROGRES | 041 | SPECIALISED HOSPITAL (DEFENCE) | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/12 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1.89 | 1 | 0 | 0 | 0 | 0 | 22104407.12 | 0 | 0 | 3600000 | 18504407.12 | 0 | 22104407.12 | 3600000 | 0 | 0 | 0 | 0 | BORAINE E F | LABUSCHAGNE JH | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | FREESTATE | BLOEMFONTEIN | DEFAULT | MANGAUNG METRO MUNICIPALITY | BLOEMSPRUIT,,BLOEMSPRUIT AIR FORCE BASE,UPGRADING OF WATER RESERVOIR | 049890 | 049890 | 85RAFS | DEFENCE: CAPITAL: LEDGER: FS | 4 | 3 - WORKS IN PROGRES | 004 | AIR FORCE BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/08/15 |  |  | 18 | 0 | 755579 | 755579 | 134443 | 0 | 0 | 3440058.36 | 134443 | 2246071 | 1059543 | 0 | 0 | 755100.01 | 200000 | 200000 | 200000 | 0 | 0 | 755100.01 | 200000 | 100000 | 0 | 0 | 0 | NETSHIONGOLWE NS | LABUSCHAGNE JH | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | FREESTATE | BLOEMFONTEIN | DEFAULT | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,TEMPE,,1 SA TANK REGIMENT: UPGRADING OF INFRASTRUCTURE/FACILITY AND REPLACEMENT OF KITCHEN EQUIPMENT | 053666 | 053666 | 85RAFS | DEFENCE: CAPITAL: LEDGER: FS | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/08/15 |  |  | 12 | 0 | 615374 | 615374 | 0 | 0 | 0 | 2637502.54 | 168088 | 2205664 | 263750 | 0 | 0 | 0 | 249783 | 249783 | 300011 | 0 | 0 | 411514 | 300010.51 | 111503.49 | 0 | 0 | 0 | DE KLERK CCE | LABUSCHAGNE JH | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | FREESTATE | BLOEMFONTEIN | DEFAULT | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,DE BRUG,MOBILISATION CENTRE,AREA SUPPORT BASE: UPGRADING OF INFRASTRUCTURE/FACILITY AND REPLACEMENT OF EQUIPMENT | 053667 | 053667 | 85RAFS | DEFENCE: CAPITAL: LEDGER: FS | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/08/15 |  |  | 6 | 0 | 238577 | 238577 | 0 | 0 | 0 | 2780191.39 | 447528 | 2332663 | 0 | 0 | 0 | 0 | 102841 | 102841 | 296559 | 0 | 0 | 433776.9 | 296559.19 | 87151.05 | 50066.66 | 0 | 0 | DE KLERK CCE | LABUSCHAGNE JH | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,,YSTERPLAAT AIR FORCE BASE,REPAIR AND RENOVATIONS FOR VIP AIRCREW AND PILOT FACILITIES | 050777 | 050777 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 7 | 1 - COMMITMENTS | 004 | AIR FORCE BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2014/03/27 | 2015/09/07 | 1003/13 | 7 | 0 | 0 | 0 | 0 | 8041392.42 | 0 | 8055551.91 | 14159 | 0 | 0 | 0 | 0 | 1561200 | 0 | 0 | 237583 | 1323616.62 | 0 | 1561200 | 237583.38 | 0 | 0 | 0 | 0 | LE ROUX R | NAUDE AL | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,SALAMANDER BOAT PARK: REPLACEMENT OF BREAKWATER | 052017 | 052017 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 6A | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/07/27 | 2017/05/25 | 1043/15 | 7 | 770598.85 | 17227302 | 17227302 | 14436021 | 11927897.75 | 4513955.34 | 26363919.37 | 14436021 | 0 | 0 | 0 | 0 | 2555400 | 320000 | 320000 | 672151 | 1883248.89 | 109099.58 | 2555400 | 672151.1 | 0.01 | 0 | 0 | 0 | LE ROUX R | TALJAARD M | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | SIMONSTOWN,,NAVAL BASE,EAST YARD: UPGRADING OF WATER DISTRIBUTION SYSTEM | 053336 | 053336 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 6A | 1 - COMMITMENTS | 049 | WATER SUPPLY/RETICUL | 03 | REFURB & REHAB CAPITAL | 2015/09/10 | 2017/04/28 | 1014/15 | 18 | 0 | 6000000 | 6000000 | 6481923 | 40661024.93 | 5231403.03 | 47142948.28 | 6481923 | 0 | 0 | 0 | 0 | 1975976 | 280000 | 280000 | 179854 | 1723807.49 | 129855.27 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | MONG B | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,RE-SURFACING OF DONKERGAT ROAD | 052455 | 052455 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 5 | 2 - TENDER STAGE | 002 | ACCESS ROAD TAR | 01 | MAINTENANCE & REPAIR CURRENT | 2017/03/31 |  | 1019/16 | 7 | 0 | 17879891 | 17879891 | 13009539 | 0 | 0 | 15229060.28 | 12420517 | 2808543 | 0 | 0 | 0 | 2137200 | 890016 | 890016 | 1165307 | 904730.14 | 0 | 2137200 | 1162827.26 | 69642.6 | 0 | 0 | 0 | LE ROUX R | TALJAARD M | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,YOUNGSFIELD,AIR FORCE BASE,UPGRADING OF FINANCE ACCOUNTING SERVICE CENTRE | 048268 | 048268 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4B | 2 - TENDER STAGE | 029 | OFFICE BUILDINGS | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/19 |  | 1032/16 | 6 | 0 | 0 | 0 | 1140716 | 0 | 0 | 1140716.9 | 1004970 | 135746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PERUMAL V | HESEWU M | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,WYNBERG,2 MILITARY HOSPITAL,UPGRADE OF FINANCE AND ACCOUNTING SATELITE OFFICE | 048269 | 048268 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4B | 2 - TENDER STAGE | 029 | OFFICE BUILDINGS | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/19 |  | 1034/16 | 6 | 0 | 0 | 0 | 1311321 | 0 | 0 | 1311321.09 | 1155272 | 156048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | HESEWU M | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,YSTERPLAAT,AIR FORCE BASE,UPGRADE OF FINANCE ACCOUNTING SATELITE OFFICE | 048270 | 048270 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4B | 2 - TENDER STAGE | 029 | OFFICE BUILDINGS | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/19 |  | 1033/16 | 6 | 0 | 0 | 0 | 765030 | 0 | 0 | 765030.41 | 673991 | 91039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PERUMAL V | HESEWU M | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | EERSTE RIVER,,9 S A INFANTRY BATALION,UPGRADE OF FINANCE ACCOUNTING SATELITE OFFICE | 048272 | 048272 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4B | 2 - TENDER STAGE | 029 | OFFICE BUILDINGS | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/19 |  | 1030/16 | 6 | 0 | 0 | 0 | 715244 | 0 | 0 | 715243.73 | 630129 | 85114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PERUMAL V | HESEWU M | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,WYNBERG,MILITARY BASE,SAMHU: AMHU WC: REPLACEMENT OF SECURITY FENCE ATMAIN ENTRANCE AS WELL AS CANOPY AND GUARD HOUSE | 052547 | 052547 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4A | 2 - TENDER STAGE | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/07/29 |  | 1050/15 | 10 | 0 | 8000000 | 8000000 | 1933280 | 0 | 0 | 17082086 | 1933280 | 15148805 | 0 | 0 | 0 | 839170.01 | 380000 | 380000 | 8807 | 516498.17 | 0 | 839170.01 | 8806.59 | 0 | 0 | 0 | 0 | LE ROUX R | SPRINGFIELD N.C | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | EERSTE RIVER,,9 S A INFANTRY BATALION,UPGRADING OF KITCHEN AND REPLACEMENT OF KITCHEN EQUIPMENT | 053739 | 053739 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4A | 2 - TENDER STAGE | 061 | MISCELLANEOUS STRUCTURES | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/08/28 |  |  | 6 | 0 | 2500000 | 2500000 | 289744 | 0 | 0 | 2500000 | 289744 | 2210256 | 0 | 0 | 0 | 772620.53 | 100000 | 100000 | 163303 | 21158.4 | 0 | 772620.53 | 163302.72 | 0 | 0 | 0 | 0 | LE ROUX R | SPRINGFIELD N.C | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,LANGEBAAN AND DONKERGAT: UPGRADING OF MESS FACILITIES | 052539 | 052539 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/11/24 |  |  | 9 | 0 | 6000000 | 6000000 | 0 | 0 | 0 | 16686925.72 | 0 | 15018233 | 1668692 | 0 | 0 | 414499.06 | 280000 | 280000 | 153355 | 241221.1 | 0 | 414499.06 | 153354.88 | 5974.86 | 0 | 0 | 0 | LE ROUX R | NAUDE AL | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | SALDANHA,,MILITARY BASE,CONSTRUCTION OF SICK BAY FACILITY | 052785 | 052785 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2018/05/15 |  | 1042/15 | 18 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 61276770.48 | 0 | 8184125 | 44961512 | 8131133 | 0 | 4515100 | 1200000 | 1200000 | 872587 | 1408008.5 | 0 | 4515100 | 1362746.5 | 470706.54 | 861867.78 | 411770.68 | 0 | LE ROUX R | TALJAARD M | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,WYNBERG,,AREA SUPPORT BASE WESTERN CAPE: NCO MESS: UPGRADING OF KITCH EN AND REPLACEMENT OF KITCHEN EQUIPMENT | 053695 | 053695 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/09/29 |  |  | 4 | 0 | 2000000 | 2000000 | 145371 | 0 | 0 | 3139058.37 | 145371 | 2993686 | 0 | 0 | 0 | 630252.08 | 155508 | 155508 | 155508 | 85736.05 | 0 | 630252.08 | 155508.41 | 0 | 0 | 0 | 0 | LE ROUX R | SPRINGFIELD N.C | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,WYNBERG,,AREA SUPPORT BASE WESTERN CAPE: OFFICERS MESS: UPGRADING OF KITCHEN EQUIPMENT | 053696 | 053696 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/09/29 |  |  | 4 | 0 | 2000000 | 2000000 | 145371 | 0 | 0 | 3139058.37 | 145371 | 2993686 | 0 | 0 | 0 | 709958.1 | 184865 | 184865 | 184865 | 28026.14 | 6091.68 | 709958.1 | 184864.5 | 0 | 0 | 0 | 0 | LE ROUX R | SPRINGFIELD N.C | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | OUDTSHOORN LOCAL MUNICIPALITY | OUDTSHOORN,,INFANTRY SCHOOL,UPGRADING OF KITCHEN AND REPLACEMENT OF KITCHEN EQUIPMENT | 053738 | 053738 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 061 | MISCELLANEOUS STRUCTURES | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/09/08 |  |  | 18 | 0 | 6500000 | 6500000 | 1048805 | 0 | 0 | 47035000 | 1048805 | 28515515 | 17470680 | 0 | 0 | 323026.41 | 250000 | 250000 | 373989 | 157034.92 | 123989.52 | 323026.41 | 153026.41 | 0 | 0 | 0 | 0 | LE ROUX R | MONG B | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,HEAD QUARTERS: ERECTION OF SECURITY FENCE | 054249 | 054249 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/09/09 |  |  | 3 | 0 | 800000 | 800000 | 95486 | 0 | 0 | 578835.36 | 95486 | 483348 | 0 | 0 | 0 | 0 | 100000 | 100000 | 92500 | 0 | 0 | 92500 | 92500 | 0 | 0 | 0 | 0 | LE ROUX R | SPRINGFIELD N.C | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | GOODWOOD,,WINGFIELD MILITARY BASE,REPLACEMENT OF SECURITY FENCE | 054254 | 054254 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/07/21 |  |  | 12 | 0 | 16000000 | 16000000 | 4609267 | 0 | 0 | 45798820.95 | 4609267 | 36609671 | 4579882 | 0 | 0 | 682398.37 | 360000 | 360000 | 762901 | 104702.95 | 15986.84 | 682398.37 | 447541.11 | 30154.31 | 0 | 0 | 0 | LE ROUX R | KRIEL JP | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,MAHONIA: DONKERGAT: REPLACE EXISTING SECURITY FENCE WITH PAL ISADE FENCE | 054499 | 054499 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/08/18 |  |  | 3 | 0 | 3041011 | 3041011 | 1010000 | 0 | 0 | 3120539.49 | 1001155 | 2119383 | 0 | 0 | 0 | 109440 | 80000 | 80000 | 160000 | 39107.05 | 0 | 109440 | 68203.99 | 2128.96 | 0 | 0 | 0 | LE ROUX R | MONG B | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,DONKERGAT: AMMUNITION STORES: ERECTION OF SECURITY FENCE | 054515 | 054515 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/08/18 |  |  | 6 | 0 | 542200 | 542200 | 703074 | 0 | 0 | 4686112 | 703074 | 3983037 | 0 | 0 | 0 | 0 | 100000 | 100000 | 95000 | 0 | 0 | 4600000 | 4418821.7 | 181178.3 | 0 | 0 | 0 | LE ROUX R | MONG B | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,WYNBERG,2 MILITARY HOSPITAL,INSTALLATION OF HIGH LEVEL SECURITY THERMAL AND RADAR PERIME TER INTRUSION MANAGEMENT SYSTEM | 054591 | 054591 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/11/30 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 9828596.86 | 0 | 7599611 | 2228985 | 0 | 0 | 0 | 330996 | 330996 | 1575762 | 0 | 0 | 1664300 | 1575762.22 | 88537.78 | 0 | 0 | 0 | LE ROUX R | MONG B | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,AIR FORCE BASE,AIR TRAFFIC CONTROL TOWER: REPLACEMENT OF AIR-CONDITIONING S YSTEM | 054892 | 054892 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 004 | AIR FORCE BASE | 05 | NEW CONSTRUCTION | 2017/08/11 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2644524.99 | 1009017 | 1635507 | 0 | 0 | 0 | 0 | 129972 | 129972 | 23000 | 0 | 0 | 462500 | 458535.44 | 3964.56 | 0 | 0 | 0 | LE ROUX R | NAUDE AL | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | SIMONSTOWN,,NAVAL BASE,MARITIME WARFARE BUILDING:REPLACEMENT OF AIR-CONDITIONING S YSTEM | 054893 | 054893 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 028 | NAVAL BASE | 05 | NEW CONSTRUCTION | 2017/09/29 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2654153.12 | 162186 | 2491966 | 0 | 0 | 0 | 0 | 129972 | 129972 | 23000 | 0 | 0 | 462500 | 340106.59 | 122393.41 | 0 | 0 | 0 | LE ROUX R | NAUDE AL | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,DONKERGAT TRAINING AREA: UPGRADE OF HIGH VOLTAGE ELECTRICITY SUPPLY | 054906 | 054906 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 4 | 3 - WORKS IN PROGRES | 062 | TRAINING FACILITIES | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/07/28 |  |  | 6 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 2623351.54 | 616346 | 2007005 | 0 | 0 | 0 | 363692.19 | 350000 | 350000 | 263948 | 0 | 0 | 363692.19 | 263948.52 | 94460.92 | 5282.75 | 0 | 0 | LE ROUX R | KRIEL JP | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,DONKERGAT: DOG KENNELS: REPLACE EXISTING SECURITY FENCE WITH NEW PALISADE FENCE | 054573 | 054573 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 3C | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/30 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 219584.43 | 178217 | 41366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37000 | 35151.3 | 1848.7 | 0 | 0 | 0 | LE ROUX R |  | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | SALDANHA,,MILITARY ACADEMY,REPLACEMENT OF FIRE ALARM SYSTEM | 055095 | 055095 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 3B | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2018/02/11 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1043354.14 | 0 | 939018 | 104335 | 0 | 0 | 0 | 0 | 0 | 101750 | 0 | 0 | 185000 | 101750 | 56906.3 | 22790.19 | 3553.51 | 0 | LE ROUX R |  | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | WESTERN CAPE | CAPE TOWN | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,SALAMANDER COMPLEX: DONKERGAT: ERECTION OF SECURITY FENCE | 055096 | 055096 | 85RAWC | DEFENCE: CAPITAL: LEDGER: WC | 3B | 3 - WORKS IN PROGRES | 013 | FENCE | 05 | NEW CONSTRUCTION | 2017/11/30 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 511250 | 0 | 511250 | 0 | 0 | 0 | 0 | 0 | 0 | 56883 | 0 | 0 | 92500 | 56883.48 | 26906.93 | 8655.9 | 53.69 | 0 | LE ROUX R |  | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | KWAZULU-NATAL | DURBAN | DEFAULT | ETHEKWINI METROPOLITAN MUNICIPALITY | DURBAN,,,ASB: SECURITY INSTALLATION: QUARTERS: MAISONETTE'S ON BLUFF & ESSENHURST ESTATE: SECURITY GATES, BURGLAR PROOFING & LIGH TING | 046330 | 046330 | 85RAKZN | DEFENCE: CAPITAL: LEDGER: KZN | 7 | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2012/02/03 | 2012/07/02 | D11/1115 | 4 | 16471.79 | 0 | 0 | 0 | 2077660.62 | 0 | 2204999.2 | 0 | 0 | 0 | 127340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOUWER M | RINDEL DJ | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | KWAZULU-NATAL | DURBAN | DEFAULT | MTUBATUBA LOCAL MUNICIPALITY | MTUBATUBA,,121 BATTALION,REPLACEMENT OF KITCHEN EQUIPMENT | 049408 | 049408 | 85RAKZN | DEFENCE: CAPITAL: LEDGER: KZN | 7 | 1 - COMMITMENTS | 022 | MILITARY BASE | 01 | MAINTENANCE & REPAIR CURRENT | 2014/04/01 | 2015/03/17 | D12/8/01 | 12 | 152051.58 | 0 | 0 | 290841 | 17160541.08 | 0 | 17451381.7 | 290841 | 0 | 0 | 0 | 0 | 5322595.54 | 0 | 0 | 0 | 4515679.46 | 0 | 5322595.54 | 520732.99 | 0 | 0 | 0 | 0 | LE ROUX R | KROUTZ CC | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | KWAZULU-NATAL | DURBAN | DEFAULT | ETHEKWINI METROPOLITAN MUNICIPALITY | DURBAN,SALISBURY ISLAND,,SA NAVY: REFURBISHMENT OF MAIN KITCHEN | 052564 | 052564 | 85RAKZN | DEFENCE: CAPITAL: LEDGER: KZN | 6A | 1 - COMMITMENTS | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2015/01/21 | 2017/05/26 | DB141001 | 12 | 3068365.87 | 1500000 | 1500000 | 8000000 | 31366884.23 | 114549.62 | 39970139.07 | 8000000 | 603256 | 0 | 0 | 0 | 34138509.38 | 2000000 | 2000000 | 2000000 | 9787354.41 | 1373202.91 | 34138509.38 | 1078210.3 | 0 | 0 | 0 | 0 | LE ROUX R | GAXELA TO | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | KWAZULU-NATAL | DURBAN | DEFAULT | MTUBATUBA LOCAL MUNICIPALITY | MTUBATUBA,,121 BATTALION,UPGRADING OF SAFI BUILDING FOR USE BY DEFENCE LEGAL SERVICES DIVISION | 049135 | 049135 | 85RAKZN | DEFENCE: CAPITAL: LEDGER: KZN | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2018/10/30 |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 6454452.63 | 0 | 0 | 5809007 | 645445 | 0 | 650000 | 0 | 0 | 0 | 440834.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DE KLERK CCE | KROUTZ CC | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | KWAZULU-NATAL | DURBAN | DEFAULT | ETHEKWINI METROPOLITAN MUNICIPALITY | DURBAN,SALISBURY ISLAND,,UPGRADING OF CRITICAL ACCOMMODATION FACILITIES | 053350 | 053350 | 85RAKZN | DEFENCE: CAPITAL: LEDGER: KZN | 4 | 3 - WORKS IN PROGRES | 028 | NAVAL BASE | 03 | REFURB & REHAB CAPITAL | 2018/02/28 |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 52773329.24 | 0 | 8369697 | 31051980 | 13351651 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 7400000 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | MAJOZI S | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | KWAZULU-NATAL | DURBAN | DEFAULT | ETHEKWINI METROPOLITAN MUNICIPALITY | UMHLOTI,,,SA ARMY SIGNAL FORMATION: UPGRADING OF KITCHEN AND REPLACEME NT OF KITCHEN EQUIPMENT | 053701 | 053701 | 85RAKZN | DEFENCE: CAPITAL: LEDGER: KZN | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2018/04/30 |  |  | 12 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 2623195.04 | 0 | 714096 | 1909098 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 0 | 0 | 370000 | 370000 | 0 | 0 | 0 | 0 | LE ROUX R | KROUTZ CC | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | KWAZULU-NATAL | DURBAN | DEFAULT | ETHEKWINI METROPOLITAN MUNICIPALITY | DURBAN,BLUFF,,AREA SUPPORT BASE: KWAZULU-NATAL: UPGRADING OF KITCHEN AND R EPLACEMENT OF KITCHEN EQUIPMENT | 053704 | 053704 | 85RAKZN | DEFENCE: CAPITAL: LEDGER: KZN | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/10/05 |  |  | 4 | 0 | 3023608 | 3023608 | 1500000 | 0 | 0 | 3150445 | 1500000 | 1650445 | 0 | 0 | 0 | 0 | 0 | 0 | 462500 | 0 | 0 | 462500 | 462500 | 0 | 0 | 0 | 0 | LE ROUX R | GAXELA TO | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | KWAZULU-NATAL | DURBAN | DEFAULT | EMNAMBITHI/LADYSMITH LOCAL MUNICIPALITY | LADYSMITH (KZN),,5 S.A.I. BATTALION,UPGRADING OF KITCHEN AND REPLACEMENT OF KITCHEN EQUIPMENT | 053740 | 053740 | 85RAKZN | DEFENCE: CAPITAL: LEDGER: KZN | 4 | 3 - WORKS IN PROGRES | 061 | MISCELLANEOUS STRUCTURES | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/10/10 |  |  | 18 | 0 | 3000000 | 3000000 | 100000 | 0 | 0 | 22075535.84 | 101545 | 11831165 | 10142825 | 0 | 0 | 0 | 1000000 | 1000000 | 1000000 | 0 | 0 | 3420000 | 3186568.7 | 233431.3 | 0 | 0 | 0 | LE ROUX R | GOVENDER S | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | JOHANNESBURG | DEFAULT | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | JOHANNESBURG,KENSINGTON,MILITARY BASE,UPGRADING OF POWER SUPPLY AT 46 SA ARMY BRIGADE | 048241 | 048241 | 85RAGTJ | DEFENCE: CAPITAL: LEDGER: GTJ | 7 | 1 - COMMITMENTS | 012 | ELECTRIC SUPPLY/RETICULATION | 02 | UPGRADE & ADDITIONS CAPITAL | 2012/07/19 | 2013/09/27 | JHB11/42 | 12 | 0 | 0 | 0 | 0 | 3458441.84 | 0 | 3653083.21 | 194641 | 0 | 0 | 0 | 0 | 859282.83 | 0 | 0 | 0 | 859282.83 | 0 | 859282.83 | 0 | 0 | 0 | 0 | 0 | PERUMAL V | NEDZAMBA NA | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | JOHANNESBURG | DEFAULT | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | JOHANNESBURG,,,UPGRADING OF KITCHEN EQUIPMENT,,ASB | 053688 | 053688 | 85RAGTJ | DEFENCE: CAPITAL: LEDGER: GTJ | 6A | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/06/22 | 2017/03/31 | JHB15/34 | 6 | 95559.92 | 214936 | 214936 | 481307 | 1808554.2 | 261273.7 | 2289861 | 481307 | 0 | 0 | 0 | 0 | 300000 | 25000 | 25000 | 234000 | 67124.71 | 0 | 300000 | 207875.29 | 25000 | 0 | 0 | 0 | TAMBANI TP | TLOLANE T | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | JOHANNESBURG | DEFAULT | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | JOHANNESBURG,,,UPGRADING OF KITCHEN EQUIPMENT,,SA ARMY GYMNASIUM. | 053687 | 053687 | 85RAGTJ | DEFENCE: CAPITAL: LEDGER: GTJ | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/30 |  |  | 36 | 0 | 5000000 | 5000000 | 1000000 | 0 | 0 | 7000000 | 1000000 | 4000000 | 1500000 | 500000 | 0 | 0 | 461145 | 461145 | 993885 | 0 | 0 | 1295000 | 993885.04 | 230422.02 | 70692.94 | 0 | 0 | TAMBANI TP | TLOLANE T | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,MILITARY AREA,SAMHS: MILITARY HEALTH TRAINING FORMATION (NURSES COLLEGE): UPGRADING AND REFURBISHMENT : PHASE 2 | 053875 | 053875 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 036 | RESEARCH FACILITIES | 03 | REFURB & REHAB CAPITAL | 2017/09/16 |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 8461402.06 | 63968 | 1463653 | 2939118 | 3039525 | 955137 | 0 | 0 | 0 | 0 | 0 | 0 | 1260000 | 853379.37 | 312200.62 | 94419.25 | 0.76 | 0 | MORARE M L | MATHEKGA L | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,THABA TSWANE,,DEFENCE WORKS FORMATION HEAD QUARTERS: UPGRADING AND INSTALL ATION OF POWER SUPPLY FOR CONTAINERISED OFFICE ACCOMMODATION | 055059 | 055059 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 029 | OFFICE BUILDINGS | 02 | UPGRADE & ADDITIONS CAPITAL | 2018/01/31 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 526854.16 | 107655 | 419199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | NOMBEWU A | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTHERN CAPE | KIMBERLEY | DEFAULT | SIYANDA DISTRICT MUNICIPALITY | POSTMASBURG,,LOHATLA COMBAT SCHOOL,UPGRADE OF FINANCE ACCOUNTING SERVICE CENTRE | 048262 | 048262 | 85RANC | DEFENCE: CAPITAL: LEDGER: NC | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/10/29 |  | CW05/16 | 4 | 0 | 0 | 0 | 322852 | 163492.39 | 0 | 486344.09 | 322852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DE WAAL AC | MOTLHALA L.B | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTHERN CAPE | KIMBERLEY | DEFAULT | FRANCES BAARD DISTRICT MUNICIPALITY | KIMBERLEY,,MILITARY BASE,DISKOBOLOS MILITARY SICK BAY: RESURFACING AND TARRING OF ACC ESS ROAD | 052546 | 052546 | 85RANC | DEFENCE: CAPITAL: LEDGER: NC | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/02/18 | 2017/02/03 | KM29/15 | 9 | 276090.05 | 119519 | 119519 | 1228996 | 2834656.12 | 0 | 4183171.46 | 1228996 | 119519 | 0 | 0 | 0 | 339977.43 | 10000 | 10000 | 140850 | 279150.38 | 0 | 339977.43 | 10000 | 0 | 0 | 0 | 0 | AYSEN G | COSA S | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTHERN CAPE | KIMBERLEY | DEFAULT | SIYANDA DISTRICT MUNICIPALITY | POSTMASBURG,,LOHATLA COMBAT SCHOOL,APPOINTMENT OF PROFESSIONAL TEAM TO INVESTIGATE THE DRILLING OF BOREHOLES AND THE BUILDING OF DAMS/RESERVOIRS | 048821 | 048821 | 85RANC | DEFENCE: CAPITAL: LEDGER: NC | 4 | 3 - WORKS IN PROGRES | 006 | BOREHOLES | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/23 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.47 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DE WAAL AC | MARAIS JP | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTHERN CAPE | KIMBERLEY | DEFAULT | RICHTERSVELD LOCAL MUNICIPALITY | ALEXANDER BAY,,,SA ARMY SIGNAL FORMATION: UPGRADING OF KITCHEN EQUIPMENT | 053699 | 053699 | 85RANC | DEFENCE: CAPITAL: LEDGER: NC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/07/28 |  | KM01/17 | 4 | 0 | 3271175 | 3271175 | 1197864 | 0 | 0 | 3225959.33 | 1181306 | 2044652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | AYSEN G | COSA S | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTHERN CAPE | KIMBERLEY | DEFAULT | FRANCES BAARD DISTRICT MUNICIPALITY | KIMBERLEY,,,HENRY SLEGKAMP: COMBINED MESS: BUILDING 200: UPGRADING OF FA CILITY/INFRASTRUCTURE (KITCHEN) AND REPLACEMENT OF KITCHEN E QUIPMENT | 054769 | 054769 | 85RANC | DEFENCE: CAPITAL: LEDGER: NC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/07/28 |  |  | 12 | 0 | 1847225 | 1847225 | 1799550 | 0 | 0 | 20000000 | 1799550 | 16200450 | 2000000 | 0 | 0 | 329893.59 | 385000 | 385000 | 2500000 | 0 | 0 | 329893.59 | 210000 | 90000 | 29893.59 | 0 | 0 | CHABALALA MP | MARTIN __G.H | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTH WEST | MMABATHO | DEFAULT | SOUTHERN DISTRICT MUNICIPALITY | POTCHEFSTROOM,,,SHAMROCK MESS: UPGRADING OF KITCHEN OF MESS AND KITCHEN KITCHEN EQUIPMENT | 053714 | 053714 | 85RANW | DEFENCE: CAPITAL: LEDGER: NW | 4B | 2 - TENDER STAGE | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/28 |  | MB16/060 | 11 | 0 | 12761558 | 12761558 | 6411579 | 0 | 0 | 17453199.04 | 6411579 | 11041619 | 0 | 0 | 0 | 2989668 | 411184 | 411184 | 1440000 | 852400.24 | 0 | 2989668 | 1440000 | 676267.76 | 21000 | 0 | 0 | MORARE M L | THOBEJANE KE | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTH WEST | MMABATHO | DEFAULT | SOUTHERN DISTRICT MUNICIPALITY | POTCHEFSTROOM,,ARTILLERY SCHOOL,WATER SUPPLY | 048239 | 048239 | 85RANW | DEFENCE: CAPITAL: LEDGER: NW | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/12 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 123631.43 | 59687 | 63944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14800 | 14800 | 0 | 0 | 0 | 0 | MORARE M L | MAHLANGU K Z | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTH WEST | MMABATHO | DEFAULT | NGAKA MODIRI MOLEMA DISTRICT MUNICIPALITY | ZEERUST,,2 S.A.I. BATTALION,ASSESMENT AND COSTING OF KITCHEN EQUIPMENT: DECENTRALISED PROJECT | 049409 | 049409 | 85RANW | DEFENCE: CAPITAL: LEDGER: NW | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2020/02/28 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 1.35 | 0 | 0 | 0 | 1 | 0 | 1650000 | 0 | 0 | 674188 | 975811.68 | 496693.54 | 1650000 | 674188.32 | 0 | 0 | 0 | 0 | MORARE M L | NKOE B.P | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | NORTH WEST | MMABATHO | DEFAULT | SOUTHERN DISTRICT MUNICIPALITY | POTCHEFSTROOM,,DEFENCE COMPLEX,ASB:CONSTAND VILJOEN MESS: UPGRADING OF KITCHEN, INSTALLATIO N OF KITCHEN EQUIPMENT, POWER GENERATOR AND REFURBISHMENT OF COLD AND FREEZER ROOM | 053715 | 053715 | 85RANW | DEFENCE: CAPITAL: LEDGER: NW | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/08/25 |  |  | 11 | 0 | 2086531 | 2086531 | 597363 | 0 | 0 | 6570890 | 597363 | 5644991 | 328536 | 0 | 0 | 603123.74 | 60000 | 60000 | 210000 | 117698.75 | 0 | 603123.74 | 210000 | 85000 | 18123.74 | 0 | 0 | MORARE M L | LWATE MEG | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | MPUMALANGA | NELSPRUIT | DEFAULT | EHLANZENI DISTRICT MUNICIPALITY | MIDDELBURG (MPU),,4 S A I BATALION,AREA MILITARY HEALTH UNIT: UPGRADING OF BUILDINGS AND CONSTR UCTION OF NEW SICK BAY FAILITY | 045457 | 045457 | 85RAMPU | DEFENCE: CAPITAL: LEDGER: MPU | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2015/12/01 | 2017/11/30 | NST15051 | 24 | 1679340.53 | 15000000 | 15000000 | 25821556 | 12621310.11 | 4608723.73 | 48219938.3 | 25821556 | 9777070 | 0 | 0 | 0 | 7360345.49 | 710411 | 710411 | 1117070 | 5637978.03 | 169192.57 | 7360345.49 | 1117069.65 | 0 | 0 | 0 | 0 | MTHEMBI J.M | LETHUBA ML | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | MPUMALANGA | NELSPRUIT | DEFAULT | GERT SIBANDE DISTRICT MUNICIPALITY | ERMELO,,CAMDEN,AREA SUPPORT BASE: UPGRADING OF KITCHEN AND ISTALLATION OF K ITCHEN EQUIPMENT | 053663 | 053663 | 85RAMPU | DEFENCE: CAPITAL: LEDGER: MPU | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/11/10 | 2017/11/09 | 16/032 | 12 | 176417.61 | 1578627 | 1578627 | 1063401 | 1447785.27 | 362259.35 | 2572686.96 | 1063401 | 61500 | 0 | 0 | 0 | 1129079.3 | 100000 | 100000 | 158057 | 726777.16 | 0 | 1129079.3 | 158057.03 | 36000 | 0 | 0 | 0 | MTHEMBI J.M | KADIAKA PM | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | LIMPOPO | POLOKWANE | DEFAULT | BA-PHALABORWA LOCAL MUNICIPALITY | PHALABORWA,,,5 SPECIAL FORCES REGIMENT: REPLACEMENT OF FUEL TANKS AND PUM PS WITH BIGGER CAPACITY | 050662 | 050662 | 85RANP | DEFENCE: CAPITAL: LEDGER: NP | 8 | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2015/03/30 | 2016/04/06 | PLK14/93 | 6 | 0 | 0 | 0 | 221179 | 2402021.14 | 221179.34 | 2623200.48 | 221179 | 0 | 0 | 0 | 0 | 543631.85 | 0 | 0 | 43783 | 499848.72 | 43783.13 | 543631.85 | 43783.13 | 0 | 0 | 0 | 0 | NCAPAYI N | TSHIDAVHU FJ | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | LIMPOPO | POLOKWANE | DEFAULT | VHEMBE DISTRICT MUNICIPALITY | LOUIS TRICHARDT,,,UPGRADING OF KITCHEN EQOUIPMEN,,,523 SIGNAL SQN | 053690 | 053690 | 85RANP | DEFENCE: CAPITAL: LEDGER: NP | 7 | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2015/09/04 | 2016/05/25 | PLK15/20 | 6 | 129513.84 | 129514 | 129514 | 129514 | 2805269.84 | 0 | 2934783 | 129514 | 0 | 0 | 0 | 0 | 443449.11 | 0 | 0 | 26599 | 416849.95 | 0 | 443449.11 | 26599.16 | 0 | 0 | 0 | 0 | TAMBANI TP | BUITENDACH FWC | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | LIMPOPO | POLOKWANE | DEFAULT | CAPRICON DISTRICT MUNICIPALITY | VUWANI,,,UPGRADING OF KITCHEN AND EQUIPMENT AT 15 SAI MESS | 053757 | 053757 | 85RANP | DEFENCE: CAPITAL: LEDGER: NP | 4B | 2 - TENDER STAGE | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/08/08 |  | PLK17/37 | 9 | 0 | 5000000 | 5000000 | 5565690 | 0 | 0 | 7764966.36 | 5565690 | 2199276 | 0 | 0 | 0 | 1242316.03 | 440000 | 440000 | 480442 | 616814.93 | 0 | 1242316.03 | 480442.13 | 0 | 0 | 0 | 0 | NCAPAYI N | BUITENDACH FWC | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | LIMPOPO | POLOKWANE | DEFAULT | BA-PHALABORWA LOCAL MUNICIPALITY | PHALABORWA,,7 S A I MILITARY BASE,SUPPLY AND REPLACEMENT OF KITCHEN EQUIPMENT AND REPAIRS TO K ITCHEN BUILDING | 050651 | 050651 | 85RANP | DEFENCE: CAPITAL: LEDGER: NP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/07/28 |  |  | 12 | 0 | 0 | 0 | 2000000 | 0 | 0 | 15322286 | 2000000 | 8322286 | 5000000 | 0 | 0 | 2758011 | 0 | 0 | 700000 | 141216.67 | 0 | 2758011 | 700000 | 1000000 | 916794.33 | 0 | 0 | NCAPAYI N | MOTIMELE MF | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | LIMPOPO | POLOKWANE | DEFAULT | BA-PHALABORWA LOCAL MUNICIPALITY | PHALABORWA,,,5 SPECIAL FORCE REGIMENT: REPAIR AND RENOVATION OF AQUATIC T RAINING FACILITY | 052105 | 051621 | 85RANP | DEFENCE: CAPITAL: LEDGER: NP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 01 | MAINTENANCE & REPAIR CURRENT | 2017/10/27 |  |  | 12 | 0 | 1100000 | 1100000 | 0 | 0 | 0 | 1265822 | 0 | 1100000 | 165822 | 0 | 0 | 234178 | 64365 | 64365 | 166115 | 0 | 0 | 234178 | 144470.67 | 69969.96 | 19737.37 | 0 | 0 | TAMBANI TP | MAKAMA S.M | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | LIMPOPO | POLOKWANE | DEFAULT | BA-PHALABORWA LOCAL MUNICIPALITY | PHALABORWA,,,UPGRADING OF KITCHEN EQUIPMENT,,,524 SIGNAL SQN | 053691 | 053691 | 85RANP | DEFENCE: CAPITAL: LEDGER: NP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/23 |  |  | 7 | 0 | 2300000 | 2300000 | 1300000 | 0 | 0 | 3326272.63 | 1300000 | 2026272 | 0 | 0 | 0 | 392622.3 | 106817 | 106817 | 106817 | 215805.69 | 0 | 392622.3 | 106816.61 | 70000 | 0 | 0 | 0 | TAMBANI TP | RAGANYA MM | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | LIMPOPO | POLOKWANE | DEFAULT | CAPRICON DISTRICT MUNICIPALITY | POLOKWANE,,,UPGRADING OF KITCHEN EQUIPMENT,,,,ASB JUNIOR RANK,ASB KAREE BASE AND NORTH SIGNAL UNIT | 053692 | 053692 | 85RANP | DEFENCE: CAPITAL: LEDGER: NP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/30 |  |  | 18 | 0 | 10000000 | 10000000 | 100000 | 0 | 0 | 32235390.51 | 100000 | 16000000 | 13900000 | 2235390 | 0 | 5963547.15 | 2151076 | 2151076 | 651077 | 297549.27 | 0 | 5963547.15 | 2151076.64 | 0 | 0 | 0 | 0 | NCAPAYI N | NDLOVU C A | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | LIMPOPO | POLOKWANE | DEFAULT | BA-PHALABORWA LOCAL MUNICIPALITY | PHALABORWA,,,UPGRADING OF KITCHEN EQUIPMENT 5SFR | 053879 | 053879 | 85RANP | DEFENCE: CAPITAL: LEDGER: NP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/23 |  |  | 10 | 0 | 2540307 | 2540307 | 1540307 | 0 | 0 | 4982849.26 | 1540307 | 3442542 | 0 | 0 | 0 | 526078.92 | 149403 | 149403 | 149403 | 286413.64 | 0 | 526078.92 | 149402.69 | 90262.59 | 0 | 0 | 0 | NCAPAYI N | RAGANYA MM | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | EASTERN CAPE | PORT ELIZABETH | DEFAULT | NELSON MANDELA BAY | PORT ELIZABETH,,,AREA MILTARY HEALT UNIT: CONSTRUCTION OF SICK BAY (BASE HOSP ITAL) AND MEDICAL STAFF HOUSING | 052744 | 052744 | 85RAEC | DEFENCE: CAPITAL: LEDGER: EC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/09/29 |  |  | 60 | 0 | 37273927 | 37273927 | 10000000 | 0 | 0 | 664573892 | 10000000 | 95150894 | 131662682 | 156625048 | 154020262 | 37695396 | 5905202 | 5905202 | 7270721 | 13063789.63 | 0 | 37695396 | 7270721 | 2814067 | 2814067 | 4100100 | 2703896 | LE ROUX R | GREYLING EL | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,,NORTHERN MILITARY POLICE HQ: MP OFFICE: SECURITY PROJECTS: P ALISADE FENCE WITH ELECTRIC WIRE ON PERIMETER & UPGRADING OF SECURITY AT THE STORES: CAPITAL WORKS | 046379 | 046379 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 7 | 1 - COMMITMENTS | 029 | OFFICE BUILDINGS | 02 | UPGRADE & ADDITIONS CAPITAL | 2013/10/07 | 2014/06/30 | PT13/022 | 6 | 46220.08 | 0 | 0 | 263454 | 1949562.77 | 0 | 2213017.19 | 263454 | 0 | 0 | 0 | 0 | 419387.07 | 0 | 0 | 202326 | 217061.45 | 0 | 419387.07 | 202325.62 | 0 | 0 | 0 | 0 | GENGAPPEN J | NOMBEWU A | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,WONDERBOOM,ARMY SUPPORT BASE,SIGNAL FORMATION: UPGRADING OF THE MESS AND REPLACEMENT OF KITCHEN EQUIPMENT | 052454 | 052454 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/02/03 | 2018/08/02 | PT16/209 | 18 | 157955.58 | 0 | 0 | 12838793 | 0 | 1620624.24 | 40770151.19 | 12838793 | 25092564 | 2838794 | 0 | 0 | 9492637.62 | 0 | 0 | 700000 | 1377978.93 | 475303.17 | 9492637.62 | 1928075.64 | 633027.44 | 0 | 0 | 0 | GENGAPPEN J | MASHA TS | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,DEFENCE COMPLEX,SA ARMY ENGINEER FMN COMBINED MESS: UPGRADING OF KITCHEN EQUIPMENT | 053713 | 053713 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/01/20 | 2018/01/19 | PT16/040 | 12 | 707523.33 | 14400000 | 14400000 | 14472820 | 2494816.41 | 4764372.93 | 18852931.19 | 14472820 | 1885293 | 0 | 0 | 0 | 4111846.76 | 866508 | 866508 | 1837315 | 1694057.97 | 627809.64 | 4111846.76 | 1837315.28 | 93550.79 | 0 | 0 | 0 | MORARE M L | NOMBEWU A | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,,JSB GARRISON KIEPERSOL OFFICERS MESS: UPGRADING OF KITCHEN EQUIPMENT | 053742 | 053742 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 5B | 1 - COMMITMENTS | 061 | MISCELLANEOUS STRUCTURES | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/03/22 | 2018/03/21 | PT16/045 | 12 | 283463.7 | 12476552 | 12476552 | 12476552 | 0 | 2908337.59 | 14778380.55 | 13247364 | 1531015 | 0 | 0 | 0 | 1864000 | 504000 | 504000 | 1200000 | 1157618.55 | 237563 | 1864000 | 504000 | 0 | 0 | 0 | 0 | MORARE M L | NOMBEWU A | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | GAUTENG | PRETORIA | SA ARMY | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA, WONDERBOOM, SIGNAL SCHOOL, UPGRADING OF POWER SUPPLY | 048240 | 050652 | 85D1GTP | DEFENCE: REC: SA ARMY: GTP | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/07/05 | 2018/07/08 | PT15/102 | 24 | 1655154.4 | 0 | 0 | 15322137 | 12066289.43 | 3613113.37 | 34125000 | 15322137 | 6736573 | 0 | 0 | 0 | 4661510.3 | 0 | 0 | 366151 | 2480464.26 | 238184.65 | 4661510.3 | 366151.03 | 300000 | 0 | 0 | 0 | PERUMAL V | NOMBEWU A | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,,SA ARMY COLLEGE THABA TSHWANE: UPGRADING OF KITCHEN EQUIPMENT | 053747 | 053747 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 5 | 2 - TENDER STAGE | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/27 |  | PT17/012 | 12 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 49774994.59 | 12500000 | 28000000 | 9274994 | 0 | 0 | 14400000 | 3879485 | 3879485 | 3879485 | 2532637.28 | 939339.32 | 14400000 | 3879485.99 | 0 | 0 | 0 | 0 | MORARE M L | MATHEKGA L | N | Y | Y
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,AIR FORCE HEAD QUARTERS,LOFTUS AND BLENNY: REPLACEMENT OF UPS BATTERIES | 055076 | 055076 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 5 | 2 - TENDER STAGE | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/05/19 |  | PTQ17/49 | 2 | 0 | 0 | 0 | 3948567 | 0 | 0 | 3948567.84 | 3948567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 3760540.8 | 2293825.68 | 1107009.99 | 352007.82 | 7697.31 | 0 | LE ROUX R | DITSHEGO T.K | N | N | Y
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,SWARTKOP,DEFENCE COMPLEX,CJOPS/ SPECIAL FORCES HQ: UPGRADING OF THE MAIN GATE ( DECENTRALISED SERVICE) | 052563 | 052563 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/07/14 |  |  | 5 | 0 | 0 | 0 | 3023452 | 0 | 0 | 3023452.22 | 1175344 | 1848108 | 0 | 0 | 0 | 637434.49 | 0 | 0 | 165632 | 133073.44 | 0 | 637434.49 | 165632.22 | 25598.12 | 0 | 0 | 0 | MORARE M L | MASHA TS | N | N | Y
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,,BELMONT HOUSE (CHURCH STREET): REFURBISHMENT FOR USE AS ACCOMODATION | 053352 | 053352 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 028 | NAVAL BASE | 03 | REFURB & REHAB CAPITAL | 2018/03/29 |  |  | 10 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 7000000 | 0 | 3370116 | 3629884 | 0 | 0 | 0 | 800000 | 800000 | 0 | 0 | 0 | 1260000 | 907542.9 | 208728.9 | 143728.2 | 0 | 0 | LE ROUX R | MATHEKGA L | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,DEFENCE COMPLEX,JSB GARRISON NATIONAL CEREMONIAL GUARD MESS: UPGRADING OF KITCHEN EQUIPMENT | 053711 | 053711 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/10/27 |  |  | 11 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 13286328.65 | 0 | 11900681 | 1385646 | 0 | 0 | 4259271.32 | 550000 | 550000 | 1700000 | 465691.51 | 444123.69 | 4259271.32 | 1036156.19 | 163726.09 | 0 | 0 | 0 | MORARE M L | MASHA TS | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,DEFENCE COMPLEX,JSB GARRISON GERBERA OFFR MESS ( THABA-TSHANE) UPGRADING OF KITCHEN EQUIPMENT. | 053716 | 053716 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/10/27 |  |  | 11 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 10795187.48 | 0 | 9669344 | 1125842 | 0 | 0 | 6145348.8 | 500000 | 500000 | 1600000 | 285241.29 | 525294.9 | 6145348.8 | 1542906.76 | 232698.43 | 0 | 0 | 0 | MORARE M L | MASHA TS | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,TECH BASE,MAIN ORDINANCE DEPOT: CONSTRUCTION OF SECURITY FENCE | 054885 | 054885 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/06/12 |  |  | 6 | 0 | 350000 | 350000 | 0 | 0 | 0 | 525053.75 | 253486 | 271567 | 0 | 0 | 0 | 0 | 70000 | 70000 | 70000 | 0 | 0 | 92500 | 76867.08 | 13072.33 | 2560.59 | 0 | 0 | LE ROUX R | NDLOVU C | N | Y | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,,ROOIWAL MILITARY BASE: CONSTRUCTION OF SECURITY FENCE | 054886 | 054886 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/09/01 |  |  | 6 | 0 | 350000 | 350000 | 0 | 0 | 0 | 500000 | 51613 | 448387 | 0 | 0 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 92500 | 76867.08 | 13072.33 | 2560.59 | 0 | 0 | LE ROUX R | MATHEKGA L | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | GAUTENG | PRETORIA | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,THABA TSWANE,SWARTKOP PARK,CONSTRUCTION OF INNER SECURITY PERIMETER FENCE | 054988 | 054988 | 85RAGTP | DEFENCE: CAPITAL: LEDGER: GTP | 4 | 3 - WORKS IN PROGRES | 013 | FENCE | 05 | NEW CONSTRUCTION | 2017/07/23 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2588715.61 | 668374 | 1920341 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 462500 | 334382.32 | 99961.26 | 28156.42 | 0 | 0 | LE ROUX R | NDLOVU C | N | Y | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,SITE CLEARANCE FOR THE CONSTRUCTION OF 20 MARRIED QUARTERS | 046344 | 046344 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 020 | LAND UNDEVELOPED | 05 | NEW CONSTRUCTION | 2018/03/31 |  |  | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1.71 | 0 | 0 | 1 | 0 | 0 | 750664.01 | 0 | 0 | 0 | 750664.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BOUWER M | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,THABA TSWANE,SAMS TRAINING CENTRE,SAMH TRAINING FORMATION CONSTRUCTION OF NEW REQUIREMENTS, RE PAIR, RENOVATION AND UPGRADING OF ADMIN BUILDING | 047845 | 047845 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 020 | LAND UNDEVELOPED | 05 | NEW CONSTRUCTION | 2017/06/30 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.51 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PERUMAL V | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | KWAZULU-NATAL | PROF SERV:TOWN PLANNING | DEFAULT | ETHEKWINI METROPOLITAN MUNICIPALITY | DURBAN,,MILITARY BASE,AREA MEDICAL HEALTH UNIT: CONSTRUCTION OF MILITARY HEALTH CE NTRE: SITE CLEARANCE | 048911 | 048911 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 020 | LAND UNDEVELOPED | 05 | NEW CONSTRUCTION | 2017/12/31 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 1241237.97 | 0 | 0 | 0 | 404096.58 | 0 | 1241237.97 | 200000 | 637141.39 | 0 | 0 | 0 | DE KLERK CCE | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | EASTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | NELSON MANDELA BAY | PORT ELIZABETH,,,AREA SUPPORT BASE EASTERN CAPE: CAPE RECIFE SHOOTING RANGE: ERECTION OF A SECURITY FENCE: SITE CLEARANCE | 053824 | 053824 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 4 - NEW SERVICES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2018/09/30 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | SIMONSTOWN,,SIGNAL SCHOOL,SMHT SATTELITE: CONSTRUCTION OF A NEW LEVEL SECURITY FENCE WITH MAIN GUARD HOUSE EQUIPPED WITH BIO-METRIC ACCESS CONTRO L SYSTEM: SITE CLEARANCE | 053825 | 053825 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/12/31 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,,WYNBERG MILITARY BASE,AMHU WC: CONSTRUCTION OF A NEW MEDIUM LEVEL SECURTY FENCE WI TH MAIN ENTRANCE CONOPY AND GUARD HOUSE EQUIPPED WITH BIO-ME TRIC ACCESS CONTROL AND EARLY WARNING SYSTEM: SITE CLEARAN | 053826 | 053826 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/06/30 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,BOEKENHOUTSKLOOF MILITARY BASE,SA ARMY SUPPORT FORMATION:_SITE CLEARANCE FOR THE CONSTRUCTI ON OF A SECURITY FENCE_: SITE CLEARANCE | 053857 | 053857 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 013 | FENCE | 05 | NEW CONSTRUCTION | 2017/06/30 |  |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396000 | 395994.45 | 5.55 | 0 | 0 | 0 | MORARE M L | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | SIMONSTOWN,,,SA NAVY SIGNAL SCHOOL: REPLACE EXISTING SECURITY FENCE WITH NEW PALISADE FENCE | 053861 | 053861 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 028 | NAVAL BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/12/31 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343459.9 | 343459.9 | 0 | 0 | 0 | 0 | LE ROUX R | BLACKMORE DJ | N | Y | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | SIMONSTOWN,,,SA NAVY: GLENCAIRN SPORTS COMPLEX: REPLACE EXISTING SECURITY FENCE WITH NEW PALISADE FENCE | 053862 | 053862 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 028 | NAVAL BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/12 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421518.98 | 421518.98 | 0 | 0 | 0 | 0 | LE ROUX R | BLACKMORE DJ | N | Y | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,MILITARY BASE,SOUTH AFRICAN DEFENCE INTELLIGENCE (SADIC),AND EDUCATION, DEVELOPMENT AND TRAINING (ETD) (COLLEGE): REQUEST FOR SITE CLEARANCE. | 053864 | 053864 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 4 - NEW SERVICES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2018/12/31 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1276047.6 | 81550 | 81550 | 138700 | 1071360.6 | 0 | 1276047.6 | 204687 | 0 | 0 | 0 | 0 | MORARE M L | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | NORTHERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | FRANCES BAARD DISTRICT MUNICIPALITY | JAN KEMPDORP,,93 AMMUNITION DEPOT,CONSTRUCTION OF A SECURITY WALL AROUND FACILITY: SITE CLEARA NCE | 053868 | 053868 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 013 | FENCE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/12/31 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 1.21 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DE KLERK CCE | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,SALAMANDER COMPLEX (DONKERGAT): REPLACE EXISTING SECURITY FE NCE WITH NEW CONCRETE/PALISADE FENCE: SITE CLEARANCE | 053869 | 053869 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 013 | FENCE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/30 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,DONKERGAT TRAINING COMMANDO: PLACEMENT OF PARK HOME: SITE CL EARANCE | 053889 | 053889 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2017/12/31 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,MILITARY BASE,MURRAY HILL: SPECIAL FORCES SCHOOL: PHASE 2 OF MASTER PLAN: REQUEST FOR SITE CLEARANCE. | 054063 | 054063 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2018/03/31 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1942360.82 | 490200 | 490200 | 1355261 | 587100 | 0 | 1942360.82 | 1355260.82 | 0 | 0 | 0 | 0 | MORARE M L | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | NORTH WEST | PROF SERV:TOWN PLANNING | DEFAULT | MAFIKENG LOCAL MUNICIPALITY | MAHIKENG,,MILITARY BASE,MAFIKENG 10 SAI BN: REPLACEMENT OF LEAKING SEWERAGE SYSTEM: REQUEST FOR SITE CLEARANCE | 054332 | 054332 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 057 | SEWERS | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/12 |  |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 810000 | 807099.25 | 2900.75 | 0 | 0 | 0 | MORARE M L |  | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | ATTERIDGEVILLE,,,WORKS TRAINING SCHOOL | 054793 | 054793 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 4 - NEW SERVICES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2018/12/31 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 5980273.75 | 0 | 0 | 3989724 | 1990549 | 0 | 0 | 500000 | 500000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | BLACKMORE DJ | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,91 AMMUNITION DEPOT,PROJECT SERETO: CONSTRUCTION OF HEAD OFFICE BUILDING FOR SA DEFENCE INTELLIGENCE DIVISION | 054797 | 054797 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 029 | OFFICE BUILDINGS | 05 | NEW CONSTRUCTION | 2018/01/01 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0.1 | 0.06 | 0.02 | 0 | 0 | LE ROUX R |  | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | FREESTATE | PROF SERV:TOWN PLANNING | DEFAULT | FEZILE DABI DISTRICT MUNICIPALITY | KROONSTAD,,ENGINEERS SCHOOL,PROJECT PANTILE: CONSTRUCTION OF VEHICLE FACILITY: SITE CLEA RANCE | 054807 | 054807 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 4 - NEW SERVICES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2018/04/24 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DE KLERK CCE |  | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,UPGRADING OF DONKERGAT AND FLAMINGO JETTIES AND SLIPWAY: SIT E CLEARANCE | 054891 | 054891 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/12 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0.11 | 0 | 0.07 | 0 | 0 | LE ROUX R |  | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | WESTERN CAPE | PROF SERV:TOWN PLANNING | DEFAULT | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,WINGFIELD,,SAS WINGFIELD AND NAVAL STORES DEPOT: UPGRADING OF WATER RET ICULATION SYSTEM | 054895 | 054895 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 028 | NAVAL BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/12 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0.11 | 0 | 0.07 | 0 | 0 | LE ROUX R |  | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | FREESTATE | PROF SERV:TOWN PLANNING | DEFAULT | FEZILE DABI DISTRICT MUNICIPALITY | KROONSTAD,,,BOSSIESPRUIT TRAINING BASE: CONSTRUCTION OF OVERHEAD POWER S UPPLY LINE TO WATER PUMP STATION: SITE CLEARANCE | 054903 | 054903 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 4 - NEW SERVICES | 022 | MILITARY BASE | 05 | NEW CONSTRUCTION | 2018/07/26 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.12 | 0 | 1 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DE KLERK CCE |  | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | PROF SERV:TOWN PLANNING | DEFAULT | EKURHULENI METROPOLITAN MUNICIPALITY | DUNNOTTAR,,,CONSTRUCTION OF VEHICLE FACILITIES: SITE CLEARANCE | 054926 | 054926 | 85RAHPT | DEFENCE: CAPITAL: LEDGER: HPT | 3A | 3 - WORKS IN PROGRES | 030 | PARKING COVER & OPEN | 05 | NEW CONSTRUCTION | 2017/09/06 |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0.18 | 0.11 | 0.02 | 0.05 | 0 | 0 | PERUMAL R |  | N | N | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | SPECIAL & MAJOR PROJECTS | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,MILITARY HOSPITAL,UPGRADING AND REFURBISHMENT OF THE 1ST FLOOR AND RELATED SUPPORT SERVICES FOR THE 1 MILITARY HOSPITAL: PHASE 1 PROJECT | 051627 | 051627 | 85RAHSM | DEFENCE: CAPITAL: LEDGER: HSM | 4 | 3 - WORKS IN PROGRES | 041 | SPECIALISED HOSPITAL (DEFENCE) | 03 | REFURB & REHAB CAPITAL | 2017/09/29 |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 55598000.78 | 404859 | 19308941 | 30324400 | 5559800 | 0 | 13039320 | 50000 | 50000 | 0 | 4267476.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MORARE M L | GERICKE HP | N | Y | N
2017 | DEFENCE | H | CAPITAL WORKS | PACE | GAUTENG | SPECIAL & MAJOR PROJECTS | DEFAULT | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,MILITARY BASE,HERITAGE - SA DEFENCE INTELLIGENCE COLLEGE (SADIC): UPGRADIN G OF INFRAS TRUCTURE: PHASE 1 | 055057 | 055057 | 85RAHSM | DEFENCE: CAPITAL: LEDGER: HSM | 4 | 3 - WORKS IN PROGRES | 061 | MISCELLANEOUS STRUCTURES | 02 | UPGRADE & ADDITIONS CAPITAL | 2018/01/15 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 8956520.8 | 0 | 5440570 | 3515950 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | MANAGA AE | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | EASTERN CAPE | UMTATA | DEFAULT | O R TAMBO DISTRICT MUNICIPALITY | UMTATA,,S A I BATTALION,UPGRADE OF FINANCE ACCOUNTING SATELITE OFFICE | 048275 | 048275 | 85RAUMT | DEFENCE: CAPITAL: LEDGER: UMT | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2011/12/20 | 2012/06/20 | MTHSAIB1 | 6 | 60979.23 | 0 | 0 | 0 | 625646.89 | 0 | 1083031.24 | 457384 | 0 | 0 | 0 | 0 | 852457.78 | 0 | 0 | 0 | 797178.98 | 0 | 852457.78 | 0 | 55278.8 | 0 | 0 | 0 | ZEMBE P.C. | YAKA L.D | N | N | N
2017 | DEFENCE | R | CAPITAL WORKS | PACE | EASTERN CAPE | UMTATA | DEFAULT | ALFRED NZO DISTRICT MUNICIPALITY | MALUTI,,MILITARY BASE,UPGRADING OF WATER RETICULATION SYSTEM | 051781 | 051781 | 85RAUMT | DEFENCE: CAPITAL: LEDGER: UMT | 5 | 2 - TENDER STAGE | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/06/01 |  | MTHMLB16 | 12 | 0 | 32943009 | 32943009 | 500000 | 0 | 0 | 40887723.06 | 500000 | 20000000 | 20387723 | 0 | 0 | 1700000 | 850000 | 850000 | 1555933 | 1390667.7 | 0 | 1700000 | 209332.3 | 100000 | 0 | 0 | 0 | ZEMBE P.C. | YAKA L.D | N | N | N
[10 empty] | 106 | [13 empty] | 10702516.47 | 283366422 | 283366422 | 201899520 | 169912093.31 | 29777063.43 | 1681317349.37 | 208673112 | 483216389 | 355219406 | 192205882 | 154975399 | 216104853.52 | 32565299 | 32565299 | 49521925 | 88613053.31 | 5955513.41 | 229991854.81 | 58396403.53 | 10871852.22 | 5462405.33 | 4523175.95 | 2703896
[24 empty] | CONTRACTOR |  | 283366422 | 201899520 |  |  |  | 208673112
[24 empty] | CONSULTANT |  | 32565299 | 49521925 |  |  |  | 58396403.53
[24 empty] | TOTAL |  | 315931721 | 251421445 |  |  |  | 267069515.53
[29 empty] | 35732576.84 | 11.31%