## WCS20170612
FINANCIAL YEAR | CLIENT DEPT | OFFICE TYPE | CATEGORY TYPE | PROJECT TYPE | PROVINCE | OFFICE | TYPE | MUNICIPALITY | DESCRIPTION | WCS NO | PROJECT NO | CATEGORY CODE | CATEGORY | STATUS | STATUS TYPE | ASSET TYPE | ASSET TYPE DESCRIPTION | INFRA CLASS | INFRA CLASS DESCRIPTION | FINANCIAL TENDER DATE | FIRST DELIVERY DATE | TENDER NO | CONTRACT PERIOD | RETENSION | CONTRACTOR ORIGINAL ALLOCATION | CONTRACTOR LATEST ALLOCATION | CONTRACTOR NEW ALLOCATION | CONTRACTOR EXPENDITURE PREVIOUS YEARS | CONTRACTOR EXPENDITURE CURRENT YEAR | CONTRACTOR CASH FLOW AMOUNT | CONTRACTOR CASH FLOW YEAR 2017/2018 | CONTRACTOR CASH FLOW YEAR 1 | CONTRACTOR CASH FLOW YEAR 2 | CONTRACTOR CASH FLOW YEAR 3 | CONTRACTOR CASH FLOW YEAR 4 | CONSULTANT AUTHORISATION | CONSULTANT ORIGINAL ALLOCATION | CONSULTANT LATEST ALLOCATION | CONSULTANT NEW ALLOCATION | CONSULTANT EXPENDITURE PREVIOUS YEARS | CONSULTANT EXPENDITURE CURRENT YEAR | CONSULTANT CASH FLOW AMOUNT | CONSULTANT CASH FLOW YEAR 2017/2018 | CONSULTANT CASH FLOW YEAR 1 | CONSULTANT CASH FLOW YEAR 2 | CONSULTANT CASH FLOW YEAR 3 | CONSULTANT CASH FLOW YEAR 4 | KAM MANAGER | PROJECT MANAGER | RAMP | ENDOWMENT PROPERTY | LITIGATION IND
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,DE BRUG,MOBILISATION CENTRE,UPGRADE OF THE ELECTRICAL POWER SUPPLY AND ELECTRICAL INFRAS TRUCTURE: REPLACEMENT OF TRANSFORMER | 052039 | 052039 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 7 | 1 - COMMITMENTS | 012 | ELECTRIC SUPPLY/RETICULATION | 03 | REFURB & REHAB CAPITAL | 2014/04/24 | 2015/11/19 | BL13/146 | 24 | 1849920.15 | 0 | 0 | 2890168 | 40069270.44 | 0 | 42959438.43 | 2890168 | 0 | 0 | 0 | 0 | 4947500 | 0 | 0 | 1064327 | 3883172.73 | 0 | 4947500 | 1064327.27 | 0 | 0 | 0 | 0 | DE KLERK CCE | LABUSCHAGNE JH | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,TEMPE,1 PARACHUTE BATTALION,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 033649 | 033434 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 6A | 1 - COMMITMENTS | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2015/03/30 | 2016/12/05 | BL14/095 | 21 | 1050034 | 2660021 | 2660021 | 2660021 | 22743736.46 | 0 | 26254281.97 | 3510546 | 0 | 0 | 0 | 0 | 6987179.58 | 433258 | 433258 | 633258 | 3748758.88 | 0 | 6987179.58 | 433257.85 | 933421.29 | 0 | 0 | 0 | DE KLERK CCE | LABUSCHAGNE JH | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | THABO MOFUTSANYANE DISTRICT MUNICIPALITY | BETHLEHEM,,2 FIELD ENGINEER REGIMENT,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 036117 | 036117 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 6A | 1 - COMMITMENTS | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2014/11/21 | 2017/02/24 | BL14/028 | 26 | 0 | 6711975 | 6711975 | 2217236 | 68652700.69 | 1277215.55 | 70869936.83 | 2217236 | 0 | 0 | 0 | 0 | 18490526.33 | 205988 | 205988 | 801137 | 14103598.94 | 128665.29 | 18490526.33 | 305988.36 | 0 | 0 | 0 | 0 | DE KLERK CCE | LABUSCHAGNE JH | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,,SPECIAL SERVICE BATALION,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 047081 | 047081 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2014/09/22 | 2017/07/20 | BL14/029 | 30 | 2659901.22 | 13781934 | 13781934 | 15697347 | 55276407.38 | 3432918.2 | 70973756.33 | 15697347 | 0 | 0 | 0 | 0 | 12201600 | 205417 | 205417 | 605417 | 9888802.84 | 77943.3 | 12201600 | 205417.42 | 0 | 0 | 0 | 0 | DE KLERK CCE | LABUSCHAGNE JH | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,TEMPE,SCHOOL OF ARMOUR,MAJOR REFURBISHMENT OF TRAINING FACILITIES: BUILDINGS NO 103 0 AND 1045 (REPLACEMENT OF MAIN AUDITORIUM CHILLER), LECTURE ROOMS 1 - 4 AND SAHARA LECTURE ROOM) | 052538 | 052538 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 5B | 1 - COMMITMENTS | 062 | TRAINING FACILITIES | 03 | REFURB & REHAB CAPITAL | 2016/10/18 | 2017/10/17 | BL16/034 | 12 | 378603.09 | 4000000 | 4000000 | 2798821 | 2845341.53 | 1141405.16 | 5644163.1 | 2234404 | 564417 | 0 | 0 | 0 | 1319120 | 60000 | 60000 | 688305 | 612784.7 | 1621.08 | 1319120 | 688304.55 | 15775.91 | 0 | 0 | 0 | DE KLERK CCE | KRAUSE EH | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | FEZILE DABI DISTRICT MUNICIPALITY | KROONSTAD,,SCHOOL OF ENGINEERING,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 036116 | 036116 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 4A | 2 - TENDER STAGE | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/07/21 |  | BL16/030 | 42 | 0 | 19000000 | 19000000 | 3562128 | 0 | 0 | 183033644.37 | 3562128 | 28872605 | 52776122 | 66318434 | 31504354 | 27760315.43 | 3215182 | 3215182 | 3215181 | 13108520.29 | 0 | 27760315.43 | 3215181.25 | 1918772.15 | 2277691.22 | 0 | 0 | DE KLERK CCE | LABUSCHAGNE JH | N | N | Y
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,TEMPE,1 SAI BATTALION,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 033646 | 033646 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/08/28 |  | BL14/085 | 30 | 0 | 1800000 | 1800000 | 0 | 0 | 0 | 86408151.89 | 1332621 | 21840101 | 42907117 | 20328312 | 0 | 7232040.66 | 349853 | 349853 | 27880160 | 5925617.47 | 0 | 7232040.66 | 349853.05 | 249853.05 | 150873.96 | 0.42 | 0 | DE KLERK CCE | SEEMANE K | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,TEMPE,44 PARACHUTE BRIGADE,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 033647 | 033647 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/08/28 |  | BL14/096 | 24 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 79971157.19 | 1668646 | 30880247 | 39425148 | 7997115 | 0 | 6925298.61 | 180788 | 180788 | 29716811 | 6120271.29 | 0 | 6925298.61 | 180788.3 | 0 | 0 | 0 | 0 | DE KLERK CCE | SEEMANE K | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,,BLOEMSPRUIT AIR FORCE BASE,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 052536 | 052536 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 4 | 3 - WORKS IN PROGRES | 004 | AIR FORCE BASE | 03 | REFURB & REHAB CAPITAL | 2018/03/27 |  |  | 72 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 805699625.3 | 0 | 21568257 | 65301551 | 99386272 | 133780621 | 0 | 16000000 | 16000000 | 0 | 0 | 0 | 137303301.85 | 0 | 20595495.28 | 54921320.74 | 10982382.61 | 6862029.2 | DE KLERK CCE | LABUSCHAGNE JH | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | FREESTATE | BLOEMFONTEIN | DOD REFURBISHMENTS | MANGAUNG METRO MUNICIPALITY | BLOEMFONTEIN,TEMPE,,SAMHS: SCHOOL FOR HEALTH TRAINING SATELLITE: MAJOR REFURBISH MENT OF OFFICE/TRAINING ACCOMMODATION, ROAD INFRASTRUCTURE A ND CLASS ROOMS | 052537 | 052537 | 85DRFS | DEFENCE: REC: REFURBISMENT: FS | 4 | 3 - WORKS IN PROGRES | 062 | TRAINING FACILITIES | 03 | REFURB & REHAB CAPITAL | 2017/08/18 |  |  | 24 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 18916928.38 | 491961 | 7513032 | 9020242 | 1891692 | 0 | 0 | 1200000 | 1200000 | 16719911 | 0 | 0 | 3145000 | 2044464.18 | 471101.85 | 629428.36 | 5.61 | 0 | DE KLERK CCE | BARNES JS | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | EERSTE RIVER,,9 S A INFANTRY BATALION,SICK BAY: UPGRADING OF BUILDINGS 1,9,10,11,12,19,20,22,39 AN D 84 | 050316 | 050316 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 7 | 1 - COMMITMENTS | 029 | OFFICE BUILDINGS | 02 | UPGRADE & ADDITIONS CAPITAL | 2013/06/05 | 2014/07/11 | 1011/12 | 9 | 0 | 0 | 0 | 600000 | 14259116.08 | 0 | 16323865.48 | 2064749 | 0 | 0 | 0 | 0 | 3494446.21 | 0 | 0 | 175823 | 3494445.21 | 0 | 3494446.21 | 1 | 0 | 0 | 0 | 0 | LE ROUX R | SPRINGFIELD N.C | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,,THE CASTLE,HERITAGE - REPAIR AND MAINTENANCE: PHASE 2 | 052148 | 052148 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 7 | 1 - COMMITMENTS | 026 | NATIONAL MONUMENT | 01 | MAINTENANCE & REPAIR CURRENT | 2014/12/04 | 2016/10/28 | 1018/14 | 21 | 0 | 7500000 | 7500000 | 6002233 | 110283385.32 | 1824155.44 | 116285618.71 | 6002233 | 0 | 0 | 0 | 0 | 15311215 | 1000000 | 1000000 | 6303321 | 9007893.49 | 301338.13 | 15311215 | 1235710.05 | 0 | 0 | 0 | 0 | LE ROUX R | TALJAARD M | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | SALDANHA BAY LOCAL MUNICIPALITY | SALDANHA,,MILITARY ACADEMY,REPAIR AND RENOVATION | 052153 | 052153 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 6A | 1 - COMMITMENTS | 022 | MILITARY BASE | 01 | MAINTENANCE & REPAIR CURRENT | 2014/12/08 | 2016/08/18 | 1011/14 | 18 | 0 | 0 | 0 | 3289390 | 178490464.65 | 886330.95 | 181779855.55 | 3289390 | 0 | 0 | 0 | 0 | 11679850 | 0 | 0 | 3003693 | 8676156.96 | 221414.46 | 11679850 | 3003693.04 | 0 | 0 | 0 | 0 | LE ROUX R | TALJAARD M | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | SALDANHA BAY LOCAL MUNICIPALITY | SALDANHA,,NAVAL BASE,SAMHS: REFURBISHMENT OF BUILDING 142 AS SICK BAY FACILITY | 053370 | 053370 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 6A | 1 - COMMITMENTS | 028 | NAVAL BASE | 03 | REFURB & REHAB CAPITAL | 2015/04/24 | 2017/02/28 | 1047/14 | 6 | 208053.66 | 0 | 0 | 531178 | 7345732.97 | 323125.1 | 7502138.99 | 323125 | 0 | 0 | 0 | 0 | 250230 | 0 | 0 | 204744 | 45486 | 159537.61 | 250230 | 204744 | 0 | 0 | 0 | 0 | LE ROUX R | HESEWU M | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,WYNBERG,2 MILITARY HOSPITAL,REFURBISHMENT AND ADDITIONS TO HOSPITAL | 049009 | 049009 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 5B | 1 - COMMITMENTS | 041 | SPECIALISED HOSPITAL (DEFENCE) | 01 | MAINTENANCE & REPAIR CURRENT | 2012/07/30 | 2018/03/01 | 1003/12 | 54 | 0 | 160000000 | 160000000 | 160054989 | 546725374.34 | 6719675.58 | 861457998.93 | 112278740 | 202453883 | 0 | 0 | 0 | 74694110 | 1200000 | 1200000 | 3249572 | 51433696.33 | 1123270.53 | 74694110 | 765000 | 0 | 0 | 0 | 0 | LE ROUX R | MONG B | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | OVERBERG DISTRICT MUNICIPALITY | BREDASDORP,,AIR FORCE BASE,OVERBERG: REFURBISHMENT OF SEWER PLANT | 052437 | 052437 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 5B | 1 - COMMITMENTS | 040 | SEWERAGE PUMP STATION | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/10/20 | 2017/08/19 | 1049/15 | 10 | 0 | 15021063 | 15021063 | 8688713 | 8408402.57 | 1083604.37 | 17097117.17 | 8688713 | 0 | 0 | 0 | 0 | 2607100 | 500000 | 500000 | 381699 | 1914092.3 | 231699.07 | 2607100 | 634536.51 | 58471.19 | 0 | 0 | 0 | LE ROUX R | MONG B | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | SIMONSTOWN,,NAVAL BASE,KLAWER VALLEY: REFURBISHMENT AND REPLACEMENT OF WATER DISTRI BUTION SYSTEM | 052453 | 052453 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 5B | 1 - COMMITMENTS | 028 | NAVAL BASE | 03 | REFURB & REHAB CAPITAL | 2015/05/28 | 2016/05/27 | 1003/15 | 12 | 861651.69 | 1158603 | 1158603 | 1158603 | 8558396.34 | 0 | 12034205.48 | 3475809 | 0 | 0 | 0 | 0 | 1485903 | 50000 | 50000 | 60000 | 1355859.18 | 0 | 1485903 | 130043.82 | 0 | 0 | 0 | 0 | LE ROUX R | MONG B | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | OVERBERG DISTRICT MUNICIPALITY | BREDASDORP,,AIR FORCE BASE,OVERBERG: UPGRADING, REPAIR AND MAINTENANCE OF BUILDING, MEC HANICAL, ELECTRICAL AND CIVIL INFRASTRUCTURE | 052456 | 052456 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 5B | 1 - COMMITMENTS | 004 | AIR FORCE BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2016/12/06 | 2019/12/05 | 1008/16 | 36 | 0 | 54626519 | 54626519 | 54626519 | 8656295.14 | 2714554.34 | 285205543.42 | 43609402 | 113847103 | 90572188 | 28520554 | 0 | 19114142.25 | 1241190 | 1241190 | 919631 | 7855575.61 | 204380.09 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | MONG B | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | SALDANHA BAY LOCAL MUNICIPALITY | LANGEBAAN,,4 SPES FORCES REGIMENT,OESTERSKULP DUPLEX UNITS: RENOVATION | 052793 | 052793 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 5B | 1 - COMMITMENTS | 037 | RESIDENCES (PERSONNEL/OFFICIALS) | 03 | REFURB & REHAB CAPITAL | 2016/07/25 | 2017/07/24 | 1052/15 | 12 | 1015409.01 | 8036861 | 8036861 | 6823286 | 7888415.9 | 2529680.56 | 15621245.5 | 7732827 | 0 | 0 | 0 | 0 | 1425924.51 | 450000 | 450000 | 615771 | 810152.65 | 278288.56 | 1425924.51 | 388478.46 | 0 | 0 | 0 | 0 | LE ROUX R | HESEWU M | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | OUDTSHOORN LOCAL MUNICIPALITY | OUDTSHOORN,,DEFENCE COMPLEX,ORAL HEALTH CENTRE: SOUTH COAST: INSTALLATION OF CENTRALISED VENTILATION SYSTEM | 054351 | 054351 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/04/06 | 2017/10/05 | 1020/16 | 6 | 0 | 2030446 | 2030446 | 2214968 | 0 | 0 | 2331546.49 | 2098391 | 233154 | 0 | 0 | 0 | 266426.4 | 100000 | 100000 | 90000 | 165544.42 | 0 | 266426.4 | 90000 | 10881.98 | 0 | 0 | 0 | LE ROUX R | KRIEL JP | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | OVERBERG DISTRICT MUNICIPALITY | BREDASDORP,,AIR FORCE BASE,SAMHS: REFURBISHMENT AND UPGRADING OF SICK BAY COMPLEX | 053914 | 053914 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 4B | 2 - TENDER STAGE | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/07/06 |  | 1024/16 | 12 | 0 | 12000000 | 12000000 | 5221649 | 0 | 0 | 17388663.96 | 5221649 | 12167014 | 0 | 0 | 0 | 962738.8 | 130000 | 130000 | 373612 | 548126.42 | 0 | 962738.8 | 373612.38 | 41000 | 0 | 0 | 0 | LE ROUX R | KRIEL JP | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | MUIZENBERG,,,NAVAL COLLEGE: REPAIR AND RENOVATION | 052790 | 052790 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 4 | 3 - WORKS IN PROGRES | 062 | TRAINING FACILITIES | 03 | REFURB & REHAB CAPITAL | 2017/08/25 |  |  | 12 | 0 | 16000000 | 16000000 | 12000000 | 0 | 0 | 30024978.94 | 1547713 | 25474768 | 3002497 | 0 | 0 | 2206569.84 | 800000 | 800000 | 1603302 | 603266.96 | 175304.14 | 2206569.84 | 567711.16 | 109038.17 | 0 | 0 | 0 | LE ROUX R | HESEWU M | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | SIMONSTOWN,,,SOUTH AFRICAN MILITARY HEALTH SERVICES: INSTITUTE FOR MARITI ME MEDICINE: PHARMACY: BUILDING 70: UPGRADING AND REFURBISHM ENT | 053823 | 053823 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/10/29 |  |  | 12 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 5543843.68 | 0 | 4731763 | 812080 | 0 | 0 | 0 | 210000 | 210000 | 672511 | 0 | 0 | 832500 | 672511 | 159989 | 0 | 0 | 0 | LE ROUX R | SPRINGFIELD N.C | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | WESTERN CAPE | CAPE TOWN | DOD REFURBISHMENTS | CITY OF CAPE TOWN METROPOLITAN MUNICIPALITY | CAPE TOWN,YSTERPLAAT,AIR FORCE BASE,FAMILY QUARTERS: JACK FROST COURTS: BUILDING NO 340: MAJOR R EFURBISHMENT | 054763 | 054763 | 85DRWC | DEFENCE: REC: REFURBISHMENT: WC | 4 | 3 - WORKS IN PROGRES | 004 | AIR FORCE BASE | 03 | REFURB & REHAB CAPITAL | 2018/03/23 |  |  | 18 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 35824311.18 | 0 | 7556691 | 24685189 | 3582431 | 0 | 0 | 800000 | 800000 | 23000 | 0 | 0 | 2640000 | 1743276.25 | 533356.25 | 363367.5 | 0 | 0 | LE ROUX R | NAUDE AL | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | KWAZULU-NATAL | DURBAN | DOD REFURBISHMENTS | ETHEKWINI METROPOLITAN MUNICIPALITY | DURBAN,SALISBURY ISLAND,,REFURBISHMENT OF NAVAL BASE: PHASE 2 | 053596 | 053596 | 85DRKZN | DEFENCE: REC: REFURBISHMENT: KZN | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2018/06/30 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 17933100.68 | 0 | 2460914 | 13678876 | 1793310 | 0 | 0 | 1000000 | 1000000 | 500000 | 0 | 0 | 2944090 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | RINDEL DJ | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | NORTH WEST | MMABATHO | DOD REFURBISHMENTS | SOUTHERN DISTRICT MUNICIPALITY | POTCHEFSTROOM,,SCHOOL OF INTELLIGENCE,REPAIR AND RENOVATION OF WAREHOUSE T97 EQUIPMENT STORE | 048291 | 048291 | 85DRNW | DEFENCE: REC: REFURBISHMENT: NW | 6A | 1 - COMMITMENTS | 022 | MILITARY BASE | 01 | MAINTENANCE & REPAIR CURRENT | 2011/09/13 | 2016/06/30 | MB11/003 | 10 | 0 | 0 | 0 | 207076 | 5444864.51 | 0 | 5651940.44 | 207076 | 0 | 0 | 0 | 0 | 2832103.51 | 0 | 0 | 548829 | 2283274.37 | 0 | 2832103.51 | 548829.14 | 0 | 0 | 0 | 0 | MORARE M L | KADI NA | N | Y | Y
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | NORTH WEST | MMABATHO | DOD REFURBISHMENTS | NGAKA MODIRI MOLEMA DISTRICT MUNICIPALITY | ZEERUST,,2 S.A.I. BATTALION,SUPPLY AND INSTALLATION OF KITCHEN EQUIPMENT,AND REPLACEMENT OF ROOF AND CEILING OF THE KITCHEN. | 051944 | 051944 | 85DRNW | DEFENCE: REC: REFURBISHMENT: NW | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2015/03/06 | 2016/04/01 | MB14/097 | 12 | 0 | 1208189 | 1208189 | 2207518 | 4839550.68 | 1986518.37 | 7983342.42 | 3143791 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MORARE M L | NKOE B.P | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | NORTH WEST | MMABATHO | DOD REFURBISHMENTS | SOUTHERN DISTRICT MUNICIPALITY | POTCHEFSTROOM,,DEFENCE COMPLEX,SA ARMY - 1 TAC INT REGT, POTCHEFSTROOM: REFURBISHMENT | 052562 | 052562 | 85DRNW | DEFENCE: REC: REFURBISHMENT: NW | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2018/04/28 |  |  | 24 | 0 | 6186504 | 6186504 | 0 | 0 | 0 | 64162886.4 | 0 | 6581668 | 33846205 | 23735012 | 0 | 6440310.05 | 1100000 | 1100000 | 1100000 | 367097.67 | 0 | 6440310.05 | 1100000 | 2138670.05 | 0 | 0 | 0 | MORARE M L | KADI NA | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | NORTH WEST | MMABATHO | DOD REFURBISHMENTS | SOUTHERN DISTRICT MUNICIPALITY | POTCHEFSTROOM,,ARMY SUPPORT BASE,CONSTANT VILJOEN ARMY SUPPORT: INSTALLATION OF NEW AIR CONDITIONERS | 054327 | 054327 | 85DRNW | DEFENCE: REC: REFURBISHMENT: NW | 4 | 4 - NEW SERVICES | 061 | MISCELLANEOUS STRUCTURES | 03 | REFURB & REHAB CAPITAL | 2018/11/30 |  |  | 8 | 0 | 1109160 | 1109160 | 0 | 0 | 0 | 1412071.89 | 0 | 0 | 1270864 | 141207 | 0 | 0 | 66145 | 66145 | 0 | 0 | 0 | 222000 | 212917.41 | 9082.59 | 0 | 0 | 0 | MORARE M L | MAHLANGU K Z | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | LIMPOPO | POLOKWANE | DOD REFURBISHMENTS | MARULENG DISTRICT MUNICIPALITY | HOEDSPRUIT,,AIR FORCE BASE,REPAIR THRESHOLDS ON MAIN RUNWAY AND REPAIR RADAR FOOTINGS | 048254 | 048254 | 85DRNP | DEFENCE: REC: REFURBISHMENTS: NP | 6A | 1 - COMMITMENTS | 002 | ACCESS ROAD TAR | 01 | MAINTENANCE & REPAIR CURRENT | 2011/11/11 | 2013/03/05 | PLK11/35 | 6 | 282891.67 | 0 | 0 | 0 | 6119083.45 | 0 | 6119083.45 | 0 | 0 | 0 | 0 | 0 | 1169551.08 | 0 | 0 | 328147 | 841404.31 | 0 | 1169551.08 | 328146.77 | 0 | 0 | 0 | 0 | PERUMAL V | MOJAPELO D.M | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | LIMPOPO | POLOKWANE | DOD REFURBISHMENTS | MARULENG DISTRICT MUNICIPALITY | HOEDSPRUIT,,AIR FORCE BASE,REPAIRS TO DAMAGED FACILITIES AND INFRASSTRUCTURE CAUSED BY THE FLOOD | 050751 | 050751 | 85DRNP | DEFENCE: REC: REFURBISHMENTS: NP | 5B | 1 - COMMITMENTS | 004 | AIR FORCE BASE | 01 | MAINTENANCE & REPAIR CURRENT | 2014/02/18 | 2015/06/09 | PLK13/85 | 12 | 0 | 6554803 | 6554803 | 11337218 | 10101992.46 | 1430794.65 | 21439211.2 | 11337218 | 0 | 0 | 0 | 0 | 8055944.75 | 570430 | 570430 | 2219500 | 5579920.76 | 0 | 8055944.75 | 2219500.29 | 256523.7 | 0 | 0 | 0 | NCAPAYI N | BUITENDACH FWC | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | LIMPOPO | POLOKWANE | DOD REFURBISHMENTS | WATERBERG DISTRICT MUNICIPALITY | ELLISRAS,,TRAINING CENTRE,UPGRADING,REPAIR AND RENOVATIONS OF ALL OFFICES AND TRAINING ACCOMMODATION, LOGISTICS, SUPPORTING FACILITIES AND KITCHEN COMPLEX | 052565 | 052565 | 85DRNP | DEFENCE: REC: REFURBISHMENTS: NP | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2019/01/31 |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 63348100.58 | 0 | 0 | 6053443 | 17815513 | 26690601 | 0 | 0 | 0 | 0 | 0 | 0 | 7749392.29 | 1162408.84 | 3099756.92 | 1101656.86 | 773526.25 | 773526.25 | NCAPAYI N | RAGANYA MM | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | EASTERN CAPE | PORT ELIZABETH | DOD REFURBISHMENTS | CACADU DISTRICT MUNICIPALITY | GRAHAMSTOWN,,6 SAI BATTALION,COMPLETE REFURBISHMENT AND REHABILITATION OF BASE SECURITY F ENCES, INFRASTRUCTURE AND BUILDINGS | 036138 | 055061 | 85DREC | DEFENCE: REC: REFURBISHMENT: EC | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 01 | MAINTENANCE & REPAIR CURRENT | 2022/04/28 |  |  | 36 | 0 | 27522523 | 27522523 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 32455216.59 | 1670000 | 1670000 | 4563475 | 22309212.22 | 0 | 32455216.59 | 4563475.03 | 1920000 | 1800000 | 1807529.34 | 0 | LE ROUX R | GREYLING EL | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | EASTERN CAPE | PORT ELIZABETH | DOD REFURBISHMENTS | CACADU DISTRICT MUNICIPALITY | GRAHAMSTOWN,,6 SAI BATTALION,REPLACEMENT OF PERIMETER AND INTERNAL SECURITY FENCING | 054748 | 055061 | 85DREC | DEFENCE: REC: REFURBISHMENT: EC | 4 | 3 - WORKS IN PROGRES | 013 | FENCE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/09/16 |  |  | 18 | 0 | 0 | 0 | 1434509 | 0 | 0 | 82397600 | 1434509 | 48617287 | 32345804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | GREYLING EL | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | EASTERN CAPE | PORT ELIZABETH | DOD REFURBISHMENTS | CACADU DISTRICT MUNICIPALITY | GRAHAMSTOWN,,6 SAI BATTALION,PHASE 1: REFURBISHMENT AND REHABILITATION OF INFRASTRUCTURE AND BUILDINGS | 054749 | 055061 | 85DREC | DEFENCE: REC: REFURBISHMENT: EC | 4 | 3 - WORKS IN PROGRES | 029 | OFFICE BUILDINGS | 03 | REFURB & REHAB CAPITAL | 2017/09/22 |  |  | 36 | 0 | 0 | 0 | 2673665 | 0 | 0 | 432107499.25 | 2673665 | 73182979 | 148643727 | 157455349 | 50151778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LE ROUX R | GREYLING EL | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | GAUTENG | PRETORIA | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,THABA TSWANE,DEFENCE COMPLEX,SA ARMY - B MESS : REFURBISHMENT | 052561 | 052561 | 85DRGTP | DEFENCE: REC: REFURBISHMENT: GTP | 4B | 2 - TENDER STAGE | 023 | MILITARY PERSONNEL DWELLINGS | 03 | REFURB & REHAB CAPITAL | 2017/06/12 |  | PT16/025 | 8 | 0 | 21000000 | 21000000 | 5000000 | 0 | 0 | 46752032.68 | 21000000 | 21076829 | 4675203 | 0 | 0 | 8862702.45 | 2500000 | 2500000 | 2500000 | 6305985.74 | 0 | 8862702.45 | 125720.2 | 0 | 0 | 0 | 0 | MORARE M L | NDLOVU C | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | GAUTENG | PRETORIA | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,LYTTELTON,DEFENCE COMPLEX,SOUTH AFRICAN MILITARY HEALTH SERVICE (NEXT TO DOD AUCTION CENTRE): REFURBISHMENT | 052554 | 052554 | 85DRGTP | DEFENCE: REC: REFURBISHMENT: GTP | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2018/09/28 |  |  | 18 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 117257146.93 | 0 | 1224165 | 65854146 | 50178835 | 0 | 0 | 7500000 | 7500000 | 0 | 0 | 0 | 14400000 | 10135156.63 | 2157044.15 | 2107799.22 | 0 | 0 | MORARE M L | NOMBEWU A | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | GAUTENG | PRETORIA | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,DEFENCE COMPLEX,SOUTH AFRICAN MILITARY HEALTH SERVICE - AT TEK BASE COMPLEX: REFURBISHMENT | 052555 | 052555 | 85DRGTP | DEFENCE: REC: REFURBISHMENT: GTP | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2018/11/30 |  |  | 24 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 90000000 | 0 | 0 | 22500077 | 58499923 | 9000000 | 0 | 7500000 | 7500000 | 0 | 0 | 0 | 16200000 | 13920901.43 | 1840896.21 | 438202.36 | 0 | 0 | MORARE M L | MATHEKGA L | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | GAUTENG | PRETORIA | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,SWARTKOP,DEFENCE COMPLEX,SANDF - SPECIAL FORCE HEAD QUARTERS, SWARTKOP PARK: REFURBISHMENT | 052556 | 052556 | 85DRGTP | DEFENCE: REC: REFURBISHMENT: GTP | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2018/06/30 |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 7700000 | 0 | 730969 | 5184028 | 1785003 | 0 | 700000 | 0 | 0 | 0 | 173910.58 | 0 | 700000 | 176089.42 | 0 | 0 | 0 | 0 | MORARE M L | MATHEKGA L | N | N | Y
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | GAUTENG | PRETORIA | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,DEFENCE COMPLEX,JOINT SUPPORT BASE ( JSB) GARRISON FINANCE OFFICE: PRETORIA: REFURBISHMENT | 052557 | 052557 | 85DRGTP | DEFENCE: REC: REFURBISHMENT: GTP | 4 | 3 - WORKS IN PROGRES | 029 | OFFICE BUILDINGS | 03 | REFURB & REHAB CAPITAL | 2017/06/30 |  |  | 8 | 0 | 8900000 | 8900000 | 810050 | 0 | 0 | 3300000 | 810050 | 2489950 | 0 | 0 | 0 | 1108781.61 | 322082 | 322082 | 322082 | 136592.04 | 88178.27 | 1108781.61 | 322082.01 | 76167.3 | 0 | 0 | 0 | MORARE M L | MASHA TS | N | Y | Y
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | GAUTENG | PRETORIA | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,DEFENCE COMPLEX,SA ARMY - 1 SIG REGIMENT, ROOIWAL: REFURBISHMENT. | 052558 | 052558 | 85DRGTP | DEFENCE: REC: REFURBISHMENT: GTP | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2018/11/30 |  |  | 24 | 0 | 500000 | 500000 | 0 | 0 | 0 | 56743000 | 0 | 0 | 6000000 | 45068700 | 5674300 | 0 | 5500000 | 5500000 | 0 | 0 | 0 | 10213740 | 8245042.4 | 1308410.48 | 660287.12 | 0 | 0 | MORARE M L | MATHEKGA L | N | N | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | GAUTENG | PRETORIA | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,THABA TSWANE,DEFENCE COMPLEX,HUMAN RESOURCE DIVISION - DEFENCE COLLEGE: REFURBISHMENT | 052560 | 052560 | 85DRGTP | DEFENCE: REC: REFURBISHMENT: GTP | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/10/20 |  |  | 12 | 0 | 15000000 | 15000000 | 0 | 0 | 0 | 75140607.76 | 51329 | 65022180 | 10067097 | 0 | 0 | 15375101.48 | 3000000 | 3000000 | 3000000 | 501599.38 | 1063939.63 | 15375101.48 | 3165292.31 | 1393238.13 | 0 | 0 | 0 | MORARE M L | MASHA TS | N | Y | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | GAUTENG | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,1 MILITARY HOSPITAL,RAMP: REPAIR AND MAINTENANCE OF MECHANICAL AND ELECTRICAL IN FRASTRUCTURE | 042452 | 047668 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 7 | 1 - COMMITMENTS | 041 | SPECIALISED HOSPITAL (DEFENCE) | 01 | MAINTENANCE & REPAIR CURRENT | 2006/10/12 | 2012/11/16 | H06/027 | 36 | 0 | 0 | 0 | 0 | 212741216.45 | 0 | 212741216.47 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 300000 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | DE KLERK CCE | MANAGA AE | N | Y | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | GAUTENG | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | JOHANNESBURG,DOORNKOP,,21 SAI BATTALION: REPAIR AND 36 MONTH MAINTENANCE (RAMP) OF CIVIL, BUILDING STRUCTURAL & WET SERVICES | 047078 | 047078 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 7 | 1 - COMMITMENTS | 022 | MILITARY BASE | 01 | MAINTENANCE & REPAIR CURRENT | 2010/12/08 | 2015/05/15 | H10007 | 30 | 0 | 800000 | 800000 | 600000 | 145539208.09 | 0 | 168845427.14 | 23306219 | 0 | 0 | 0 | 0 | 24858965.96 | 300000 | 300000 | 400000 | 22364740.37 | 0 | 24858965.96 | 2494225.59 | 0 | 0 | 0 | 0 | DE KLERK CCE | MANAGA AE | N | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | NORTHERN CAPE | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | SIYANDA DISTRICT MUNICIPALITY | POSTMASBURG,LOHATHLA,COMBAT SCHOOL,SA ARMY COMBAT TRAINING CENTRE: MAJOR REFURBISHMENT OF FACIL ITIES AND CIVIL SERVICES | 047080 | 047080 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 6A | 1 - COMMITMENTS | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2011/02/18 | 2015/05/14 | H10014 | 30 | 1155295.78 | 150000 | 150000 | 1000000 | 118584057.23 | 829426.55 | 120905440.93 | 2321383 | 0 | 0 | 0 | 0 | 22047867.32 | 150000 | 150000 | 300000 | 21881981.91 | 0 | 22047867.32 | 165885.41 | 0 | 0 | 0 | 0 | DE KLERK CCE | MANAGA AE | N | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | NORTHERN CAPE | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | SIYANDA DISTRICT MUNICIPALITY | UPINGTON,,8 S A I BATALION,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 036133 | 036133 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2011/02/18 | 2016/11/25 | H10013 | 30 | 19135403.4 | 10000000 | 10000000 | 6000000 | 195483065.84 | 1151427.6 | 206828010 | 20286830 | 0 | 0 | 0 | 0 | 39442456.99 | 500000 | 500000 | 3000000 | 37022780.21 | 0 | 39442456.99 | 2419676.78 | 0 | 0 | 0 | 0 | DE KLERK CCE | MANAGA AE | N | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | MPUMALANGA | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | EHLANZENI DISTRICT MUNICIPALITY | MIDDELBURG (MPU),,4 S A I BATALION,SPECIAL RAMP: REPAIR AND MAINTENANCE TO CIVIL INFRASTRUCTURE | 045183 | 045183 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2010/12/10 | 2013/07/30 | H10008 | 30 | 3004668.9 | 1500000 | 1500000 | 0 | 31600068.21 | 0 | 41600068.21 | 10000000 | 0 | 0 | 0 | 0 | 71637.86 | 300000 | 300000 | 0 | 71637.86 | 0 | 71637.86 | 0 | 0 | 0 | 0 | 0 | DE KLERK CCE | MANAGA AE | Y | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | NORTH WEST | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | MOLOPO-KAGISANO MUNICIPALITY | MMABATHO,,,10 SAI BATTALION: REPAIR AND 36 MONTH MAINTENANCE (RAMP) OF CIVIL, BUILDING STRUCTURAL & WET SERVICES INFRASTRUCTURE | 047079 | 047079 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 01 | MAINTENANCE & REPAIR CURRENT | 2010/12/08 | 2014/06/10 | H10005 | 30 | 0 | 1500000 | 1500000 | 0 | 64513674.3 | 0 | 151331366.64 | 86817692 | 0 | 0 | 0 | 0 | 30057953.74 | 300000 | 300000 | 0 | 28160830.41 | 0 | 30057953.74 | 2109492.62 | 0 | 0 | 0 | 0 | DE KLERK CCE | MANAGA AE | N | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | NORTH WEST | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | SOUTHERN DISTRICT MUNICIPALITY | POTCHEFSTROOM,,ARTILLERY SCHOOL,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 033655 | 033655 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2018/01/19 |  |  | 24 | 0 | 200000 | 200000 | 0 | 0 | 0 | 89301718.31 | 0 | 18199253 | 54008392 | 17094072 | 0 | 10815197.25 | 190000 | 190000 | 2300000 | 3202955.17 | 0 | 10815197.25 | 7612242.08 | 0 | 0 | 0 | 0 | DE KLERK CCE | PINGO N | N | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | NORTH WEST | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | SOUTHERN DISTRICT MUNICIPALITY | POTCHEFSTROOM,,4 ARTILLERY REGIMENT,MAJOR REFURBISHMENT OF FACILITIES AND CIVIL SERVICES | 033657 | 033657 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/09/29 |  |  | 12 | 0 | 500000 | 500000 | 0 | 0 | 0 | 140048766.64 | 2159888 | 122859894 | 15028983 | 0 | 0 | 10069590.54 | 200000 | 200000 | 3000000 | 5140204.8 | 1870841.24 | 10069590.54 | 496186 | 200000 | 0 | 0 | 0 | DE KLERK CCE | PINGO N | N | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | MPUMALANGA | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | EHLANZENI DISTRICT MUNICIPALITY | MIDDELBURG (MPU),,4 S A I BATALION,RAMP: MULTI DISCIPLINE, DESIGN AND CONSTRUCTION | 036125 | 036125 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 4 | 4 - NEW SERVICES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2018/12/30 |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18159223.72 | 0 | 0 | 0 | 17408995.03 | 0 | 18159223.72 | 750228.69 | 0 | 0 | 0 | 0 | DE KLERK CCE | MANAGA AE | N | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | GAUTENG | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,THABA TSWANE,,A MESS: UPGRADING OF REMAINDER OF THE FACILITIES NOT INCLUDE D IN WCS 047936 | 048408 | 048408 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/08/31 |  |  | 36 | 0 | 600000 | 600000 | 1000000 | 0 | 0 | 574128981.63 | 6510106 | 103477563 | 203605255 | 198716604 | 61819453 | 31663569.74 | 1500000 | 1500000 | 3000000 | 28025049.01 | 0 | 31663569.74 | 1006228 | 629338.58 | 20000 | 0 | 0 | DE KLERK CCE | LIDOVHO S.H | N | Y | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | GAUTENG | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,,AIR COMMAND HEAD QUARTERS AND BLENNY BUILDINGS: APPOINTMENT OF CONSULTANT TEAM TO UNDERTAKE THE DESIGN AND DOCUMENTATION OF THE DIFFERENT DISCIPLINES IN UPGRADING ALL INSTALLATIONS | 048536 | 048536 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/06/30 |  |  | 30 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 46400000 | 600000 | 600000 | 0 | 35193947.59 | 0 | 46400000 | 11206052.41 | 0 | 0 | 0 | 0 | DE KLERK CCE | MANAGA AE | N | Y | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | GAUTENG | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,WATERKLOOF AIR FORCE BASE,REFURBISHMENT OF THE HOSTELS (SINGLE QUARTERS) | 048756 | 048756 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 03 | REFURB & REHAB CAPITAL | 2017/08/31 |  |  | 18 | 0 | 900000 | 900000 | 0 | 0 | 0 | 104229042.49 | 2870468 | 65042831 | 36315743 | 0 | 0 | 6254099.97 | 2188107 | 2188107 | 200000 | 1621083.32 | 0 | 6254099.97 | 2230000 | 1858106.92 | 544908.42 | 0 | 0 | DE KLERK CCE | LUKHELE ____GK | N | N | N
2017 | DEFENCE | H | CLAIMS | RECOVERABLE | GAUTENG | SPECIAL & MAJOR PROJECTS | DOD REFURBISHMENTS | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA,,ARMY OPERATIONAL HEAD QUARTERS,UPGRADING/RENOVATION OF THE SA ARMY HEAD QUARTERS COMPLEX | 050794 | 050794 | 85DRHSM | DEFENCE: REC: REFURBISHMENT: HSM | 4 | 3 - WORKS IN PROGRES | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2017/10/20 |  |  | 48 | 0 | 4500000 | 4500000 | 0 | 0 | 0 | 714479358.79 | 161401 | 71744945 | 141127392 | 210348439 | 197633778 | 0 | 2000000 | 2000000 | 5000000 | 0 | 0 | 498797500 | 498797500 | 0 | 0 | 0 | 0 | MORARE M L | MOHLOPI C.K | N | Y | N
2017 | DEFENCE | R | CLAIMS | RECOVERABLE | EASTERN CAPE | UMTATA | DOD REFURBISHMENTS | O R TAMBO DISTRICT MUNICIPALITY | UMTATA,,14 SAI BATTALION,REPLACEMENT OF KITCHEN EQUIPMENT | 051777 | 051777 | 85DRUMT | DEFENCE: REC: REFURBISHMENT: UMT | 5B | 1 - COMMITMENTS | 022 | MILITARY BASE | 02 | UPGRADE & ADDITIONS CAPITAL | 2014/02/06 | 2014/09/18 | MTH14KQ1 | 6 | 241116.54 | 3133897 | 3133897 | 3133897 | 2398144.03 | 0 | 5532040.84 | 3133897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZEMBE P.C. | MAZWANA M | N | N | N
[10 empty] | 56 | [13 empty] | 31842949.11 | 445792498 | 445792498 | 326441182 | 1877567965.06 | 27330832.42 | 6624571080.05 | 428163320 | 1080414462 | 1128707369 | 1010656777 | 516254885 | 536202512.23 | 67323440 | 67323440 | 131583219 | 381895025.42 | 5926421.4 | 1211535894.12 | 593810180.36 | 41984391.15 | 65015535.76 | 13563444.23 | 7635555.45
[24 empty] | CONTRACTOR |  | 445792498 | 326441182 |  |  |  | 428163320
[24 empty] | CONSULTANT |  | 67323440 | 131583219 |  |  |  | 593810180.36
[24 empty] | TOTAL |  | 513115938 | 458024401 |  |  |  | 1021973500.36
[29 empty] | 33257253.82 | 6.481%