## Slide 1
NATIONAL YOUTH DEVELOPMENT AGENCY
QUARTERLY REPORTING: PORTFOLIO COMMITTEE ON PUBLIC SERVICE AND ADMINSITRATION

## Slide 2: Agenda
Situational Analysis
Quarter two performance report
Quarter two financial report

## Slide 3: Quarter 2 (2017/2018)

## Slide 4: Situational Analysis
The NYDA has achieved 65% of its year to date targets for the quarter under review. For targets not achieved in the quarter, the Chief Executive Officer implemented strict performance measures in line with the Agency’s performance management policy and high performance culture.
The Agency has spent an estimated 46% of its annual budget with the main areas of underspending on two programmes.
The Agency is preparing scenario plans for the establishment of offices to provide universal access to opportunities, that will then be used to negotiate with local and district municipalities for the provision of products and services to young people.
The Agency Chief Executive Officer took the decision to step down in October 2017. The Board of Directors has named the Chief Financial Officer as the Acting CEO for a period of four months during the transitional period until a permanent Chief Executive is identified and appointed. The Board’s desire is to have a stable and functional agency during this period.
The National Youth Service Coordination Framework was approved by Cabinet in October 2017 which establishes the NYDA as the National Coordinator of the programme.
The Agency will conduct in the second half of the year deep stick assessments of its entrepreneurship and jobs programmes to influence future planning.

## Slide 5: Situational analysis – continued
About 70% of South Africa’s 20 million young people were more likely to be victims and perpetrators of assault, robbery and property theft than adults (35 years and above).
Unemployment of young people is at 60.2%
Youth headed households stand at 26.1%.
Young people without matric is at 59.4%

## Slide 6: Detailed QUARTER 2 (2017/2018) performance report

## Slide 7
Chart: Summary of Quarter 2 Performance
| Target met | Target not met | No target in Q2
 | 14 | 5 | 2

## Slide 8
PROGRAMME AREA 1: ECONOMIC PARTICIPATION |  |  |  | 
STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATOR | QUARTER 2 TARGET | QUARTER 2 ACHIEVEMENT | REASON FOR VARIANCE
To enhance the participation of young people in the economy | Number of youth owned enterprises created through Business Development Support Services | 250 | 344 | The overachievement was due to the system picking up and being consistently functional thus allowing payment for carry overs from Quarter 1
 | Number of beneficiaries supported with key fundamentals for success offered by the NYDA | 5000 | 4208 | Timeliness of the delivery of trainings was affected by the introduction of the ILO tool that trainers were adjusting to Mitigation More Beneficiaries will be trained on Mentorship, Sales Pitch and BBEE as they take shorter time to be completed which our target will be achieved by end of quarter 3
 | Number of jobs created and sustained through supporting entrepreneurs and enterprises | 900 | 1425 | Increase in issuance of grants led to increase in jobs created
 | Number of jobs facilitated through placements in job opportunities | 1250 | 3587 | The overachievement was due to appointment of two service providers during Quarter 2 to facilitate the placement process
To provide access to information and create awareness on youth | Number of young people provided with youth development information | 375 000 | 592 475 | The overachievement was due to outreach campaigns that happened at the branches during women and heritage months

## Slide 9
PROGRAMME AREA 2: EDUCATION AND SKILLS DEVELOPMENT |  |  |  | 
STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATOR | QUARTER 2 TARGET | QUARTER 2 ACHIEVEMENT | REASON FOR VARIANCE
To facilitate and implement skills programmes | Number of young people skilled to enter the job market | 16 125 | 28 318 | The overachievement was attributed by more dates for training that was scheduled to conduct more training
To facilitate and implement education opportunities in order to improve the quality education attainment for the youth | Number of youth supported to access higher education | Target applicable in quarter 4 | Target applicable in quarter 4 | Target applicable in quarter 4
To engage young people in service activities geared towards fostering patriotism, social cohesion and nation building |  |  |  | 
 | National Youth Service Unit configured to deliver on its mandate | Approval by Board and initiated advertising of positions | NYS structure presented to Board HRR committee and approved Advertising of positions not initiated | The approval process took longer than expected. Cabinet took long to approve the NYSP National Coordination Framework. Mitigation The process of advertising for filling the posts will be initiated in Quarter 3
 | Norms and standards for National Youth Service Programme (NYSP) developed and capacity building interventions provided | Consulted key stakeholders and finalised the norms and standards document Submitted 3 capacity building interventions and progress report to NYDA EXCO | Consultation workshop was held with stakeholders to finalise the norms and standards document 3 capacity building interventions conducted and progress report presented to EXCO | Target achieved

## Slide 10
PROGRAMME AREA 2: EDUCATION AND SKILLS DEVELOPMENT |  |  |  | 
STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATOR | QUARTER 2 TARGET | QUARTER 2 ACHIEVEMENT | REASON FOR VARIANCE
To engage young people in service activities geared towards fostering patriotism, social cohesion and nation building | National Youth Service Programme (NYSP) Central Information Management System developed | Develop specifications for an IMS approved | IMS concept document with specifications produced and approved | Target achieved
 | Annual planning Framework developed and 3018/19 NYSP plans finalised | Presented concept framework draft for approval | NYSP Annual Planning Framework approved | Target achieved
To engage young people in service activities geared towards fostering patriotism, social cohesion and nation building | NYSP Communication and Marketing plan developed and implemented | Presented concept for the Communication and Marketing plan for approval | Communication and Marketing Plan approved | Target achieved
 | Number of National Youth Service Programme projects registered | 25 | 31 | Target was over achieved due to willingness of stakeholders to register projects with NYS

## Slide 11
PROGRAMME AREA 3: RESEARCH AND POLICY |  |  |  | 
STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATOR | QUARTER 2 TARGET | QUARTER 2 ACTUAL | REASON FOR VARIANCE
To create and produce information and knowledge for better youth development planning and decision making | Number of programme evaluations and stakeholder satisfaction surveys conducted | Target Applicable in quarter 3&4 | 2 | Target is applicable in quarter 3&4, however the programme managed to conduct two satisfaction surveys during the quarter
To mobilise and leverage financial resources from key stakeholders | Total value of funds sourced from the public and private sectors to support the youth development programme base | R 30 million | R60 478 852,20 | Target was over-achieved due to increased buy-in from stakeholders
To lobby key stakeholders to support and implement youth development programmes | Number of public and private key stakeholders lobbied to implement youth development programmes | 3 | 5 | Target was over-achieved due to willingness of stakeholders to meet and partner with NYDA

## Slide 12
PROGRAMME AREA 4: GOVERNANCE |  |  |  | 
STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATOR | QUARTER 2 TARGET | QUARTER 2 ACTUALS | REASON FOR VARIANCE
To establish a credible, efficient and effective organization | ICT Road Map implemented | Implemented 50% of phase 1 to 4 of the ICT road map Reviewed 30% of phase 1 to 4 of ICT road map | Achieved 70% implementation and reviewed phase 1 to 4 of ICT road map | Target Achieved
 | Human Resources (HR) strategy reviewed and implemented | Implemented phase 1 of the HR strategy (Aspects of Phase 1 of the HR Strategy are as follows: Review HR policies, Re-grading of jobs, Implementation of year 1 of 3-year training plan, Induction programme and Change Management) | The programme managed to conduct Induction, review of policies and the other deliverables on the HR Strategy were not achieved | The programme could not find suitable service provider for re-grading due to non-compliance to SCM requirements Mitigation The process of sourcing a service provider has started, regrading will be concluded before the end of the financial year
 | Year 1 of the 3 year training plan implemented | Rolled out year 1 of the 3 years training plan | Technical training was conducted as prioritised and in a process to review the training plan to align to the training needs of the organisation | The roll out of Year 1 of the training plan could not be implemented as the unit prioritised technical training due to its urgency. Mitigation Training plan will be implemented as from quarter 3 and will be completed by end of the financial year 2017/18

## Slide 13
PROGRAMME AREA 4: GOVERNANCE |  |  |  | 
STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATOR | QUARTER 2 TARGET | QUARTER ACTUALS | REASON FOR VARIANCE
To establish a credible, efficient and effective organization | Implement an integrated marketing and communication strategy | Finalized local media partnership contracts | Local media partnership contracts not finalised | The partnership contracts could not be finalised as the agreement was not concluded due to delays that affected the signing off. Mitigation Currently waiting for sign off from partners and the Local media partnership contracts will be finalised by end of quarter 3
 | Payment of legitimate service provider invoices within the 30 day period | 100% of legitimate service provider invoices paid within the 30-day period | Paid 100% of legitimate service provider invoices within the 30-day period | Target achieved

## Slide 14: Financial performance Quarter 2 2017 / 2018

## Slide 15: Budget allocation
Key Programmatic Area | Budget allocation 15 / 16 | % change | Budget allocation 16 / 17 | % change | Budget allocation 17 / 18 | Medium Term Strategic Framework outcome
Economic Participation | R46 776 209 | 27% | R59 253 300 | 16% | R68 777 015 | Decent employment through inclusive economic growth
Education and skills development | R51 987 305 | 43% | R74 099 686 | 1% | R72 853 169 | Quality basic education & decent employment through inclusive economic growth
National Youth Service | R20 496 050 | 177% | R56 802 100 | 1% | R40 043 329 | Nation building and social cohesion
Service Delivery Channel | R31 391 913 | -22% | R24 611 821 | 39% | R34 140 983 | An efficient, effective and development orientated public service
Research and Policy | R12 371 896 | -18% | R10 173 573 | -4% | R9 726 600 | Decent employment through inclusive economic growth
Administration | R87 716 405 | -7% | R81 283 719 | -2% | R79 852 400 | An efficient, effective and development orientated public service
Employee costs | R189 819 214 | -23% | R145 529 300 | 5% | R152 461 700 | An efficient, effective and development orientated public service
Total | R427 289 000 |  | R451 753 500 |  | R457 855 196 | 

## Slide 16: Quarter two performance
Key Programmatic Area | Q2 budget | Annual budget | Q2 Actual | Percentage
Economic Participation | R 31,112,304 | R 68,777,015 | R 30,226,562 | 97%
Education and skills development | R 34,917,530 | R 72,853,169 | R 28,779,703 | 82%
National Youth Service | R 17,640,520 | R 40,043,329 | R 15,226,334 | 86%
Service Delivery Channel | R 16,640,380 | R 34,140,983 | R 15,583,783 | 94%
Research and Policy | R 2,113,970 | R 9,726,600 | R 2,103,688 | 100%
Administration | R 37,501,302 | R 79,852,400 | R 36,567,783 | 98%
Employee costs | R 81,598,874 | R 152,461,700 | R 81,672,736 | 100%
Total | R 221,524,880 | R 457,855,196 | R 210,160,589 | 95%

## Slide 17: Quarter two financial summary
Financial performance has caught up and is close to expected spending lying at 95% of estimates. There are pockets of underspending in relation to the jobs and technical skills programme which should catch up during the third quarter.

## Slide 18: Upcoming events
Launch of the new NYDA Head Office, named after the late struggle hero Tsietsi Mashinini, as “Tsietsi Mashinini House”
Launch of Wi-Fi hotspots of all NYDA branches in Nelspruit.

## Slide 19: questions