## Slide 1: Western Cape Status Report to Portfolio Committee Rural Development and Land Reform
CPA Amendment Bill
8th November 2017

## Slide 2: Masincedane CPA
CPA Info | Issues Raised | Outcome/ Output of the Actions | Dates
Reg No. CPA/98/0126/A Beneficiaries: 46 Beneficiaries Property Description: PORTION 6 OF THE FARM UITKYK NO.124 | No access to water; Lack of knowledge, Requested DRDLR for training and development Penalties paid to release impounded livestock Harsh and inhumane treatment by white people; Request Minister’s intervention | Meetings between Western Cape Department of Agriculture and DRDLR took place to resolve the water allocation matter with Department of Water Affairs. The latter referred the DRDLR to the Breede Gouritz Catchment Management Area. This matter is not yet resolved and will be followed up with the Breede Gouritz Catchment Management Area in November. WCPDOA has confirmed that the CPA is currently leasing out land to the Thembalethu township livestock owners. The District Office have scheduled a meeting with CPA to assess current situation in the CPA and what interventions are required | 8 November 2017. 17 November 2017

## Slide 3: Haarlem CPA
CPA Info | Issues Raised | Outcome/ Output of the Actions | Dates
CPA Registration | Mr Esau raised the matter of the beneficiary list to be checked to ensure that no one is excluded Mr October commented on the TRANCRAA National Task Team and the link of their mandate to other applicable Acts/legislation related to the understanding of property rights/resources and transformation process (S2, p3 and S3 p9) | Haarlem CPA is due to hold the AGM before the end of January 2018. The Tenure Directorate will refer Haarlem CPA to LRMF for assistance regarding the updating of membership and facilitation of the AGM. The issues raised around the TRANCRAA National Task Team have been referred to national office for guidance and as agenda points at the next National Task Team (NTT) meeting. | 01/2018 Next NTT meeting

## Slide 4: Kranshoek CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA/15/1434/A Beneficiaries: 445 Individuals Property Description: PORTION 4 AND PORTION 6 OF FARM KRANSHOEK NO. 432 | They are landless and wants government to fast track land redistribution. They waited for land for a long time. They also requested complementary support to land reform. Their area is poverty stricken, hence asking parliament for assistance. | Department to engage with the speaker and find out what sort of land needs they have and how government could assist them. | DRDLR is in the process of appointing a service provider to provide planning and conveyancing services for KRANSHOEK TRANCRAA Project. A submission was made for approval Bitou Local Municipality council committed that erf 1; erf 454; portion 4 & 6 be transferred to the Kranshoek Communal Property Association. The Kranshoek support from WCPDOA: Food Security project 2010-2011, shade cloth, inputs, water harvesting equipment Krans Hydro (Mr Abroue) 2013-2014 R40 000 for water tanks, irrigation (This project suffered fire damage in the June 2017 fires. A damage assessment was conducted by DAFF, WCPDOA and RDLR. A report was submitted to the national disaster management committee) 2015-2016 Garden plots R25 000 garden tools and production inputs Kranshoek Primary School : 2017-2018: R120 000 water harvesting equipment Kranshoek Community garden (.5ha), inputs, fencing, water harvesting: R120 000 (2017-2018) | Closing dates for bids 17 November 2017 Site damage Assessment was done on the 21 June 2017.

## Slide 5: Pacaltsdorp CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA/00/0244/A Beneficiaries: 56 Households Property Description: PORTIONS 42 AND 56 OF THE FARM HANS MOES KRAAL 202, MOSSEL BAY RD | “We want land rights; we have never been recognised. We want to ask South Africa to look after its people. Please look after the “!Xam Koranna” Please respect us – give us our land rights so that you restore our dignity. The municipalities and City Councils must respect us”. | What is the state of affairs regarding the land rights for the Khoi and San communities? Progress report regarding consultations and policy proposals being discussed must be submitted to the Committee. | The approval of the Traditional khoisan Bill (B23/201 5) facilitated through the COGTA to provide clarity on how to deal with Khoi and San Communities Chief Director PSSC will refer the matter to Legal Services at national office before the end of November 2017 via the office of the acting DDG: LTA | 31/11/2017

## Slide 6: Toekoms CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA/99/0158/A Beneficiaries: 29 Households Property Description: PORTION 40 (A PORTION OF PORTION 38) OF THE FARM NO.136 | They received land in 1999 but have not received any support from government. Mr Claassen has been to meetings in Johannesburg (called by the Minister), but it appears that there is nothing happening or no one prepared to help. CPAs do not understand Constitutions Many CPAs do not have title Deeds | - Post settlement support is required. The Department to coordinate interventions with DAFF. - A report should be sent to the committee about the interventions proposed. | On the 3rd November 2017, the district office engaged with the WC Department of Agriculture to look at the support that is available for smallholder farmers and agree on how they will be working together to ensure that CPAs also benefit. A report will be compiled and sent to the Portfolio Committee after December workshop LRMF Panelist to be appointed in order to provide the CPA with regularization and training on the Constitution. Branch will conduct an audit of all CPAs to establish whether they have Title DEEDS and if not they will linked with the DEEDS office for assistance to obtain them. | Road map workshop before 15 December hosted by DAFF 22 November 2018 Jan 2018 15 December 2017

## Slide 7: Mossel Bay African Farmers Union CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA/98/0096/A Beneficiaries: 106 Households Property Description: The Farm Buffelskraal South No.168 and Portion 2 of the Farm Buffelskraal South No.167 in Mossel Bay RD | The group owns 1500 ha, and the group comprises some 106 households. The difficult is that the land is barren and they cannot plant anything. No water, houses dilapidated and inhabitable. They tried to do game farming. We approached DRDLR promised us, submitted everything but the grants are not reaching us. The request government to give us fund. Promised recap and they were still waiting. | The Department must engage with its clients about policy developments and shifts. For example, now that Recap is phased out, how is the DRDLR going to assist communities. What mechanisms are in place to ensure that there is a link between DRDLR, CPAs or communities with DAFF. What other government departments are going to be playing a key role in this matter. | Panellist was appointed to assist with regularisation of CPA, 24 Jan 2016 members meeting. Training was provided on the CPA Act, Constitutions, Basic Governance, Roles and responsibilities at the EDEN CPA FORUM. A meeting was held 15/05/2016 to finalise constitution and to elect executive A farm assessment was conducted by WCPDOA, MAFU representatives and DRDLR . This was submitted to the DLRC for consideration. A meeting was held in 2016 with the representatives and Mentor of MAFU to explain that the RECAP will be moving to DAFF. On the 3rd November 2017, the district office engaged with the WC Department of Agriculture to look at the support that is available for smallholder farmers and agree on how they will be working together to ensure that CPAs also benefit. It was agreed that: 1. An application will be made for CASP Funding. | 15 November 2017

## Slide 8: Karatara Settlement
 | Issues Raised | Outcome/ Output of the Actions | Dates
 | The need for low cost housing was expressed. Furthermore the concern was raised that the Knysna Municipality should not allocate land | A meeting between Knysna local municipality and DRDLR was held to explore ways to collaborate on matters related to land development George office met with the Karatara housing Committee to follow up to Mr Daniels’ input in September. Mr Oelf of the Kraaibosch claim was present. The Committee raised matters pertaining to development projects, housing and bulk services. A report was submitted to Knysna Municipality. The DRDLR request WCPDOA to advise on potential of agricultural projects (1HH/1HA). A follow up meeting will take place in November 2017 as soon as Knysna municipality confirms their availability to attend. | 30 November 2017

## Slide 9
Issues Raised | Outcome/ Output of the Actions | Dates
Mr Jacobs made the statement that the transformation process (TRANCRAA) is too slow. He indicated that the capacity to deal with matters in the George office is limited to one official | (The Chief Director PSSC has initiated a request to Department of Social Development to avail interns to work with the George office to add to capacity with regards to the administration of ESTA Matters. This will allow the Tenure official more time to focus more on the TRANCRAA matters. This will also be discussed at the National Task Team as part of the revised strategy plan for TRANCRAA | 
Ruiterbos |  | 
In 1999 a process was initiated to transfer state land (Public Works) to the community with very little being achieved. The result is that there is limited development taking place. Due to distance from schools, transport providers are making money from the poor through scholar transpor | A meeting took place with the Mossel Bay Municipal Manager on 27 October 2017 and a resolution was taken that the technical manager would engage with the Surveyor in George to provide a quote to DRDLR for the amendment of the general plan. This is to be done by 3 November 2017. The transport matter was referred to the Western Cape Department of Education for follow-up WCPDOA has supported the community with 18 household gardens. A joint follow up meeting with stakeholders will be held on 15 November to follow up on determining additional intervention support. | 
Zoar

## Slide 10: KRAAIBOSCH COMMUNITY CLAIM
Information | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
The property, viz. Kraaibosch Woodcutter’s Location (“Allotments’) and “Vrygrond” (Free Land), is located between the Homtini River to Karatara River between the Outeniqua Mountains and the N2 National Road, Knysna Local Municipality in the Eden District of the Western Cape | Despite Minister’s promise to finalize the Kraaibosch claim during 2010, the current state of affairs are unknown to the Committee; and That the claimants are prompted to opt for financial compensation by the George satellite office of the Regional Land Claims Commissioner: Western Cape. | Continuous communication between the Kraaibosch Land Claim Committee and the Commission office since the Minister’s visit during 2010 was instrumental with progress made to date; - Latest meeting on 6th July 2017 outlined progress; - Responded to Ministerial Enquiry on 6th September 2017; - The Commission explains Financial Compensation is one of three options during a compulsory workshop | The list of 12 untraceable claimants have been escalated to the Office of the Chief Land Claims Commission after the attempts made by the Regional Land Claims Commissioner failed Negotiations for land to the benefit of the 3 is in progress, though no timeframe can be placed due to negotiations for restoration of land and related processes and the availability of land. | timeframes depend on outcome of tracing process

## Slide 11: Elandskloof CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA 96/0001/A Beneficiaries:301 households confirmed by court (1353 inclusive of descendants with claims to membership) Property Description: FARM NO .475 AND 476 ELANDKLOOF, CLANWILLIAM RD | 1. Restitution : A member said the land claim was not properly settled, they did not receive what they claimed. 2. Property rented out without their consent 3. Placed under administration 4. Retention of previous members as mentors 5. On-going dispute amongst members 6. Request to conduct oversight visit |  | The Land Claims Commission has at many occasions met with the CPA to explain the initial claim and has advised that they submit a new/additional claim for the land that was not part of the initial claim. Land Tenure Administration branch in the West Coast District Office will visit the CPA and investigate this matter to establish the detail on the statement. Conflict amongst members resulting in High court case made it impossible to continue with the work of the CPA. The DRDLR; through the mediator that was appointed July 2017; intends approaching the Western Cape High Court to set aside the administration order and hand back the administration/management of the CPA to the community 1996/97 Previous Owners were mentors CPA released them. Second mediator appointed in July 2017 through the Land Rights Management Facility has to date held several meetings with the community as well as with different structures within the community. : - resolve disputes within the community, - regularising the CPA by ensuring that an Annual General Meeting is held since this has not been taking place. - This is to form a single structure that will enable more effective interaction between the community and DRDLR. - It will further enable the department to hand back the administrative duties of Elandkloof once a CPA Executive has been elected. | 24 November 2017 Before the end of February 2018

## Slide 12: Middelpos CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA 13/1363/A Beneficiaries: 13 Households; 26 Members (16 Female; 13 Youth) Property Description: Portion 3 (a portion of portion 2) of the farm Middelpos No 611 in the Malmesbury Registration Division | Not a lot has happened on the farm; 8 million funding from DRDLR but there are cash flow problems Need training Contract with Goedgedacht Title Deed monitoring by DRDLR. Rational for building houses where there is no food (why not use funds for cash crops) Reasons the Trust withdrew from the CPA. Whether there has been full compliance by all parties involved Copies of signed contract Detailed report Goedgedacht-financials | The report on Middelpos should indicate(not exhaustive): 1. the terms of signed agreement, whether there has been full compliance of these terms by all parties concerned; | SLA Requirements were met District office has scheduled a meeting with Western Cape Department of Agriculrure to address the training needs of the CPA Training arranged for the CPA could not be attended as it was a full-time course. A short-course training is being envisaged for the first quarter of 2018 | 20 November 2017 April 2018

## Slide 13: Middelpos CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA 13/1363/A Beneficiaries: 13 Households; 26 Members (16 Female; 13 Youth) Property Description: Portion 3 (a portion of portion 2) of the farm Middelpos No 611 in the Malmesbury Registration Division | Not a lot has happened on the farm; R8 million funding from DRDLR but there are cash flow problems Need training Contract with Goedgedacht Title Deed monitoring by DRDLR. Rational for building houses where there is no food (why not use funds for cash crops) Reasons the Trust withdrew from the CPA. Whether there has been full compliance by all parties involved Copies of signed contract Detailed report Goedgedacht-financials | The report on Middelpos should indicate(not exhaustive): 2. circumstances surrounding the withdrawal of the Goedgedacht Trust, the implication of this withdrawal on the project, the financial loss (if any) as well as all the legal implications; | 2. The breakdown in the relationship between Ms. Ingrid Le Strade and Goedgedacht Trust impacted negatively on Middelpos. She has been the face of Goedgedacht Trust and central in negotiating financial support from both the DRDLR and in general with other stakeholders. The agreement with Goedgedacht Trust as strategic partner and the Recap funding and all other support provided by DRDLR was to ensure that Middelpos become a self-sustaining unit. This was placed in jeopardy with the break of the Le Strade-Goedgedacht relationship. The Middelpos main house was upgraded through a loan (R400 000) provided for by the Goedgedacht Trust. Records of the decision to incur this debt by the Middelpos CPA could not be provided. Loan investigation- confirmed by both parties – CPA unable to repay the loan because of the breakdown relationship. Dept will make legal support available to the CPA should the trust take legal action though no indication of such | Matter to be resolved regarding legal assistance if required by 30 November 2017

## Slide 14: Middelpos CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA 13/1363/A Beneficiaries: 13 Households; 26 Members (16 Female; 13 Youth) Property Description: Portion 3 (a portion of portion 2) of the farm Middelpos No 611 in the Malmesbury Registration Division | Not a lot has happened on the farm; 8 million funding from DRDLR but there are cash flow problems Need training Contract with Goedgedacht Title Deed monitoring by DRDLR. Rational for building houses where there is no food (why not use funds for cash crops) Reasons the Trust withdrew from the CPA. Whether there has been full compliance by all parties involved Copies of signed contract Detailed report Goedgedacht-financials | The report on Middelpos should indicate(not exhaustive): 3. the rationale behind the housing project as opposed to providing funding (in the interim) for cash crops whilst waiting for the 5 year period for olives to come into produce. The report should go further to explain whether the Department foresaw this 5 year waiting period in the planning phase, if so what plans were put in place to the benefit of this farming community; 4. the financial breakdown of the R8 million investment by the department; | 3. CPA was linked with Goedgedacht Trust as a strategic partner took responsibility for the running and operations of Middlepos. The break in the relationship brought about a shift in putting interim measures in place. The 1 Household 1 Hectare programme was explored as a option to produce cash crops. The DOA was approached to undertake a soil analysis that was not positive. Application made in July with DOA on the production of the cash crops and it is at an advance stage. To be in the new financial year CPA was aware of the waiting period, if the trust did not withdraw this would not have been the fact. 4. R4.1 Land Acquisition and R3.7 RECAP | 

## Slide 15: Brandwacht CPA
CPA Info | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Reg No. CPA/97/0016/A Beneficiaries: 257 households Property Description: 13 residential erven and portion 23 of Farm No 154 and portion 5 of 164 in Mossel Bay RD registered with Brandwacht CPA. the remaining residential erven transferred to beneficiaries | Municipalities do not know what CPA is; and do not understand what their functions are. Land development projects | 1. The Department must begin thinking about forging relations with municipalities so that CPAs are well understood at that level. Determine land development projects: Commodities include vegetables. | A request was made by DRDLR that the roles and functioning of CPA’s and a proposal for a worksession are discussed at the Eden Joint District Committee (DJOC) meeting of November 2017. The proposal will be to roll-out training session though out the district. A Training Schedule will be tabled at the meeting for buy-in and be communicated to all the CPAs in the district. 2. Meeting held with Mosselbay Municipality on 27 Oct 2017. Mosselbay Municipality confirmed tunnel farming and 1HH/1HA as project options. | 27/11/2017 (DJOC) Training Sessions to start in January 2018 Meeting held with WCPDOA on project assessment. Follow up meeting due on 15 Nov 2017, CPA, Mosselbay Mun, RDLR, WCPDOA on site

## Slide 16: Other issues
Speaker | Issues Raised | Actions/Milestones | Outcome/ Output of the Actions | Dates
Save Farm | No assistance received. (we have problems because our land has been abandoned) Peter John-Paul invited the Committee to the experimental farm where things have taken a different route than original envisaged. They tried to report the cases to the Police but when cases go to court, cases disappear and livestock were poisoned. He asked for government to build a house for him. Grass problems on farm No security on farm Case disappeared in court Problem of snakes on the farm | The Department must investigate the matter and assist in dealing with the conflicts within the group. Regarding the cases referred to Court, the Department must consider assessing the case and determine if the LRMF could not intervene in the case. The Department must report to the Committee regarding progress in this matter. | The DRDLR Eden District Office is in the process on investigating conflict amongst the group and will do an application to LRMF for legal aid and mediation if needed Meetings are set up for November 2017 to further engage Mr Paul, his group as well as relevant stakeholders The concern of Mr Paul on livestock theft and poisoning and the lack of support for their project by the George experimental farm is one of the matters outstanding and will be addressed in a joint working session with WCPDOA that was held on 3rd November 2017. Feedback will be provided on the outcome of these discussions and other meeting outcomes. | 30/11/2017

## Slide 17
THANK YOU