## Slide 1: Progress:Implementing Recommendations from the PC’s visits to Limpopo and Mpumalanga Provinces
Presentation by the DPSA to the Portfolio Committee on Public Service and Administration, Planning Monitoring and Evaluation
15 November 2017

## Slide 2: CONTENTS
Introduction
Purpose of the presentation
Generic Findings and recommendations
Generic Findings & Summation of Progress made
Conclusion

## Slide 3: INTRODUCTION
The Portfolio Committee undertook oversight visits to assess the state of service delivery in the Mpumalanga and the Limpopo provinces from the 27 - 31 March 2017
The Ministry for the Public Service and Administration coordinated the visits
  The Portfolio Committee was accompanied by officials from the Provincial Offices of the Premier (OTPs), the DPSA, the DPME, OPSC and NSG, and visited several service sites in the provinces.

## Slide 4: INTRODUCTION
  In the engagements, presentations were made on the:
    State of the Provinces (PSC);
    Service Delivery Improvement Programme (DPSA); and
    Management of Performance Assessment Tool (DPME).
  Sites visited included the Thusong Service Centres, hospitals, and NYDA offices.
Key issues looked at were:
  the service delivery environment in hospitals;
  the management and governance arrangements, queue management procedures and systems, complaints management processes, and operations management in the TSCs and the NYDA.

## Slide 5: PURPOSE
The purpose of this presentation is to brief the Portfolio Committee on the progress made in addressing the recommendations that they made during the oversight visits in March 2017 in Limpopo and Mpumalanga Provinces.

## Slide 6: ACTUAL SITES VISITED
MPUMALANGA | LIMPOPO
National Youth Development Agency, Emalahleni | National Youth Development Agency, Polokwane
Phola Thusong Service Centre | Moletjie Thusong Service Centre
Casteel Thusong Service Centre | Mankweng Provincial Hospital
Matikwana District Hospital | WF Knobel District Hospital

## Slide 7: GENERIC FINDINGS AND RECOMMENDATIONS
The need for ongoing support and continuous improvement in the operations and governance arrangements of the Health Sector;
Water remains a serious challenge. Mpumalanga Health, e.g. uses the maintenance budget to fill-up the Jojo Tanks;
Need for new and repairs to infrastructure. Some of the buildings are very old;
Filing and document management remains a major challenge as it affects the turnaround times of operations;

## Slide 8: GENERIC FINDINGS AND RECOMMENDATIONS
DPSA to urgently strengthen the integrated approach for govt interventions, through improved support for the Thusong Service Centre Programme;
The Thusong Service Centre Programme are now part of Outcome 12 Programme of Action with regular monitoring and reporting;
A multi-stakeholder Conference on Thusong Service Centres is envisaged to take place in February 2018. Consultations are taking place, and support is being garnered form stakeholders, to ensure meaningful engagements and value-add at the envisaged conference.

## Slide 9: GENERIC FINDINGS AND RECOMMENDATIONS
The NYDA needs to strengthen its visibility and accessibility across the country. This will strengthen Youth Sector Development;
The NYDA centres are mostly in affluent towns.
Equity targets for SMS women and mainstreaming of disability remain challenges in the public service and require urgent and sustainable interventions.

## Slide 10: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress made thus far
1. Executive Authority should ensure payment of suppliers within 30 days. This must be part of the performance contracts of HoDs | Departments | Payment of suppliers within 30 days is one of the Outcome 12 indicator. It also forms part of the Performance Agreements of the Heads of Departments. The DoH has an electronic system to enhance the management of the 30 day payment requirement. The 30 day payment is a standing item at senior and executive management meetings, CEOs included. Mpumalanga DoH has another system called the Siyabhadala system, which monitors overdue account payments. Provincial and District Health offices have Financial Management Committees who monitor and enforce adherence to the 30 day payment requirement.
2. Incongruence between budgets and performance targets | DoH | Both provinces noted the discrepancies between financial performance and non financial targets which do not always correlates, e.g. Mpumalanga cited the provincial financial constraints and influx of foreigners put pressure to the system. Both the DoH and Provincial Treasury are looking at the issue.

## Slide 11: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far | Code
3. Sustainable and consistent implementation and monitoring of approved SDIPs in line with annual performance plans, resource allocations and displaying of the service charter. MTSF Target on SDIPs: 90% of Departments meet the quality minimum standards by 2019 (in line with APPs and resource allocations) Displaying of Service Charters | DPSA, National and Provincial Departments | 86% SDIPs submissions realised (and quality assured) by 31 March 2017. Support provided on a request basis (Provinces; Departments) DPSA hosted two national workshops in August 2017 (PE and Gauteng: national and provincial departments in attendance) Advocacy sessions with top management. Appointment of Accounting Officers undertaken by departments Strategy for institutionalising SDIPs (in Strategic Planning units) includes inclusion into tool for analysing departmental plans administered by DPME, DPSA and OTPs. Submitted SDIPs indicate existence of Service Charters. The display thereof is differential. A comprehensive study is planned with StatsSA on implementation of BP principles, which will include physical visits to selected population sites. DPSA to monitor MPAT performance improvements | 

## Slide 12: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
3. Sustainable and consistent implementation and monitoring of approved SDIPs in line with annual performance plans, resource allocations and displaying of the service charters a. Improve the turn-around time for EMS | DPSA, National and Provincial Departments | Matikwane Hospital in Mpumalanga, like all other hospitals, implements the National Core Standards. Performance over the past two years improved from 43% (2015) to 70% (2016). Quality improvement plans have been developed for the hospital to reach the compliance status. The DoH is installing a vehicle management system that will ensure that ambulances are monitored at all times and assist with identifying ambulances that are within close proximity to an incident to reduce turn-around time. The system will further assist to curb abuse. The Department is in the process of integrating PPTS into EMS that will alleviate the workload from primary ambulance, freeing them up for emergency response. The DoH is commissioning a Computer Aided Dispatch system that will provide management with tools to manage calls and dispatch ambulances quicker to incidents

## Slide 13: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
4. Accounting Officers should ensure signed performance agreements aligned to the delivery outcomes and must be evaluated accordingly. a. The Committee proposed establishment of an independent Committee comprising key stakeholders to assess or evaluate performance of the Accounting Officers. | DPSA and Provincial Departments | PC recommendation for the establishment of Independent Committees is still being processed. MPSA Directives (letters dated 15 June 2015 ad 24 November 2015) were issued to guide implementation and finalization of performance agreements and evaluations, and especially for outstanding evaluations for 2014 and 2015. Mpumalanga: has concluded HoDs’ performance agreements and evaluations (2016/17) in July 2017. The PAs for 2017/18 cycle will be finalised in Nov 2017. 80% of HoDs have submitted. Limpopo: Majority of HoDs have not finalised their PAs (2017/18) and their evaluations (2016/17).

## Slide 14: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
5. The Department of Planning, Monitoring and Evaluation together with the Public Service Commission should work together and ensure collaboration in monitoring the state of the public service to avoid conflicting findings. | DPME and OPSC | DPME and OPSC to provide comprehensive reports. The proposal of the Portfolio Committee is noted and mechanisms will be put in place to ensure integrated approach and alignment in monitoring the state of the public service. Careful considerations will be ensured that the PSC should still maintain its independence as enshrined in the Constitution (of investigating, monitoring and evaluating the public service & administration).
6. The DPSA should report to the Committee regarding a new strategy to deal with grievances backlog in the public sector in the third quarter of 2017/18 financial year. | DPSA and Offices of the Premier | Noted. Follow-up is in progress to ensure presentation and reporting as per the Committee’s request by mid-December.

## Slide 15: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
7. Employment of people with disabilities and 50% of women in senior management should be taken seriously in the provinces. There should be consequence management for departments failing to reach this equity targets. | Offices of the Premier LP and MP | Mpumalanga Province: Employment Equity: The provincial status with regard to the employment of women in senior management is 36%. Total number of SMS as at March 2017 is 335. Breakdown: 214 Males and 121 Women. The Province’s employment of people with disabilities stands at 0.56. Five (5) provincial departments meet the 2% threshold whilst seven (7) are not. The lowest are the Departments of Health and of Education. N.B. these two are exempted from the provincial employment moratorium. However, they are being encouraged to prioritise people of the designated groups. Limpopo Province: All Departments meet the 2% employment of people with disabilities, except for the Departments of Education, Community Safety and Health. The Province has achieved an 3% target for Persons with Disabilities at SMS Level.

## Slide 16: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
8. The development of mechanisms to speed up the closure of the grievances lodged in the public sector. | DPSA and Offices of the Premier | The DPSA has developed the precautionary suspension and sanctioning guidelines to ensure prompt and consistent application of discipline in the public service. The Disciplinary Code and Procedure for the Public Service has been reviewed and is currently being negotiated by parties in the Public Service Coordinating Bargaining Council. The amendments in the Disciplinary Code and Procedure for the Public Service will, inter alia, require that disciplinary processes are finalized within 90 days, and cases of precautionary suspensions are finalized within 60 days.

## Slide 17: Summary of achievements
Recommendation | Responsible Department(s) | Progress thus far
9. The Department of Public Works should ensure that maintenance of government buildings remains a priority. The Department of Education is advised to establish a school for the deaf as there is none in the Mpumalanga province. There should be a plan to assist deaf learners with transport as they are currently being transported by NGOs to attend schools in other provinces. | DPW and DBE | The DPW is one of the key departments and central to the successful implementation of Outcome 12 deliverables. One of the key actions being monitored with regular reporting is the department’s strategy on the maintenance of government infrastructure which prioritises service delivery departments that include Health and Education. The school for the deaf is at the planning and design stage in line with the Infrastructure Plan of the Department of Education. It will be built in Mbombela and construction will commence in the next financial year (2018/19).

## Slide 18: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
10. Maintenance of hospital buildings and infrastructure development especially those very old should be prioritised to avoid dilapidation of buildings. | DPW & departments | The DPW reports on Outcome 12 deliverables. The department has a strategy on the maintenance of government infrastructure which prioritises service delivery departments such as Health and Education. Budgetary constraints limit the DPW’s progress
11. Maintenance of hospital buildings and infrastructure development especially those very old should be prioritised to avoid dilapidation of buildings. a. | Provincial Health & Provincial Public Works | The Mpumalanga Province has allocated a R10 Million budget per district, for the maintenance of health facilities and is prioritised according to the needs. DPW is in the process of appointing a service provider to install the laundry equipment at a cost of R1.8 million in Matikwane hospital. This will address the loss of linen as laundry services will be done in-house. In the interim the hospital introduced a control mechanism through a release and returns register of laundry items.

## Slide 19: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
12. The Matikwane Hospital is seriously underfunded with the need to review the organogram among others in the quest to deliver quality service delivery. | DoH | Matikwane Hospital used to be a Public Private Partnership and the provincial government took over total control of the institution (when?). As part of the takeover process the budget for Matikwane hospital has been reviewed for the current financial year, further review will be conducted though the MTEF to ensure that it is on par with institutions of similar size in the province. The department is in the process of reviewing organogram of institutions and is projected to be finalised by the end of the financial year. The OD team already conducted inspection of the facility. Matikwane hospital is one of the institutions identified to pilot the Workload Indicator of Staffing needs (WISN) tool which is envisaged to ensure standardisation of norms and standards for staff allocation in health facilities.

## Slide 20: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
13. Adequate provision of medication to 13 clinics which are a feeder to Matikwane Hospital. | DoH | Availability of Medicine in the province improved from 89% in 2013/14 to 92% by September 2017 which includes essential Drugs in the feeder Clinics to Matikwane Hospital Availability of Medicines is closely monitored as one of the key Six priority areas of the Idea Clinic programme. Medicines are classified as non-negotiables in the DoH

## Slide 21: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
14. The W.F Knobel District hospital in Limpopo requires urgent interventions due to its state of deterioration, the building infrastructure is very old as the hospital was built in 1936. 15. What is the Provincial Plan about the certain equipment's that were acquired some time back but to date remain unused for Polokwane Hospital due to wrong specifications. | DoH & OTP | The Provincial Administration has a plan to address the dire state of Knobel District Hospital. The hospital has purchased the missing parts based on the correct specifications which include the connections and new parts for the Bucky Table. The parts are awaiting delivery after which it will be installed and therefore ensure that the hospital uses the X-Ray equipment.

## Slide 22: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
16. Fast racking the finalising and implementation of the Thusong Service Centres business case report. a. These include the governance arrangements, lease agreements, funding model and ensuring presence of all key departments in the Thusong Service Centres including satellite South African Police Service. | DPSA, COGTA, Treasury, DPW & Office of the Premiers | Business Case Studies on Thusong Programme finalised and consultative process with the key affected departments in progress
17. Consultative conference on the Thusong Service Centre Programme with all relevant stakeholders. | DPSA | The National Institutional Coordination and Funding Options and proposed way forward for the Thusong Service Centre Programme was presented to the Portfolio Committee in May 2017

## Slide 23: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
18. Strengthened Institutional arrangements and Intergovernmental relations in the Thusong Service Centres to promote integrated planning and provision of quality services as envisaged in the NDP and delivery agreements on outcome 12. | DPSA and GCIS | Thusong Service Centres Improvement Programme is now one of the Actions of the NDP and a delivery agreement on Outcome 12 with monthly monitoring and reporting to the G & A structures.
19. Sustainable Service Delivery Improvement of Thusong Service Centres (TSC) visited. Mpumalanga Province (Phola TSC & Casteel TSC) Limpopo Province: Moletjie Thusong Service Centre | DPSA, GCIS, Offices Of the Premiers and COGTA | DPSA is providing technical support to facilitate the development and payment of the lease agreements for all the visited Thusong Service Centres. A long term solution of the funding model is being considered. Interventions are being pursued towards improving access for people with disability at Casteel TSC IGR being strengthened

## Slide 24: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
20. Collaborative Involvement of the Centre for Public Service Innovation in resolving queue management in most of the hospitals. | DoH | The recommendation of working with the Centre for Public Service Innovation in resolving queue management is being pursued. Some exploratory engagements have taken place.
21. The Department of Health should replicate and learn best practices on queue management from the Department of Home Affairs. |  | Mpumalanga Provincial Health received a presentation on lessons learnt on queue management system made by the DHA. In the meantime to mitigate the challenge, officials are assigned on rotational basis for queue marshalling to alleviate challenges in hospitals like Matikwani. Follow up is being made to ensure internet connectivity and appropriate budget for the queue management system at Mankweng Tertiary and Academic Hospital.

## Slide 25: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
22. The Department must develop a recruitment strategy to fill up funded critical vacancies in the hospitals especially the shortage of nurses and medical practitioners in hospitals. | DoH and OTPs | DoH is reviewing the current recruitment strategy which includes reviewing delegations. Staffing norms are being developed to ensure equitable distribution of health professionals across all health facilities.
23. The Department of Health should develop a Health Intra and Cross Trade Africa Border policy to address challenges facing South African hospitals (e.g. of assisting patients from other countries which is costly for the SA State). |  | Provinces are considering proposals on how to deal with intra- and cross-boarder challenges. Mpumalanga Provincial Health currently has the Mozambique, South Africa and Swaziland (MOSASWA) agreement which is specifically aimed at Malaria elimination. DoH has cross boundary agreements (MoUs) with other provinces like Limpopo, Gauteng, and KZN on improving access to health services.

## Slide 26: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
24. The Department of Health should develop a Health Intra and Cross Trade Africa Border policy to address challenges facing South African hospitals (e.g. of assisting patients from other countries which is costly for the SA State (continued). | DoH | Measures to alleviate the impact of cross boarder on the resources of Mankweng Hospital are being considered. There is need for a comprehensive budget allocation to give the hospital resource capacity to cater for a broader catchment area (including for people outside their catchment area).
25. The Department of Health should take the frontline service officials as a priority regarding funding and resources. |  | The Department is prioritising the filling of low category staff in facilities in the next financial year (2018/19). 551 posts have being advertised so far. Protective clothing for lower categories of staff i.e. Cleaners, Grounds men, Laundry and Food Services Aids to the value R150 000 have been procured by Matikwane hospital.

## Slide 27: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
26. There is a shortage of filing cabinets and boxes in the filing room (most rural hospitals and clinics). Files are lying on the floor and this results in difficulty when locating them and thus affects the service delivery operations adversely. a. There is a need to establish an effective records management system for the visited hospitals. | DoH | DPSA to deploy staff to assist with file management in identified service sites (e.g. Matikwane hospital). Benchmarking with similar health institutions from other provinces across the country to be undertaken The Mpumalanga DoH has put the following systems in place: Approved record management policy Approved filing system Approved Optic Plan focusing of patient files Health Patient Records System (HPRS) focusing on medical records. Matikwane hospital utilises the approved Provincial Waste Management Policy of 2016

## Slide 28: SUMMARY OF ACHIEVEMENTS
Recommendation | Responsible Department(s) | Progress thus far
27. Strengthen the visibility and accessibility of the NYDA programmes to young people in both Limpopo and Mpumalanga Provinces | NYDA | The NYDA’s institutionalised approach and programmes, which includes skills and competency development, is commended. There is a need to strengthen the access and visibility of the Agency throughout provinces as the offices are concentrated in affluent towns.

## Slide 29: CONCLUSION
The Committee to note the progress made on the issues raised during the oversight visits of Mpumalanga and Limpopo.
Institutional arrangements put in place to support implementation, monitor and report on progress for the issues raised during the oversights for Mpumalanga, Limpopo and Free State Provinces. Task team by the three provinces led by DDGs in the Offices of the Premiers, high level officials in the affected departments, DPSA, DPME and NSG.