## Slide 1: The new Northern Cape Mental Health Hospital
Presentation to MEC – April 2013
from Dr. G Pistorius

## Slide 2: Contents
Introduction
Current mental health bed capacity
Strengthened hospital management
Strengthened infrastructure management
Improved joint working
Progress with current construction project
Challenges

## Slide 3: Introduction
The new Northern Cape Mental Health Hospital in Kimberley remains a serious challenge, whilst there is noticeable progress being made since construction under a new contractor resumed in early 2012. The contract with the current contractor states that the construction of this hospital will complete in 2014.
However this contract did not take into consideration alterations that need to be made to the original design as a result of new legislation. This relates to provision being made for the full segregation of male from female patients, the segregation of patients who are admitted through the directive of the courts from voluntary mental health patients, the provision of single and shared room to improve patient confidentiality, and significant changes to the design of the pharmacy to meet the requirements of “Good Pharmacy Practice” as published by the Pharmacy Council.
Currently the Department has not been allocated a specific budget for the further construction of this hospital. However, the Department is in negotiations with the National Department of Health to secure additional funding for this project.

## Slide 4: Current mental health bed capacity
The West End Mental Hospital in Kimberley consists of:
  37 Chronic beds
  28 Acute beds
  21 Voluntary/Assisted beds
  12 State Patient beds

## Slide 5: Increasing bed capacity
Every week there are pressure for additional beds for involuntary admissions
Currently there are 19 State Patients in Correctional Services facilities
We are implementing a plan to create an additional 18 beds for Involuntary Patients and 18 beds for State Patients

## Slide 6: Strengthened hospital management
We have strengthened the management at our specialised TB and mental health hospital:
  Deputy Director appointed at West End Hospital
We have strengthened the management of a two principal referring acute hospitals:
  Chief Director appointed at Kimberley tertiary hospital
  Director appointed at Upington regional hospital

## Slide 7: Strengthened infrastructure management
As required by National DoH we have advertised 14 posts for professionals from construction industry (3-year contracts using DORA allocations):
  Chief Director
  Directors x 3 (Planning, Health Technology, Maintenance)
  Professionals x 10 (Engineers/Quantity Surveyors)

## Slide 8: Classic contract implementation arrangement

## Slide 9: Improved joint working
Utilising the Intergovernmental Relations Framework Act we have established a Joint Management Committee (JMC) to oversee and co-ordinate this project:
  Chaired by National Department of Health (Dr Shaker)
  HoD Northern Cape Department of Health
  HoD Northern Cape Department of Roads & Public Works

## Slide 10: Improved contract implementation arrangement

## Slide 11: New contract: Scope & description
Project Name : Mental Health Facility Kimberley
Project number : DRPW007/2011
Project Location : Portion 84 of farm 80 Bultfontein Kimberley
Client Department : NC Department of Health
Implementing Department : NC Department of Public Works
Consultants
  Principal Agent : Ntaba Resource and Project Management
  Architects : HDG Architects- Architect
  Mechanical Engineers : Mekan Engineering Services
  Electrical Engineers : Worley Parsons
  Civil & Structural Engineers : Babereki Engineers
  Security Engineers : Secelec
  Landscape Architects : Green Inc
  Quantity Surveyors : KDM Quantity Surveyors
Contractor and Grading : Inyatsi Construction SA Pty Ltd, 9 GB

## Slide 12: Scope & description (cont.)
Type of Infrastructure : Mental Health Facility
Project Status : Under construction
Nature of Investment : Social Development
Project Details : 266 bed hospital serving the needs of young and adolescent children, voluntary and involuntary patients as well as State & forensic patients
CPG : 30% of labour is local
Training Provided : People are trained during the course of construction although this was not a tender requirement

## Slide 13: New Project: Time management
Tender Awarded : 27 November 2011
Contract Signed : 28 November 2011
Contractor on site : 22 December 2011
Project start date : 7 January 2012
Original Construction period : 24 months
Extension of Time approved : 42 days excluding costs
Contract Completion date : 4 March 2014 (will be impacted by design changes)
Design report approved : To be finalised by end April 2013
Contractual conditions met : on-going
Construction Completion Date : 4 March 2014
Final Payment : Within 3 months after final completion

## Slide 14: New contract: Costs
 | Total Estimated | Previous Expenditure | Actual Expenditure 28 March 2013
Construction | R 400 570 000 | + R354 000 000 | R 79, 043, 218.91
Professional fees | R 80 000 000 | + R 81 000 000 | R 23, 699, 018.06
Total | R 480 570 000 | R435, 000, 000 | R102, 742 236.97
Potential Variation Orders
The items are still under consideration and to be established and can be re measured
Redesigning to comply with the new Legislation (all design changes will be finalised by 30th April 2013. No further design changes will be permitted)
Relocation of the Air con plant

## Slide 15: New Project: Job creation
DESIGNATED GROUP | NO OF JOB OPPORTUNITIES
Women | 20
Youth | 170 (150 male and 20 female)
People with Disability | 1
Men | 118
TOTAL | 288

## Slide 16: New Project: Monitoring & control
Physical verification done before payment approval and confirmed by the respective consultants, QS, DRPW and DoH
Monthly reporting by DRPW to Client (DoH)
Site Visits: Site visits are bi weekly
A Joint Management Committee (JMC) responsible for overall management of project
Project Steering Committee responsible for monitoring of quality, expenditure and performance

## Slide 17: Challenges
Redesign : To meet new regulatory requirements in terms of pharmacy, segregation of patients by gender, segregation of forensic patients & improved patient privacy, the National DoH have assisted in redesigning some internal aspects of the hospital.
Budget: The budget needed for continued construction is still under negotiation with NDoH and Treasury.
Rate of construction: Contractor certificates average R5.2M per month.