## Slide 1: 2017/18 Financial Year: Status Report to Parliament
NORTH WEST PROVINCE
27 February 2018

## Slide 2: Contents
Aim
Background
Performance
  Expenditure Summary
  Delivery Summary
  Current delivery of sites and units
  Mining Towns delivery
  MTSF objectives
Key Interventions
H.D.A
Title Deeds
NHBRC

## Slide 3: Aim
The intention of this presentation is to brief the Committee on the challenges faced by the province in meeting it’s financial and non-financial targets for April to 31 January 2017/18.
To present to the committee the recovery plan that the province has developed.

## Slide 4: Background
By the end of January the expenditure was at R 1 6 15 739 901, the annual budget was reduced by R 300 000 to R2 079 679 260. 00, leaving a remaining balance of R466 939 359 to be spent during the final two months.
The province has delivered 5 285 Housing units of the expected target of 10 476, 3050 sites of the expected 4 442, and 2 924 title deeds have been registered

## Slide 5: Background
Province experienced slow housing delivery than planned due to the
Following:
Poor performance by contractors and developers and lack of capacity.
Delays in procurement.
Lack of serviced sites from municipalities.
Shortage of beneficiaries
Community unrest.
Municipalities do not have functional SPLUMA tribunals leading to delays in township establishments, which also affect Title Deeds Restoration programme

## Slide 6: Financial Performance
Months | Original Cash Flow | Actual Expenditure | Revised Cash Flow (September Business plan) | Balance vs reduced budget
April | R 161 052 496 | 133 493 203.52 | R 133 493 204 | R 1 946 186 056
May | R 178 983 276 | 117 908 389.22 | R 117 908 389 | R 1 828 277 667
June | R 196 317 546 | 83 278 395.52 | R 83 278 396 | R 1 744 999 272
July | R 201 703 666 | 140 179 784.41 | R 140 179 784 | R 1 604 819 487
August | R 210 083 966 | 109 106 342.42 | R 109 106 342 | R 1 495 713 145
September | R 205 352 866 | 196 098 464.00 | R 198 412 000 | R 1 299 614 681
October | R 187 050 846 | 123 278 937.95 | R 255 459 667 | R 1 176 335 743
November | R 179 805 146 | 121 852 862.07 | R 245 564 047 | R 1 054 482 881
December | R 155 301 476 | 480 808 239.60 | R 212 098 818 | R 573 674 641
January | R 145 096 116 | 109 735 282.33 | R 198 161 122 | R 463 939 359
February | R 169 554 906 |  | R 231 565 057 | 
March | R 196 376 954 |  | R 268 196 549 | 
Total | R 2 186 679 260 | R 1 615 739 901 | R 2 193 423 375 | 

## Slide 7: Expenditure Summary: Graph
Chart: 
| April | May | June | July | August | September | October | November | December | January | February | March
Original Cash Flow | 161052496 | 178983276 | 196317546 | 201703666 | 210083966 | 205352866 | 187050846 | 179805146 | 155301476 | 145096116 | 169554906 | 196376954
Actual Expenditure | 133493203.52 | 117908389.22 | 83278395.52 | 140179784.41 | 109106342.42 | 196098464 | 123278937.95 | 121852862.07 | 480808239.6 | 109735282.33

## Slide 8
QUARTER MONTH |  | SITES |  |  | UNITS |  | 
 |  | PLAN. | Rev Plan | Actual | PLAN. | Rev Plan | Actual
Q1 |  | 1260 | 0 | 0 | 3066 | 882 | 882
Apr |  | 392 | 0 | 0 | 896 | 154 | 154
May |  | 420 | 0 | 0 | 1023 | 229 | 229
Jun |  | 448 | 0 | 0 | 1147 | 499 | 499
Q2 |  | 1455 | 975 | 975 | 3565 | 1721 | 1721
Jul |  | 497 | 0 | 0 | 1158 | 301 | 301
Aug |  | 483 | 975 | 975 | 1216 | 168 | 168
Sep |  | 475 | 0 | 0 | 1191 | 1252 | 1252
Q3 |  | 1313 | 1621 | 1617 | 3017 | 5053 | 879
Oct |  | 461 | 466 | 0 | 1075 | 1804 | 484
Nov |  | 440 | 743 | 1617 | 1039 | 1740 | 596
Dec |  | 412 | 412 | 0 | 903 | 1508 | 1189
Q4 |  | 1221 | 1221 | 458 | 2970 | 4962 | 
Jan |  | 414 | 414 | 458 | 828 | 1394 | 413
Feb |  | 411 | 411 | 0 | 967 | 1628 | 
Mar |  | 396 | 396 | 0 | 1175 | 1941 | 
Total |  | 5249 | 3817 | 3050 | 12618 | 12618 | 5 285
The delivery stats above excludes the CRU in Mafikeng, Matlosana and Moses Kotane. |  |  |  |  |  |  | 300
Mafikeng: Rooigrond | The units are at practical completion stage but not handed over due to the lack bulk services. The Department has approved funds and good progress had been recorded in the installation of the bulk. |  |  |  |  |  | 436
Tswaing Delareyville ext: 8 |  |  |  |  |  |  | 998
Grand Total |  |  |  |  |  |  | 7 019
Delivery Summary per month

## Slide 9: Delivery summary per municipality
Municipality | Sites Planned | Sites Completed | Units Planned | Units Completed
Bojanala Platinum District | 1600 | 1433 | 4153 | 833
Madibeng | 167 |  | 721 | 302
Moretele | 0 |  | 544 | 11
Moses Kotane | 0 |  | 875 | 245
Rustenburg | 1433 | 1433 | 1599 | 100
Kgetlengrivier | 0 |  | 414 | 175
Dr Kenneth Kaunda District | 2349 | 1318 | 2615 | 1666
Maquassi Hills | 1053 |  | 32 | 23
Matlosana | 317 | 0 | 1656 | 1388
Tlokwe/Ventersdorp |  |  |  | 
JB Marks | 979 | 1318 | 927 | 255
Dr Ruth Segomotsi Mompati District | 800 | 88 | 2491 | 1371
Greater Taung | 0 | 0 | 477 | 410
Kagisano-Molopo | 0 |  | 357 | 51
Lekwa-Teemane | 0 | 0 | 738 | 624
Mamusa | 500 |  | 502 | 69
Naledi | 300 | 88 | 417 | 217
Ngaka Modiri Molema District | 500 | 211 | 3259 | 1185
Ditsobotla | 500 | 211 | 742 | 505
Ramotshere Moiloa | 0 |  | 444 | 59
Ratlou | 0 |  | 476 | 
Tswaing | 0 |  | 686 | 101
Mahikeng | 0 | 0 | 911 | 520
North West Provincial | 0 | 0 | 100 | 230
North West Provincial | 0 | 0 | 100 | 230
Grand Total | 5249 | 3050 | 12618 | 5285

## Slide 10: Delivery Summary per month: Graph
Sites
Units
Chart: 
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Rev Plan | 0 | 0 | 0 | 0 | 975 | 0 | 466 | 743 | 412 | 414 | 411 | 396
Actual | 0 | 0 | 0 | 0 | 975 | 0 | 0 | 1617 | 0 | 458 | 0 | 0
Chart: 
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Rev Plan | 154 | 229 | 499 | 301 | 168 | 1252 | 1804 | 1740 | 1508 | 1394 | 1628 | 1941
Actual | 154 | 229 | 499 | 301 | 168 | 1252 | 484 | 596 | 1189 | 413

## Slide 11: Revitalisation of distressed mining communities
Chart: Expenditure per mining town
| Madibeng | Moses Kotane | Rustenburg | Matlosana | Kgetlengrivier
Budget | 148644716 | 135330844 | 286658110 | 296693740 | 54515470
Expenditure | 88999958.3872 | 50462282.456 | 340909102.8765 | 127165137.5059 | 33983884.0462
Municipality | Sites Planned | Sites Completed | Units Planned | Units Completed | Budget | Expenditure
Madibeng | 167 |  | 721 | 302 | R 148 644 716.00 | R 88 999 958.39
Moses Kotane | 0 |  | 875 | 245 | R 135 330 844.00 | R 50 462 282.46
Rustenburg | 1433 | 1433 | 1599 | 100 | R 286 658 110.00 | R 340 909 102.88
Matlosana | 317 | 0 | 1656 | 1388 | R 296 693 740.00 | R 127 165 137.51
Kgetlengrivier | 0 |  | 414 | 175 | R 54 515 470.00 | R 33 983 884.05
Grand Total | 1917 | 1433 | 5265 | 2210 | R 921 842 880.00 | R 641 520 365.27

## Slide 12: MTSF Objectives
MTSF Objective | Provincial MTSF Target 2019 | ACTUAL DELIVERY PROGRESS |  |  |  | 
 |  | 2014/15 | 2015/16 | 2016/17 | 2017/18 - Jan | Total to date
563 000 individual units for subsidy housing submarket provided (Individual, IRDP, UISP, Rural, PHP, Consolidation) | 41 380 | 9206 | 10988 | 9080 | 5250 | 34 524
6 000 individual units for military veterans |  | 4 | 1 | 16 | 9 | 30
Affordable housing loans for new houses in the affordable-gap housing submarket: | 9020 | 0 | 0 | 60 | 35 | 95
27 000 Government led Social housing | 2850 | 0 | 0 | 0 | 680 | 680
10 000 CRU units completed | 800 | 200 | 252 | 0 | 0 | 452
750 000 households in informal settlements upgraded: | 86255 | 4564 | 6564 | 5273 | 3050 | 19 451
Number of Informal Settlements assessed |  | 8 | 34 | 0 | 0 | 42
Number of settlement-level upgrading plans compiled |  | 2 | 19 | 0 | 0 | 21

## Slide 13: Title deeds projects
Project Description | Number of Units | Status
Madibeng Lethabile Block D (i) Ref B98010003 [1000 Subs] | 1000 | Complete township establishment and opening of township register
Madibeng L M Oukasie Proper (1271 Subs) | 905 | Conduct beneficiary verification
Maquassi Hills Housing Project (1803 Subs) | 681 | Send instructions andPrepare transfer documents
Rustenburg Hartebeesfontein Pls (1417 Subs) | 1289 | Conduct beneficiary verification
Rustenburg - Boitekong Ext 13 (440 Subsidies) | 413 | Conduct beneficiary verification
Potchefstroom Muni - Ikageng Ext. 7(1000subs) | 200 | Conduct beneficiary verification
Potchefstroom - Ikageng (2000 Subs) B96040028 Sn 028 | 800 | Conduct beneficiary verification
POTCHEFSTROOM - IKAGENG EXTENSION 4 | 238 | Conduct beneficiary verification
Projects assigned to ministerial task team member

## Slide 14: 23 February claim status
Claim status | Sum of Amount
Amount paid Apr - 23 Feb | R 1 667 993 900.61
Amount for claims on authorised status | R 20 543 769.34
Amount for claims on received status | R 13 379 015.84
Grand Total | R 1 701 916 685.79
PROVINCIAL: Target for Year: Total Budget | R 2 378 379 000
Less: | R 300 000 000
Revised HSDG Target | R 2 078 379 000
Less: Expenditure to Date (23/02/2018) | R 1 667 993 900
Balance of Annual Target | R 410 385 100

## Slide 15: Key Interventions: Projects with a potential to deliver
Stella 700 sites to be serviced – which is a quick process to install internal services infrastructure with machinery
Coligny 500 sites to be serviced
Mafikeng Rooigrond 1000 top structures – to enable reporting on non-financials when bulk infrastructure is commissioned
Rustenburg Bokamoso – 4 contractors with capacity to develop a combined 1600 units are being relocated to ready areas i.e. Madibeng, Moses Kotane villages and Kgetleng Derby and Borolelo which are still under mining towns and will not reduce figures under this programme. The entire costing is R171m including standard geotechnical allowance.
For the financial year 18/19 Bokamoso 1600 units will be implemented by the HDA.
Alabama Ext 5 (2255) internal services – issues resolved and contractor is on site working.
Alabama Ext 4 (948) top structure contractor is on site to construct houses.

## Slide 16: HDA
Project | Expenses by H.D.A | Balance
Flamwood Bulk | 0 | R 58 101 228.00
Matlosana Catalytic | R 57 930 910.00 | R 32 766 943.00
Bokamoso Catalytic | 0 | R 184 800 000.00
Madibeng Bulk | 0 | R 26 250 000.00
Naledi Stella | 0 | R 32 065 110.00
Ditsobotla Coligny IRDP | 0 | R 69 993 554.00
 |  | R 403 976 835.00

## Slide 17: CRUs
Mafikeng CRU have been allocated to tenants. Most tenants have not taken occupation yet due to repairs.
Matlosana CRUs have been handed over to North West Housing Corporation. The Corporation is currently handling the allocation to tenants. The housing corporation has already allocated 21 units and are currently busy the process of allocation the remaining units.

## Slide 18: NHBRC
The relationship has improved.
Held a joint training session of inspectors.
Agreed on the joint programme to visit municipalities to engage on the way forward regarding the undevelopable areas.
MEC and NHBRC CEO have scheduled a meeting for Tuesday 27th Feb.

## Slide 19: NHBRC Enrolments
NAME OF PROJECT | NUMBER OF UNITS ENROLLED | EXPENDITURE
Mogopa-125 | 125 | R 320 567.50
Dini Estate | 300 | R 769 362.00
Moretele villages phase 2 | 300 | R 856 667.83
Borothamadi Village-50 | 50 | R 128 227.00
Driefontein-50 | 50 | R 128 227.00
Rietpan Village | 50 | R 128 227.00
Ipelegeng ext 3-119 | 119 | R 305 180.25
Phaphosane-93 | 93 | R 238 502.21
Alabama ext 4-951 | 951 | R 2 438 887.45
Glaudina-500 | 500 | R 1 282 270.00
Moretele villages phase 1 | 66 | R 169 259.64
Ipelegeng ext 5-93 | 93 | R 238 502.21
Pella Village-81 | 81 | R 207 727.73
Tseoge-340 | 340 | R 871 943.60
Total | 3118 | R 8 083 551.42

## Slide 20: THANK YOU!